## Progress 0
ID | Outline_Number | Name | Duration | Start_Date | Finish_Date | Predecessors | Successors | Actual_Start | Actual_End | Delay | Trade | Progress | Worker_Score | Temp | Rain_Probability | Wind_Speed
2 | 1.1 | MILESTONES / KEY DATES | 633 | 17 April 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 17 April 2023 7:00 AM | - | 0 | Carpenter | 0 | 35 | 21 | 37 | 7
3 | 1.1.1 | Site Establishment | 0 | 5 June 2023 7:00 AM | 5 June 2023 7:00 AM |  | 25SS | - | - | 0 | Plasterboarder | 0 | 33 | 30 | 69 | 19
4 | 1.1.2 | Basement Completed (B2) | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 88 |  | - | - | 0 | Timber Floorer | 0 | 93 | 24 | 2 | 16
5 | 1.1.3 | Building A Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 444,753,746,714 | 3466,9 | - | - | 0 | Floor Sealer | 0 | 72 | 30 | 36 | 57
6 | 1.1.4 | Building B Complete | 0 | 29 March 2025 5:00 PM | 29 March 2025 5:00 PM | 228,482,306,1737 | 3466,9 | - | - | 0 | Scaffolder | 0 | 89 | 22 | 78 | 33
7 | 1.1.5 | Building C Complete | 0 | 16 April 2025 5:00 PM | 16 April 2025 5:00 PM | 306,360,503,3169 | 3466,9 | - | - | 0 | Painter | 0 | 19 | 14 | 44 | 60
8 | 1.1.6 | Building D Complete | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 360,396,519,3439 | 3466,9 | - | - | 0 | Post Tension | 0 | 72 | 18 | 31 | 43
9 | 1.1.7 | Practical Completion (Net) | 0 | 28 May 2025 5:00 PM | 28 May 2025 5:00 PM | 3465,3440,5,3460,6,7,8 |  | - | - | 0 | Admin | 0 | 56 | 30 | 35 | 39
10 | 1.1.8 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | - | - | 0 | Plasterboarder | 0 | 34 | 14 | 40 | 35
11 | 1.1.9 | Inclement Weatherallowed (Spent) | 19 | 29 May 2025 8:00 AM | 21 June 2025 5:00 PM | 3466 | 12 | - | - | 0 | Subcontractor | 0 | 15 | 12 | 75 | 32
12 | 1.1.10 | Inclement Weatherallowed (Remaining) | 1 | 23 June 2025 8:00 AM | 23 June 2025 5:00 PM | 11 | 3469 | - | - | 0 | Painter | 0 | 50 | 33 | 73 | 35
13 | 1.1.11 | Practical Completion (Gross) - Building Handover | 0 | 23 June 2025 5:00 PM | 23 June 2025 5:00 PM | 3469 |  | - | - | 0 | Contract Administrator | 0 | 88 | 22 | 67 | 45
14 | 1.1.12 | PRE CONSTRUCTION WORKS | 210.13 | 17 April 2023 7:00 AM | 16 January 2024 5:00 PM |  |  | - | - | 0 | Stone Mason | 0 | 70 | 22 | 98 | 35
15 | 1.1.12.1 | Authority Approvals, (Access Deeds by Client etc (Ultra to assist in coordination) These are qualifying causes of delay resulting in EOT time & costs) | 372 | 17 April 2023 7:00 AM | 1 August 2024 5:00 PM |  |  | - | - | 0 | Scaffolder | 0 | 19 | 24 | 60 | 26
16 | 1.1.12.1.1 | Section 73 - BPA Design & Stormwater Works | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | - | - | 0 | Mechanical | 0 | 85 | 35 | 39 | 22
17 | 1.1.12.1.2 | Rail Approval | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | - | - | 0 | Scaffolder | 0 | 63 | 17 | 5 | 5
18 | 1.1.12.1.3 | CC1 - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  | 25,19 | - | - | 0 | Electrician | 0 | 93 | 19 | 7 | 35
19 | 1.1.12.1.4 | CC1a - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM | 18 | 25,20 | - | - | 0 | Post Tension | 0 | 60 | 35 | 80 | 46
20 | 1.1.12.1.5 | CC2 - Structure (SoG - Podium) | 120 | 17 April 2023 8:00 AM | 12 September 2023 5:00 PM | 19 | 21 | - | - | 0 | Floor Sealer | 0 | 75 | 15 | 51 | 10
21 | 1.1.12.1.6 | CC3 - Structure (Podium - Roof) + Facade | 156 | 13 September 2023 8:00 AM | 8 April 2024 5:00 PM | 20 | 22 | - | - | 0 | Window | 0 | 13 | 24 | 47 | 16
22 | 1.1.12.1.7 | CC4 - Services & Fit Out | 60 | 9 April 2024 8:00 AM | 20 June 2024 5:00 PM | 21 | 23 | - | - | 0 | Plumber | 0 | 71 | 25 | 85 | 39
23 | 1.1.12.1.8 | CC5 - External Works and Public Domain | 36 | 21 June 2024 8:00 AM | 1 August 2024 5:00 PM | 22 |  | - | - | 0 | Development Manager | 0 | 46 | 24 | 87 | 24
24 | 1.1.12.2 | SITE ESTABLISHMENT | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 85 | 10 | 99 | 53
25 | 1.1.12.2.1 | Site Establishment, Enviro Protection, Survey Set out & Hoardings | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM | 18,3SS,19 | 28 | - | - | 0 | Painter | 0 | 22 | 30 | 48 | 39
26 | 1.2 | CONSTRUCTION WORKS | 571 | 3 July 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | - | - | 0 | Mechanical | 0 | 65 | 11 | 2 | 33
27 | 1.2.1 | EARTHWORKS, PILING - BASEMENT | 234 | 3 July 2023 7:00 AM | 2 May 2024 5:00 PM |  |  | - | - | 0 | Contract Administrator | 0 | 25 | 23 | 51 | 8
28 | 1.2.1.1 | Demolition, Clear & Cut/Level Site | 6 | 3 July 2023 7:00 AM | 8 July 2023 5:00 PM | 25 | 10SS,29SS | - | - | 0 | Plasterboarder | 0 | 22 | 25 | 82 | 58
29 | 1.2.1.2 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | - | - | 0 | Head Contractor | 0 | 26 | 29 | 29 | 19
30 | 1.2.1.3 | Install Piling Matt | 12 | 16 August 2023 8:00 AM | 30 August 2023 5:00 PM | 10,29 | 34FS-6d | - | - | 0 | Tiler | 0 | 11 | 21 | 74 | 41
31 | 1.2.1.4 | Crane Base Ex, Piles & FRP | 8 | 18 December 2023 8:00 AM | 5 January 2024 5:00 PM | 53 | 3442FS+8d | - | - | 0 | Cleaner | 0 | 44 | 29 | 28 | 18
32 | 1.2.1.5 | Piling and Capping Beam | 58 | 28 August 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | - | - | 0 | Concretor | 0 | 14 | 26 | 34 | 47
33 | 1.2.1.5.1 | Buildings A | 28 | 28 August 2023 8:00 AM | 3 October 2023 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 45 | 22 | 36 | 9
34 | 1.2.1.5.1.1 | Perimeter Piling (75 Piles) | 16 | 28 August 2023 8:00 AM | 15 September 2023 5:00 PM | 30FS-6d | 35FS-6d,37,46 | - | - | 0 | Electrician | 0 | 54 | 20 | 97 | 34
35 | 1.2.1.5.1.2 | Capping Beam - Detailed Excavation & FRP | 18 | 9 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34FS-6d |  | - | - | 0 | Metal Work | 0 | 74 | 14 | 48 | 11
36 | 1.2.1.5.2 | Buildings B | 24 | 16 September 2023 8:00 AM | 17 October 2023 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 40 | 32 | 55 | 50
37 | 1.2.1.5.2.1 | Perimeter Piling (56 Piles) | 12 | 16 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34 | 38FS-6d,40 | - | - | 0 | Carpenter | 0 | 71 | 11 | 93 | 37
38 | 1.2.1.5.2.2 | Capping Beam - Detailed Excavation & FRP | 18 | 25 September 2023 8:00 AM | 17 October 2023 5:00 PM | 37FS-6d | 56 | - | - | 0 | Development Manager | 0 | 88 | 10 | 11 | 60
39 | 1.2.1.5.3 | Buildings C & D | 30 | 4 October 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | - | - | 0 | Foreman | 0 | 16 | 11 | 37 | 11
40 | 1.2.1.5.3.1 | Foundation Piling (Gnd Lvl) - (17 Piles) | 6 | 4 October 2023 8:00 AM | 10 October 2023 5:00 PM | 37 | 41 | - | - | 0 | Cleaner | 0 | 70 | 34 | 70 | 4
41 | 1.2.1.5.3.2 | Perimeter Piling (82 Piles) | 18 | 11 October 2023 8:00 AM | 1 November 2023 5:00 PM | 40 | 42FS-6d | - | - | 0 | Reinforcement Fixer | 0 | 79 | 19 | 79 | 48
42 | 1.2.1.5.3.3 | Capping Beam - Detailed Excavation & FRP | 12 | 26 October 2023 8:00 AM | 9 November 2023 5:00 PM | 41FS-6d | 66 | - | - | 0 | Excavation | 0 | 30 | 35 | 30 | 58
43 | 1.2.1.6 | Bulk Excavation & Shotcrete | 142 | 16 September 2023 8:00 AM | 22 March 2024 5:00 PM |  |  | - | - | 0 | Reinforcement Fixer | 0 | 32 | 10 | 20 | 3
44 | 1.2.1.6.1 | Building A | 70 | 16 September 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 47 | 27 | 11 | 3
45 | 1.2.1.6.1.1 | Excavate - Gnd - B1 | 57 | 16 September 2023 8:00 AM | 28 November 2023 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 31 | 18 | 47 | 57
46 | 1.2.1.6.1.1.1 | Excavation | 21 | 16 September 2023 8:00 AM | 13 October 2023 5:00 PM | 34 | 47,56,51,71 | - | - | 0 | Carpet | 0 | 94 | 28 | 49 | 30
47 | 1.2.1.6.1.1.2 | Installation of Anchors | 8 | 20 October 2023 8:00 AM | 30 October 2023 5:00 PM | 46 | 48,49SS+11d | - | - | 0 | Plumber | 0 | 37 | 26 | 54 | 53
48 | 1.2.1.6.1.1.3 | Install Bracing | 4 | 31 October 2023 8:00 AM | 3 November 2023 5:00 PM | 47 |  | - | - | 0 | Project Manager | 0 | 95 | 14 | 28 | 46
49 | 1.2.1.6.1.1.4 | Shotcrete | 20 | 3 November 2023 8:00 AM | 28 November 2023 5:00 PM | 47SS+11d |  | - | - | 0 | Painter | 0 | 29 | 12 | 72 | 3
50 | 1.2.1.6.1.2 | Excavate - B1-B2 | 44 | 20 October 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 28 | 16 | 21 | 7
51 | 1.2.1.6.1.2.1 | Excavation | 14 | 20 October 2023 8:00 AM | 7 November 2023 5:00 PM | 46 | 52,53,56,71 | - | - | 0 | Electrician | 0 | 77 | 15 | 71 | 59
52 | 1.2.1.6.1.2.2 | Shotcrete | 16 | 15 November 2023 8:00 AM | 7 December 2023 5:00 PM | 51 | 53 | - | - | 0 | Fire | 0 | 45 | 28 | 74 | 4
53 | 1.2.1.6.1.2.3 | Foundation Piling (Basement 2 Lvl) - (35 Piles) | 8 | 8 December 2023 8:00 AM | 16 December 2023 5:00 PM | 51,52 | 63,31 | - | - | 0 | Formworker | 0 | 71 | 27 | 59 | 40
54 | 1.2.1.6.2 | Building B | 66 | 15 November 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | - | - | 0 | Site Manager | 0 | 77 | 28 | 81 | 47
55 | 1.2.1.6.2.1 | Excavate - Gnd - B1 | 46 | 15 November 2023 8:00 AM | 22 January 2024 5:00 PM |  |  | - | - | 0 | Plumber | 0 | 34 | 23 | 60 | 57
56 | 1.2.1.6.2.1.1 | Excavation | 22 | 15 November 2023 8:00 AM | 14 December 2023 5:00 PM | 38,46,51 | 57,59,61,71 | - | - | 0 | Excavation | 0 | 69 | 18 | 68 | 16
57 | 1.2.1.6.2.1.2 | Installation of Anchors | 8 | 20 December 2023 8:00 AM | 8 January 2024 5:00 PM | 56 | 58 | - | - | 0 | Cleaner | 0 | 62 | 31 | 70 | 45
58 | 1.2.1.6.2.1.3 | Install Bracing | 4 | 9 January 2024 8:00 AM | 12 January 2024 5:00 PM | 57 | 59 | - | - | 0 | Head Contractor | 0 | 21 | 14 | 72 | 38
59 | 1.2.1.6.2.1.4 | Shotcrete | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,58 | 61 | - | - | 0 | Floor Sealer | 0 | 52 | 13 | 62 | 23
60 | 1.2.1.6.2.2 | Excavate - B1-B2 | 40 | 20 December 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | - | - | 0 | Fire | 0 | 61 | 24 | 64 | 15
61 | 1.2.1.6.2.2.1 | Excavation | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,59 | 66,63,71,62 | - | - | 0 | Metal Work | 0 | 66 | 19 | 85 | 18
62 | 1.2.1.6.2.2.2 | Shotcrete | 10 | 1 February 2024 8:00 AM | 12 February 2024 5:00 PM | 61 | 63 | - | - | 0 | Contract Administrator | 0 | 56 | 26 | 17 | 44
63 | 1.2.1.6.2.2.3 | Foundation Piling (Basement 2 Lvl) - (23 Piles) | 4 | 13 February 2024 8:00 AM | 16 February 2024 5:00 PM | 61,53,62 | 74 | - | - | 0 | Stone Mason | 0 | 88 | 13 | 37 | 14
64 | 1.2.1.6.3 | Buildings C & D | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | - | - | 0 | Mechanical | 0 | 61 | 21 | 14 | 43
65 | 1.2.1.6.3.1 | Excavate - Gnd - B2 | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | - | - | 0 | Foreman | 0 | 20 | 13 | 44 | 37
66 | 1.2.1.6.3.1.1 | Excavation | 30 | 23 January 2024 8:00 AM | 28 February 2024 5:00 PM | 42,61 | 67,71 | - | - | 0 | Plumber | 0 | 61 | 32 | 20 | 2
67 | 1.2.1.6.3.1.2 | Installation of Anchors | 8 | 29 February 2024 8:00 AM | 8 March 2024 5:00 PM | 66 | 68 | - | - | 0 | Site Manager | 0 | 84 | 28 | 71 | 35
68 | 1.2.1.6.3.1.3 | Install Bracing | 4 | 9 March 2024 8:00 AM | 13 March 2024 5:00 PM | 67 | 69 | - | - | 0 | Fire | 0 | 64 | 12 | 34 | 26
69 | 1.2.1.6.3.1.4 | Shotcrete | 6 | 14 March 2024 8:00 AM | 20 March 2024 5:00 PM | 68 | 70,84 | - | - | 0 | Contract Administrator | 0 | 83 | 31 | 66 | 32
70 | 1.2.1.6.3.1.5 | Foundation Piling (Basement 2 Lvl) - (5 Piles) | 2 | 21 March 2024 8:00 AM | 22 March 2024 5:00 PM | 69 | 86 | - | - | 0 | Mechanical | 0 | 46 | 14 | 21 | 20
71 | 1.2.1.6.4 | Complete Bulk Exacavation | 0 | 28 February 2024 5:00 PM | 28 February 2024 5:00 PM | 46,51,56,61,66 |  | - | - | 0 | Admin | 0 | 78 | 19 | 72 | 21
72 | 1.2.1.7 | Detail Excavation, Services & Base course | 61 | 17 February 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | - | - | 0 | Window | 0 | 97 | 11 | 6 | 28
73 | 1.2.1.7.1 | Stage 1 (Building A) | 32 | 17 February 2024 8:00 AM | 25 March 2024 5:00 PM |  |  | - | - | 0 | Concretor | 0 | 46 | 20 | 55 | 55
74 | 1.2.1.7.1.1 | Detailed Excavation | 11 | 17 February 2024 8:00 AM | 29 February 2024 5:00 PM | 63 | 75,79 | - | - | 0 | Formworker | 0 | 63 | 10 | 29 | 2
75 | 1.2.1.7.1.2 | In-Ground Services | 8 | 1 March 2024 8:00 AM | 9 March 2024 5:00 PM | 74 | 76 | - | - | 0 | Plumber | 0 | 63 | 27 | 4 | 44
76 | 1.2.1.7.1.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 11 March 2024 8:00 AM | 15 March 2024 5:00 PM | 75 | 77 | - | - | 0 | Foreman | 0 | 66 | 35 | 9 | 4
77 | 1.2.1.7.1.4 | Base Course to Basement | 8 | 16 March 2024 8:00 AM | 25 March 2024 5:00 PM | 76 | 88 | - | - | 0 | Metal Work | 0 | 99 | 31 | 70 | 35
78 | 1.2.1.7.2 | Stage 2 (Building B) | 32 | 1 March 2024 8:00 AM | 10 April 2024 5:00 PM |  |  | - | - | 0 | Reinforcement Fixer | 0 | 81 | 25 | 57 | 46
79 | 1.2.1.7.2.1 | Detailed Excavation | 12 | 1 March 2024 8:00 AM | 14 March 2024 5:00 PM | 74 | 80 | - | - | 0 | Surveyor | 0 | 75 | 13 | 36 | 59
80 | 1.2.1.7.2.2 | In-Ground Services | 9 | 15 March 2024 8:00 AM | 25 March 2024 5:00 PM | 79 | 81 | - | - | 0 | Surveyor | 0 | 57 | 16 | 68 | 31
81 | 1.2.1.7.2.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 6 | 26 March 2024 8:00 AM | 4 April 2024 5:00 PM | 80 | 82 | - | - | 0 | Metal Work | 0 | 84 | 33 | 87 | 55
82 | 1.2.1.7.2.4 | Base Course to Basement | 5 | 5 April 2024 8:00 AM | 10 April 2024 5:00 PM | 81 | 93 | - | - | 0 | Window | 0 | 74 | 23 | 47 | 26
83 | 1.2.1.7.3 | Stage 3 (Buildings C&D) | 33 | 21 March 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | - | - | 0 | Development Manager | 0 | 58 | 16 | 40 | 18
84 | 1.2.1.7.3.1 | Detailed Excavation | 12 | 21 March 2024 8:00 AM | 6 April 2024 5:00 PM | 69 | 85 | - | - | 0 | Floor Sealer | 0 | 83 | 24 | 55 | 42
85 | 1.2.1.7.3.2 | In-Ground Services | 8 | 8 April 2024 8:00 AM | 16 April 2024 5:00 PM | 84 | 86 | - | - | 0 | Carpenter | 0 | 49 | 29 | 96 | 44
86 | 1.2.1.7.3.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 17 April 2024 8:00 AM | 22 April 2024 5:00 PM | 85,70 | 87 | - | - | 0 | Line Market | 0 | 56 | 21 | 86 | 21
87 | 1.2.1.7.3.4 | Base Course to Basement | 8 | 23 April 2024 8:00 AM | 2 May 2024 5:00 PM | 86 | 88 | - | - | 0 | Painter | 0 | 69 | 24 | 95 | 20
88 | 1.2.1.7.4 | Basement Earthworks and Piling Complete | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 87,77 | 122,4 | - | - | 0 | Concretor | 0 | 33 | 29 | 65 | 33
89 | 1.2.2 | STRUCTURE WORKS | 217 | 11 April 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 93 | 29 | 22 | 38
90 | 1.2.2.1 | CC2 - Basement to Podium L1 - A, B, C, D | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  |  | - | - | 0 | Line Market | 0 | 70 | 28 | 43 | 3
91 | 1.2.2.1.1 | Basement to Podium (Level 1 - A & B ) | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | - | - | 0 | Development Manager | 0 | 91 | 25 | 80 | 35
92 | 1.2.2.1.1.1 | Basement 2 - FRP - SoG | 23 | 11 April 2024 8:00 AM | 8 May 2024 5:00 PM |  |  | - | - | 0 | Cleaner | 0 | 34 | 10 | 40 | 32
93 | 1.2.2.1.1.1.1 | Reinforcement Fix | 13 | 11 April 2024 8:00 AM | 26 April 2024 5:00 PM | 82 | 94 | - | - | 0 | Plumber | 0 | 37 | 26 | 87 | 37
94 | 1.2.2.1.1.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 9 | 27 April 2024 8:00 AM | 7 May 2024 5:00 PM | 93 | 95 | - | - | 0 | Stone Mason | 0 | 60 | 20 | 3 | 24
95 | 1.2.2.1.1.1.3 | Pour | 1 | 8 May 2024 8:00 AM | 8 May 2024 5:00 PM | 94 | 97 | - | - | 0 | Landscaper | 0 | 98 | 22 | 82 | 45
96 | 1.2.2.1.1.2 | Basement 1 - FRP - Suspended Slab | 25 | 9 May 2024 8:00 AM | 6 June 2024 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 75 | 17 | 82 | 59
97 | 1.2.2.1.1.2.1 | Scaffold Stair Removal/Adjustment | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 95 | 98SS | - | - | 0 | Subcontractor | 0 | 51 | 34 | 11 | 7
98 | 1.2.2.1.1.2.2 | Setout and Install Lift/Stair Formwork | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 97SS | 99 | - | - | 0 | Plasterboarder | 0 | 96 | 21 | 14 | 41
99 | 1.2.2.1.1.2.3 | Formworker setout, drop material and 80% Deck | 9 | 11 May 2024 8:00 AM | 21 May 2024 5:00 PM | 98 | 100FS-1d,101 | - | - | 0 | Formworker | 0 | 12 | 19 | 62 | 33
100 | 1.2.2.1.1.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 21 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99FS-1d | 102,103 | - | - | 0 | Plumber | 0 | 10 | 19 | 40 | 37
101 | 1.2.2.1.1.2.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 22 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99 |  | - | - | 0 | Painter | 0 | 61 | 13 | 13 | 59
102 | 1.2.2.1.1.2.6 | Services | 4 | 25 May 2024 8:00 AM | 29 May 2024 5:00 PM | 100 | 104FS-1d | - | - | 0 | Reinforcement Fixer | 0 | 88 | 28 | 69 | 29
103 | 1.2.2.1.1.2.7 | Post Tension | 3 | 25 May 2024 8:00 AM | 28 May 2024 5:00 PM | 100 | 104FS-1d | - | - | 0 | Plasterboarder | 0 | 79 | 33 | 69 | 19
104 | 1.2.2.1.1.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 29 May 2024 8:00 AM | 31 May 2024 5:00 PM | 102FS-1d,103FS-1d | 105 | - | - | 0 | Admin | 0 | 45 | 32 | 46 | 47
105 | 1.2.2.1.1.2.9 | Formworker setdowns and edge boards | 4 | 1 June 2024 8:00 AM | 5 June 2024 5:00 PM | 104 | 106 | - | - | 0 | Window | 0 | 27 | 12 | 89 | 21
106 | 1.2.2.1.1.2.10 | Pour | 1 | 6 June 2024 8:00 AM | 6 June 2024 5:00 PM | 105 | 109 | - | - | 0 | Mechanical | 0 | 99 | 23 | 73 | 48
107 | 1.2.2.1.1.3 | Strip Formwork - Basement 1 | 5 | 7 September 2024 8:00 AM | 12 September 2024 5:00 PM | 161FS+5d | 522 | - | - | 0 | Contract Administrator | 0 | 99 | 26 | 5 | 2
108 | 1.2.2.1.1.4 | Lvl 1 - FRP - Suspended Slab | 28 | 7 June 2024 8:00 AM | 11 July 2024 5:00 PM |  |  | - | - | 0 | Plasterboarder | 0 | 26 | 32 | 4 | 10
109 | 1.2.2.1.1.4.1 | Scaffold Stair Removal/Adjustment | 1 | 7 June 2024 8:00 AM | 7 June 2024 5:00 PM | 106 | 110SS | - | - | 0 | Surveyor | 0 | 68 | 27 | 6 | 52
110 | 1.2.2.1.1.4.2 | Setout and Install Lift/Stair Formwork | 3 | 7 June 2024 8:00 AM | 12 June 2024 5:00 PM | 109SS | 111 | - | - | 0 | Metal Work | 0 | 36 | 18 | 80 | 49
111 | 1.2.2.1.1.4.3 | Formworker setout, drop material and 80% Deck | 10 | 13 June 2024 8:00 AM | 24 June 2024 5:00 PM | 110 | 112FS-1d,113,128 | - | - | 0 | Project Manager | 0 | 24 | 10 | 65 | 53
112 | 1.2.2.1.1.4.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 6 | 24 June 2024 8:00 AM | 29 June 2024 5:00 PM | 111FS-1d | 114,115 | - | - | 0 | Renderer | 0 | 24 | 12 | 4 | 18
113 | 1.2.2.1.1.4.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 25 June 2024 8:00 AM | 28 June 2024 5:00 PM | 111 | 118 | - | - | 0 | Tiler | 0 | 77 | 13 | 3 | 4
114 | 1.2.2.1.1.4.6 | Services | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 112 | 116FS-1d | - | - | 0 | Carpet | 0 | 45 | 11 | 23 | 33
115 | 1.2.2.1.1.4.7 | Post Tension | 4 | 1 July 2024 8:00 AM | 4 July 2024 5:00 PM | 112 | 116FS-1d | - | - | 0 | Reinforcement Fixer | 0 | 69 | 14 | 14 | 45
116 | 1.2.2.1.1.4.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 114FS-1d,115FS-1d | 117,401FS+5d | - | - | 0 | Carpet | 0 | 54 | 32 | 56 | 47
117 | 1.2.2.1.1.4.9 | Formworker setdowns and edge boards | 3 | 8 July 2024 8:00 AM | 10 July 2024 5:00 PM | 116 | 118 | - | - | 0 | Carpenter | 0 | 47 | 27 | 60 | 5
118 | 1.2.2.1.1.4.10 | Pour | 1 | 11 July 2024 8:00 AM | 11 July 2024 5:00 PM | 117,113 | 140 | - | - | 0 | Carpet | 0 | 52 | 13 | 56 | 16
119 | 1.2.2.1.1.5 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d | 535 | - | - | 0 | Painter | 0 | 99 | 22 | 40 | 25
120 | 1.2.2.1.2 | Basement to Podium (Level 1 - C & D) | 127 | 3 May 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | - | - | 0 | Concretor | 0 | 80 | 34 | 63 | 14
121 | 1.2.2.1.2.1 | Basement 2 - FRP - SoG | 12 | 3 May 2024 8:00 AM | 16 May 2024 5:00 PM |  |  | - | - | 0 | Subcontractor | 0 | 28 | 23 | 64 | 48
122 | 1.2.2.1.2.1.1 | Reinforcement Fix | 6 | 3 May 2024 8:00 AM | 9 May 2024 5:00 PM | 88 | 123 | - | - | 0 | Cleaner | 0 | 44 | 26 | 11 | 5
123 | 1.2.2.1.2.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 5 | 10 May 2024 8:00 AM | 15 May 2024 5:00 PM | 122 | 124 | - | - | 0 | Line Market | 0 | 53 | 21 | 24 | 48
124 | 1.2.2.1.2.1.3 | Pour | 1 | 16 May 2024 8:00 AM | 16 May 2024 5:00 PM | 123 | 126 | - | - | 0 | Stone Mason | 0 | 39 | 27 | 43 | 48
125 | 1.2.2.1.2.2 | Lvl 1 - FRP - Suspended Slab | 48 | 17 May 2024 8:00 AM | 13 July 2024 5:00 PM |  |  | - | - | 0 | Plasterboarder | 0 | 18 | 25 | 20 | 29
126 | 1.2.2.1.2.2.1 | Scaffold Stair Removal/Adjustment | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 124 | 127SS | - | - | 0 | Foreman | 0 | 82 | 25 | 6 | 25
127 | 1.2.2.1.2.2.2 | Setout and Install Lift/Stair Formwork | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 126SS | 128 | - | - | 0 | Plasterboarder | 0 | 82 | 10 | 14 | 31
128 | 1.2.2.1.2.2.3 | Formworker setout, drop material and 80% Deck | 6 | 25 June 2024 8:00 AM | 1 July 2024 5:00 PM | 127,111 | 129FS-1d,130 | - | - | 0 | Electrician | 0 | 13 | 32 | 94 | 17
129 | 1.2.2.1.2.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128FS-1d | 131,132 | - | - | 0 | Project Manager | 0 | 63 | 18 | 49 | 36
130 | 1.2.2.1.2.2.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128 |  | - | - | 0 | Waterproofer | 0 | 37 | 23 | 9 | 37
131 | 1.2.2.1.2.2.6 | Services | 2 | 4 July 2024 8:00 AM | 5 July 2024 5:00 PM | 129 | 133FS-1d | - | - | 0 | Window | 0 | 26 | 32 | 43 | 18
132 | 1.2.2.1.2.2.7 | Post Tension | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 129 | 133FS-1d | - | - | 0 | Line Market | 0 | 31 | 29 | 60 | 39
133 | 1.2.2.1.2.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 6 July 2024 8:00 AM | 9 July 2024 5:00 PM | 131FS-1d,132FS-1d | 134 | - | - | 0 | Line Market | 0 | 24 | 13 | 97 | 51
134 | 1.2.2.1.2.2.9 | Formworker setdowns and edge boards | 3 | 10 July 2024 8:00 AM | 12 July 2024 5:00 PM | 133 | 135 | - | - | 0 | Concretor | 0 | 76 | 31 | 78 | 40
135 | 1.2.2.1.2.2.10 | Pour | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 134 | 309,233 | - | - | 0 | Cleaner | 0 | 60 | 25 | 97 | 51
136 | 1.2.2.1.2.3 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d |  | - | - | 0 | Mechanical | 0 | 87 | 20 | 70 | 35
137 | 1.2.2.2 | CC3 - Remainder of Structure | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 11 | 12 | 74 | 43
138 | 1.2.2.2.1 | Building A | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | - | - | 0 | Landscaper | 0 | 73 | 35 | 83 | 56
139 | 1.2.2.2.1.1 | Lvl 2 - FRP - Suspended Slab | 26 | 12 July 2024 8:00 AM | 10 August 2024 5:00 PM |  |  | - | - | 0 | Reinforcement Fixer | 0 | 12 | 14 | 16 | 47
140 | 1.2.2.2.1.1.1 | Scaffold Perimeter Protection | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 118 | 141SS | - | - | 0 | Tiler | 0 | 71 | 20 | 3 | 30
141 | 1.2.2.2.1.1.2 | Setout and Install Lift/Stair Formwork | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 140SS | 142 | - | - | 0 | Reinforcement Fixer | 0 | 14 | 28 | 59 | 28
142 | 1.2.2.2.1.1.3 | Formworker setout, drop material and 80% Deck | 6 | 17 July 2024 8:00 AM | 23 July 2024 5:00 PM | 141 | 143FS-1d,144 | - | - | 0 | Painter | 0 | 95 | 28 | 48 | 32
143 | 1.2.2.2.1.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 23 July 2024 8:00 AM | 26 July 2024 5:00 PM | 142FS-1d | 145,146 | - | - | 0 | Window | 0 | 44 | 17 | 30 | 18
144 | 1.2.2.2.1.1.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 24 July 2024 8:00 AM | 27 July 2024 5:00 PM | 142 | 146 | - | - | 0 | Post Tension | 0 | 33 | 15 | 46 | 15
145 | 1.2.2.2.1.1.6 | Services | 3 | 27 July 2024 8:00 AM | 30 July 2024 5:00 PM | 143 | 147FS-1d | - | - | 0 | Painter | 0 | 53 | 18 | 21 | 10
146 | 1.2.2.2.1.1.7 | Post Tension | 3 | 29 July 2024 8:00 AM | 31 July 2024 5:00 PM | 143,144 | 147FS-1d | - | - | 0 | Window | 0 | 84 | 29 | 22 | 37
147 | 1.2.2.2.1.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 5 | 31 July 2024 8:00 AM | 5 August 2024 5:00 PM | 145FS-1d,146FS-1d | 148 | - | - | 0 | Foreman | 0 | 72 | 23 | 63 | 47
148 | 1.2.2.2.1.1.9 | Formworker setdowns and edge boards | 4 | 6 August 2024 8:00 AM | 9 August 2024 5:00 PM | 147 | 149 | - | - | 0 | Excavation | 0 | 16 | 12 | 86 | 43
149 | 1.2.2.2.1.1.10 | Pour | 1 | 10 August 2024 8:00 AM | 10 August 2024 5:00 PM | 148 | 152,407FS+5d | - | - | 0 | Fire | 0 | 26 | 31 | 7 | 44
150 | 1.2.2.2.1.2 | Strip Formwork - Lvl 2 | 5 | 15 October 2024 8:00 AM | 19 October 2024 5:00 PM | 185FS+5d | 577,550,409FS-10d | - | - | 0 | Window | 0 | 21 | 32 | 33 | 50
151 | 1.2.2.2.1.3 | Lvl 3 - FRP - Suspended Slab | 18 | 12 August 2024 8:00 AM | 31 August 2024 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 54 | 21 | 84 | 43
152 | 1.2.2.2.1.3.1 | Scaffold Perimeter Protection | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 149 | 153SS | - | - | 0 | Project Manager | 0 | 73 | 26 | 14 | 53
153 | 1.2.2.2.1.3.2 | Setout and Install Lift/Stair Formwork | 1 | 12 August 2024 8:00 AM | 12 August 2024 5:00 PM | 152SS | 154 | - | - | 0 | Waterproofer | 0 | 58 | 15 | 65 | 49
154 | 1.2.2.2.1.3.3 | Formworker setout, drop material and 80% Deck | 6 | 13 August 2024 8:00 AM | 19 August 2024 5:00 PM | 153 | 155FS-1d,156 | - | - | 0 | Formworker | 0 | 67 | 27 | 20 | 11
155 | 1.2.2.2.1.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 19 August 2024 8:00 AM | 22 August 2024 5:00 PM | 154FS-1d | 157,158 | - | - | 0 | Tiler | 0 | 53 | 28 | 80 | 13
156 | 1.2.2.2.1.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 August 2024 8:00 AM | 21 August 2024 5:00 PM | 154 |  | - | - | 0 | Hoarding | 0 | 21 | 13 | 70 | 55
157 | 1.2.2.2.1.3.6 | Services | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | - | - | 0 | Mechanical | 0 | 92 | 26 | 26 | 24
158 | 1.2.2.2.1.3.7 | Post Tension | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | - | - | 0 | Development Manager | 0 | 15 | 22 | 3 | 14
159 | 1.2.2.2.1.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 24 August 2024 8:00 AM | 27 August 2024 5:00 PM | 157FS-1d,158FS-1d | 160 | - | - | 0 | Cleaner | 0 | 66 | 20 | 3 | 40
160 | 1.2.2.2.1.3.9 | Formworker setdowns and edge boards | 3 | 28 August 2024 8:00 AM | 30 August 2024 5:00 PM | 159 | 161 | - | - | 0 | Electrician | 0 | 93 | 10 | 18 | 18
161 | 1.2.2.2.1.3.10 | Pour | 1 | 31 August 2024 8:00 AM | 31 August 2024 5:00 PM | 160 | 164,3445,107FS+5d | - | - | 0 | Floor Sealer | 0 | 31 | 34 | 93 | 35
162 | 1.2.2.2.1.4 | Strip Formwork - Lvl 3 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d |  | - | - | 0 | Timber Floorer | 0 | 39 | 21 | 97 | 12
163 | 1.2.2.2.1.5 | Lvl 4 - FRP - Suspended Slab | 15 | 2 September 2024 8:00 AM | 18 September 2024 5:00 PM |  |  | - | - | 0 | Window | 0 | 68 | 18 | 31 | 45
164 | 1.2.2.2.1.5.1 | Scaffold Perimeter Protection | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 161 | 165SS | - | - | 0 | Joiner | 0 | 10 | 20 | 38 | 32
165 | 1.2.2.2.1.5.2 | Setout and Install Lift/Stair Formwork | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 164SS | 166FS-1d | - | - | 0 | Foreman | 0 | 66 | 15 | 38 | 18
166 | 1.2.2.2.1.5.3 | Formworker setout, drop material and 80% Deck | 6 | 2 September 2024 8:00 AM | 7 September 2024 5:00 PM | 165FS-1d | 167FS-1d,168 | - | - | 0 | Head Contractor | 0 | 58 | 28 | 78 | 49
167 | 1.2.2.2.1.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 7 September 2024 8:00 AM | 11 September 2024 5:00 PM | 166FS-1d | 169,170 | - | - | 0 | Landscaper | 0 | 76 | 13 | 63 | 35
168 | 1.2.2.2.1.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 9 September 2024 8:00 AM | 10 September 2024 5:00 PM | 166 |  | - | - | 0 | Timber Floorer | 0 | 98 | 12 | 53 | 38
169 | 1.2.2.2.1.5.6 | Services | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | - | - | 0 | Surveyor | 0 | 17 | 11 | 21 | 54
170 | 1.2.2.2.1.5.7 | Post Tension | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | - | - | 0 | Reinforcement Fixer | 0 | 25 | 20 | 49 | 38
171 | 1.2.2.2.1.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 13 September 2024 8:00 AM | 14 September 2024 5:00 PM | 169FS-1d,170FS-1d | 172 | - | - | 0 | Fire | 0 | 35 | 30 | 29 | 49
172 | 1.2.2.2.1.5.9 | Formworker setdowns and edge boards | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 171 | 173 | - | - | 0 | Floor Sealer | 0 | 27 | 30 | 28 | 15
173 | 1.2.2.2.1.5.10 | Pour | 1 | 18 September 2024 8:00 AM | 18 September 2024 5:00 PM | 172 | 176,119FS+5d,136FS+5d | - | - | 0 | Surveyor | 0 | 57 | 28 | 17 | 22
174 | 1.2.2.2.1.6 | Strip Formwork - Lvl 4 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d | 413FS+5d,604,415FS-10d | - | - | 0 | Window | 0 | 35 | 12 | 75 | 30
175 | 1.2.2.2.1.7 | Lvl 5 - FRP - Suspended Slab | 15 | 19 September 2024 8:00 AM | 8 October 2024 5:00 PM |  |  | - | - | 0 | Site Manager | 0 | 26 | 15 | 40 | 9
176 | 1.2.2.2.1.7.1 | Scaffold Perimeter Protection | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 173 | 177SS | - | - | 0 | Joiner | 0 | 73 | 35 | 64 | 7
177 | 1.2.2.2.1.7.2 | Setout and Install Lift/Stair Formwork | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 176SS | 178FS-1d | - | - | 0 | Tiler | 0 | 57 | 35 | 77 | 60
178 | 1.2.2.2.1.7.3 | Formworker setout, drop material and 80% Deck | 6 | 19 September 2024 8:00 AM | 25 September 2024 5:00 PM | 177FS-1d | 179FS-1d,180 | - | - | 0 | Post Tension | 0 | 69 | 28 | 4 | 37
179 | 1.2.2.2.1.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 25 September 2024 8:00 AM | 28 September 2024 5:00 PM | 178FS-1d | 181,182 | - | - | 0 | Tiler | 0 | 82 | 23 | 80 | 49
180 | 1.2.2.2.1.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 26 September 2024 8:00 AM | 27 September 2024 5:00 PM | 178 |  | - | - | 0 | Floor Sealer | 0 | 20 | 20 | 13 | 34
181 | 1.2.2.2.1.7.6 | Services | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | - | - | 0 | Landscaper | 0 | 68 | 32 | 14 | 18
182 | 1.2.2.2.1.7.7 | Post Tension | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | - | - | 0 | Electrician | 0 | 47 | 25 | 79 | 6
183 | 1.2.2.2.1.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 1 October 2024 8:00 AM | 2 October 2024 5:00 PM | 181FS-1d,182FS-1d | 184 | - | - | 0 | Painter | 0 | 57 | 35 | 71 | 3
184 | 1.2.2.2.1.7.9 | Formworker setdowns and edge boards | 2 | 3 October 2024 8:00 AM | 4 October 2024 5:00 PM | 183 | 185 | - | - | 0 | Concretor | 0 | 44 | 21 | 46 | 43
185 | 1.2.2.2.1.7.10 | Pour | 1 | 8 October 2024 8:00 AM | 8 October 2024 5:00 PM | 184 | 188,150FS+5d | - | - | 0 | Subcontractor | 0 | 40 | 28 | 7 | 21
186 | 1.2.2.2.1.8 | Strip Formwork - Lvl 5 | 5 | 5 December 2024 8:00 AM | 10 December 2024 5:00 PM | 221FS+5d | 631,421FS-10d,419FS+5d | - | - | 0 | Carpet | 0 | 89 | 33 | 25 | 12
187 | 1.2.2.2.1.9 | Lvl 6 - FRP - Suspended Slab | 15 | 9 October 2024 8:00 AM | 25 October 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 76 | 24 | 22 | 41
188 | 1.2.2.2.1.9.1 | Scaffold Perimeter Protection | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 185 | 189SS | - | - | 0 | Contract Administrator | 0 | 80 | 11 | 28 | 60
189 | 1.2.2.2.1.9.2 | Setout and Install Lift/Stair Formwork | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 188SS | 190FS-1d | - | - | 0 | Mechanical | 0 | 34 | 19 | 68 | 34
190 | 1.2.2.2.1.9.3 | Formworker setout, drop material and 80% Deck | 6 | 9 October 2024 8:00 AM | 15 October 2024 5:00 PM | 189FS-1d | 191FS-1d,192 | - | - | 0 | Concretor | 0 | 84 | 24 | 74 | 20
191 | 1.2.2.2.1.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 October 2024 8:00 AM | 18 October 2024 5:00 PM | 190FS-1d | 193,194 | - | - | 0 | Carpenter | 0 | 24 | 23 | 15 | 58
192 | 1.2.2.2.1.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 190 |  | - | - | 0 | Waterproofer | 0 | 80 | 33 | 92 | 10
193 | 1.2.2.2.1.9.6 | Services | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | - | - | 0 | Floor Sealer | 0 | 62 | 13 | 93 | 12
194 | 1.2.2.2.1.9.7 | Post Tension | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | - | - | 0 | Landscaper | 0 | 10 | 13 | 44 | 45
195 | 1.2.2.2.1.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 193FS-1d,194FS-1d | 196 | - | - | 0 | Contract Administrator | 0 | 62 | 20 | 76 | 15
196 | 1.2.2.2.1.9.9 | Formworker setdowns and edge boards | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 195 | 197 | - | - | 0 | Reinforcement Fixer | 0 | 79 | 25 | 61 | 55
197 | 1.2.2.2.1.9.10 | Pour | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 196 | 200 | - | - | 0 | Electrician | 0 | 11 | 23 | 50 | 58
198 | 1.2.2.2.1.10 | Strip Formwork - Lvl 6 | 5 | 6 December 2024 8:00 AM | 11 December 2024 5:00 PM | 225 | 657,425FS+5d,427FS-10d | - | - | 0 | Hoarding | 0 | 71 | 25 | 70 | 38
199 | 1.2.2.2.1.11 | Lvl 7 - FRP - Suspended Slab | 15 | 26 October 2024 8:00 AM | 12 November 2024 5:00 PM |  |  | - | - | 0 | Subcontractor | 0 | 19 | 30 | 10 | 19
200 | 1.2.2.2.1.11.1 | Scaffold Perimeter Protection | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 197 | 201SS | - | - | 0 | Metal Work | 0 | 36 | 21 | 71 | 55
201 | 1.2.2.2.1.11.2 | Setout and Install Lift/Stair Formwork | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 200SS | 202FS-1d | - | - | 0 | Concretor | 0 | 62 | 30 | 36 | 14
202 | 1.2.2.2.1.11.3 | Formworker setout, drop material and 80% Deck | 6 | 26 October 2024 8:00 AM | 1 November 2024 5:00 PM | 201FS-1d | 203FS-1d,204 | - | - | 0 | Concretor | 0 | 93 | 27 | 83 | 45
203 | 1.2.2.2.1.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 1 November 2024 8:00 AM | 5 November 2024 5:00 PM | 202FS-1d | 205,206 | - | - | 0 | Project Manager | 0 | 20 | 35 | 85 | 35
204 | 1.2.2.2.1.11.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 202 |  | - | - | 0 | Painter | 0 | 59 | 20 | 40 | 17
205 | 1.2.2.2.1.11.6 | Services | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | - | - | 0 | Plasterboarder | 0 | 67 | 31 | 58 | 14
206 | 1.2.2.2.1.11.7 | Post Tension | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | - | - | 0 | Admin | 0 | 58 | 31 | 82 | 23
207 | 1.2.2.2.1.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 205FS-1d,206FS-1d | 208 | - | - | 0 | Excavation | 0 | 100 | 17 | 22 | 16
208 | 1.2.2.2.1.11.9 | Formworker setdowns and edge boards | 2 | 9 November 2024 8:00 AM | 11 November 2024 5:00 PM | 207 | 209 | - | - | 0 | Subcontractor | 0 | 11 | 14 | 24 | 9
209 | 1.2.2.2.1.11.10 | Pour | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 208 | 212,162FS+5d,174FS+5d,431FS+5d | - | - | 0 | Carpenter | 0 | 31 | 22 | 62 | 46
210 | 1.2.2.2.1.12 | Strip Formwork - Lvl 7 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 225FS+5d | 690,432FS-10d | - | - | 0 | Concretor | 0 | 70 | 20 | 35 | 15
211 | 1.2.2.2.1.13 | Lvl 8 (Roof) - FRP - Suspended Slab | 14 | 13 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 56 | 10 | 95 | 37
212 | 1.2.2.2.1.13.1 | Scaffold Perimeter Protection | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 209 | 213SS | - | - | 0 | Electrician | 0 | 10 | 17 | 73 | 54
213 | 1.2.2.2.1.13.2 | Setout and Install Lift/Stair Formwork | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 212SS | 214FS-1d | - | - | 0 | Joiner | 0 | 50 | 21 | 64 | 35
214 | 1.2.2.2.1.13.3 | Formworker setout, drop material and 80% Deck | 6 | 13 November 2024 8:00 AM | 19 November 2024 5:00 PM | 213FS-1d | 215FS-1d,216 | - | - | 0 | Cleaner | 0 | 85 | 11 | 3 | 54
215 | 1.2.2.2.1.13.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214FS-1d | 217,218 | - | - | 0 | Timber Floorer | 0 | 10 | 22 | 18 | 31
216 | 1.2.2.2.1.13.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214 |  | - | - | 0 | Mechanical | 0 | 47 | 25 | 6 | 48
217 | 1.2.2.2.1.13.6 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | - | - | 0 | Contract Administrator | 0 | 90 | 13 | 59 | 43
218 | 1.2.2.2.1.13.7 | Post Tension | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | - | - | 0 | Stone Mason | 0 | 87 | 12 | 15 | 58
219 | 1.2.2.2.1.13.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 217FS-1d,218FS-1d | 220 | - | - | 0 | Surveyor | 0 | 68 | 28 | 31 | 3
220 | 1.2.2.2.1.13.9 | Formworker setdowns and edge boards | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 219 | 221 | - | - | 0 | Renderer | 0 | 36 | 10 | 44 | 53
221 | 1.2.2.2.1.13.10 | Pour - Structure Top Out | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 220 | 223FS+12d,222,225,186FS+5d,437FS+5d | - | - | 0 | Admin | 0 | 50 | 23 | 37 | 5
222 | 1.2.2.2.1.13.11 | Structure Top Out | 0 | 28 November 2024 5:00 PM | 28 November 2024 5:00 PM | 221 |  | - | - | 0 | Head Contractor | 0 | 92 | 22 | 2 | 16
223 | 1.2.2.2.1.14 | Strip Formwork - Lvl 8 | 4 | 13 December 2024 8:00 AM | 17 December 2024 5:00 PM | 221FS+12d | 716,439FS+10d | - | - | 0 | Development Manager | 0 | 46 | 11 | 45 | 57
224 | 1.2.2.2.1.15 | Lift Shaft | 23 | 29 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | - | - | 0 | Plasterboarder | 0 | 69 | 14 | 89 | 28
225 | 1.2.2.2.1.15.1 | FRP Lift Over-run | 6 | 29 November 2024 8:00 AM | 5 December 2024 5:00 PM | 221 | 226FS+5d,228,198,210FS+5d | - | - | 0 | Cleaner | 0 | 88 | 16 | 77 | 14
226 | 1.2.2.2.1.15.2 | Strip Lift Shaft Formwork | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 225FS+5d | 227 | - | - | 0 | Contract Administrator | 0 | 31 | 32 | 89 | 37
227 | 1.2.2.2.1.15.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 17 December 2024 8:00 AM | 3 January 2025 5:00 PM | 226 | 3451 | - | - | 0 | Timber Floorer | 0 | 84 | 21 | 61 | 25
228 | 1.2.2.2.1.15.4 | Building A Structure Complete | 0 | 5 December 2024 5:00 PM | 5 December 2024 5:00 PM | 225 | 6 | - | - | 0 | Reinforcement Fixer | 0 | 25 | 33 | 88 | 26
229 | 1.2.2.2.2 | Building B | 119 | 13 July 2024 8:00 AM | 30 November 2024 5:00 PM |  | 397 | - | - | 0 | Head Contractor | 0 | 77 | 13 | 22 | 10
230 | 1.2.2.2.2.1 | Lvl 2 - FRP - Suspended Slab | 18 | 13 July 2024 8:00 AM | 2 August 2024 5:00 PM |  |  | - | - | 0 | Plumber | 0 | 87 | 16 | 16 | 19
231 | 1.2.2.2.2.1.1 | Scaffold Perimeter Protection | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 232SS |  | - | - | 0 | Window | 0 | 85 | 14 | 22 | 16
232 | 1.2.2.2.2.1.2 | Setout and Install Lift/Stair Formwork | 1 | 13 July 2024 8:00 AM | 15 July 2024 8:00 AM | 233SF | 231SS | - | - | 0 | Plumber | 0 | 42 | 23 | 34 | 45
233 | 1.2.2.2.2.1.3 | Formworker setout, drop material and 80% Deck | 6 | 15 July 2024 8:00 AM | 20 July 2024 5:00 PM | 135 | 234FS-1d,235,232SF | - | - | 0 | Joiner | 0 | 74 | 21 | 8 | 18
234 | 1.2.2.2.2.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 20 July 2024 8:00 AM | 24 July 2024 5:00 PM | 233FS-1d | 236,237 | - | - | 0 | Subcontractor | 0 | 14 | 23 | 99 | 27
235 | 1.2.2.2.2.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 22 July 2024 8:00 AM | 23 July 2024 5:00 PM | 233 |  | - | - | 0 | Floor Sealer | 0 | 86 | 32 | 8 | 43
236 | 1.2.2.2.2.1.6 | Services | 2 | 25 July 2024 8:00 AM | 26 July 2024 5:00 PM | 234 | 238FS-1d | - | - | 0 | Excavation | 0 | 81 | 28 | 46 | 3
237 | 1.2.2.2.2.1.7 | Post Tension | 3 | 25 July 2024 8:00 AM | 27 July 2024 5:00 PM | 234 | 238FS-1d | - | - | 0 | Floor Sealer | 0 | 16 | 12 | 9 | 57
238 | 1.2.2.2.2.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 27 July 2024 8:00 AM | 29 July 2024 5:00 PM | 236FS-1d,237FS-1d | 239 | - | - | 0 | Plumber | 0 | 18 | 35 | 80 | 35
239 | 1.2.2.2.2.1.9 | Formworker setdowns and edge boards | 3 | 30 July 2024 8:00 AM | 1 August 2024 5:00 PM | 238 | 240 | - | - | 0 | Hoarding | 0 | 71 | 33 | 37 | 2
240 | 1.2.2.2.2.1.10 | Pour | 1 | 2 August 2024 8:00 AM | 2 August 2024 5:00 PM | 239 | 243,309FS+30d | - | - | 0 | Hoarding | 0 | 51 | 13 | 53 | 60
241 | 1.2.2.2.2.2 | Strip Formwork - Lvl 2 | 5 | 28 September 2024 8:00 AM | 3 October 2024 5:00 PM | 276 | 447 | - | - | 0 | Excavation | 0 | 46 | 22 | 79 | 17
242 | 1.2.2.2.2.3 | Lvl 3 - FRP - Suspended Slab | 18 | 3 August 2024 8:00 AM | 23 August 2024 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 29 | 17 | 51 | 21
243 | 1.2.2.2.2.3.1 | Scaffold Perimeter Protection | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 240 | 244SS | - | - | 0 | Concretor | 0 | 80 | 10 | 4 | 48
244 | 1.2.2.2.2.3.2 | Setout and Install Lift/Stair Formwork | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 243SS | 245 | - | - | 0 | Surveyor | 0 | 66 | 32 | 67 | 54
245 | 1.2.2.2.2.3.3 | Formworker setout, drop material and 80% Deck | 6 | 5 August 2024 8:00 AM | 10 August 2024 5:00 PM | 244 | 246FS-1d,247 | - | - | 0 | Admin | 0 | 79 | 17 | 61 | 51
246 | 1.2.2.2.2.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 10 August 2024 8:00 AM | 14 August 2024 5:00 PM | 245FS-1d | 248,249 | - | - | 0 | Carpenter | 0 | 11 | 32 | 17 | 27
247 | 1.2.2.2.2.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 245 |  | - | - | 0 | Floor Sealer | 0 | 96 | 23 | 80 | 13
248 | 1.2.2.2.2.3.6 | Services | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | - | - | 0 | Carpet | 0 | 11 | 12 | 82 | 25
249 | 1.2.2.2.2.3.7 | Post Tension | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | - | - | 0 | Concretor | 0 | 11 | 13 | 70 | 46
250 | 1.2.2.2.2.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 16 August 2024 8:00 AM | 19 August 2024 5:00 PM | 248FS-1d,249FS-1d | 251 | - | - | 0 | Admin | 0 | 89 | 25 | 72 | 5
251 | 1.2.2.2.2.3.9 | Formworker setdowns and edge boards | 3 | 20 August 2024 8:00 AM | 22 August 2024 5:00 PM | 250 | 252 | - | - | 0 | Plumber | 0 | 62 | 24 | 40 | 50
252 | 1.2.2.2.2.3.10 | Pour | 1 | 23 August 2024 8:00 AM | 23 August 2024 5:00 PM | 251 | 255,3447 | - | - | 0 | Fire | 0 | 61 | 12 | 16 | 54
253 | 1.2.2.2.2.4 | Strip Formwork - Lvl 3 | 5 | 21 October 2024 8:00 AM | 25 October 2024 5:00 PM | 288 | 453,1605 | - | - | 0 | Scaffolder | 0 | 77 | 24 | 57 | 27
254 | 1.2.2.2.2.5 | Lvl 4 - FRP - Suspended Slab | 15 | 24 August 2024 8:00 AM | 10 September 2024 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 12 | 14 | 47 | 13
255 | 1.2.2.2.2.5.1 | Scaffold Perimeter Protection | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 252 | 256SS | - | - | 0 | Foreman | 0 | 89 | 31 | 19 | 29
256 | 1.2.2.2.2.5.2 | Setout and Install Lift/Stair Formwork | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 255SS | 257FS-1d | - | - | 0 | Project Manager | 0 | 10 | 25 | 31 | 6
257 | 1.2.2.2.2.5.3 | Formworker setout, drop material and 80% Deck | 6 | 24 August 2024 8:00 AM | 30 August 2024 5:00 PM | 256FS-1d | 258FS-1d,259 | - | - | 0 | Excavation | 0 | 85 | 19 | 29 | 5
258 | 1.2.2.2.2.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 30 August 2024 8:00 AM | 3 September 2024 5:00 PM | 257FS-1d | 260,261 | - | - | 0 | Fire | 0 | 29 | 11 | 0 | 12
259 | 1.2.2.2.2.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 31 August 2024 8:00 AM | 2 September 2024 5:00 PM | 257 |  | - | - | 0 | Plumber | 0 | 50 | 33 | 57 | 59
260 | 1.2.2.2.2.5.6 | Services | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | - | - | 0 | Foreman | 0 | 27 | 10 | 80 | 55
261 | 1.2.2.2.2.5.7 | Post Tension | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | - | - | 0 | Waterproofer | 0 | 44 | 23 | 67 | 32
262 | 1.2.2.2.2.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 5 September 2024 8:00 AM | 6 September 2024 5:00 PM | 260FS-1d,261FS-1d | 263 | - | - | 0 | Admin | 0 | 23 | 10 | 1 | 20
263 | 1.2.2.2.2.5.9 | Formworker setdowns and edge boards | 2 | 7 September 2024 8:00 AM | 9 September 2024 5:00 PM | 262 | 264 | - | - | 0 | Window | 0 | 27 | 14 | 19 | 15
264 | 1.2.2.2.2.5.10 | Pour | 1 | 10 September 2024 8:00 AM | 10 September 2024 5:00 PM | 263 | 267 | - | - | 0 | Plasterboarder | 0 | 30 | 26 | 100 | 18
265 | 1.2.2.2.2.6 | Strip Formwork - Lvl 4 | 5 | 11 November 2024 8:00 AM | 15 November 2024 5:00 PM | 300 | 459,1632 | - | - | 0 | Carpet | 0 | 55 | 27 | 95 | 24
266 | 1.2.2.2.2.7 | Lvl 5 - FRP - Suspended Slab | 15 | 11 September 2024 8:00 AM | 27 September 2024 5:00 PM |  |  | - | - | 0 | Plasterboarder | 0 | 41 | 16 | 55 | 29
267 | 1.2.2.2.2.7.1 | Scaffold Perimeter Protection | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 264 | 268SS | - | - | 0 | Carpet | 0 | 81 | 28 | 82 | 12
268 | 1.2.2.2.2.7.2 | Setout and Install Lift/Stair Formwork | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 267SS | 269FS-1d | - | - | 0 | Floor Sealer | 0 | 80 | 28 | 59 | 25
269 | 1.2.2.2.2.7.3 | Formworker setout, drop material and 80% Deck | 6 | 11 September 2024 8:00 AM | 17 September 2024 5:00 PM | 268FS-1d | 270FS-1d,271 | - | - | 0 | Excavation | 0 | 78 | 21 | 94 | 36
270 | 1.2.2.2.2.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 17 September 2024 8:00 AM | 20 September 2024 5:00 PM | 269FS-1d | 272,273 | - | - | 0 | Floor Sealer | 0 | 97 | 13 | 12 | 11
271 | 1.2.2.2.2.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 18 September 2024 8:00 AM | 19 September 2024 5:00 PM | 269 |  | - | - | 0 | Line Market | 0 | 16 | 21 | 10 | 43
272 | 1.2.2.2.2.7.6 | Services | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | - | - | 0 | Carpenter | 0 | 30 | 17 | 80 | 15
273 | 1.2.2.2.2.7.7 | Post Tension | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | - | - | 0 | Admin | 0 | 41 | 29 | 5 | 11
274 | 1.2.2.2.2.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 September 2024 8:00 AM | 24 September 2024 5:00 PM | 272FS-1d,273FS-1d | 275 | - | - | 0 | Plumber | 0 | 92 | 22 | 98 | 18
275 | 1.2.2.2.2.7.9 | Formworker setdowns and edge boards | 2 | 25 September 2024 8:00 AM | 26 September 2024 5:00 PM | 274 | 276 | - | - | 0 | Timber Floorer | 0 | 78 | 16 | 63 | 34
276 | 1.2.2.2.2.7.10 | Pour | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 275 | 279,241 | - | - | 0 | Site Manager | 0 | 89 | 22 | 17 | 56
277 | 1.2.2.2.2.8 | Strip Formwork - Lvl 5 | 5 | 18 November 2024 8:00 AM | 22 November 2024 5:00 PM | 303 | 465,1659 | - | - | 0 | Hoarding | 0 | 38 | 13 | 66 | 5
278 | 1.2.2.2.2.9 | Lvl 6 - FRP - Suspended Slab | 17 | 28 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | - | - | 0 | Joiner | 0 | 28 | 29 | 86 | 2
279 | 1.2.2.2.2.9.1 | Scaffold Perimeter Protection | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 276 | 280SS | - | - | 0 | Post Tension | 0 | 70 | 24 | 6 | 18
280 | 1.2.2.2.2.9.2 | Setout and Install Lift/Stair Formwork | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 279SS | 281FS-1d | - | - | 0 | Electrician | 0 | 19 | 31 | 15 | 47
281 | 1.2.2.2.2.9.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 280FS-1d | 282FS-1d,283 | - | - | 0 | Site Manager | 0 | 31 | 12 | 42 | 51
282 | 1.2.2.2.2.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 281FS-1d | 284,285 | - | - | 0 | Cleaner | 0 | 42 | 28 | 32 | 26
283 | 1.2.2.2.2.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 281 |  | - | - | 0 | Admin | 0 | 47 | 10 | 55 | 40
284 | 1.2.2.2.2.9.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | - | - | 0 | Concretor | 0 | 63 | 32 | 3 | 58
285 | 1.2.2.2.2.9.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | - | - | 0 | Mechanical | 0 | 80 | 33 | 84 | 46
286 | 1.2.2.2.2.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 284FS-1d,285FS-1d | 287 | - | - | 0 | Development Manager | 0 | 99 | 27 | 100 | 60
287 | 1.2.2.2.2.9.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 286 | 288 | - | - | 0 | Concretor | 0 | 37 | 21 | 13 | 42
288 | 1.2.2.2.2.9.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 287 | 291,253 | - | - | 0 | Head Contractor | 0 | 87 | 13 | 86 | 53
289 | 1.2.2.2.2.10 | Strip Formwork - Lvl 6 | 5 | 20 November 2024 8:00 AM | 25 November 2024 5:00 PM | 300FS+8d | 657,471,1686 | - | - | 0 | Window | 0 | 26 | 23 | 2 | 29
290 | 1.2.2.2.2.11 | Lvl 7 (Roof) - FRP - Suspended Slab | 18 | 21 October 2024 8:00 AM | 9 November 2024 5:00 PM |  |  | - | - | 0 | Stone Mason | 0 | 35 | 25 | 64 | 32
291 | 1.2.2.2.2.11.1 | Scaffold Perimeter Protection | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 288 | 292SS | - | - | 0 | Surveyor | 0 | 44 | 26 | 32 | 29
292 | 1.2.2.2.2.11.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 291SS | 293FS-1d | - | - | 0 | Carpenter | 0 | 23 | 12 | 54 | 58
293 | 1.2.2.2.2.11.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 292FS-1d | 294FS-1d,295 | - | - | 0 | Fire | 0 | 37 | 13 | 35 | 6
294 | 1.2.2.2.2.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293FS-1d | 296,297 | - | - | 0 | Foreman | 0 | 78 | 32 | 87 | 51
295 | 1.2.2.2.2.11.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 28 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293 |  | - | - | 0 | Plasterboarder | 0 | 96 | 29 | 13 | 42
296 | 1.2.2.2.2.11.6 | Services | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | - | - | 0 | Formworker | 0 | 17 | 19 | 46 | 16
297 | 1.2.2.2.2.11.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | - | - | 0 | Line Market | 0 | 25 | 30 | 95 | 16
298 | 1.2.2.2.2.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 296FS-1d,297FS-1d | 299 | - | - | 0 | Plasterboarder | 0 | 91 | 18 | 39 | 11
299 | 1.2.2.2.2.11.9 | Formworker setdowns and edge boards | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 298 | 300 | - | - | 0 | Electrician | 0 | 60 | 22 | 61 | 28
300 | 1.2.2.2.2.11.10 | Pour | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 299 | 303,289FS+8d,301FS+12d,1739FS+24d,265 | - | - | 0 | Carpenter | 0 | 47 | 13 | 42 | 57
301 | 1.2.2.2.2.12 | Strip Formwork - Lvl 7 | 5 | 25 November 2024 8:00 AM | 29 November 2024 5:00 PM | 300FS+12d | 716,748FS+24d,477,1713 | - | - | 0 | Head Contractor | 0 | 73 | 12 | 92 | 46
302 | 1.2.2.2.2.13 | Lift Shaft | 18 | 11 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Electrician | 0 | 28 | 12 | 83 | 39
303 | 1.2.2.2.2.13.1 | FRP Lift Over-run | 6 | 11 November 2024 8:00 AM | 16 November 2024 5:00 PM | 300 | 304,277 | - | - | 0 | Carpet | 0 | 25 | 12 | 12 | 19
304 | 1.2.2.2.2.13.2 | Strip Lift Shaft Formwork | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 303 | 305 | - | - | 0 | Waterproofer | 0 | 100 | 10 | 61 | 48
305 | 1.2.2.2.2.13.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 304 | 3452,306 | - | - | 0 | Post Tension | 0 | 30 | 12 | 4 | 34
306 | 1.2.2.2.2.13.4 | Building B Structure Complete | 0 | 30 November 2024 5:00 PM | 30 November 2024 5:00 PM | 305 | 7,6 | - | - | 0 | Electrician | 0 | 15 | 19 | 24 | 31
307 | 1.2.2.2.3 | Building C | 90 | 7 September 2024 8:00 AM | 23 December 2024 5:00 PM |  | 397 | - | - | 0 | Metal Work | 0 | 12 | 25 | 39 | 11
308 | 1.2.2.2.3.1 | Lvl 2 - FRP - Suspended Slab | 17 | 7 September 2024 8:00 AM | 26 September 2024 5:00 PM |  |  | - | - | 0 | Joiner | 0 | 25 | 33 | 86 | 59
309 | 1.2.2.2.3.1.1 | Scaffold Stair Removal/Adjustment | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 135,240FS+30d | 310SS | - | - | 0 | Line Market | 0 | 67 | 31 | 25 | 59
310 | 1.2.2.2.3.1.2 | Setout and Install Lift/Stair Formwork | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 309SS | 311 | - | - | 0 | Plasterboarder | 0 | 56 | 13 | 4 | 45
311 | 1.2.2.2.3.1.3 | Formworker setout, drop material and 80% Deck | 6 | 9 September 2024 8:00 AM | 14 September 2024 5:00 PM | 310 | 312FS-1d,313,365FS+10d | - | - | 0 | Plasterboarder | 0 | 78 | 29 | 77 | 3
312 | 1.2.2.2.3.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 14 September 2024 8:00 AM | 18 September 2024 5:00 PM | 311FS-1d | 314,315 | - | - | 0 | Excavation | 0 | 12 | 13 | 66 | 25
313 | 1.2.2.2.3.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 311 |  | - | - | 0 | Development Manager | 0 | 31 | 33 | 72 | 21
314 | 1.2.2.2.3.1.6 | Services | 2 | 19 September 2024 8:00 AM | 20 September 2024 5:00 PM | 312 | 316FS-1d | - | - | 0 | Carpet | 0 | 48 | 22 | 4 | 24
315 | 1.2.2.2.3.1.7 | Post Tension | 3 | 19 September 2024 8:00 AM | 21 September 2024 5:00 PM | 312 | 316FS-1d | - | - | 0 | Project Manager | 0 | 13 | 11 | 9 | 49
316 | 1.2.2.2.3.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 314FS-1d,315FS-1d | 317 | - | - | 0 | Project Manager | 0 | 18 | 24 | 94 | 28
317 | 1.2.2.2.3.1.9 | Formworker setdowns and edge boards | 2 | 24 September 2024 8:00 AM | 25 September 2024 5:00 PM | 316 | 318 | - | - | 0 | Stone Mason | 0 | 11 | 16 | 64 | 18
318 | 1.2.2.2.3.1.10 | Pour | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 317 | 321 | - | - | 0 | Head Contractor | 0 | 75 | 29 | 52 | 48
319 | 1.2.2.2.3.2 | Strip Formwork - Lvl 2 | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 354 | 331FS+5d | - | - | 0 | Carpet | 0 | 57 | 31 | 81 | 35
320 | 1.2.2.2.3.3 | Lvl 3 - FRP - Suspended Slab | 17 | 27 September 2024 8:00 AM | 18 October 2024 5:00 PM |  |  | - | - | 0 | Surveyor | 0 | 28 | 17 | 25 | 10
321 | 1.2.2.2.3.3.1 | Scaffold Stair Removal/Adjustment | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 318 | 322SS | - | - | 0 | Post Tension | 0 | 42 | 35 | 66 | 28
322 | 1.2.2.2.3.3.2 | Setout and Install Lift/Stair Formwork | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 321SS | 323 | - | - | 0 | Timber Floorer | 0 | 10 | 33 | 88 | 5
323 | 1.2.2.2.3.3.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 322 | 324FS-1d,325 | - | - | 0 | Post Tension | 0 | 56 | 31 | 18 | 40
324 | 1.2.2.2.3.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 323FS-1d | 326,327 | - | - | 0 | Plasterboarder | 0 | 27 | 33 | 100 | 40
325 | 1.2.2.2.3.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 323 |  | - | - | 0 | Formworker | 0 | 89 | 12 | 11 | 50
326 | 1.2.2.2.3.3.6 | Services | 2 | 11 October 2024 8:00 AM | 12 October 2024 5:00 PM | 324 | 328FS-1d | - | - | 0 | Line Market | 0 | 100 | 35 | 91 | 46
327 | 1.2.2.2.3.3.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 324 | 328FS-1d | - | - | 0 | Reinforcement Fixer | 0 | 80 | 23 | 63 | 58
328 | 1.2.2.2.3.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 326FS-1d,327FS-1d | 329 | - | - | 0 | Metal Work | 0 | 48 | 31 | 80 | 56
329 | 1.2.2.2.3.3.9 | Formworker setdowns and edge boards | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 328 | 330 | - | - | 0 | Waterproofer | 0 | 24 | 22 | 11 | 24
330 | 1.2.2.2.3.3.10 | Pour | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 329 | 333 | - | - | 0 | Excavation | 0 | 99 | 16 | 69 | 16
331 | 1.2.2.2.3.4 | Strip Formwork - Lvl 3 | 5 | 10 December 2024 8:00 AM | 14 December 2024 5:00 PM | 319FS+5d | 490,1748,2151,1774,2177FS+5d | - | - | 0 | Line Market | 0 | 53 | 10 | 24 | 52
332 | 1.2.2.2.3.5 | Lvl 4 - FRP - Suspended Slab | 17 | 19 October 2024 8:00 AM | 7 November 2024 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 20 | 20 | 8 | 48
333 | 1.2.2.2.3.5.1 | Scaffold Stair Removal/Adjustment | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 330 | 334SS | - | - | 0 | Contract Administrator | 0 | 86 | 10 | 45 | 39
334 | 1.2.2.2.3.5.2 | Setout and Install Lift/Stair Formwork | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 333SS | 335 | - | - | 0 | Site Manager | 0 | 55 | 27 | 13 | 30
335 | 1.2.2.2.3.5.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 334 | 336FS-1d,337 | - | - | 0 | Cleaner | 0 | 78 | 27 | 31 | 53
336 | 1.2.2.2.3.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 335FS-1d | 338,339 | - | - | 0 | Plumber | 0 | 66 | 24 | 13 | 2
337 | 1.2.2.2.3.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 335 |  | - | - | 0 | Project Manager | 0 | 37 | 16 | 2 | 25
338 | 1.2.2.2.3.5.6 | Services | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 336 | 340FS-1d | - | - | 0 | Concretor | 0 | 54 | 11 | 23 | 48
339 | 1.2.2.2.3.5.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 336 | 340FS-1d | - | - | 0 | Carpenter | 0 | 34 | 30 | 11 | 31
340 | 1.2.2.2.3.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 338FS-1d,339FS-1d | 341 | - | - | 0 | Head Contractor | 0 | 24 | 22 | 94 | 59
341 | 1.2.2.2.3.5.9 | Formworker setdowns and edge boards | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 340 | 342 | - | - | 0 | Mechanical | 0 | 20 | 28 | 46 | 30
342 | 1.2.2.2.3.5.10 | Pour | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 341 | 345 | - | - | 0 | Surveyor | 0 | 13 | 27 | 50 | 2
343 | 1.2.2.2.3.6 | Strip Formwork - Lvl 4 | 5 | 16 December 2024 8:00 AM | 20 December 2024 5:00 PM | 354FS+15d | 495,2648,2674FS+5d | - | - | 0 | Plasterboarder | 0 | 44 | 25 | 20 | 49
344 | 1.2.2.2.3.7 | Lvl 5 (Roof) - FRP - Suspended Slab | 17 | 8 November 2024 8:00 AM | 27 November 2024 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 41 | 16 | 65 | 59
345 | 1.2.2.2.3.7.1 | Scaffold Stair Removal/Adjustment | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 342 | 346SS | - | - | 0 | Waterproofer | 0 | 94 | 20 | 29 | 45
346 | 1.2.2.2.3.7.2 | Setout and Install Lift/Stair Formwork | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 345SS | 347 | - | - | 0 | Renderer | 0 | 45 | 13 | 45 | 15
347 | 1.2.2.2.3.7.3 | Formworker setout, drop material and 80% Deck | 6 | 9 November 2024 8:00 AM | 15 November 2024 5:00 PM | 346 | 348FS-1d,349 | - | - | 0 | Excavation | 0 | 86 | 23 | 90 | 17
348 | 1.2.2.2.3.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 November 2024 8:00 AM | 19 November 2024 5:00 PM | 347FS-1d | 350,351 | - | - | 0 | Carpet | 0 | 62 | 31 | 0 | 48
349 | 1.2.2.2.3.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 347 |  | - | - | 0 | Timber Floorer | 0 | 50 | 33 | 21 | 58
350 | 1.2.2.2.3.7.6 | Services | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 348 | 352FS-1d | - | - | 0 | Project Manager | 0 | 48 | 23 | 91 | 43
351 | 1.2.2.2.3.7.7 | Post Tension | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 348 | 352FS-1d | - | - | 0 | Carpet | 0 | 15 | 16 | 45 | 5
352 | 1.2.2.2.3.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 350FS-1d,351FS-1d | 353 | - | - | 0 | Fire | 0 | 81 | 25 | 7 | 10
353 | 1.2.2.2.3.7.9 | Formworker setdowns and edge boards | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 352 | 354 | - | - | 0 | Contract Administrator | 0 | 62 | 14 | 26 | 39
354 | 1.2.2.2.3.7.10 | Pour | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 353 | 357,355FS+12d,343FS+15d,360,319 | - | - | 0 | Admin | 0 | 90 | 32 | 90 | 5
355 | 1.2.2.2.3.8 | Strip Formwork - Lvl 5 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 354FS+12d | 500,3145,3171FS+5d | - | - | 0 | Renderer | 0 | 77 | 28 | 95 | 22
356 | 1.2.2.2.3.9 | Lift Shaft | 22 | 28 November 2024 8:00 AM | 23 December 2024 5:00 PM |  |  | - | - | 0 | Plasterboarder | 0 | 76 | 18 | 87 | 33
357 | 1.2.2.2.3.9.1 | FRP Lift Over-run | 10 | 28 November 2024 8:00 AM | 9 December 2024 5:00 PM | 354 | 358 | - | - | 0 | Plumber | 0 | 87 | 34 | 41 | 50
358 | 1.2.2.2.3.9.2 | Strip Lift Shaft Formwork | 4 | 10 December 2024 8:00 AM | 13 December 2024 5:00 PM | 357 | 359 | - | - | 0 | Project Manager | 0 | 64 | 22 | 33 | 50
359 | 1.2.2.2.3.9.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 14 December 2024 8:00 AM | 23 December 2024 5:00 PM | 358 | 3453,360 | - | - | 0 | Head Contractor | 0 | 79 | 31 | 19 | 15
360 | 1.2.2.2.3.10 | Building C Structure Complete | 0 | 23 December 2024 5:00 PM | 23 December 2024 5:00 PM | 354,359 | 8,7 | - | - | 0 | Excavation | 0 | 42 | 15 | 38 | 18
361 | 1.2.2.2.4 | Building D | 76 | 26 September 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | - | - | 0 | Landscaper | 0 | 21 | 24 | 58 | 35
362 | 1.2.2.2.4.1 | Lvl 2 - FRP - Suspended Slab | 19 | 26 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | - | - | 0 | Joiner | 0 | 75 | 22 | 86 | 50
363 | 1.2.2.2.4.1.1 | Scaffold Stair Removal/Adjustment | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 364SS |  | - | - | 0 | Tiler | 0 | 57 | 12 | 77 | 24
364 | 1.2.2.2.4.1.2 | Setout and Install Lift/Stair Formwork | 1 | 26 September 2024 8:00 AM | 27 September 2024 8:00 AM | 365SF | 363SS | - | - | 0 | Fire | 0 | 28 | 15 | 96 | 13
365 | 1.2.2.2.4.1.3 | Formworker setout, drop material and 80% Deck | 6 | 27 September 2024 8:00 AM | 3 October 2024 5:00 PM | 311FS+10d | 366FS-1d,367,364SF | - | - | 0 | Cleaner | 0 | 68 | 23 | 31 | 35
366 | 1.2.2.2.4.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 3 October 2024 8:00 AM | 10 October 2024 5:00 PM | 365FS-1d | 368,369 | - | - | 0 | Joiner | 0 | 54 | 19 | 41 | 54
367 | 1.2.2.2.4.1.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 4 October 2024 8:00 AM | 9 October 2024 5:00 PM | 365 |  | - | - | 0 | Head Contractor | 0 | 59 | 15 | 80 | 12
368 | 1.2.2.2.4.1.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | - | - | 0 | Line Market | 0 | 49 | 32 | 36 | 58
369 | 1.2.2.2.4.1.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | - | - | 0 | Admin | 0 | 49 | 26 | 41 | 31
370 | 1.2.2.2.4.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 368FS-1d,369FS-1d | 371 | - | - | 0 | Formworker | 0 | 82 | 14 | 37 | 43
371 | 1.2.2.2.4.1.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 370 | 372 | - | - | 0 | Site Manager | 0 | 83 | 26 | 63 | 13
372 | 1.2.2.2.4.1.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 371 | 375 | - | - | 0 | Post Tension | 0 | 88 | 25 | 45 | 5
373 | 1.2.2.2.4.2 | Strip Formwork - Lvl 2 | 5 | 21 November 2024 8:00 AM | 26 November 2024 5:00 PM | 384FS+8d | 485,506 | - | - | 0 | Tiler | 0 | 100 | 17 | 91 | 44
374 | 1.2.2.2.4.3 | Lvl 3 - FRP - Suspended Slab | 19 | 21 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | - | - | 0 | Timber Floorer | 0 | 38 | 15 | 46 | 60
375 | 1.2.2.2.4.3.1 | Scaffold Stair Removal/Adjustment | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 372 | 376SS | - | - | 0 | Foreman | 0 | 88 | 14 | 31 | 6
376 | 1.2.2.2.4.3.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 375SS | 377 | - | - | 0 | Project Manager | 0 | 22 | 14 | 84 | 29
377 | 1.2.2.2.4.3.3 | Formworker setout, drop material and 80% Deck | 6 | 22 October 2024 8:00 AM | 28 October 2024 5:00 PM | 376 | 378FS-1d,379 | - | - | 0 | Fire | 0 | 18 | 29 | 29 | 52
378 | 1.2.2.2.4.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 377FS-1d | 380,381 | - | - | 0 | Contract Administrator | 0 | 24 | 35 | 11 | 26
379 | 1.2.2.2.4.3.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 29 October 2024 8:00 AM | 31 October 2024 5:00 PM | 377 |  | - | - | 0 | Formworker | 0 | 54 | 33 | 68 | 59
380 | 1.2.2.2.4.3.6 | Services | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | - | - | 0 | Project Manager | 0 | 25 | 32 | 83 | 57
381 | 1.2.2.2.4.3.7 | Post Tension | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | - | - | 0 | Development Manager | 0 | 13 | 10 | 64 | 18
382 | 1.2.2.2.4.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 5 November 2024 8:00 AM | 7 November 2024 5:00 PM | 380FS-1d,381FS-1d | 383 | - | - | 0 | Electrician | 0 | 20 | 28 | 19 | 23
383 | 1.2.2.2.4.3.9 | Formworker setdowns and edge boards | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 382 | 384 | - | - | 0 | Electrician | 0 | 63 | 25 | 29 | 19
384 | 1.2.2.2.4.3.10 | Pour | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 383 | 385FS+12d,373FS+8d,387 | - | - | 0 | Contract Administrator | 0 | 62 | 22 | 84 | 16
385 | 1.2.2.2.4.4 | Strip Formwork - Lvl 3 | 5 | 26 November 2024 8:00 AM | 30 November 2024 5:00 PM | 384FS+12d | 511 | - | - | 0 | Plasterboarder | 0 | 62 | 21 | 100 | 9
386 | 1.2.2.2.4.5 | L4 Strucutral Steel Roof | 38 | 12 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | - | - | 0 | Electrician | 0 | 77 | 15 | 39 | 7
387 | 1.2.2.2.4.5.1 | Scaffold Perimeter Protection | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 384 | 388SS | - | - | 0 | Window | 0 | 52 | 23 | 73 | 38
388 | 1.2.2.2.4.5.2 | Setout | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 387SS | 389 | - | - | 0 | Metal Work | 0 | 48 | 13 | 47 | 47
389 | 1.2.2.2.4.5.3 | Formworker setout, drop material and 80% Walls | 5 | 14 November 2024 8:00 AM | 19 November 2024 5:00 PM | 388 | 390FS-1d | - | - | 0 | Line Market | 0 | 21 | 16 | 11 | 22
390 | 1.2.2.2.4.5.4 | Steel Fixer - Walls | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 389FS-1d | 391 | - | - | 0 | Cleaner | 0 | 63 | 13 | 28 | 24
391 | 1.2.2.2.4.5.5 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 390 | 392 | - | - | 0 | Floor Sealer | 0 | 18 | 16 | 48 | 13
392 | 1.2.2.2.4.5.6 | Pour | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 391 | 393 | - | - | 0 | Renderer | 0 | 13 | 14 | 42 | 34
393 | 1.2.2.2.4.5.7 | Strip Formwork | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 392 | 394 | - | - | 0 | Carpenter | 0 | 17 | 22 | 28 | 56
394 | 1.2.2.2.4.5.8 | Structural Steel Setout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 393 | 395 | - | - | 0 | Timber Floorer | 0 | 19 | 10 | 30 | 43
395 | 1.2.2.2.4.5.9 | Install Structural Steel | 8 | 29 November 2024 8:00 AM | 7 December 2024 5:00 PM | 394 | 396 | - | - | 0 | Subcontractor | 0 | 57 | 15 | 78 | 52
396 | 1.2.2.2.4.5.10 | Install Metal Deck Roofing | 15 | 9 December 2024 8:00 AM | 3 January 2025 5:00 PM | 395 | 516,8 | - | - | 0 | Joiner | 0 | 13 | 15 | 19 | 29
397 | 1.2.2.3 | Structural Works Complete | 0 | 3 January 2025 5:00 PM | 3 January 2025 5:00 PM | 120,307,361,91,138,229 |  | - | - | 0 | Subcontractor | 0 | 80 | 10 | 40 | 9
398 | 1.2.3 | FAÇADE WORKS | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | - | - | 0 | Landscaper | 0 | 91 | 30 | 47 | 7
399 | 1.2.3.1 | Building A | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | - | - | 0 | Contract Administrator | 0 | 79 | 31 | 16 | 54
400 | 1.2.3.1.1 | Lvl 1 | 44 | 13 July 2024 8:00 AM | 2 September 2024 5:00 PM |  |  | - | - | 0 | Joiner | 0 | 76 | 30 | 37 | 33
401 | 1.2.3.1.1.1 | Survey & Setout | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 116FS+5d | 402 | - | - | 0 | Surveyor | 0 | 27 | 20 | 0 | 53
402 | 1.2.3.1.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 15 July 2024 8:00 AM | 19 July 2024 5:00 PM | 401 | 403 | - | - | 0 | Concretor | 0 | 69 | 29 | 46 | 39
403 | 1.2.3.1.1.3 | Façade & External Walls | 20 | 20 July 2024 8:00 AM | 12 August 2024 5:00 PM | 402 | 404 | - | - | 0 | Cleaner | 0 | 33 | 10 | 87 | 8
404 | 1.2.3.1.1.4 | Windows Install | 18 | 13 August 2024 8:00 AM | 2 September 2024 5:00 PM | 403 | 405,411 | - | - | 0 | Subcontractor | 0 | 96 | 15 | 65 | 15
405 | 1.2.3.1.1.5 | Level 1 Weathertight | 0 | 2 September 2024 5:00 PM | 2 September 2024 5:00 PM | 404 | 558 | - | - | 0 | Electrician | 0 | 91 | 19 | 14 | 34
406 | 1.2.3.1.2 | Lvl 2 | 83 | 17 August 2024 8:00 AM | 23 November 2024 5:00 PM |  |  | - | - | 0 | Concretor | 0 | 23 | 10 | 64 | 51
407 | 1.2.3.1.2.1 | Survey & Setout | 1 | 17 August 2024 8:00 AM | 17 August 2024 5:00 PM | 149FS+5d | 408 | - | - | 0 | Concretor | 0 | 57 | 15 | 97 | 38
408 | 1.2.3.1.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 19 August 2024 8:00 AM | 23 August 2024 5:00 PM | 407 | 577 | - | - | 0 | Reinforcement Fixer | 0 | 67 | 16 | 10 | 3
409 | 1.2.3.1.2.3 | Façade & External Walls | 22 | 9 October 2024 8:00 AM | 2 November 2024 5:00 PM | 150FS-10d | 410 | - | - | 0 | Metal Work | 0 | 98 | 22 | 20 | 50
410 | 1.2.3.1.2.4 | Windows Install | 18 | 4 November 2024 8:00 AM | 23 November 2024 5:00 PM | 409 | 411 | - | - | 0 | Painter | 0 | 77 | 31 | 94 | 37
411 | 1.2.3.1.2.5 | Level 2 Weathertight | 0 | 23 November 2024 5:00 PM | 23 November 2024 5:00 PM | 404,410 | 585 | - | - | 0 | Electrician | 0 | 96 | 27 | 20 | 55
412 | 1.2.3.1.3 | Lvl 3 | 40 | 13 November 2024 8:00 AM | 7 January 2025 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 59 | 24 | 27 | 46
413 | 1.2.3.1.3.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 174FS+5d | 414FS-1d | - | - | 0 | Renderer | 0 | 12 | 10 | 90 | 39
414 | 1.2.3.1.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 413FS-1d |  | - | - | 0 | Tiler | 0 | 91 | 14 | 53 | 19
415 | 1.2.3.1.3.3 | Façade & External Walls | 22 | 13 November 2024 8:00 AM | 7 December 2024 5:00 PM | 174FS-10d | 416 | - | - | 0 | Stone Mason | 0 | 37 | 18 | 39 | 29
416 | 1.2.3.1.3.4 | Windows Install | 18 | 9 December 2024 8:00 AM | 7 January 2025 5:00 PM | 415 | 610FS-6d,417 | - | - | 0 | Excavation | 0 | 34 | 14 | 73 | 27
417 | 1.2.3.1.3.5 | Level 3 Weathertight | 0 | 7 January 2025 5:00 PM | 7 January 2025 5:00 PM | 416 | 612,444 | - | - | 0 | Waterproofer | 0 | 96 | 19 | 62 | 46
418 | 1.2.3.1.4 | Lvl 4 | 44 | 17 December 2024 8:00 AM | 15 February 2025 5:00 PM |  |  | - | - | 0 | Site Manager | 0 | 74 | 12 | 20 | 55
419 | 1.2.3.1.4.1 | Survey & Setout | 1 | 17 December 2024 8:00 AM | 17 December 2024 5:00 PM | 186FS+5d | 420FS-1d | - | - | 0 | Waterproofer | 0 | 67 | 22 | 67 | 7
420 | 1.2.3.1.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 17 December 2024 8:00 AM | 20 December 2024 5:00 PM | 419FS-1d | 421 | - | - | 0 | Project Manager | 0 | 29 | 14 | 43 | 31
421 | 1.2.3.1.4.3 | Façade & External Walls | 22 | 21 December 2024 8:00 AM | 24 January 2025 5:00 PM | 186FS-10d,420 | 422 | - | - | 0 | Mechanical | 0 | 14 | 33 | 78 | 2
422 | 1.2.3.1.4.4 | Windows Install | 18 | 27 January 2025 8:00 AM | 15 February 2025 5:00 PM | 421 | 637FS-6d,423 | - | - | 0 | Plasterboarder | 0 | 66 | 11 | 41 | 13
423 | 1.2.3.1.4.5 | Level 4 Weathertight | 0 | 15 February 2025 5:00 PM | 15 February 2025 5:00 PM | 422 | 639,444 | - | - | 0 | Landscaper | 0 | 83 | 33 | 19 | 8
424 | 1.2.3.1.5 | Lvl 5 | 40 | 30 November 2024 8:00 AM | 24 January 2025 5:00 PM |  |  | - | - | 0 | Electrician | 0 | 98 | 28 | 100 | 16
425 | 1.2.3.1.5.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 198FS+5d | 426FS-1d | - | - | 0 | Contract Administrator | 0 | 40 | 14 | 30 | 12
426 | 1.2.3.1.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 425FS-1d | 663 | - | - | 0 | Stone Mason | 0 | 19 | 21 | 28 | 56
427 | 1.2.3.1.5.3 | Façade & External Walls | 22 | 30 November 2024 8:00 AM | 3 January 2025 5:00 PM | 198FS-10d | 428 | - | - | 0 | Site Manager | 0 | 67 | 31 | 12 | 56
428 | 1.2.3.1.5.4 | Windows Install | 18 | 4 January 2025 8:00 AM | 24 January 2025 5:00 PM | 427 | 669FS-6d,429,444 | - | - | 0 | Surveyor | 0 | 61 | 19 | 96 | 54
429 | 1.2.3.1.5.5 | Level 5 Weathertight | 0 | 24 January 2025 5:00 PM | 24 January 2025 5:00 PM | 428 | 671 | - | - | 0 | Timber Floorer | 0 | 21 | 14 | 65 | 18
430 | 1.2.3.1.6 | Lvl 6 | 59 | 19 November 2024 8:00 AM | 5 February 2025 5:00 PM |  |  | - | - | 0 | Timber Floorer | 0 | 75 | 31 | 91 | 33
431 | 1.2.3.1.6.1 | Survey & Setout | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 209FS+5d | 432 | - | - | 0 | Admin | 0 | 80 | 18 | 56 | 36
432 | 1.2.3.1.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 6 December 2024 8:00 AM | 10 December 2024 5:00 PM | 210FS-10d,431 | 433,690 | - | - | 0 | Tiler | 0 | 17 | 15 | 95 | 46
433 | 1.2.3.1.6.3 | Façade & External Walls | 22 | 11 December 2024 8:00 AM | 14 January 2025 5:00 PM | 432 | 434 | - | - | 0 | Scaffolder | 0 | 96 | 35 | 91 | 32
434 | 1.2.3.1.6.4 | Windows Install | 18 | 15 January 2025 8:00 AM | 5 February 2025 5:00 PM | 433 | 696FS-6d,435 | - | - | 0 | Contract Administrator | 0 | 87 | 15 | 50 | 22
435 | 1.2.3.1.6.5 | Level 6 Weathertight | 0 | 5 February 2025 5:00 PM | 5 February 2025 5:00 PM | 434 | 698,444 | - | - | 0 | Floor Sealer | 0 | 79 | 32 | 11 | 36
436 | 1.2.3.1.7 | Lvl 7 | 59 | 5 December 2024 8:00 AM | 21 February 2025 5:00 PM |  |  | - | - | 0 | Post Tension | 0 | 27 | 26 | 42 | 43
437 | 1.2.3.1.7.1 | Survey & Setout | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 221FS+5d | 438FS-1d | - | - | 0 | Metal Work | 0 | 26 | 27 | 61 | 28
438 | 1.2.3.1.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 5 December 2024 8:00 AM | 9 December 2024 5:00 PM | 437FS-1d | 722 | - | - | 0 | Metal Work | 0 | 94 | 31 | 77 | 46
439 | 1.2.3.1.7.3 | Façade & External Walls | 22 | 8 January 2025 8:00 AM | 3 February 2025 5:00 PM | 223FS+10d | 440 | - | - | 0 | Plasterboarder | 0 | 74 | 29 | 65 | 40
440 | 1.2.3.1.7.4 | Windows Install | 16 | 4 February 2025 8:00 AM | 21 February 2025 5:00 PM | 439 | 728FS-6d,441,3446FS-5d | - | - | 0 | Tiler | 0 | 51 | 20 | 13 | 53
441 | 1.2.3.1.7.5 | Level 7 Weathertight | 0 | 21 February 2025 5:00 PM | 21 February 2025 5:00 PM | 440 | 730,442 | - | - | 0 | Floor Sealer | 0 | 82 | 28 | 52 | 10
442 | 1.2.3.1.8 | Defect Rectification | 15 | 22 February 2025 8:00 AM | 11 March 2025 5:00 PM | 441 | 443 | - | - | 0 | Subcontractor | 0 | 53 | 17 | 30 | 56
443 | 1.2.3.1.9 | Strip Scaffold | 10 | 12 March 2025 8:00 AM | 22 March 2025 5:00 PM | 442 | 444,3456 | - | - | 0 | Reinforcement Fixer | 0 | 74 | 19 | 1 | 11
444 | 1.2.3.1.10 | Building A Façade Complete | 0 | 22 March 2025 5:00 PM | 22 March 2025 5:00 PM | 443,435,428,423,417 | 5 | - | - | 0 | Electrician | 0 | 38 | 11 | 61 | 40
445 | 1.2.3.2 | Building B | 89 | 4 October 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | - | - | 0 | Admin | 0 | 45 | 27 | 52 | 17
446 | 1.2.3.2.1 | Lvl 1 | 44 | 4 October 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | - | - | 0 | Window | 0 | 62 | 25 | 58 | 11
447 | 1.2.3.2.1.1 | Survey & Setout | 1 | 4 October 2024 8:00 AM | 4 October 2024 5:00 PM | 241 | 448 | - | - | 0 | Window | 0 | 48 | 20 | 10 | 2
448 | 1.2.3.2.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 8 October 2024 8:00 AM | 12 October 2024 5:00 PM | 447 | 449,758,852,1322FS+6d,1510FS+6d,1416FS+6d,946FS+2d,1040FS+2d,1134FS+4d,1228FS+4d | - | - | 0 | Reinforcement Fixer | 0 | 39 | 11 | 83 | 58
449 | 1.2.3.2.1.3 | Façade & External Walls | 20 | 14 October 2024 8:00 AM | 5 November 2024 5:00 PM | 448 | 450 | - | - | 0 | Project Manager | 0 | 87 | 23 | 59 | 30
450 | 1.2.3.2.1.4 | Windows Install | 18 | 6 November 2024 8:00 AM | 26 November 2024 5:00 PM | 449 | 451 | - | - | 0 | Plumber | 0 | 89 | 22 | 82 | 38
451 | 1.2.3.2.1.5 | Level 1 Weathertight | 0 | 26 November 2024 5:00 PM | 26 November 2024 5:00 PM | 450 | 1640 | - | - | 0 | Electrician | 0 | 75 | 13 | 15 | 59
452 | 1.2.3.2.2 | Lvl 2 | 42 | 26 October 2024 8:00 AM | 13 December 2024 5:00 PM |  |  | - | - | 0 | Concretor | 0 | 31 | 28 | 24 | 10
453 | 1.2.3.2.2.1 | Survey & Setout | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 253 | 454 | - | - | 0 | Window | 0 | 33 | 31 | 79 | 40
454 | 1.2.3.2.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 453 | 455 | - | - | 0 | Head Contractor | 0 | 16 | 10 | 12 | 59
455 | 1.2.3.2.2.3 | Façade & External Walls | 20 | 2 November 2024 8:00 AM | 25 November 2024 5:00 PM | 454 | 456 | - | - | 0 | Painter | 0 | 10 | 29 | 31 | 8
456 | 1.2.3.2.2.4 | Windows Install | 16 | 26 November 2024 8:00 AM | 13 December 2024 5:00 PM | 455 | 457 | - | - | 0 | Mechanical | 0 | 98 | 30 | 18 | 36
457 | 1.2.3.2.2.5 | Level 2 Weathertight | 0 | 13 December 2024 5:00 PM | 13 December 2024 5:00 PM | 456 |  | - | - | 0 | Excavation | 0 | 64 | 29 | 0 | 22
458 | 1.2.3.2.3 | Lvl 3 | 43 | 16 November 2024 8:00 AM | 14 January 2025 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 61 | 35 | 2 | 14
459 | 1.2.3.2.3.1 | Survey & Setout | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 265 | 460 | - | - | 0 | Joiner | 0 | 82 | 35 | 42 | 13
460 | 1.2.3.2.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 459 | 461 | - | - | 0 | Project Manager | 0 | 73 | 11 | 23 | 51
461 | 1.2.3.2.3.3 | Façade & External Walls | 20 | 22 November 2024 8:00 AM | 14 December 2024 5:00 PM | 460 | 462 | - | - | 0 | Contract Administrator | 0 | 10 | 27 | 47 | 3
462 | 1.2.3.2.3.4 | Windows Install | 18 | 16 December 2024 8:00 AM | 14 January 2025 5:00 PM | 461 | 1638FS-6d,463 | - | - | 0 | Reinforcement Fixer | 0 | 56 | 20 | 94 | 39
463 | 1.2.3.2.3.5 | Level 3 Weathertight | 0 | 14 January 2025 5:00 PM | 14 January 2025 5:00 PM | 462 | 1640 | - | - | 0 | Admin | 0 | 88 | 34 | 32 | 37
464 | 1.2.3.2.4 | Lvl 4 | 42 | 23 November 2024 8:00 AM | 20 January 2025 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 10 | 28 | 85 | 56
465 | 1.2.3.2.4.1 | Survey & Setout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 277 | 466FS-1d | - | - | 0 | Metal Work | 0 | 67 | 10 | 83 | 24
466 | 1.2.3.2.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 23 November 2024 8:00 AM | 27 November 2024 5:00 PM | 465FS-1d | 467 | - | - | 0 | Landscaper | 0 | 16 | 28 | 32 | 10
467 | 1.2.3.2.4.3 | Façade & External Walls | 20 | 28 November 2024 8:00 AM | 20 December 2024 5:00 PM | 466 | 468 | - | - | 0 | Line Market | 0 | 82 | 15 | 4 | 34
468 | 1.2.3.2.4.4 | Windows Install | 18 | 21 December 2024 8:00 AM | 20 January 2025 5:00 PM | 467 | 1665FS-6d,469 | - | - | 0 | Landscaper | 0 | 84 | 31 | 84 | 37
469 | 1.2.3.2.4.5 | Level 4 Weathertight | 0 | 20 January 2025 5:00 PM | 20 January 2025 5:00 PM | 468 | 1665FS-6d | - | - | 0 | Carpet | 0 | 64 | 17 | 59 | 54
470 | 1.2.3.2.5 | Lvl 5 | 42 | 26 November 2024 8:00 AM | 22 January 2025 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 18 | 13 | 15 | 57
471 | 1.2.3.2.5.1 | Survey & Setout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 289 | 472FS-1d | - | - | 0 | Subcontractor | 0 | 73 | 18 | 44 | 21
472 | 1.2.3.2.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 26 November 2024 8:00 AM | 29 November 2024 5:00 PM | 471FS-1d | 473 | - | - | 0 | Window | 0 | 33 | 16 | 0 | 18
473 | 1.2.3.2.5.3 | Façade & External Walls | 20 | 30 November 2024 8:00 AM | 23 December 2024 5:00 PM | 472 | 474 | - | - | 0 | Timber Floorer | 0 | 100 | 35 | 16 | 11
474 | 1.2.3.2.5.4 | Windows Install | 18 | 24 December 2024 8:00 AM | 22 January 2025 5:00 PM | 473 | 475 | - | - | 0 | Surveyor | 0 | 94 | 16 | 53 | 13
475 | 1.2.3.2.5.5 | Level 5 Weathertight | 0 | 22 January 2025 5:00 PM | 22 January 2025 5:00 PM | 474 | 1692FS-4d | - | - | 0 | Foreman | 0 | 67 | 33 | 38 | 8
476 | 1.2.3.2.6 | Lvl 6 | 42 | 30 November 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 37 | 25 | 13 | 3
477 | 1.2.3.2.6.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 301 | 478FS-1d | - | - | 0 | Concretor | 0 | 77 | 27 | 46 | 8
478 | 1.2.3.2.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 477FS-1d | 479 | - | - | 0 | Fire | 0 | 57 | 14 | 10 | 17
479 | 1.2.3.2.6.3 | Façade & External Walls | 20 | 5 December 2024 8:00 AM | 6 January 2025 5:00 PM | 478 | 480 | - | - | 0 | Window | 0 | 26 | 30 | 99 | 52
480 | 1.2.3.2.6.4 | Windows Install | 18 | 7 January 2025 8:00 AM | 28 January 2025 5:00 PM | 479 | 481 | - | - | 0 | Painter | 0 | 46 | 22 | 90 | 44
481 | 1.2.3.2.6.5 | Level 6 Weathertight | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 480 | 1719FS-6d,482 | - | - | 0 | Excavation | 0 | 63 | 14 | 80 | 9
482 | 1.2.3.2.6.6 | Building B Façade Complete | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 481 | 6 | - | - | 0 | Landscaper | 0 | 59 | 23 | 12 | 56
483 | 1.2.3.3 | Building C | 63 | 27 November 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 52 | 24 | 76 | 2
484 | 1.2.3.3.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | - | - | 0 | Site Manager | 0 | 51 | 22 | 13 | 7
485 | 1.2.3.3.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 486 | - | - | 0 | Timber Floorer | 0 | 30 | 24 | 84 | 51
486 | 1.2.3.3.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 485 | 487 | - | - | 0 | Timber Floorer | 0 | 68 | 32 | 57 | 34
487 | 1.2.3.3.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 486 | 488 | - | - | 0 | Joiner | 0 | 75 | 21 | 52 | 7
488 | 1.2.3.3.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 487 |  | - | - | 0 | Floor Sealer | 0 | 27 | 21 | 33 | 29
489 | 1.2.3.3.2 | Lvl 2 | 44 | 16 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | - | - | 0 | Project Manager | 0 | 40 | 22 | 72 | 57
490 | 1.2.3.3.2.1 | Survey & Setout | 1 | 16 December 2024 8:00 AM | 16 December 2024 5:00 PM | 331 | 491 | - | - | 0 | Hoarding | 0 | 46 | 20 | 49 | 11
491 | 1.2.3.3.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 17 December 2024 8:00 AM | 21 December 2024 5:00 PM | 490 | 492 | - | - | 0 | Electrician | 0 | 55 | 31 | 23 | 14
492 | 1.2.3.3.2.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 491 | 493 | - | - | 0 | Tiler | 0 | 49 | 27 | 33 | 47
493 | 1.2.3.3.2.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 492 |  | - | - | 0 | Window | 0 | 35 | 35 | 100 | 52
494 | 1.2.3.3.3 | Lvl 3 | 42 | 21 December 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | - | - | 0 | Waterproofer | 0 | 66 | 14 | 80 | 32
495 | 1.2.3.3.3.1 | Survey & Setout | 1 | 21 December 2024 8:00 AM | 21 December 2024 5:00 PM | 343 | 496FS-1d | - | - | 0 | Excavation | 0 | 50 | 14 | 72 | 14
496 | 1.2.3.3.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 21 December 2024 8:00 AM | 3 January 2025 5:00 PM | 495FS-1d | 497 | - | - | 0 | Stone Mason | 0 | 90 | 22 | 53 | 3
497 | 1.2.3.3.3.3 | Façade & External Walls | 20 | 4 January 2025 8:00 AM | 28 January 2025 5:00 PM | 496 | 498 | - | - | 0 | Waterproofer | 0 | 12 | 29 | 40 | 4
498 | 1.2.3.3.3.4 | Windows Install | 18 | 29 January 2025 8:00 AM | 18 February 2025 5:00 PM | 497 | 2654FS-6d | - | - | 0 | Tiler | 0 | 82 | 24 | 98 | 38
499 | 1.2.3.3.4 | Lvl 4 | 42 | 18 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | - | - | 0 | Admin | 0 | 56 | 13 | 19 | 58
500 | 1.2.3.3.4.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 355 | 501FS-1d | - | - | 0 | Carpenter | 0 | 80 | 33 | 92 | 50
501 | 1.2.3.3.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 500FS-1d | 502 | - | - | 0 | Timber Floorer | 0 | 17 | 33 | 94 | 51
502 | 1.2.3.3.4.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 501 | 503 | - | - | 0 | Development Manager | 0 | 56 | 35 | 78 | 59
503 | 1.2.3.3.4.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 502 | 3151FS-6d,7 | - | - | 0 | Cleaner | 0 | 10 | 26 | 50 | 22
504 | 1.2.3.4 | Building D | 62 | 27 November 2024 8:00 AM | 17 February 2025 5:00 PM |  |  | - | - | 0 | Landscaper | 0 | 67 | 12 | 11 | 54
505 | 1.2.3.4.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | - | - | 0 | Electrician | 0 | 74 | 21 | 86 | 30
506 | 1.2.3.4.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 507 | - | - | 0 | Mechanical | 0 | 66 | 24 | 83 | 49
507 | 1.2.3.4.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 506 | 508,3361 | - | - | 0 | Stone Mason | 0 | 76 | 13 | 96 | 10
508 | 1.2.3.4.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 507 | 509 | - | - | 0 | Electrician | 0 | 66 | 16 | 70 | 26
509 | 1.2.3.4.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 508 |  | - | - | 0 | Tiler | 0 | 14 | 19 | 78 | 58
510 | 1.2.3.4.2 | Lvl 2 | 44 | 2 December 2024 8:00 AM | 31 January 2025 5:00 PM |  |  | - | - | 0 | Admin | 0 | 20 | 30 | 80 | 28
511 | 1.2.3.4.2.1 | Survey & Setout | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 385 | 512 | - | - | 0 | Cleaner | 0 | 18 | 11 | 72 | 41
512 | 1.2.3.4.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 3 December 2024 8:00 AM | 7 December 2024 5:00 PM | 511 | 513,3388 | - | - | 0 | Tiler | 0 | 21 | 11 | 94 | 35
513 | 1.2.3.4.2.3 | Façade & External Walls | 20 | 9 December 2024 8:00 AM | 9 January 2025 5:00 PM | 512 | 514 | - | - | 0 | Subcontractor | 0 | 67 | 16 | 12 | 3
514 | 1.2.3.4.2.4 | Windows Install | 18 | 10 January 2025 8:00 AM | 31 January 2025 5:00 PM | 513 |  | - | - | 0 | Mechanical | 0 | 91 | 20 | 6 | 26
515 | 1.2.3.4.3 | Lvl 3 | 37 | 4 January 2025 8:00 AM | 17 February 2025 5:00 PM |  |  | - | - | 0 | Fire | 0 | 49 | 16 | 38 | 19
516 | 1.2.3.4.3.1 | Survey & Setout | 1 | 4 January 2025 8:00 AM | 4 January 2025 5:00 PM | 396 | 517FS-1d | - | - | 0 | Development Manager | 0 | 44 | 15 | 71 | 31
517 | 1.2.3.4.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 3 | 4 January 2025 8:00 AM | 7 January 2025 5:00 PM | 516FS-1d | 518,3415 | - | - | 0 | Hoarding | 0 | 47 | 28 | 91 | 6
518 | 1.2.3.4.3.3 | Façade & External Walls | 18 | 8 January 2025 8:00 AM | 29 January 2025 5:00 PM | 517 | 519 | - | - | 0 | Excavation | 0 | 71 | 16 | 93 | 52
519 | 1.2.3.4.3.4 | Windows Install | 16 | 30 January 2025 8:00 AM | 17 February 2025 5:00 PM | 518 | 3421FS-6d,8 | - | - | 0 | Carpenter | 0 | 85 | 28 | 29 | 43
520 | 1.2.4 | FIT-OUT WORKS | 185 | 13 September 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 11 | 17 | 61 | 51
521 | 1.2.4.1 | Basement 2 - Services & Fitoff | 140 | 13 September 2024 8:00 AM | 7 March 2025 5:00 PM |  |  | - | - | 0 | Landscaper | 0 | 43 | 27 | 67 | 13
522 | 1.2.4.1.1 | Services rough in | 60 | 13 September 2024 8:00 AM | 23 November 2024 5:00 PM | 107 | 523 | - | - | 0 | Plumber | 0 | 58 | 33 | 81 | 31
523 | 1.2.4.1.2 | Block walls (Metal Door Frames) | 6 | 25 November 2024 8:00 AM | 30 November 2024 5:00 PM | 522 | 524,525 | - | - | 0 | Window | 0 | 57 | 31 | 65 | 10
524 | 1.2.4.1.3 | Render works as specified | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 527 | - | - | 0 | Reinforcement Fixer | 0 | 39 | 27 | 92 | 16
525 | 1.2.4.1.4 | Carpentry fitoff | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 526 | - | - | 0 | Painter | 0 | 79 | 13 | 2 | 50
526 | 1.2.4.1.5 | Services Plant & Equipment Install | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 525 |  | - | - | 0 | Post Tension | 0 | 54 | 24 | 59 | 3
527 | 1.2.4.1.6 | Doors & Hardware | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 524 | 528 | - | - | 0 | Carpet | 0 | 34 | 34 | 93 | 12
528 | 1.2.4.1.7 | Services Fitoff | 12 | 8 January 2025 8:00 AM | 21 January 2025 5:00 PM | 527 | 529 | - | - | 0 | Carpet | 0 | 11 | 35 | 69 | 33
529 | 1.2.4.1.8 | Finishes & Painting | 12 | 22 January 2025 8:00 AM | 5 February 2025 5:00 PM | 528 | 530 | - | - | 0 | Carpet | 0 | 81 | 23 | 76 | 58
530 | 1.2.4.1.9 | Metalwork Items | 8 | 6 February 2025 8:00 AM | 14 February 2025 5:00 PM | 529 | 531 | - | - | 0 | Carpet | 0 | 27 | 26 | 22 | 18
531 | 1.2.4.1.10 | Builders Clean | 6 | 15 February 2025 8:00 AM | 21 February 2025 5:00 PM | 530 | 532 | - | - | 0 | Painter | 0 | 61 | 20 | 60 | 9
532 | 1.2.4.1.11 | Car Park Clean, Patch and Floor Sealer | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 531 | 533 | - | - | 0 | Waterproofer | 0 | 72 | 31 | 23 | 38
533 | 1.2.4.1.12 | Line Marking | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 532 |  | - | - | 0 | Excavation | 0 | 93 | 31 | 3 | 27
534 | 1.2.4.2 | Basement 1 - Services & Fitoff | 140 | 1 October 2024 8:00 AM | 25 March 2025 5:00 PM |  |  | - | - | 0 | Painter | 0 | 47 | 22 | 79 | 3
535 | 1.2.4.2.1 | Services rough in | 60 | 1 October 2024 8:00 AM | 11 December 2024 5:00 PM | 119 | 536 | - | - | 0 | Electrician | 0 | 89 | 18 | 24 | 34
536 | 1.2.4.2.2 | Block walls (Metal Door Frames) | 6 | 12 December 2024 8:00 AM | 18 December 2024 5:00 PM | 535 | 537,538 | - | - | 0 | Plasterboarder | 0 | 81 | 24 | 44 | 31
537 | 1.2.4.2.3 | Render works as specified | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 540 | - | - | 0 | Carpet | 0 | 40 | 20 | 22 | 15
538 | 1.2.4.2.4 | Carpentry fitoff | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 539 | - | - | 0 | Timber Floorer | 0 | 46 | 22 | 0 | 41
539 | 1.2.4.2.5 | Services Plant & Equipment Install | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 538 |  | - | - | 0 | Subcontractor | 0 | 67 | 16 | 77 | 36
540 | 1.2.4.2.6 | Doors & Hardware | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 537 | 541 | - | - | 0 | Joiner | 0 | 83 | 32 | 11 | 27
541 | 1.2.4.2.7 | Services Fitoff | 12 | 27 January 2025 8:00 AM | 8 February 2025 5:00 PM | 540 | 542 | - | - | 0 | Hoarding | 0 | 92 | 14 | 63 | 43
542 | 1.2.4.2.8 | Finishes & Painting | 12 | 10 February 2025 8:00 AM | 22 February 2025 5:00 PM | 541 | 543 | - | - | 0 | Head Contractor | 0 | 59 | 22 | 30 | 11
543 | 1.2.4.2.9 | Metalwork Items | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 542 | 544 | - | - | 0 | Concretor | 0 | 100 | 19 | 7 | 53
544 | 1.2.4.2.10 | Builders Clean | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 543 | 545 | - | - | 0 | Reinforcement Fixer | 0 | 99 | 33 | 94 | 29
545 | 1.2.4.2.11 | Car Park Clean, Patch and Floor Sealer | 8 | 12 March 2025 8:00 AM | 20 March 2025 5:00 PM | 544 | 546 | - | - | 0 | Concretor | 0 | 93 | 33 | 72 | 28
546 | 1.2.4.2.12 | Line Marking | 4 | 21 March 2025 8:00 AM | 25 March 2025 5:00 PM | 545 |  | - | - | 0 | Electrician | 0 | 67 | 20 | 100 | 35
547 | 1.2.4.3 | Building A | 155 | 21 October 2024 8:00 AM | 5 May 2025 5:00 PM |  | 3440 | - | - | 0 | Tiler | 0 | 83 | 19 | 61 | 32
548 | 1.2.4.3.1 | Lvl 1 - Services & Finishes | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 73 | 13 | 48 | 17
549 | 1.2.4.3.1.1 | Internal Works | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | - | - | 0 | Scaffolder | 0 | 83 | 34 | 44 | 35
550 | 1.2.4.3.1.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 150 | 551FS-2d | - | - | 0 | Site Manager | 0 | 59 | 35 | 31 | 51
551 | 1.2.4.3.1.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 550FS-2d | 552 | - | - | 0 | Landscaper | 0 | 75 | 12 | 67 | 49
552 | 1.2.4.3.1.1.3 | Internal Wall Framing | 10 | 1 November 2024 8:00 AM | 12 November 2024 5:00 PM | 551 | 554,553 | - | - | 0 | Floor Sealer | 0 | 22 | 22 | 76 | 45
553 | 1.2.4.3.1.1.4 | Sheet one side of walls | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 556,555 | - | - | 0 | Excavation | 0 | 53 | 28 | 29 | 24
554 | 1.2.4.3.1.1.5 | Service Rough-In | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 555 | - | - | 0 | Cleaner | 0 | 47 | 28 | 97 | 26
555 | 1.2.4.3.1.1.6 | ITP for services in the walls | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 553,554 | 556,562 | - | - | 0 | Reinforcement Fixer | 0 | 73 | 29 | 73 | 42
556 | 1.2.4.3.1.1.7 | Sheet other side of walls | 8 | 25 November 2024 8:00 AM | 3 December 2024 5:00 PM | 553,555 | 557 | - | - | 0 | Stone Mason | 0 | 70 | 15 | 12 | 40
557 | 1.2.4.3.1.1.8 | Frame & Sheet Ceilings | 8 | 4 December 2024 8:00 AM | 12 December 2024 5:00 PM | 556 | 558 | - | - | 0 | Excavation | 0 | 76 | 34 | 73 | 3
558 | 1.2.4.3.1.1.9 | Sheet, Set & Sand Ceilings | 8 | 13 December 2024 8:00 AM | 21 December 2024 5:00 PM | 557,405 | 559 | - | - | 0 | Formworker | 0 | 51 | 27 | 13 | 4
559 | 1.2.4.3.1.1.10 | Paint undercoat | 4 | 23 December 2024 8:00 AM | 4 January 2025 5:00 PM | 558 | 560 | - | - | 0 | Window | 0 | 84 | 27 | 82 | 10
560 | 1.2.4.3.1.1.11 | Floor Levelling and Floor Finish | 6 | 6 January 2025 8:00 AM | 11 January 2025 5:00 PM | 559 | 561 | - | - | 0 | Hoarding | 0 | 51 | 20 | 38 | 39
561 | 1.2.4.3.1.1.12 | Timber Flooring | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 560 | 567,568,563 | - | - | 0 | Line Market | 0 | 81 | 24 | 88 | 18
562 | 1.2.4.3.1.1.13 | Measure & Manufacture Joinery | 40 | 25 November 2024 8:00 AM | 18 January 2025 5:00 PM | 555 | 563 | - | - | 0 | Mechanical | 0 | 57 | 17 | 8 | 20
563 | 1.2.4.3.1.1.14 | Install Joinery | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 561,562 | 565 | - | - | 0 | Cleaner | 0 | 91 | 27 | 64 | 6
564 | 1.2.4.3.1.1.15 | Measure & Manufacture Stone Benchtops | 12 | 17 January 2025 8:00 AM | 1 February 2025 8:00 AM | 565SF |  | - | - | 0 | Project Manager | 0 | 59 | 16 | 15 | 52
565 | 1.2.4.3.1.1.16 | Install Stone Benchtops | 5 | 1 February 2025 8:00 AM | 6 February 2025 5:00 PM | 563 | 564SF,566 | - | - | 0 | Contract Administrator | 0 | 43 | 30 | 30 | 29
566 | 1.2.4.3.1.1.17 | Fixtures & Fittings Fit-off | 3 | 7 February 2025 8:00 AM | 10 February 2025 5:00 PM | 565 | 574 | - | - | 0 | Surveyor | 0 | 44 | 30 | 46 | 13
567 | 1.2.4.3.1.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 561 | 569 | - | - | 0 | Cleaner | 0 | 83 | 15 | 32 | 27
568 | 1.2.4.3.1.1.19 | Lighting Fit-off | 3 | 22 January 2025 8:00 AM | 24 January 2025 5:00 PM | 561 | 569 | - | - | 0 | Site Manager | 0 | 35 | 23 | 18 | 57
569 | 1.2.4.3.1.1.20 | Setting Defects | 4 | 28 January 2025 8:00 AM | 31 January 2025 5:00 PM | 567,568 | 570 | - | - | 0 | Landscaper | 0 | 90 | 31 | 80 | 7
570 | 1.2.4.3.1.1.21 | Paint Finish Coat | 4 | 1 February 2025 8:00 AM | 5 February 2025 5:00 PM | 569 | 573,571 | - | - | 0 | Development Manager | 0 | 16 | 34 | 94 | 22
571 | 1.2.4.3.1.1.22 | Carpet | 3 | 6 February 2025 8:00 AM | 8 February 2025 5:00 PM | 570 | 572 | - | - | 0 | Head Contractor | 0 | 26 | 29 | 74 | 55
572 | 1.2.4.3.1.1.23 | Final Clean & Commissioning | 4 | 10 February 2025 8:00 AM | 13 February 2025 5:00 PM | 571 |  | - | - | 0 | Cleaner | 0 | 23 | 31 | 0 | 10
573 | 1.2.4.3.1.1.24 | Defects Inspections & Rectifications | 6 | 6 February 2025 8:00 AM | 12 February 2025 5:00 PM | 570 | 574 | - | - | 0 | Carpenter | 0 | 48 | 15 | 56 | 10
574 | 1.2.4.3.1.2 | LVL 1 - FITOUT COMPLETE | 0 | 12 February 2025 5:00 PM | 12 February 2025 5:00 PM | 566,573 |  | - | - | 0 | Project Manager | 0 | 40 | 22 | 65 | 37
575 | 1.2.4.3.2 | Lvl 2 - Services & Finishes | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | - | - | 0 | Window | 0 | 18 | 28 | 79 | 12
576 | 1.2.4.3.2.1 | Internal Works | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | - | - | 0 | Plumber | 0 | 27 | 19 | 42 | 60
577 | 1.2.4.3.2.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 408,150 | 578FS-2d | - | - | 0 | Fire | 0 | 67 | 20 | 94 | 20
578 | 1.2.4.3.2.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 577FS-2d | 579 | - | - | 0 | Hoarding | 0 | 31 | 14 | 67 | 34
579 | 1.2.4.3.2.1.3 | Internal Wall Framing | 8 | 1 November 2024 8:00 AM | 9 November 2024 5:00 PM | 578 | 581,580 | - | - | 0 | Carpet | 0 | 79 | 19 | 63 | 33
580 | 1.2.4.3.2.1.4 | Sheet one side of walls | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 583,582 | - | - | 0 | Contract Administrator | 0 | 91 | 30 | 89 | 25
581 | 1.2.4.3.2.1.5 | Service Rough-In | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 582 | - | - | 0 | Carpenter | 0 | 73 | 12 | 13 | 40
582 | 1.2.4.3.2.1.6 | ITP for services in the walls | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 580,581 | 583,589 | - | - | 0 | Mechanical | 0 | 66 | 22 | 30 | 39
583 | 1.2.4.3.2.1.7 | Sheet other side of walls | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 580,582 | 584 | - | - | 0 | Contract Administrator | 0 | 66 | 34 | 18 | 45
584 | 1.2.4.3.2.1.8 | Frame & Sheet Ceilings | 8 | 2 December 2024 8:00 AM | 10 December 2024 5:00 PM | 583 | 585 | - | - | 0 | Head Contractor | 0 | 80 | 23 | 70 | 7
585 | 1.2.4.3.2.1.9 | Sheet, Set & Sand Ceilings | 8 | 11 December 2024 8:00 AM | 19 December 2024 5:00 PM | 584,411 | 586 | - | - | 0 | Line Market | 0 | 61 | 18 | 62 | 31
586 | 1.2.4.3.2.1.10 | Paint undercoat | 4 | 20 December 2024 8:00 AM | 24 December 2024 5:00 PM | 585 | 587 | - | - | 0 | Foreman | 0 | 80 | 12 | 26 | 8
587 | 1.2.4.3.2.1.11 | Floor Levelling and Floor Finish | 6 | 3 January 2025 8:00 AM | 9 January 2025 5:00 PM | 586 | 588 | - | - | 0 | Concretor | 0 | 72 | 30 | 38 | 38
588 | 1.2.4.3.2.1.12 | Timber Flooring | 6 | 10 January 2025 8:00 AM | 16 January 2025 5:00 PM | 587 | 594,595,590 | - | - | 0 | Head Contractor | 0 | 44 | 32 | 67 | 10
589 | 1.2.4.3.2.1.13 | Measure & Manufacture Joinery | 40 | 22 November 2024 8:00 AM | 16 January 2025 5:00 PM | 582 | 590 | - | - | 0 | Hoarding | 0 | 44 | 10 | 45 | 49
590 | 1.2.4.3.2.1.14 | Install Joinery | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 588,589 | 592 | - | - | 0 | Plumber | 0 | 25 | 29 | 85 | 19
591 | 1.2.4.3.2.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 January 2025 8:00 AM | 28 January 2025 8:00 AM | 592SF |  | - | - | 0 | Metal Work | 0 | 66 | 24 | 95 | 25
592 | 1.2.4.3.2.1.16 | Install Stone Benchtops | 5 | 28 January 2025 8:00 AM | 1 February 2025 5:00 PM | 590 | 591SF,593 | - | - | 0 | Concretor | 0 | 36 | 11 | 73 | 44
593 | 1.2.4.3.2.1.17 | Fixtures & Fittings Fit-off | 3 | 3 February 2025 8:00 AM | 5 February 2025 5:00 PM | 592 | 601 | - | - | 0 | Plumber | 0 | 59 | 22 | 44 | 18
594 | 1.2.4.3.2.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 17 January 2025 8:00 AM | 21 January 2025 5:00 PM | 588 | 596 | - | - | 0 | Formworker | 0 | 36 | 13 | 27 | 48
595 | 1.2.4.3.2.1.19 | Lighting Fit-off | 3 | 17 January 2025 8:00 AM | 20 January 2025 5:00 PM | 588 | 596 | - | - | 0 | Painter | 0 | 96 | 15 | 29 | 31
596 | 1.2.4.3.2.1.20 | Setting Defects | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 594,595 | 597 | - | - | 0 | Formworker | 0 | 33 | 33 | 86 | 9
597 | 1.2.4.3.2.1.21 | Paint Finish Coat | 3 | 28 January 2025 8:00 AM | 30 January 2025 5:00 PM | 596 | 600,598 | - | - | 0 | Electrician | 0 | 40 | 19 | 61 | 5
598 | 1.2.4.3.2.1.22 | Carpet | 2 | 31 January 2025 8:00 AM | 1 February 2025 5:00 PM | 597 | 599 | - | - | 0 | Post Tension | 0 | 58 | 20 | 17 | 47
599 | 1.2.4.3.2.1.23 | Final Clean & Commissioning | 4 | 3 February 2025 8:00 AM | 6 February 2025 5:00 PM | 598 |  | - | - | 0 | Waterproofer | 0 | 27 | 32 | 89 | 27
600 | 1.2.4.3.2.1.24 | Defects Inspections & Rectifications | 6 | 31 January 2025 8:00 AM | 6 February 2025 5:00 PM | 597 | 601 | - | - | 0 | Plasterboarder | 0 | 75 | 21 | 82 | 32
601 | 1.2.4.3.2.2 | LVL 2 - FITOUT COMPLETE | 0 | 6 February 2025 5:00 PM | 6 February 2025 5:00 PM | 593,600 |  | - | - | 0 | Carpenter | 0 | 92 | 34 | 14 | 53
602 | 1.2.4.3.3 | Lvl 3 - Services & Finishes | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | - | - | 0 | Scaffolder | 0 | 92 | 27 | 92 | 7
603 | 1.2.4.3.3.1 | Internal Works | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | - | - | 0 | Foreman | 0 | 24 | 27 | 76 | 22
604 | 1.2.4.3.3.1.1 | Pre-load Levels | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 174 | 605FS-2d | - | - | 0 | Carpenter | 0 | 70 | 21 | 11 | 60
605 | 1.2.4.3.3.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 25 November 2024 8:00 AM | 5 December 2024 5:00 PM | 604FS-2d | 606 | - | - | 0 | Stone Mason | 0 | 36 | 27 | 51 | 47
606 | 1.2.4.3.3.1.3 | Internal Wall Framing | 8 | 6 December 2024 8:00 AM | 14 December 2024 5:00 PM | 605 | 608,607 | - | - | 0 | Surveyor | 0 | 28 | 30 | 2 | 15
607 | 1.2.4.3.3.1.4 | Sheet one side of walls | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 610,609 | - | - | 0 | Renderer | 0 | 59 | 19 | 60 | 60
608 | 1.2.4.3.3.1.5 | Service Rough-In | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 609 | - | - | 0 | Carpet | 0 | 82 | 14 | 10 | 17
609 | 1.2.4.3.3.1.6 | ITP for services in the walls | 2 | 3 January 2025 8:00 AM | 4 January 2025 5:00 PM | 607,608 | 610,616 | - | - | 0 | Subcontractor | 0 | 85 | 15 | 41 | 46
610 | 1.2.4.3.3.1.7 | Sheet other side of walls | 8 | 6 January 2025 8:00 AM | 14 January 2025 5:00 PM | 607,609,416FS-6d | 611 | - | - | 0 | Fire | 0 | 97 | 19 | 28 | 22
611 | 1.2.4.3.3.1.8 | Frame & Sheet Ceilings | 8 | 15 January 2025 8:00 AM | 23 January 2025 5:00 PM | 610 | 612 | - | - | 0 | Reinforcement Fixer | 0 | 91 | 29 | 19 | 19
612 | 1.2.4.3.3.1.9 | Sheet, Set & Sand Ceilings | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 611,417 | 613 | - | - | 0 | Fire | 0 | 38 | 26 | 2 | 39
613 | 1.2.4.3.3.1.10 | Paint undercoat | 4 | 4 February 2025 8:00 AM | 7 February 2025 5:00 PM | 612 | 614 | - | - | 0 | Mechanical | 0 | 94 | 13 | 3 | 59
614 | 1.2.4.3.3.1.11 | Floor Levelling and Floor Finish | 7 | 8 February 2025 8:00 AM | 15 February 2025 5:00 PM | 613 | 615 | - | - | 0 | Surveyor | 0 | 80 | 34 | 75 | 48
615 | 1.2.4.3.3.1.12 | Timber Flooring | 6 | 17 February 2025 8:00 AM | 22 February 2025 5:00 PM | 614 | 621,622,617 | - | - | 0 | Plasterboarder | 0 | 63 | 24 | 42 | 51
616 | 1.2.4.3.3.1.13 | Measure & Manufacture Joinery | 40 | 6 January 2025 8:00 AM | 21 February 2025 5:00 PM | 609 | 617 | - | - | 0 | Metal Work | 0 | 91 | 11 | 40 | 36
617 | 1.2.4.3.3.1.14 | Install Joinery | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 615,616 | 619 | - | - | 0 | Renderer | 0 | 15 | 32 | 55 | 14
618 | 1.2.4.3.3.1.15 | Measure & Manufacture Stone Benchtops | 12 | 19 February 2025 8:00 AM | 5 March 2025 8:00 AM | 619SF |  | - | - | 0 | Carpet | 0 | 77 | 34 | 38 | 29
619 | 1.2.4.3.3.1.16 | Install Stone Benchtops | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 617 | 618SF,620 | - | - | 0 | Tiler | 0 | 99 | 31 | 51 | 44
620 | 1.2.4.3.3.1.17 | Fixtures & Fittings Fit-off | 3 | 12 March 2025 8:00 AM | 14 March 2025 5:00 PM | 619 | 628 | - | - | 0 | Foreman | 0 | 10 | 28 | 2 | 14
621 | 1.2.4.3.3.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 24 February 2025 8:00 AM | 27 February 2025 5:00 PM | 615 | 623 | - | - | 0 | Head Contractor | 0 | 15 | 16 | 80 | 23
622 | 1.2.4.3.3.1.19 | Lighting Fit-off | 3 | 24 February 2025 8:00 AM | 26 February 2025 5:00 PM | 615 | 623 | - | - | 0 | Formworker | 0 | 43 | 34 | 89 | 35
623 | 1.2.4.3.3.1.20 | Setting Defects | 4 | 28 February 2025 8:00 AM | 4 March 2025 5:00 PM | 621,622 | 624 | - | - | 0 | Concretor | 0 | 43 | 16 | 75 | 19
624 | 1.2.4.3.3.1.21 | Paint Finish Coat | 3 | 5 March 2025 8:00 AM | 7 March 2025 5:00 PM | 623 | 627,625 | - | - | 0 | Plasterboarder | 0 | 68 | 30 | 22 | 46
625 | 1.2.4.3.3.1.22 | Carpet | 2 | 8 March 2025 8:00 AM | 10 March 2025 5:00 PM | 624 | 626 | - | - | 0 | Plumber | 0 | 29 | 21 | 10 | 52
626 | 1.2.4.3.3.1.23 | Final Clean & Commissioning | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 625 |  | - | - | 0 | Hoarding | 0 | 50 | 11 | 93 | 48
627 | 1.2.4.3.3.1.24 | Defects Inspections & Rectifications | 8 | 8 March 2025 8:00 AM | 17 March 2025 5:00 PM | 624 | 628 | - | - | 0 | Head Contractor | 0 | 40 | 10 | 75 | 23
628 | 1.2.4.3.3.2 | LVL 3 - FITOUT COMPLETE | 0 | 17 March 2025 5:00 PM | 17 March 2025 5:00 PM | 620,627 | 753 | - | - | 0 | Project Manager | 0 | 24 | 13 | 28 | 40
629 | 1.2.4.3.4 | Lvl 4 - Services & Finishes | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 14 | 34 | 100 | 22
630 | 1.2.4.3.4.1 | Internal Works | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 82 | 18 | 41 | 26
631 | 1.2.4.3.4.1.1 | Pre-load Levels | 2 | 11 December 2024 8:00 AM | 12 December 2024 5:00 PM | 186 | 632FS-2d | - | - | 0 | Tiler | 0 | 13 | 31 | 12 | 31
632 | 1.2.4.3.4.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 11 December 2024 8:00 AM | 21 December 2024 5:00 PM | 631FS-2d | 633 | - | - | 0 | Renderer | 0 | 31 | 21 | 15 | 12
633 | 1.2.4.3.4.1.3 | Internal Wall Framing | 8 | 23 December 2024 8:00 AM | 9 January 2025 5:00 PM | 632 | 635,634 | - | - | 0 | Waterproofer | 0 | 64 | 33 | 14 | 24
634 | 1.2.4.3.4.1.4 | Sheet one side of walls | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 637,636 | - | - | 0 | Reinforcement Fixer | 0 | 98 | 18 | 56 | 44
635 | 1.2.4.3.4.1.5 | Service Rough-In | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 636 | - | - | 0 | Development Manager | 0 | 20 | 10 | 7 | 17
636 | 1.2.4.3.4.1.6 | ITP for services in the walls | 2 | 20 January 2025 8:00 AM | 21 January 2025 5:00 PM | 634,635 | 637,643 | - | - | 0 | Renderer | 0 | 23 | 28 | 56 | 25
637 | 1.2.4.3.4.1.7 | Sheet other side of walls | 8 | 10 February 2025 8:00 AM | 18 February 2025 5:00 PM | 634,636,422FS-6d | 638 | - | - | 0 | Concretor | 0 | 100 | 22 | 22 | 51
638 | 1.2.4.3.4.1.8 | Frame & Sheet Ceilings | 8 | 19 February 2025 8:00 AM | 27 February 2025 5:00 PM | 637 | 639 | - | - | 0 | Carpenter | 0 | 79 | 12 | 63 | 20
639 | 1.2.4.3.4.1.9 | Sheet, Set & Sand Ceilings | 8 | 28 February 2025 8:00 AM | 8 March 2025 5:00 PM | 638,423 | 640 | - | - | 0 | Timber Floorer | 0 | 25 | 16 | 9 | 38
640 | 1.2.4.3.4.1.10 | Paint undercoat | 4 | 10 March 2025 8:00 AM | 13 March 2025 5:00 PM | 639 | 641 | - | - | 0 | Tiler | 0 | 34 | 26 | 56 | 52
641 | 1.2.4.3.4.1.11 | Floor Levelling and Floor Finish | 6 | 14 March 2025 8:00 AM | 20 March 2025 5:00 PM | 640 | 642 | - | - | 0 | Post Tension | 0 | 70 | 28 | 21 | 49
642 | 1.2.4.3.4.1.12 | Timber Flooring | 6 | 21 March 2025 8:00 AM | 27 March 2025 5:00 PM | 641 | 648,649,644 | - | - | 0 | Electrician | 0 | 27 | 20 | 3 | 14
643 | 1.2.4.3.4.1.13 | Measure & Manufacture Joinery | 40 | 22 January 2025 8:00 AM | 10 March 2025 5:00 PM | 636 | 644 | - | - | 0 | Carpet | 0 | 26 | 30 | 28 | 29
644 | 1.2.4.3.4.1.14 | Install Joinery | 8 | 28 March 2025 8:00 AM | 5 April 2025 5:00 PM | 642,643 | 646 | - | - | 0 | Mechanical | 0 | 49 | 31 | 60 | 48
645 | 1.2.4.3.4.1.15 | Measure & Manufacture Stone Benchtops | 12 | 24 March 2025 8:00 AM | 7 April 2025 8:00 AM | 646SF |  | - | - | 0 | Development Manager | 0 | 17 | 34 | 30 | 47
646 | 1.2.4.3.4.1.16 | Install Stone Benchtops | 6 | 7 April 2025 8:00 AM | 12 April 2025 5:00 PM | 644 | 645SF,647 | - | - | 0 | Fire | 0 | 26 | 31 | 58 | 39
647 | 1.2.4.3.4.1.17 | Fixtures & Fittings Fit-off | 3 | 14 April 2025 8:00 AM | 16 April 2025 5:00 PM | 646 | 655 | - | - | 0 | Plumber | 0 | 55 | 19 | 34 | 25
648 | 1.2.4.3.4.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 28 March 2025 8:00 AM | 1 April 2025 5:00 PM | 642 | 650 | - | - | 0 | Metal Work | 0 | 59 | 17 | 67 | 54
649 | 1.2.4.3.4.1.19 | Lighting Fit-off | 3 | 28 March 2025 8:00 AM | 31 March 2025 5:00 PM | 642 | 650 | - | - | 0 | Electrician | 0 | 42 | 11 | 43 | 46
650 | 1.2.4.3.4.1.20 | Setting Defects | 4 | 2 April 2025 8:00 AM | 5 April 2025 5:00 PM | 648,649 | 651 | - | - | 0 | Plasterboarder | 0 | 19 | 28 | 75 | 54
651 | 1.2.4.3.4.1.21 | Paint Finish Coat | 3 | 7 April 2025 8:00 AM | 9 April 2025 5:00 PM | 650 | 654,652 | - | - | 0 | Subcontractor | 0 | 65 | 26 | 87 | 54
652 | 1.2.4.3.4.1.22 | Carpet | 2 | 10 April 2025 8:00 AM | 11 April 2025 5:00 PM | 651 | 653 | - | - | 0 | Cleaner | 0 | 77 | 11 | 66 | 5
653 | 1.2.4.3.4.1.23 | Final Clean & Commissioning | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 652 |  | - | - | 0 | Metal Work | 0 | 92 | 31 | 33 | 43
654 | 1.2.4.3.4.1.24 | Defects Inspections & Rectifications | 8 | 10 April 2025 8:00 AM | 22 April 2025 5:00 PM | 651 | 655 | - | - | 0 | Concretor | 0 | 68 | 19 | 96 | 23
655 | 1.2.4.3.4.2 | LVL 4 - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 647,654 | 753 | - | - | 0 | Timber Floorer | 0 | 13 | 30 | 94 | 45
656 | 1.2.4.3.5 | Lvl 5 - Services & Finishes | 100 | 12 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | - | - | 0 | Development Manager | 0 | 70 | 19 | 59 | 10
657 | 1.2.4.3.5.1 | Survey & Setout | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 289,198 | 658FS-1d | - | - | 0 | Landscaper | 0 | 95 | 16 | 42 | 25
658 | 1.2.4.3.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 657FS-1d | 660,663 | - | - | 0 | Scaffolder | 0 | 57 | 13 | 46 | 39
659 | 1.2.4.3.5.3 | External Works | 34 | 17 December 2024 8:00 AM | 4 February 2025 5:00 PM |  |  | - | - | 0 | Project Manager | 0 | 45 | 13 | 9 | 23
660 | 1.2.4.3.5.3.1 | Façade & External Walls | 18 | 17 December 2024 8:00 AM | 15 January 2025 5:00 PM | 658 | 661 | - | - | 0 | Electrician | 0 | 89 | 18 | 89 | 35
661 | 1.2.4.3.5.3.2 | Windows Install | 16 | 16 January 2025 8:00 AM | 4 February 2025 5:00 PM | 660 | 669FS-6d | - | - | 0 | Surveyor | 0 | 91 | 24 | 92 | 50
662 | 1.2.4.3.5.4 | Internal Works | 91 | 23 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | - | - | 0 | Painter | 0 | 10 | 26 | 28 | 39
663 | 1.2.4.3.5.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 658,426 | 664FS-2d | - | - | 0 | Project Manager | 0 | 25 | 25 | 33 | 17
664 | 1.2.4.3.5.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 663FS-2d | 665 | - | - | 0 | Joiner | 0 | 95 | 23 | 52 | 17
665 | 1.2.4.3.5.4.3 | Internal Wall Framing | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 664 | 667,666 | - | - | 0 | Mechanical | 0 | 25 | 17 | 54 | 3
666 | 1.2.4.3.5.4.4 | Sheet one side of walls | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 669,668 | - | - | 0 | Window | 0 | 48 | 33 | 18 | 58
667 | 1.2.4.3.5.4.5 | Service Rough-In | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 668 | - | - | 0 | Landscaper | 0 | 26 | 20 | 86 | 54
668 | 1.2.4.3.5.4.6 | ITP for services in the walls | 2 | 1 February 2025 8:00 AM | 3 February 2025 5:00 PM | 666,667 | 669,675 | - | - | 0 | Cleaner | 0 | 32 | 24 | 85 | 55
669 | 1.2.4.3.5.4.7 | Sheet other side of walls | 8 | 4 February 2025 8:00 AM | 12 February 2025 5:00 PM | 661FS-6d,666,668,428FS-6d | 670 | - | - | 0 | Stone Mason | 0 | 98 | 28 | 22 | 31
670 | 1.2.4.3.5.4.8 | Frame & Sheet Ceilings | 8 | 13 February 2025 8:00 AM | 21 February 2025 5:00 PM | 669 | 671 | - | - | 0 | Hoarding | 0 | 72 | 33 | 21 | 18
671 | 1.2.4.3.5.4.9 | Sheet, Set & Sand Ceilings | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 670,429 | 672 | - | - | 0 | Waterproofer | 0 | 94 | 28 | 34 | 18
672 | 1.2.4.3.5.4.10 | Paint undercoat | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 671 | 673 | - | - | 0 | Renderer | 0 | 56 | 12 | 56 | 51
673 | 1.2.4.3.5.4.11 | Floor Levelling and Floor Finish | 6 | 8 March 2025 8:00 AM | 14 March 2025 5:00 PM | 672 | 674 | - | - | 0 | Excavation | 0 | 36 | 22 | 100 | 60
674 | 1.2.4.3.5.4.12 | Timber Flooring | 6 | 15 March 2025 8:00 AM | 21 March 2025 5:00 PM | 673 | 680,681,676 | - | - | 0 | Plumber | 0 | 72 | 35 | 60 | 40
675 | 1.2.4.3.5.4.13 | Measure & Manufacture Joinery | 40 | 4 February 2025 8:00 AM | 21 March 2025 5:00 PM | 668 | 676 | - | - | 0 | Window | 0 | 27 | 15 | 20 | 5
676 | 1.2.4.3.5.4.14 | Install Joinery | 8 | 22 March 2025 8:00 AM | 31 March 2025 5:00 PM | 674,675 | 678 | - | - | 0 | Site Manager | 0 | 93 | 10 | 6 | 26
677 | 1.2.4.3.5.4.15 | Measure & Manufacture Stone Benchtops | 15 | 14 March 2025 8:00 AM | 1 April 2025 8:00 AM | 678SF | 687 | - | - | 0 | Foreman | 0 | 22 | 28 | 88 | 43
678 | 1.2.4.3.5.4.16 | Install Stone Benchtops | 6 | 1 April 2025 8:00 AM | 7 April 2025 5:00 PM | 676 | 677SF,679 | - | - | 0 | Scaffolder | 0 | 77 | 11 | 97 | 41
679 | 1.2.4.3.5.4.17 | Fixtures & Fittings Fit-off | 8 | 8 April 2025 8:00 AM | 16 April 2025 5:00 PM | 678 | 687 | - | - | 0 | Head Contractor | 0 | 20 | 32 | 99 | 3
680 | 1.2.4.3.5.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 674 | 682 | - | - | 0 | Waterproofer | 0 | 93 | 21 | 9 | 37
681 | 1.2.4.3.5.4.19 | Lighting Fit-off | 3 | 22 March 2025 8:00 AM | 25 March 2025 5:00 PM | 674 | 682 | - | - | 0 | Contract Administrator | 0 | 26 | 19 | 42 | 28
682 | 1.2.4.3.5.4.20 | Setting Defects | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 680,681 | 683 | - | - | 0 | Tiler | 0 | 60 | 32 | 59 | 17
683 | 1.2.4.3.5.4.21 | Paint Finish Coat | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 682 | 686,684 | - | - | 0 | Painter | 0 | 58 | 24 | 14 | 36
684 | 1.2.4.3.5.4.22 | Carpet | 2 | 4 April 2025 8:00 AM | 5 April 2025 5:00 PM | 683 | 685 | - | - | 0 | Head Contractor | 0 | 51 | 13 | 28 | 38
685 | 1.2.4.3.5.4.23 | Final Clean & Commissioning | 10 | 7 April 2025 8:00 AM | 17 April 2025 5:00 PM | 684 | 687 | - | - | 0 | Plasterboarder | 0 | 76 | 32 | 42 | 13
686 | 1.2.4.3.5.4.24 | Defects Inspections & Rectifications | 8 | 4 April 2025 8:00 AM | 12 April 2025 5:00 PM | 683 | 687 | - | - | 0 | Waterproofer | 0 | 12 | 34 | 47 | 13
687 | 1.2.4.3.5.5 | LVL 5 - FITOUT COMPLETE | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 679,686,685,677 |  | - | - | 0 | Site Manager | 0 | 58 | 34 | 96 | 20
688 | 1.2.4.3.6 | Lvl 6 - Services & Finishes | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 75 | 26 | 38 | 12
689 | 1.2.4.3.6.1 | Internal Works | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | - | - | 0 | Excavation | 0 | 50 | 11 | 43 | 24
690 | 1.2.4.3.6.1.1 | Pre-load Levels | 2 | 18 December 2024 8:00 AM | 19 December 2024 5:00 PM | 432,210 | 691FS-2d | - | - | 0 | Project Manager | 0 | 11 | 11 | 31 | 44
691 | 1.2.4.3.6.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 18 December 2024 8:00 AM | 7 January 2025 5:00 PM | 690FS-2d | 692 | - | - | 0 | Carpet | 0 | 59 | 20 | 63 | 37
692 | 1.2.4.3.6.1.3 | Internal Wall Framing | 8 | 8 January 2025 8:00 AM | 16 January 2025 5:00 PM | 691 | 694,693 | - | - | 0 | Plumber | 0 | 67 | 29 | 3 | 59
693 | 1.2.4.3.6.1.4 | Sheet one side of walls | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 696,695 | - | - | 0 | Subcontractor | 0 | 17 | 16 | 36 | 24
694 | 1.2.4.3.6.1.5 | Service Rough-In | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 695 | - | - | 0 | Waterproofer | 0 | 56 | 33 | 28 | 49
695 | 1.2.4.3.6.1.6 | ITP for services in the walls | 2 | 28 January 2025 8:00 AM | 29 January 2025 5:00 PM | 693,694 | 696,702 | - | - | 0 | Foreman | 0 | 82 | 22 | 59 | 46
696 | 1.2.4.3.6.1.7 | Sheet other side of walls | 8 | 30 January 2025 8:00 AM | 7 February 2025 5:00 PM | 693,695,434FS-6d | 697 | - | - | 0 | Subcontractor | 0 | 39 | 13 | 97 | 6
697 | 1.2.4.3.6.1.8 | Frame & Sheet Ceilings | 8 | 8 February 2025 8:00 AM | 17 February 2025 5:00 PM | 696 | 698 | - | - | 0 | Scaffolder | 0 | 33 | 20 | 78 | 15
698 | 1.2.4.3.6.1.9 | Sheet, Set & Sand Ceilings | 8 | 18 February 2025 8:00 AM | 26 February 2025 5:00 PM | 697,435 | 699 | - | - | 0 | Stone Mason | 0 | 59 | 16 | 74 | 48
699 | 1.2.4.3.6.1.10 | Paint undercoat | 4 | 27 February 2025 8:00 AM | 3 March 2025 5:00 PM | 698 | 700 | - | - | 0 | Floor Sealer | 0 | 86 | 17 | 47 | 59
700 | 1.2.4.3.6.1.11 | Floor Levelling and Floor Finish | 6 | 4 March 2025 8:00 AM | 10 March 2025 5:00 PM | 699 | 701 | - | - | 0 | Renderer | 0 | 86 | 20 | 62 | 39
701 | 1.2.4.3.6.1.12 | Timber Flooring | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 700 | 707,708,703 | - | - | 0 | Carpet | 0 | 18 | 30 | 38 | 34
702 | 1.2.4.3.6.1.13 | Measure & Manufacture Joinery | 40 | 30 January 2025 8:00 AM | 17 March 2025 5:00 PM | 695 | 703 | - | - | 0 | Project Manager | 0 | 17 | 30 | 51 | 11
703 | 1.2.4.3.6.1.14 | Install Joinery | 8 | 18 March 2025 8:00 AM | 26 March 2025 5:00 PM | 701,702 | 705 | - | - | 0 | Metal Work | 0 | 22 | 25 | 29 | 58
704 | 1.2.4.3.6.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 March 2025 8:00 AM | 27 March 2025 8:00 AM | 705SF |  | - | - | 0 | Reinforcement Fixer | 0 | 49 | 18 | 92 | 14
705 | 1.2.4.3.6.1.16 | Install Stone Benchtops | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 703 | 704SF,706 | - | - | 0 | Metal Work | 0 | 35 | 13 | 97 | 55
706 | 1.2.4.3.6.1.17 | Fixtures & Fittings Fit-off | 7 | 3 April 2025 8:00 AM | 10 April 2025 5:00 PM | 705 | 714 | - | - | 0 | Formworker | 0 | 18 | 26 | 72 | 56
707 | 1.2.4.3.6.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 18 March 2025 8:00 AM | 21 March 2025 5:00 PM | 701 | 709 | - | - | 0 | Post Tension | 0 | 49 | 24 | 9 | 8
708 | 1.2.4.3.6.1.19 | Lighting Fit-off | 3 | 18 March 2025 8:00 AM | 20 March 2025 5:00 PM | 701 | 709 | - | - | 0 | Development Manager | 0 | 63 | 24 | 48 | 24
709 | 1.2.4.3.6.1.20 | Setting Defects | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 707,708 | 710 | - | - | 0 | Waterproofer | 0 | 42 | 10 | 85 | 34
710 | 1.2.4.3.6.1.21 | Paint Finish Coat | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 709 | 713,711 | - | - | 0 | Subcontractor | 0 | 50 | 14 | 7 | 10
711 | 1.2.4.3.6.1.22 | Carpet | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 710 | 712 | - | - | 0 | Admin | 0 | 30 | 13 | 22 | 28
712 | 1.2.4.3.6.1.23 | Final Clean & Commissioning | 10 | 4 April 2025 8:00 AM | 15 April 2025 5:00 PM | 711 |  | - | - | 0 | Development Manager | 0 | 94 | 12 | 39 | 9
713 | 1.2.4.3.6.1.24 | Defects Inspections & Rectifications | 8 | 1 April 2025 8:00 AM | 9 April 2025 5:00 PM | 710 | 714 | - | - | 0 | Waterproofer | 0 | 76 | 24 | 75 | 35
714 | 1.2.4.3.6.2 | LVL 6 - FITOUT COMPLETE | 0 | 10 April 2025 5:00 PM | 10 April 2025 5:00 PM | 706,713 | 5 | - | - | 0 | Surveyor | 0 | 95 | 34 | 44 | 9
715 | 1.2.4.3.7 | Lvl 7 - Services & Finishes | 105 | 18 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | - | - | 0 | Development Manager | 0 | 69 | 33 | 76 | 3
716 | 1.2.4.3.7.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 301,223 | 717FS-1d | - | - | 0 | Window | 0 | 34 | 23 | 7 | 12
717 | 1.2.4.3.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 716FS-1d | 719,722 | - | - | 0 | Plumber | 0 | 48 | 26 | 48 | 29
718 | 1.2.4.3.7.3 | External Works | 34 | 23 December 2024 8:00 AM | 10 February 2025 5:00 PM |  |  | - | - | 0 | Site Manager | 0 | 96 | 31 | 23 | 51
719 | 1.2.4.3.7.3.1 | Façade & External Walls | 18 | 23 December 2024 8:00 AM | 21 January 2025 5:00 PM | 717 | 720 | - | - | 0 | Metal Work | 0 | 96 | 27 | 72 | 51
720 | 1.2.4.3.7.3.2 | Windows Install | 16 | 22 January 2025 8:00 AM | 10 February 2025 5:00 PM | 719 | 728FS-6d | - | - | 0 | Window | 0 | 70 | 30 | 88 | 53
721 | 1.2.4.3.7.4 | Internal Works | 101 | 23 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 32 | 14 | 26 | 58
722 | 1.2.4.3.7.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 717,438 | 723FS-2d | - | - | 0 | Reinforcement Fixer | 0 | 77 | 20 | 86 | 58
723 | 1.2.4.3.7.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 722FS-2d | 724 | - | - | 0 | Carpet | 0 | 81 | 18 | 41 | 60
724 | 1.2.4.3.7.4.3 | Internal Wall Framing | 10 | 13 January 2025 8:00 AM | 23 January 2025 5:00 PM | 723 | 726,725 | - | - | 0 | Foreman | 0 | 30 | 12 | 89 | 43
725 | 1.2.4.3.7.4.4 | Sheet one side of walls | 9 | 24 January 2025 8:00 AM | 4 February 2025 5:00 PM | 724 | 728,727 | - | - | 0 | Head Contractor | 0 | 37 | 18 | 82 | 13
726 | 1.2.4.3.7.4.5 | Service Rough-In | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 724 | 727 | - | - | 0 | Stone Mason | 0 | 50 | 24 | 18 | 56
727 | 1.2.4.3.7.4.6 | ITP for services in the walls | 2 | 5 February 2025 8:00 AM | 6 February 2025 5:00 PM | 725,726 | 728,734 | - | - | 0 | Painter | 0 | 77 | 17 | 86 | 47
728 | 1.2.4.3.7.4.7 | Sheet other side of walls | 8 | 15 February 2025 8:00 AM | 24 February 2025 5:00 PM | 720FS-6d,725,727,440FS-6d | 729 | - | - | 0 | Metal Work | 0 | 57 | 17 | 25 | 58
729 | 1.2.4.3.7.4.8 | Frame & Sheet Ceilings | 8 | 25 February 2025 8:00 AM | 5 March 2025 5:00 PM | 728 | 730 | - | - | 0 | Tiler | 0 | 50 | 19 | 25 | 51
730 | 1.2.4.3.7.4.9 | Sheet, Set & Sand Ceilings | 8 | 6 March 2025 8:00 AM | 14 March 2025 5:00 PM | 729,441 | 731 | - | - | 0 | Concretor | 0 | 91 | 33 | 1 | 57
731 | 1.2.4.3.7.4.10 | Paint undercoat | 4 | 15 March 2025 8:00 AM | 19 March 2025 5:00 PM | 730 | 732 | - | - | 0 | Tiler | 0 | 31 | 27 | 87 | 30
732 | 1.2.4.3.7.4.11 | Floor Levelling and Floor Finish | 6 | 20 March 2025 8:00 AM | 26 March 2025 5:00 PM | 731 | 733 | - | - | 0 | Stone Mason | 0 | 11 | 17 | 42 | 35
733 | 1.2.4.3.7.4.12 | Timber Flooring | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 732 | 739,740,735 | - | - | 0 | Subcontractor | 0 | 38 | 17 | 63 | 56
734 | 1.2.4.3.7.4.13 | Measure & Manufacture Joinery | 40 | 7 February 2025 8:00 AM | 25 March 2025 5:00 PM | 727 | 735 | - | - | 0 | Surveyor | 0 | 47 | 18 | 68 | 3
735 | 1.2.4.3.7.4.14 | Install Joinery | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733,734 | 737 | - | - | 0 | Metal Work | 0 | 64 | 34 | 18 | 26
736 | 1.2.4.3.7.4.15 | Measure & Manufacture Stone Benchtops | 12 | 29 March 2025 8:00 AM | 12 April 2025 8:00 AM | 737SF | 746 | - | - | 0 | Contract Administrator | 0 | 29 | 17 | 24 | 36
737 | 1.2.4.3.7.4.16 | Install Stone Benchtops | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 735 | 736SF,738 | - | - | 0 | Renderer | 0 | 98 | 34 | 94 | 13
738 | 1.2.4.3.7.4.17 | Fixtures & Fittings Fit-off | 7 | 23 April 2025 8:00 AM | 2 May 2025 5:00 PM | 737 | 746 | - | - | 0 | Foreman | 0 | 18 | 26 | 40 | 24
739 | 1.2.4.3.7.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733 | 741 | - | - | 0 | Mechanical | 0 | 32 | 34 | 96 | 55
740 | 1.2.4.3.7.4.19 | Lighting Fit-off | 5 | 3 April 2025 8:00 AM | 8 April 2025 5:00 PM | 733 | 741 | - | - | 0 | Hoarding | 0 | 41 | 27 | 65 | 20
741 | 1.2.4.3.7.4.20 | Setting Defects | 4 | 12 April 2025 8:00 AM | 16 April 2025 5:00 PM | 739,740 | 742 | - | - | 0 | Cleaner | 0 | 46 | 27 | 81 | 59
742 | 1.2.4.3.7.4.21 | Paint Finish Coat | 4 | 17 April 2025 8:00 AM | 24 April 2025 5:00 PM | 741 | 745,743 | - | - | 0 | Cleaner | 0 | 40 | 31 | 56 | 23
743 | 1.2.4.3.7.4.22 | Carpet | 3 | 28 April 2025 8:00 AM | 30 April 2025 5:00 PM | 742 | 744 | - | - | 0 | Contract Administrator | 0 | 60 | 24 | 92 | 22
744 | 1.2.4.3.7.4.23 | Final Clean & Commissioning | 4 | 1 May 2025 8:00 AM | 5 May 2025 5:00 PM | 743 | 746 | - | - | 0 | Painter | 0 | 21 | 14 | 10 | 5
745 | 1.2.4.3.7.4.24 | Defects Inspections & Rectifications | 6 | 28 April 2025 8:00 AM | 3 May 2025 5:00 PM | 742 | 746 | - | - | 0 | Window | 0 | 75 | 11 | 92 | 36
746 | 1.2.4.3.7.5 | LVL 7 - FITOUT COMPLETE | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 738,745,744,736 | 5,754 | - | - | 0 | Tiler | 0 | 91 | 16 | 37 | 46
747 | 1.2.4.3.8 | Lvl 8 (Roof) - Services | 96 | 7 January 2025 8:00 AM | 5 May 2025 5:00 PM |  |  | - | - | 0 | Concretor | 0 | 62 | 35 | 34 | 55
748 | 1.2.4.3.8.1 | Survey & Setout | 1 | 7 January 2025 8:00 AM | 7 January 2025 5:00 PM | 301FS+24d | 749FS-1d | - | - | 0 | Tiler | 0 | 41 | 11 | 98 | 58
749 | 1.2.4.3.8.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 7 January 2025 8:00 AM | 10 January 2025 5:00 PM | 748FS-1d | 751 | - | - | 0 | Plasterboarder | 0 | 65 | 17 | 27 | 3
750 | 1.2.4.3.8.3 | External Services (Plant) | 56 | 11 January 2025 8:00 AM | 18 March 2025 5:00 PM |  |  | - | - | 0 | Excavation | 0 | 60 | 26 | 27 | 19
751 | 1.2.4.3.8.3.1 | Heat Pumps & Associated Services | 32 | 11 January 2025 8:00 AM | 18 February 2025 5:00 PM | 749 | 752 | - | - | 0 | Reinforcement Fixer | 0 | 95 | 29 | 53 | 54
752 | 1.2.4.3.8.3.2 | Louvres, Balustrades & Roof Safety System | 24 | 19 February 2025 8:00 AM | 18 March 2025 5:00 PM | 751 | 753 | - | - | 0 | Subcontractor | 0 | 31 | 25 | 38 | 47
753 | 1.2.4.3.8.4 | LVL 8 (ROOF) - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 752,655,628 | 5,754 | - | - | 0 | Fire | 0 | 33 | 19 | 1 | 35
754 | 1.2.4.3.8.5 | Building A Fitout Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 753,746 |  | - | - | 0 | Head Contractor | 0 | 97 | 13 | 52 | 6
755 | 1.2.4.4 | Building B | 135 | 14 October 2024 8:00 AM | 29 March 2025 5:00 PM |  | 3440 | - | - | 0 | Stone Mason | 0 | 13 | 24 | 92 | 10
756 | 1.2.4.4.1 | Level 1 | 52 | 14 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 66 | 33 | 49 | 52
757 | 1.2.4.4.1.1 | Apartment B010 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 32 | 12 | 22 | 36
758 | 1.2.4.4.1.1.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 759,762,763,830 | - | - | 0 | Electrician | 0 | 85 | 16 | 54 | 39
759 | 1.2.4.4.1.1.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 758 | 761,760 | - | - | 0 | Painter | 0 | 87 | 11 | 1 | 41
760 | 1.2.4.4.1.1.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 759 |  | - | - | 0 | Metal Work | 0 | 92 | 18 | 75 | 46
761 | 1.2.4.4.1.1.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 759 | 764 | - | - | 0 | Project Manager | 0 | 99 | 19 | 12 | 8
762 | 1.2.4.4.1.1.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 771 | - | - | 0 | Carpenter | 0 | 22 | 27 | 2 | 16
763 | 1.2.4.4.1.1.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 834 | - | - | 0 | Development Manager | 0 | 30 | 21 | 82 | 25
764 | 1.2.4.4.1.1.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 761 | 765,766,767,768,769 | - | - | 0 | Contract Administrator | 0 | 38 | 31 | 91 | 7
765 | 1.2.4.4.1.1.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769 | - | - | 0 | Development Manager | 0 | 68 | 30 | 71 | 34
766 | 1.2.4.4.1.1.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769,833 | - | - | 0 | Timber Floorer | 0 | 18 | 29 | 92 | 18
767 | 1.2.4.4.1.1.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 832 | - | - | 0 | Foreman | 0 | 14 | 23 | 47 | 25
768 | 1.2.4.4.1.1.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 |  | - | - | 0 | Waterproofer | 0 | 27 | 21 | 49 | 51
769 | 1.2.4.4.1.1.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 764,765,766 | 770 | - | - | 0 | Timber Floorer | 0 | 78 | 23 | 87 | 16
770 | 1.2.4.4.1.1.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 769 | 771 | - | - | 0 | Tiler | 0 | 44 | 10 | 63 | 44
771 | 1.2.4.4.1.1.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 762,770 | 772,773,774,775,777,779 | - | - | 0 | Contract Administrator | 0 | 29 | 13 | 81 | 33
772 | 1.2.4.4.1.1.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 776,779 | - | - | 0 | Stone Mason | 0 | 92 | 20 | 44 | 19
773 | 1.2.4.4.1.1.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 779 | - | - | 0 | Scaffolder | 0 | 99 | 32 | 73 | 32
774 | 1.2.4.4.1.1.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 778,779 | - | - | 0 | Foreman | 0 | 65 | 11 | 81 | 18
775 | 1.2.4.4.1.1.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | - | - | 0 | Surveyor | 0 | 21 | 26 | 49 | 39
776 | 1.2.4.4.1.1.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 772 | 779 | - | - | 0 | Cleaner | 0 | 14 | 29 | 62 | 24
777 | 1.2.4.4.1.1.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | - | - | 0 | Fire | 0 | 31 | 28 | 89 | 18
778 | 1.2.4.4.1.1.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 774 | 779 | - | - | 0 | Foreman | 0 | 81 | 12 | 96 | 15
779 | 1.2.4.4.1.1.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 771,772,773,774,775,776,777,778 | 780 | - | - | 0 | Post Tension | 0 | 90 | 14 | 88 | 32
780 | 1.2.4.4.1.1.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 779 | 781 | - | - | 0 | Joiner | 0 | 38 | 24 | 55 | 48
781 | 1.2.4.4.1.1.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 780 | 782,799,816 | - | - | 0 | Floor Sealer | 0 | 22 | 30 | 15 | 33
782 | 1.2.4.4.1.1.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 783 | - | - | 0 | Waterproofer | 0 | 77 | 25 | 2 | 58
783 | 1.2.4.4.1.1.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 782 | 784 | - | - | 0 | Head Contractor | 0 | 62 | 35 | 25 | 13
784 | 1.2.4.4.1.1.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 783 | 785 | - | - | 0 | Carpet | 0 | 68 | 22 | 63 | 56
785 | 1.2.4.4.1.1.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 784 | 786 | - | - | 0 | Hoarding | 0 | 23 | 11 | 97 | 19
786 | 1.2.4.4.1.1.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 785 | 787,788 | - | - | 0 | Landscaper | 0 | 54 | 31 | 76 | 3
787 | 1.2.4.4.1.1.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 786 | 791 | - | - | 0 | Window | 0 | 81 | 20 | 66 | 18
788 | 1.2.4.4.1.1.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 786 | 789 | - | - | 0 | Metal Work | 0 | 41 | 24 | 2 | 57
789 | 1.2.4.4.1.1.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 788 | 790 | - | - | 0 | Painter | 0 | 10 | 26 | 55 | 60
790 | 1.2.4.4.1.1.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 789 |  | - | - | 0 | Development Manager | 0 | 92 | 26 | 36 | 21
791 | 1.2.4.4.1.1.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 787 | 792,793,794,795,796 | - | - | 0 | Site Manager | 0 | 46 | 15 | 77 | 46
792 | 1.2.4.4.1.1.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 791 |  | - | - | 0 | Renderer | 0 | 93 | 30 | 80 | 45
793 | 1.2.4.4.1.1.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Plumber | 0 | 71 | 24 | 58 | 5
794 | 1.2.4.4.1.1.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Floor Sealer | 0 | 100 | 23 | 41 | 4
795 | 1.2.4.4.1.1.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Waterproofer | 0 | 80 | 13 | 16 | 58
796 | 1.2.4.4.1.1.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Stone Mason | 0 | 36 | 14 | 99 | 23
797 | 1.2.4.4.1.1.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 847 | - | - | 0 | Electrician | 0 | 25 | 35 | 34 | 36
798 | 1.2.4.4.1.1.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 90 | 28 | 90 | 32
799 | 1.2.4.4.1.1.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 800 | - | - | 0 | Window | 0 | 97 | 27 | 14 | 10
800 | 1.2.4.4.1.1.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 799 | 801 | - | - | 0 | Concretor | 0 | 15 | 24 | 52 | 9
801 | 1.2.4.4.1.1.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 800 | 802 | - | - | 0 | Mechanical | 0 | 67 | 19 | 84 | 29
802 | 1.2.4.4.1.1.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 801 | 803 | - | - | 0 | Scaffolder | 0 | 13 | 27 | 48 | 47
803 | 1.2.4.4.1.1.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 802 | 804 | - | - | 0 | Excavation | 0 | 10 | 19 | 19 | 26
804 | 1.2.4.4.1.1.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 803 | 805 | - | - | 0 | Plumber | 0 | 26 | 15 | 76 | 17
805 | 1.2.4.4.1.1.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 804 | 806 | - | - | 0 | Waterproofer | 0 | 58 | 24 | 36 | 46
806 | 1.2.4.4.1.1.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 805 | 807 | - | - | 0 | Window | 0 | 35 | 20 | 92 | 7
807 | 1.2.4.4.1.1.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 806 | 808 | - | - | 0 | Tiler | 0 | 70 | 19 | 69 | 51
808 | 1.2.4.4.1.1.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 807 | 809 | - | - | 0 | Timber Floorer | 0 | 72 | 30 | 56 | 15
809 | 1.2.4.4.1.1.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 808 | 810 | - | - | 0 | Project Manager | 0 | 50 | 27 | 44 | 11
810 | 1.2.4.4.1.1.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 809 | 814,811,812,813 | - | - | 0 | Landscaper | 0 | 83 | 22 | 90 | 7
811 | 1.2.4.4.1.1.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | - | - | 0 | Plumber | 0 | 97 | 29 | 7 | 5
812 | 1.2.4.4.1.1.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | - | - | 0 | Admin | 0 | 72 | 29 | 94 | 42
813 | 1.2.4.4.1.1.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | - | - | 0 | Excavation | 0 | 40 | 15 | 83 | 22
814 | 1.2.4.4.1.1.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 810,811,812,813 |  | - | - | 0 | Hoarding | 0 | 12 | 14 | 17 | 51
815 | 1.2.4.4.1.1.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 13 | 25 | 64 | 40
816 | 1.2.4.4.1.1.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 817 | - | - | 0 | Hoarding | 0 | 31 | 19 | 79 | 54
817 | 1.2.4.4.1.1.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 816 | 818 | - | - | 0 | Development Manager | 0 | 15 | 25 | 4 | 49
818 | 1.2.4.4.1.1.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 817 | 819 | - | - | 0 | Waterproofer | 0 | 64 | 34 | 24 | 34
819 | 1.2.4.4.1.1.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 818 | 820 | - | - | 0 | Reinforcement Fixer | 0 | 55 | 22 | 68 | 14
820 | 1.2.4.4.1.1.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 819 | 821 | - | - | 0 | Window | 0 | 84 | 18 | 61 | 58
821 | 1.2.4.4.1.1.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 820 | 822 | - | - | 0 | Site Manager | 0 | 16 | 25 | 74 | 46
822 | 1.2.4.4.1.1.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 821 | 823 | - | - | 0 | Floor Sealer | 0 | 18 | 26 | 65 | 32
823 | 1.2.4.4.1.1.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 822 | 824,825,826,827 | - | - | 0 | Mechanical | 0 | 56 | 22 | 1 | 25
824 | 1.2.4.4.1.1.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Tiler | 0 | 43 | 24 | 42 | 50
825 | 1.2.4.4.1.1.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Concretor | 0 | 100 | 10 | 96 | 49
826 | 1.2.4.4.1.1.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Head Contractor | 0 | 54 | 34 | 25 | 17
827 | 1.2.4.4.1.1.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Carpenter | 0 | 92 | 27 | 75 | 43
828 | 1.2.4.4.1.1.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 824,825,826,827 |  | - | - | 0 | Cleaner | 0 | 70 | 14 | 96 | 27
829 | 1.2.4.4.1.1.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 59 | 11 | 42 | 28
830 | 1.2.4.4.1.1.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 758 | 831 | - | - | 0 | Contract Administrator | 0 | 41 | 27 | 76 | 31
831 | 1.2.4.4.1.1.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 830 |  | - | - | 0 | Site Manager | 0 | 78 | 29 | 100 | 6
832 | 1.2.4.4.1.1.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 767 | 835 | - | - | 0 | Stone Mason | 0 | 12 | 24 | 2 | 60
833 | 1.2.4.4.1.1.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 766 | 835 | - | - | 0 | Contract Administrator | 0 | 21 | 28 | 24 | 57
834 | 1.2.4.4.1.1.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 763 | 835 | - | - | 0 | Renderer | 0 | 83 | 35 | 56 | 23
835 | 1.2.4.4.1.1.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 832,833,834 | 836 | - | - | 0 | Fire | 0 | 82 | 18 | 43 | 25
836 | 1.2.4.4.1.1.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 835 | 837 | - | - | 0 | Admin | 0 | 84 | 14 | 34 | 28
837 | 1.2.4.4.1.1.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 836 | 838 | - | - | 0 | Line Market | 0 | 84 | 23 | 79 | 51
838 | 1.2.4.4.1.1.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 837 | 839 | - | - | 0 | Contract Administrator | 0 | 52 | 32 | 36 | 27
839 | 1.2.4.4.1.1.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 838 | 840 | - | - | 0 | Scaffolder | 0 | 78 | 26 | 17 | 18
840 | 1.2.4.4.1.1.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 839 | 841 | - | - | 0 | Window | 0 | 26 | 35 | 87 | 41
841 | 1.2.4.4.1.1.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 840 | 842 | - | - | 0 | Formworker | 0 | 32 | 32 | 93 | 41
842 | 1.2.4.4.1.1.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 841 | 843,844,845,846 | - | - | 0 | Renderer | 0 | 23 | 17 | 93 | 13
843 | 1.2.4.4.1.1.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Stone Mason | 0 | 83 | 18 | 41 | 35
844 | 1.2.4.4.1.1.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Carpet | 0 | 12 | 24 | 34 | 7
845 | 1.2.4.4.1.1.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Stone Mason | 0 | 81 | 29 | 7 | 24
846 | 1.2.4.4.1.1.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Timber Floorer | 0 | 89 | 10 | 58 | 49
847 | 1.2.4.4.1.1.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 793,794,795,796,797 | 848 | - | - | 0 | Plumber | 0 | 26 | 20 | 23 | 22
848 | 1.2.4.4.1.1.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 847 | 849 | - | - | 0 | Foreman | 0 | 67 | 20 | 68 | 55
849 | 1.2.4.4.1.1.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 848 | 850 | - | - | 0 | Fire | 0 | 18 | 30 | 34 | 29
850 | 1.2.4.4.1.1.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 849 |  | - | - | 0 | Plasterboarder | 0 | 22 | 11 | 71 | 18
851 | 1.2.4.4.1.2 | Apartment B011 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 42 | 30 | 68 | 27
852 | 1.2.4.4.1.2.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 853,856,857,924 | - | - | 0 | Subcontractor | 0 | 73 | 33 | 49 | 59
853 | 1.2.4.4.1.2.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 852 | 855,854 | - | - | 0 | Line Market | 0 | 34 | 16 | 57 | 25
854 | 1.2.4.4.1.2.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 853 |  | - | - | 0 | Formworker | 0 | 72 | 14 | 22 | 9
855 | 1.2.4.4.1.2.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 853 | 858 | - | - | 0 | Development Manager | 0 | 50 | 24 | 19 | 48
856 | 1.2.4.4.1.2.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 865 | - | - | 0 | Post Tension | 0 | 26 | 26 | 19 | 44
857 | 1.2.4.4.1.2.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 928 | - | - | 0 | Subcontractor | 0 | 71 | 10 | 26 | 20
858 | 1.2.4.4.1.2.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 855 | 859,860,861,862,863 | - | - | 0 | Landscaper | 0 | 10 | 35 | 1 | 45
859 | 1.2.4.4.1.2.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863 | - | - | 0 | Carpet | 0 | 86 | 13 | 34 | 25
860 | 1.2.4.4.1.2.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863,927 | - | - | 0 | Line Market | 0 | 34 | 35 | 73 | 22
861 | 1.2.4.4.1.2.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 926 | - | - | 0 | Site Manager | 0 | 34 | 17 | 74 | 28
862 | 1.2.4.4.1.2.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 |  | - | - | 0 | Surveyor | 0 | 42 | 28 | 68 | 39
863 | 1.2.4.4.1.2.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 858,859,860 | 864 | - | - | 0 | Project Manager | 0 | 47 | 15 | 21 | 2
864 | 1.2.4.4.1.2.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 863 | 865 | - | - | 0 | Site Manager | 0 | 53 | 11 | 99 | 41
865 | 1.2.4.4.1.2.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 856,864 | 866,867,868,869,871,873 | - | - | 0 | Hoarding | 0 | 87 | 12 | 46 | 36
866 | 1.2.4.4.1.2.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 870,873 | - | - | 0 | Admin | 0 | 68 | 35 | 73 | 4
867 | 1.2.4.4.1.2.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 873 | - | - | 0 | Plasterboarder | 0 | 28 | 20 | 20 | 3
868 | 1.2.4.4.1.2.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 872,873 | - | - | 0 | Stone Mason | 0 | 18 | 21 | 37 | 39
869 | 1.2.4.4.1.2.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | - | - | 0 | Waterproofer | 0 | 91 | 17 | 7 | 45
870 | 1.2.4.4.1.2.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 866 | 873 | - | - | 0 | Scaffolder | 0 | 13 | 24 | 8 | 3
871 | 1.2.4.4.1.2.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | - | - | 0 | Waterproofer | 0 | 83 | 16 | 76 | 25
872 | 1.2.4.4.1.2.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 868 | 873 | - | - | 0 | Surveyor | 0 | 84 | 11 | 12 | 24
873 | 1.2.4.4.1.2.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 865,866,867,868,869,870,871,872 | 874 | - | - | 0 | Hoarding | 0 | 100 | 33 | 18 | 27
874 | 1.2.4.4.1.2.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 873 | 875 | - | - | 0 | Contract Administrator | 0 | 95 | 28 | 85 | 32
875 | 1.2.4.4.1.2.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 874 | 876,893,910 | - | - | 0 | Fire | 0 | 92 | 14 | 100 | 23
876 | 1.2.4.4.1.2.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 877 | - | - | 0 | Excavation | 0 | 35 | 14 | 60 | 38
877 | 1.2.4.4.1.2.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 876 | 878 | - | - | 0 | Development Manager | 0 | 40 | 24 | 95 | 24
878 | 1.2.4.4.1.2.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 877 | 879 | - | - | 0 | Fire | 0 | 60 | 24 | 8 | 8
879 | 1.2.4.4.1.2.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 878 | 880 | - | - | 0 | Head Contractor | 0 | 44 | 15 | 34 | 24
880 | 1.2.4.4.1.2.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 879 | 881,882 | - | - | 0 | Stone Mason | 0 | 78 | 22 | 87 | 58
881 | 1.2.4.4.1.2.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 880 | 885 | - | - | 0 | Post Tension | 0 | 24 | 14 | 81 | 17
882 | 1.2.4.4.1.2.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 880 | 883 | - | - | 0 | Plumber | 0 | 96 | 14 | 63 | 58
883 | 1.2.4.4.1.2.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 882 | 884 | - | - | 0 | Waterproofer | 0 | 91 | 27 | 11 | 3
884 | 1.2.4.4.1.2.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 883 |  | - | - | 0 | Reinforcement Fixer | 0 | 57 | 16 | 97 | 17
885 | 1.2.4.4.1.2.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 881 | 886,887,888,889,890 | - | - | 0 | Head Contractor | 0 | 34 | 13 | 67 | 52
886 | 1.2.4.4.1.2.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 885 |  | - | - | 0 | Hoarding | 0 | 36 | 11 | 70 | 6
887 | 1.2.4.4.1.2.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Tiler | 0 | 68 | 22 | 70 | 37
888 | 1.2.4.4.1.2.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Surveyor | 0 | 28 | 31 | 30 | 40
889 | 1.2.4.4.1.2.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Site Manager | 0 | 48 | 24 | 66 | 6
890 | 1.2.4.4.1.2.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Renderer | 0 | 67 | 33 | 28 | 22
891 | 1.2.4.4.1.2.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 941 | - | - | 0 | Carpenter | 0 | 81 | 23 | 75 | 50
892 | 1.2.4.4.1.2.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Floor Sealer | 0 | 27 | 26 | 71 | 7
893 | 1.2.4.4.1.2.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 894 | - | - | 0 | Contract Administrator | 0 | 29 | 11 | 93 | 22
894 | 1.2.4.4.1.2.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 893 | 895 | - | - | 0 | Site Manager | 0 | 45 | 26 | 28 | 12
895 | 1.2.4.4.1.2.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 894 | 896 | - | - | 0 | Foreman | 0 | 55 | 20 | 92 | 58
896 | 1.2.4.4.1.2.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 895 | 897 | - | - | 0 | Scaffolder | 0 | 88 | 25 | 20 | 19
897 | 1.2.4.4.1.2.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 896 | 898 | - | - | 0 | Development Manager | 0 | 52 | 18 | 18 | 6
898 | 1.2.4.4.1.2.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 897 | 899 | - | - | 0 | Project Manager | 0 | 27 | 21 | 24 | 41
899 | 1.2.4.4.1.2.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 898 | 900 | - | - | 0 | Plumber | 0 | 41 | 14 | 79 | 10
900 | 1.2.4.4.1.2.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 899 | 901 | - | - | 0 | Head Contractor | 0 | 46 | 11 | 89 | 52
901 | 1.2.4.4.1.2.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 900 | 902 | - | - | 0 | Hoarding | 0 | 30 | 25 | 35 | 3
902 | 1.2.4.4.1.2.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 901 | 903 | - | - | 0 | Electrician | 0 | 53 | 18 | 44 | 36
903 | 1.2.4.4.1.2.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 902 | 904 | - | - | 0 | Carpet | 0 | 66 | 13 | 94 | 40
904 | 1.2.4.4.1.2.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 903 | 908,905,906,907 | - | - | 0 | Landscaper | 0 | 46 | 17 | 65 | 50
905 | 1.2.4.4.1.2.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | - | - | 0 | Scaffolder | 0 | 78 | 24 | 14 | 14
906 | 1.2.4.4.1.2.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | - | - | 0 | Stone Mason | 0 | 38 | 24 | 8 | 37
907 | 1.2.4.4.1.2.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | - | - | 0 | Painter | 0 | 57 | 16 | 10 | 41
908 | 1.2.4.4.1.2.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 904,905,906,907 |  | - | - | 0 | Line Market | 0 | 94 | 26 | 8 | 53
909 | 1.2.4.4.1.2.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | - | - | 0 | Mechanical | 0 | 96 | 15 | 31 | 42
910 | 1.2.4.4.1.2.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 911 | - | - | 0 | Scaffolder | 0 | 70 | 34 | 81 | 27
911 | 1.2.4.4.1.2.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 910 | 912 | - | - | 0 | Line Market | 0 | 10 | 31 | 53 | 46
912 | 1.2.4.4.1.2.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 911 | 913 | - | - | 0 | Joiner | 0 | 19 | 34 | 27 | 60
913 | 1.2.4.4.1.2.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 912 | 914 | - | - | 0 | Line Market | 0 | 14 | 28 | 65 | 48
914 | 1.2.4.4.1.2.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 913 | 915 | - | - | 0 | Surveyor | 0 | 33 | 24 | 0 | 14
915 | 1.2.4.4.1.2.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 914 | 916 | - | - | 0 | Renderer | 0 | 54 | 12 | 75 | 30
916 | 1.2.4.4.1.2.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 915 | 917 | - | - | 0 | Carpet | 0 | 17 | 19 | 39 | 56
917 | 1.2.4.4.1.2.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 916 | 918,919,920,921 | - | - | 0 | Cleaner | 0 | 48 | 12 | 41 | 33
918 | 1.2.4.4.1.2.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Tiler | 0 | 81 | 16 | 67 | 53
919 | 1.2.4.4.1.2.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Surveyor | 0 | 51 | 16 | 8 | 28
920 | 1.2.4.4.1.2.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Tiler | 0 | 11 | 10 | 62 | 10
921 | 1.2.4.4.1.2.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Reinforcement Fixer | 0 | 48 | 17 | 82 | 26
922 | 1.2.4.4.1.2.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 918,919,920,921 |  | - | - | 0 | Stone Mason | 0 | 33 | 10 | 88 | 60
923 | 1.2.4.4.1.2.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | - | - | 0 | Project Manager | 0 | 48 | 32 | 94 | 30
924 | 1.2.4.4.1.2.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 852 | 925 | - | - | 0 | Plasterboarder | 0 | 23 | 20 | 13 | 57
925 | 1.2.4.4.1.2.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 924 |  | - | - | 0 | Formworker | 0 | 98 | 30 | 88 | 14
926 | 1.2.4.4.1.2.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 861 | 929 | - | - | 0 | Renderer | 0 | 75 | 27 | 60 | 44
927 | 1.2.4.4.1.2.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 860 | 929 | - | - | 0 | Carpenter | 0 | 71 | 35 | 79 | 42
928 | 1.2.4.4.1.2.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 857 | 929 | - | - | 0 | Timber Floorer | 0 | 92 | 19 | 28 | 36
929 | 1.2.4.4.1.2.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 926,927,928 | 930 | - | - | 0 | Line Market | 0 | 38 | 11 | 62 | 50
930 | 1.2.4.4.1.2.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 929 | 931 | - | - | 0 | Joiner | 0 | 15 | 24 | 65 | 6
931 | 1.2.4.4.1.2.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 930 | 932 | - | - | 0 | Concretor | 0 | 26 | 29 | 74 | 12
932 | 1.2.4.4.1.2.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 931 | 933 | - | - | 0 | Timber Floorer | 0 | 45 | 21 | 28 | 38
933 | 1.2.4.4.1.2.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 932 | 934 | - | - | 0 | Stone Mason | 0 | 38 | 18 | 1 | 55
934 | 1.2.4.4.1.2.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 933 | 935 | - | - | 0 | Development Manager | 0 | 16 | 10 | 47 | 29
935 | 1.2.4.4.1.2.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 934 | 936 | - | - | 0 | Floor Sealer | 0 | 27 | 33 | 98 | 6
936 | 1.2.4.4.1.2.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 935 | 937,938,939,940 | - | - | 0 | Hoarding | 0 | 50 | 29 | 24 | 15
937 | 1.2.4.4.1.2.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Formworker | 0 | 67 | 16 | 6 | 31
938 | 1.2.4.4.1.2.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Hoarding | 0 | 37 | 14 | 59 | 10
939 | 1.2.4.4.1.2.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Concretor | 0 | 37 | 20 | 91 | 6
940 | 1.2.4.4.1.2.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Joiner | 0 | 20 | 33 | 64 | 19
941 | 1.2.4.4.1.2.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 887,888,889,890,891 | 942 | - | - | 0 | Timber Floorer | 0 | 87 | 16 | 30 | 44
942 | 1.2.4.4.1.2.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 941 | 943 | - | - | 0 | Tiler | 0 | 48 | 26 | 45 | 7
943 | 1.2.4.4.1.2.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 942 | 944 | - | - | 0 | Renderer | 0 | 89 | 14 | 34 | 15
944 | 1.2.4.4.1.2.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 943 |  | - | - | 0 | Contract Administrator | 0 | 42 | 11 | 66 | 37
945 | 1.2.4.4.1.3 | Apartment B012 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Waterproofer | 0 | 77 | 14 | 33 | 17
946 | 1.2.4.4.1.3.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 947,950,951,1018 | - | - | 0 | Carpet | 0 | 26 | 25 | 71 | 49
947 | 1.2.4.4.1.3.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 946 | 949,948 | - | - | 0 | Waterproofer | 0 | 83 | 20 | 77 | 38
948 | 1.2.4.4.1.3.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 947 |  | - | - | 0 | Surveyor | 0 | 26 | 24 | 88 | 40
949 | 1.2.4.4.1.3.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 947 | 952 | - | - | 0 | Subcontractor | 0 | 42 | 31 | 97 | 4
950 | 1.2.4.4.1.3.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 959 | - | - | 0 | Scaffolder | 0 | 74 | 20 | 73 | 13
951 | 1.2.4.4.1.3.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 1022 | - | - | 0 | Electrician | 0 | 41 | 28 | 74 | 57
952 | 1.2.4.4.1.3.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 949 | 953,954,955,956,957 | - | - | 0 | Fire | 0 | 21 | 34 | 13 | 33
953 | 1.2.4.4.1.3.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957 | - | - | 0 | Landscaper | 0 | 86 | 24 | 38 | 21
954 | 1.2.4.4.1.3.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957,1021 | - | - | 0 | Electrician | 0 | 62 | 22 | 90 | 19
955 | 1.2.4.4.1.3.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 1020 | - | - | 0 | Landscaper | 0 | 37 | 19 | 2 | 56
956 | 1.2.4.4.1.3.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 |  | - | - | 0 | Line Market | 0 | 19 | 31 | 22 | 10
957 | 1.2.4.4.1.3.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 952,953,954 | 958 | - | - | 0 | Fire | 0 | 65 | 25 | 97 | 41
958 | 1.2.4.4.1.3.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 957 | 959 | - | - | 0 | Floor Sealer | 0 | 56 | 16 | 33 | 39
959 | 1.2.4.4.1.3.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 950,958 | 960,961,962,963,965,967 | - | - | 0 | Electrician | 0 | 72 | 31 | 25 | 45
960 | 1.2.4.4.1.3.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 964,967 | - | - | 0 | Line Market | 0 | 86 | 29 | 14 | 30
961 | 1.2.4.4.1.3.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 967 | - | - | 0 | Admin | 0 | 34 | 29 | 43 | 10
962 | 1.2.4.4.1.3.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 966,967 | - | - | 0 | Electrician | 0 | 99 | 13 | 39 | 9
963 | 1.2.4.4.1.3.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | - | - | 0 | Plasterboarder | 0 | 46 | 13 | 61 | 13
964 | 1.2.4.4.1.3.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 960 | 967 | - | - | 0 | Reinforcement Fixer | 0 | 84 | 13 | 66 | 56
965 | 1.2.4.4.1.3.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | - | - | 0 | Scaffolder | 0 | 32 | 12 | 34 | 23
966 | 1.2.4.4.1.3.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 962 | 967 | - | - | 0 | Concretor | 0 | 42 | 35 | 81 | 34
967 | 1.2.4.4.1.3.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 959,960,961,962,963,964,965,966 | 968 | - | - | 0 | Hoarding | 0 | 64 | 33 | 76 | 17
968 | 1.2.4.4.1.3.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 967 | 969 | - | - | 0 | Site Manager | 0 | 94 | 33 | 88 | 22
969 | 1.2.4.4.1.3.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 968 | 970,987,1004 | - | - | 0 | Cleaner | 0 | 75 | 29 | 17 | 18
970 | 1.2.4.4.1.3.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 971 | - | - | 0 | Tiler | 0 | 66 | 14 | 42 | 42
971 | 1.2.4.4.1.3.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 970 | 972 | - | - | 0 | Subcontractor | 0 | 49 | 14 | 46 | 58
972 | 1.2.4.4.1.3.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 971 | 973 | - | - | 0 | Plasterboarder | 0 | 56 | 10 | 68 | 6
973 | 1.2.4.4.1.3.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 972 | 974 | - | - | 0 | Excavation | 0 | 34 | 20 | 30 | 46
974 | 1.2.4.4.1.3.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 973 | 975,976 | - | - | 0 | Mechanical | 0 | 16 | 32 | 93 | 55
975 | 1.2.4.4.1.3.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 974 | 979 | - | - | 0 | Fire | 0 | 42 | 34 | 39 | 55
976 | 1.2.4.4.1.3.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 974 | 977 | - | - | 0 | Timber Floorer | 0 | 52 | 10 | 86 | 20
977 | 1.2.4.4.1.3.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 976 | 978 | - | - | 0 | Subcontractor | 0 | 59 | 29 | 16 | 25
978 | 1.2.4.4.1.3.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 977 |  | - | - | 0 | Excavation | 0 | 91 | 27 | 49 | 5
979 | 1.2.4.4.1.3.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 975 | 980,981,982,983,984 | - | - | 0 | Metal Work | 0 | 86 | 33 | 75 | 41
980 | 1.2.4.4.1.3.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 979 |  | - | - | 0 | Carpenter | 0 | 37 | 26 | 4 | 8
981 | 1.2.4.4.1.3.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Contract Administrator | 0 | 44 | 28 | 75 | 7
982 | 1.2.4.4.1.3.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Carpet | 0 | 43 | 17 | 41 | 50
983 | 1.2.4.4.1.3.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Concretor | 0 | 74 | 35 | 45 | 59
984 | 1.2.4.4.1.3.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Carpet | 0 | 91 | 15 | 98 | 28
985 | 1.2.4.4.1.3.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1035 | - | - | 0 | Waterproofer | 0 | 29 | 29 | 71 | 27
986 | 1.2.4.4.1.3.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 40 | 27 | 69 | 55
987 | 1.2.4.4.1.3.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 988 | - | - | 0 | Site Manager | 0 | 16 | 11 | 14 | 21
988 | 1.2.4.4.1.3.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 987 | 989 | - | - | 0 | Admin | 0 | 81 | 25 | 75 | 27
989 | 1.2.4.4.1.3.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 988 | 990 | - | - | 0 | Foreman | 0 | 75 | 12 | 26 | 60
990 | 1.2.4.4.1.3.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 989 | 991 | - | - | 0 | Formworker | 0 | 12 | 31 | 40 | 41
991 | 1.2.4.4.1.3.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 990 | 992 | - | - | 0 | Formworker | 0 | 53 | 17 | 68 | 19
992 | 1.2.4.4.1.3.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 991 | 993 | - | - | 0 | Subcontractor | 0 | 77 | 31 | 35 | 56
993 | 1.2.4.4.1.3.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 992 | 994 | - | - | 0 | Timber Floorer | 0 | 38 | 35 | 61 | 43
994 | 1.2.4.4.1.3.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 993 | 995 | - | - | 0 | Concretor | 0 | 41 | 24 | 10 | 28
995 | 1.2.4.4.1.3.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 994 | 996 | - | - | 0 | Metal Work | 0 | 22 | 18 | 14 | 50
996 | 1.2.4.4.1.3.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 995 | 997 | - | - | 0 | Joiner | 0 | 61 | 27 | 31 | 30
997 | 1.2.4.4.1.3.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 996 | 998 | - | - | 0 | Post Tension | 0 | 33 | 25 | 7 | 5
998 | 1.2.4.4.1.3.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 997 | 1002,999,1000,1001 | - | - | 0 | Subcontractor | 0 | 78 | 27 | 97 | 52
999 | 1.2.4.4.1.3.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | - | - | 0 | Timber Floorer | 0 | 57 | 35 | 11 | 42
1000 | 1.2.4.4.1.3.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | - | - | 0 | Mechanical | 0 | 24 | 10 | 62 | 56
1001 | 1.2.4.4.1.3.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | - | - | 0 | Reinforcement Fixer | 0 | 77 | 18 | 100 | 6
1002 | 1.2.4.4.1.3.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 998,999,1000,1001 |  | - | - | 0 | Cleaner | 0 | 86 | 35 | 71 | 50
1003 | 1.2.4.4.1.3.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | - | - | 0 | Fire | 0 | 56 | 12 | 79 | 18
1004 | 1.2.4.4.1.3.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 1005 | - | - | 0 | Admin | 0 | 39 | 25 | 66 | 31
1005 | 1.2.4.4.1.3.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1004 | 1006 | - | - | 0 | Admin | 0 | 96 | 28 | 85 | 29
1006 | 1.2.4.4.1.3.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1005 | 1007 | - | - | 0 | Mechanical | 0 | 56 | 29 | 32 | 39
1007 | 1.2.4.4.1.3.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1006 | 1008 | - | - | 0 | Excavation | 0 | 30 | 27 | 31 | 43
1008 | 1.2.4.4.1.3.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1007 | 1009 | - | - | 0 | Contract Administrator | 0 | 24 | 13 | 84 | 38
1009 | 1.2.4.4.1.3.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1008 | 1010 | - | - | 0 | Floor Sealer | 0 | 77 | 21 | 92 | 11
1010 | 1.2.4.4.1.3.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1009 | 1011 | - | - | 0 | Electrician | 0 | 88 | 28 | 70 | 30
1011 | 1.2.4.4.1.3.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1010 | 1012,1013,1014,1015 | - | - | 0 | Development Manager | 0 | 27 | 32 | 28 | 26
1012 | 1.2.4.4.1.3.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Subcontractor | 0 | 93 | 13 | 29 | 6
1013 | 1.2.4.4.1.3.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Reinforcement Fixer | 0 | 40 | 15 | 48 | 52
1014 | 1.2.4.4.1.3.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Head Contractor | 0 | 27 | 21 | 14 | 9
1015 | 1.2.4.4.1.3.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Painter | 0 | 28 | 34 | 94 | 24
1016 | 1.2.4.4.1.3.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1012,1013,1014,1015 |  | - | - | 0 | Renderer | 0 | 67 | 32 | 97 | 32
1017 | 1.2.4.4.1.3.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 80 | 10 | 26 | 46
1018 | 1.2.4.4.1.3.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 946 | 1019 | - | - | 0 | Carpenter | 0 | 44 | 17 | 93 | 31
1019 | 1.2.4.4.1.3.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1018 |  | - | - | 0 | Reinforcement Fixer | 0 | 53 | 28 | 21 | 13
1020 | 1.2.4.4.1.3.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 955 | 1023 | - | - | 0 | Site Manager | 0 | 72 | 13 | 58 | 3
1021 | 1.2.4.4.1.3.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 954 | 1023 | - | - | 0 | Site Manager | 0 | 20 | 23 | 35 | 8
1022 | 1.2.4.4.1.3.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 951 | 1023 | - | - | 0 | Floor Sealer | 0 | 60 | 32 | 27 | 46
1023 | 1.2.4.4.1.3.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1020,1021,1022 | 1024 | - | - | 0 | Post Tension | 0 | 91 | 16 | 21 | 22
1024 | 1.2.4.4.1.3.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1023 | 1025 | - | - | 0 | Joiner | 0 | 16 | 12 | 99 | 23
1025 | 1.2.4.4.1.3.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1024 | 1026 | - | - | 0 | Scaffolder | 0 | 38 | 10 | 96 | 18
1026 | 1.2.4.4.1.3.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1025 | 1027 | - | - | 0 | Contract Administrator | 0 | 100 | 27 | 17 | 21
1027 | 1.2.4.4.1.3.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1026 | 1028 | - | - | 0 | Stone Mason | 0 | 14 | 30 | 79 | 22
1028 | 1.2.4.4.1.3.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1027 | 1029 | - | - | 0 | Excavation | 0 | 69 | 17 | 77 | 11
1029 | 1.2.4.4.1.3.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1028 | 1030 | - | - | 0 | Line Market | 0 | 28 | 17 | 58 | 38
1030 | 1.2.4.4.1.3.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1029 | 1031,1032,1033,1034 | - | - | 0 | Concretor | 0 | 95 | 31 | 89 | 56
1031 | 1.2.4.4.1.3.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Concretor | 0 | 60 | 17 | 5 | 27
1032 | 1.2.4.4.1.3.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Landscaper | 0 | 83 | 18 | 86 | 60
1033 | 1.2.4.4.1.3.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Project Manager | 0 | 46 | 26 | 32 | 47
1034 | 1.2.4.4.1.3.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Stone Mason | 0 | 17 | 11 | 0 | 56
1035 | 1.2.4.4.1.3.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 981,982,983,984,985 | 1036 | - | - | 0 | Post Tension | 0 | 69 | 21 | 48 | 51
1036 | 1.2.4.4.1.3.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1035 | 1037 | - | - | 0 | Landscaper | 0 | 73 | 16 | 92 | 42
1037 | 1.2.4.4.1.3.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1036 | 1038 | - | - | 0 | Tiler | 0 | 19 | 20 | 54 | 45
1038 | 1.2.4.4.1.3.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1037 |  | - | - | 0 | Renderer | 0 | 55 | 18 | 47 | 13
1039 | 1.2.4.4.1.4 | Apartment B013 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 25 | 35 | 22 | 42
1040 | 1.2.4.4.1.4.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 1041,1044,1045,1112 | - | - | 0 | Fire | 0 | 85 | 34 | 10 | 12
1041 | 1.2.4.4.1.4.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 1040 | 1043,1042 | - | - | 0 | Contract Administrator | 0 | 95 | 16 | 54 | 23
1042 | 1.2.4.4.1.4.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1041 |  | - | - | 0 | Carpet | 0 | 79 | 11 | 96 | 54
1043 | 1.2.4.4.1.4.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1041 | 1046 | - | - | 0 | Joiner | 0 | 94 | 15 | 5 | 47
1044 | 1.2.4.4.1.4.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1053 | - | - | 0 | Reinforcement Fixer | 0 | 59 | 25 | 82 | 55
1045 | 1.2.4.4.1.4.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1116 | - | - | 0 | Surveyor | 0 | 57 | 18 | 84 | 19
1046 | 1.2.4.4.1.4.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1043 | 1047,1048,1049,1050,1051 | - | - | 0 | Carpenter | 0 | 49 | 13 | 8 | 41
1047 | 1.2.4.4.1.4.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051 | - | - | 0 | Development Manager | 0 | 47 | 20 | 61 | 45
1048 | 1.2.4.4.1.4.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051,1115 | - | - | 0 | Tiler | 0 | 20 | 23 | 75 | 33
1049 | 1.2.4.4.1.4.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1114 | - | - | 0 | Plumber | 0 | 78 | 15 | 66 | 28
1050 | 1.2.4.4.1.4.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 |  | - | - | 0 | Scaffolder | 0 | 38 | 32 | 6 | 45
1051 | 1.2.4.4.1.4.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1046,1047,1048 | 1052 | - | - | 0 | Carpet | 0 | 89 | 31 | 44 | 4
1052 | 1.2.4.4.1.4.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1051 | 1053 | - | - | 0 | Head Contractor | 0 | 96 | 12 | 16 | 38
1053 | 1.2.4.4.1.4.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1044,1052 | 1054,1055,1056,1057,1059,1061 | - | - | 0 | Carpet | 0 | 71 | 24 | 14 | 6
1054 | 1.2.4.4.1.4.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1058,1061 | - | - | 0 | Landscaper | 0 | 34 | 24 | 2 | 20
1055 | 1.2.4.4.1.4.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Contract Administrator | 0 | 67 | 18 | 58 | 27
1056 | 1.2.4.4.1.4.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1060,1061 | - | - | 0 | Metal Work | 0 | 93 | 13 | 70 | 36
1057 | 1.2.4.4.1.4.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Surveyor | 0 | 40 | 13 | 24 | 55
1058 | 1.2.4.4.1.4.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1054 | 1061 | - | - | 0 | Window | 0 | 52 | 24 | 89 | 46
1059 | 1.2.4.4.1.4.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Contract Administrator | 0 | 81 | 23 | 2 | 3
1060 | 1.2.4.4.1.4.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1056 | 1061 | - | - | 0 | Cleaner | 0 | 20 | 24 | 94 | 39
1061 | 1.2.4.4.1.4.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1053,1054,1055,1056,1057,1058,1059,1060 | 1062 | - | - | 0 | Reinforcement Fixer | 0 | 23 | 19 | 87 | 52
1062 | 1.2.4.4.1.4.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1061 | 1063 | - | - | 0 | Development Manager | 0 | 54 | 35 | 66 | 36
1063 | 1.2.4.4.1.4.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1062 | 1064,1081,1098 | - | - | 0 | Development Manager | 0 | 77 | 15 | 54 | 55
1064 | 1.2.4.4.1.4.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1065 | - | - | 0 | Renderer | 0 | 61 | 31 | 70 | 2
1065 | 1.2.4.4.1.4.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1064 | 1066 | - | - | 0 | Plasterboarder | 0 | 12 | 27 | 83 | 40
1066 | 1.2.4.4.1.4.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1065 | 1067 | - | - | 0 | Post Tension | 0 | 40 | 25 | 69 | 26
1067 | 1.2.4.4.1.4.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1066 | 1068 | - | - | 0 | Carpet | 0 | 16 | 20 | 20 | 45
1068 | 1.2.4.4.1.4.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1067 | 1069,1070 | - | - | 0 | Electrician | 0 | 68 | 17 | 82 | 60
1069 | 1.2.4.4.1.4.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1068 | 1073 | - | - | 0 | Joiner | 0 | 80 | 35 | 22 | 23
1070 | 1.2.4.4.1.4.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1068 | 1071 | - | - | 0 | Reinforcement Fixer | 0 | 40 | 17 | 31 | 24
1071 | 1.2.4.4.1.4.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1070 | 1072 | - | - | 0 | Waterproofer | 0 | 48 | 17 | 53 | 3
1072 | 1.2.4.4.1.4.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1071 |  | - | - | 0 | Window | 0 | 26 | 21 | 5 | 43
1073 | 1.2.4.4.1.4.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1069 | 1074,1075,1076,1077,1078 | - | - | 0 | Line Market | 0 | 54 | 33 | 90 | 35
1074 | 1.2.4.4.1.4.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1073 |  | - | - | 0 | Line Market | 0 | 79 | 11 | 13 | 37
1075 | 1.2.4.4.1.4.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Reinforcement Fixer | 0 | 49 | 24 | 92 | 33
1076 | 1.2.4.4.1.4.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Electrician | 0 | 44 | 27 | 41 | 53
1077 | 1.2.4.4.1.4.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Post Tension | 0 | 45 | 16 | 26 | 42
1078 | 1.2.4.4.1.4.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Plumber | 0 | 99 | 21 | 51 | 54
1079 | 1.2.4.4.1.4.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1129 | - | - | 0 | Floor Sealer | 0 | 89 | 35 | 46 | 12
1080 | 1.2.4.4.1.4.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Timber Floorer | 0 | 98 | 22 | 80 | 36
1081 | 1.2.4.4.1.4.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1082 | - | - | 0 | Admin | 0 | 92 | 14 | 0 | 53
1082 | 1.2.4.4.1.4.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1081 | 1083 | - | - | 0 | Line Market | 0 | 82 | 22 | 75 | 34
1083 | 1.2.4.4.1.4.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1082 | 1084 | - | - | 0 | Joiner | 0 | 17 | 13 | 98 | 24
1084 | 1.2.4.4.1.4.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1083 | 1085 | - | - | 0 | Waterproofer | 0 | 77 | 13 | 16 | 26
1085 | 1.2.4.4.1.4.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1084 | 1086 | - | - | 0 | Plasterboarder | 0 | 60 | 26 | 29 | 7
1086 | 1.2.4.4.1.4.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1085 | 1087 | - | - | 0 | Subcontractor | 0 | 48 | 33 | 62 | 17
1087 | 1.2.4.4.1.4.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1086 | 1088 | - | - | 0 | Metal Work | 0 | 13 | 32 | 71 | 13
1088 | 1.2.4.4.1.4.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1087 | 1089 | - | - | 0 | Renderer | 0 | 19 | 31 | 84 | 54
1089 | 1.2.4.4.1.4.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1088 | 1090 | - | - | 0 | Carpenter | 0 | 17 | 27 | 46 | 8
1090 | 1.2.4.4.1.4.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1089 | 1091 | - | - | 0 | Timber Floorer | 0 | 68 | 21 | 78 | 22
1091 | 1.2.4.4.1.4.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1090 | 1092 | - | - | 0 | Site Manager | 0 | 43 | 12 | 5 | 43
1092 | 1.2.4.4.1.4.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1091 | 1096,1093,1094,1095 | - | - | 0 | Head Contractor | 0 | 31 | 22 | 53 | 13
1093 | 1.2.4.4.1.4.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Admin | 0 | 27 | 27 | 54 | 10
1094 | 1.2.4.4.1.4.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Hoarding | 0 | 81 | 12 | 17 | 60
1095 | 1.2.4.4.1.4.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Window | 0 | 80 | 31 | 3 | 16
1096 | 1.2.4.4.1.4.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1092,1093,1094,1095 |  | - | - | 0 | Post Tension | 0 | 64 | 30 | 51 | 25
1097 | 1.2.4.4.1.4.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | - | - | 0 | Development Manager | 0 | 35 | 30 | 38 | 6
1098 | 1.2.4.4.1.4.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1099 | - | - | 0 | Tiler | 0 | 58 | 34 | 16 | 9
1099 | 1.2.4.4.1.4.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1098 | 1100 | - | - | 0 | Project Manager | 0 | 60 | 19 | 77 | 33
1100 | 1.2.4.4.1.4.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1099 | 1101 | - | - | 0 | Painter | 0 | 29 | 18 | 71 | 17
1101 | 1.2.4.4.1.4.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1100 | 1102 | - | - | 0 | Contract Administrator | 0 | 16 | 22 | 9 | 30
1102 | 1.2.4.4.1.4.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1101 | 1103 | - | - | 0 | Plumber | 0 | 12 | 33 | 61 | 17
1103 | 1.2.4.4.1.4.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1102 | 1104 | - | - | 0 | Stone Mason | 0 | 91 | 15 | 73 | 28
1104 | 1.2.4.4.1.4.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1103 | 1105 | - | - | 0 | Landscaper | 0 | 81 | 11 | 20 | 17
1105 | 1.2.4.4.1.4.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1104 | 1106,1107,1108,1109 | - | - | 0 | Foreman | 0 | 12 | 26 | 83 | 7
1106 | 1.2.4.4.1.4.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Post Tension | 0 | 62 | 20 | 33 | 29
1107 | 1.2.4.4.1.4.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Hoarding | 0 | 36 | 24 | 59 | 37
1108 | 1.2.4.4.1.4.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Excavation | 0 | 93 | 25 | 10 | 26
1109 | 1.2.4.4.1.4.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Painter | 0 | 19 | 30 | 94 | 7
1110 | 1.2.4.4.1.4.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1106,1107,1108,1109 |  | - | - | 0 | Development Manager | 0 | 81 | 14 | 45 | 10
1111 | 1.2.4.4.1.4.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | - | - | 0 | Landscaper | 0 | 92 | 35 | 4 | 10
1112 | 1.2.4.4.1.4.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 1040 | 1113 | - | - | 0 | Electrician | 0 | 51 | 30 | 80 | 10
1113 | 1.2.4.4.1.4.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1112 |  | - | - | 0 | Development Manager | 0 | 63 | 34 | 74 | 36
1114 | 1.2.4.4.1.4.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1049 | 1117 | - | - | 0 | Post Tension | 0 | 49 | 34 | 71 | 9
1115 | 1.2.4.4.1.4.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1048 | 1117 | - | - | 0 | Post Tension | 0 | 11 | 27 | 60 | 36
1116 | 1.2.4.4.1.4.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1045 | 1117 | - | - | 0 | Electrician | 0 | 45 | 18 | 38 | 12
1117 | 1.2.4.4.1.4.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1114,1115,1116 | 1118 | - | - | 0 | Surveyor | 0 | 59 | 22 | 65 | 24
1118 | 1.2.4.4.1.4.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1117 | 1119 | - | - | 0 | Renderer | 0 | 91 | 29 | 20 | 13
1119 | 1.2.4.4.1.4.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1118 | 1120 | - | - | 0 | Subcontractor | 0 | 60 | 26 | 97 | 60
1120 | 1.2.4.4.1.4.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1119 | 1121 | - | - | 0 | Post Tension | 0 | 57 | 29 | 2 | 32
1121 | 1.2.4.4.1.4.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1120 | 1122 | - | - | 0 | Plumber | 0 | 67 | 26 | 12 | 20
1122 | 1.2.4.4.1.4.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1121 | 1123 | - | - | 0 | Hoarding | 0 | 27 | 31 | 61 | 36
1123 | 1.2.4.4.1.4.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1122 | 1124 | - | - | 0 | Contract Administrator | 0 | 12 | 28 | 41 | 37
1124 | 1.2.4.4.1.4.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1123 | 1125,1126,1127,1128 | - | - | 0 | Floor Sealer | 0 | 33 | 34 | 34 | 18
1125 | 1.2.4.4.1.4.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Mechanical | 0 | 11 | 33 | 7 | 31
1126 | 1.2.4.4.1.4.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Window | 0 | 80 | 30 | 52 | 24
1127 | 1.2.4.4.1.4.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Painter | 0 | 22 | 23 | 79 | 3
1128 | 1.2.4.4.1.4.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Subcontractor | 0 | 70 | 31 | 6 | 60
1129 | 1.2.4.4.1.4.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1075,1076,1077,1078,1079 | 1130 | - | - | 0 | Plasterboarder | 0 | 72 | 23 | 81 | 39
1130 | 1.2.4.4.1.4.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1129 | 1131 | - | - | 0 | Renderer | 0 | 13 | 23 | 59 | 45
1131 | 1.2.4.4.1.4.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1130 | 1132 | - | - | 0 | Foreman | 0 | 17 | 20 | 100 | 21
1132 | 1.2.4.4.1.4.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1131 |  | - | - | 0 | Renderer | 0 | 75 | 14 | 23 | 50
1133 | 1.2.4.4.1.5 | Apartment B014 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | - | - | 0 | Joiner | 0 | 96 | 22 | 18 | 47
1134 | 1.2.4.4.1.5.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1135,1138,1139,1206 | - | - | 0 | Contract Administrator | 0 | 73 | 12 | 76 | 37
1135 | 1.2.4.4.1.5.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1134 | 1137,1136 | - | - | 0 | Formworker | 0 | 97 | 12 | 53 | 47
1136 | 1.2.4.4.1.5.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1135 |  | - | - | 0 | Project Manager | 0 | 17 | 10 | 54 | 29
1137 | 1.2.4.4.1.5.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1135 | 1140 | - | - | 0 | Line Market | 0 | 50 | 26 | 13 | 50
1138 | 1.2.4.4.1.5.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1147 | - | - | 0 | Reinforcement Fixer | 0 | 38 | 17 | 19 | 30
1139 | 1.2.4.4.1.5.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1210 | - | - | 0 | Site Manager | 0 | 45 | 18 | 63 | 37
1140 | 1.2.4.4.1.5.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1137 | 1141,1142,1143,1144,1145 | - | - | 0 | Renderer | 0 | 36 | 13 | 62 | 32
1141 | 1.2.4.4.1.5.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145 | - | - | 0 | Hoarding | 0 | 80 | 33 | 33 | 25
1142 | 1.2.4.4.1.5.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145,1209 | - | - | 0 | Project Manager | 0 | 47 | 20 | 87 | 48
1143 | 1.2.4.4.1.5.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1208 | - | - | 0 | Hoarding | 0 | 74 | 16 | 94 | 33
1144 | 1.2.4.4.1.5.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 |  | - | - | 0 | Scaffolder | 0 | 77 | 20 | 41 | 40
1145 | 1.2.4.4.1.5.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1140,1141,1142 | 1146 | - | - | 0 | Timber Floorer | 0 | 100 | 25 | 96 | 37
1146 | 1.2.4.4.1.5.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1145 | 1147 | - | - | 0 | Electrician | 0 | 54 | 29 | 33 | 48
1147 | 1.2.4.4.1.5.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1138,1146 | 1148,1149,1150,1151,1153,1155 | - | - | 0 | Cleaner | 0 | 56 | 17 | 58 | 41
1148 | 1.2.4.4.1.5.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1152,1155 | - | - | 0 | Site Manager | 0 | 59 | 13 | 30 | 18
1149 | 1.2.4.4.1.5.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Electrician | 0 | 44 | 25 | 20 | 20
1150 | 1.2.4.4.1.5.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1154,1155 | - | - | 0 | Project Manager | 0 | 84 | 17 | 5 | 56
1151 | 1.2.4.4.1.5.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Waterproofer | 0 | 24 | 32 | 34 | 29
1152 | 1.2.4.4.1.5.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1148 | 1155 | - | - | 0 | Plumber | 0 | 79 | 25 | 93 | 43
1153 | 1.2.4.4.1.5.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Stone Mason | 0 | 73 | 35 | 56 | 46
1154 | 1.2.4.4.1.5.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1150 | 1155 | - | - | 0 | Hoarding | 0 | 68 | 29 | 38 | 21
1155 | 1.2.4.4.1.5.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1147,1148,1149,1150,1151,1152,1153,1154 | 1156 | - | - | 0 | Waterproofer | 0 | 77 | 31 | 20 | 46
1156 | 1.2.4.4.1.5.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1155 | 1157 | - | - | 0 | Admin | 0 | 33 | 13 | 58 | 36
1157 | 1.2.4.4.1.5.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1156 | 1158,1175,1192 | - | - | 0 | Electrician | 0 | 97 | 21 | 26 | 45
1158 | 1.2.4.4.1.5.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1159 | - | - | 0 | Contract Administrator | 0 | 24 | 14 | 66 | 55
1159 | 1.2.4.4.1.5.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1158 | 1160 | - | - | 0 | Admin | 0 | 52 | 34 | 24 | 39
1160 | 1.2.4.4.1.5.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1159 | 1161 | - | - | 0 | Fire | 0 | 38 | 21 | 75 | 15
1161 | 1.2.4.4.1.5.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1160 | 1162 | - | - | 0 | Plasterboarder | 0 | 88 | 29 | 27 | 47
1162 | 1.2.4.4.1.5.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1161 | 1163,1164 | - | - | 0 | Formworker | 0 | 29 | 21 | 100 | 32
1163 | 1.2.4.4.1.5.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1162 | 1167 | - | - | 0 | Scaffolder | 0 | 49 | 14 | 83 | 19
1164 | 1.2.4.4.1.5.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1162 | 1165 | - | - | 0 | Contract Administrator | 0 | 98 | 30 | 15 | 39
1165 | 1.2.4.4.1.5.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1164 | 1166 | - | - | 0 | Development Manager | 0 | 71 | 30 | 37 | 23
1166 | 1.2.4.4.1.5.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1165 |  | - | - | 0 | Project Manager | 0 | 35 | 10 | 60 | 9
1167 | 1.2.4.4.1.5.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1163 | 1168,1169,1170,1171,1172 | - | - | 0 | Admin | 0 | 88 | 28 | 74 | 12
1168 | 1.2.4.4.1.5.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1167 |  | - | - | 0 | Admin | 0 | 55 | 29 | 3 | 37
1169 | 1.2.4.4.1.5.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Admin | 0 | 66 | 13 | 81 | 53
1170 | 1.2.4.4.1.5.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Joiner | 0 | 43 | 24 | 30 | 33
1171 | 1.2.4.4.1.5.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Cleaner | 0 | 35 | 14 | 73 | 8
1172 | 1.2.4.4.1.5.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Foreman | 0 | 99 | 14 | 72 | 55
1173 | 1.2.4.4.1.5.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1223 | - | - | 0 | Fire | 0 | 46 | 19 | 94 | 48
1174 | 1.2.4.4.1.5.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Plumber | 0 | 89 | 28 | 26 | 33
1175 | 1.2.4.4.1.5.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1176 | - | - | 0 | Renderer | 0 | 14 | 26 | 7 | 37
1176 | 1.2.4.4.1.5.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1175 | 1177 | - | - | 0 | Formworker | 0 | 88 | 11 | 22 | 3
1177 | 1.2.4.4.1.5.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1176 | 1178 | - | - | 0 | Plumber | 0 | 34 | 24 | 16 | 34
1178 | 1.2.4.4.1.5.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1177 | 1179 | - | - | 0 | Subcontractor | 0 | 77 | 26 | 71 | 3
1179 | 1.2.4.4.1.5.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1178 | 1180 | - | - | 0 | Carpenter | 0 | 87 | 30 | 35 | 51
1180 | 1.2.4.4.1.5.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1179 | 1181 | - | - | 0 | Timber Floorer | 0 | 68 | 30 | 93 | 48
1181 | 1.2.4.4.1.5.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1180 | 1182 | - | - | 0 | Carpenter | 0 | 56 | 29 | 80 | 42
1182 | 1.2.4.4.1.5.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1181 | 1183 | - | - | 0 | Renderer | 0 | 59 | 35 | 81 | 49
1183 | 1.2.4.4.1.5.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1182 | 1184 | - | - | 0 | Floor Sealer | 0 | 47 | 23 | 48 | 15
1184 | 1.2.4.4.1.5.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1183 | 1185 | - | - | 0 | Head Contractor | 0 | 29 | 23 | 45 | 8
1185 | 1.2.4.4.1.5.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1184 | 1186 | - | - | 0 | Development Manager | 0 | 86 | 27 | 28 | 9
1186 | 1.2.4.4.1.5.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1185 | 1190,1187,1188,1189 | - | - | 0 | Painter | 0 | 90 | 33 | 60 | 20
1187 | 1.2.4.4.1.5.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Development Manager | 0 | 87 | 13 | 81 | 34
1188 | 1.2.4.4.1.5.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Concretor | 0 | 39 | 14 | 73 | 15
1189 | 1.2.4.4.1.5.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Reinforcement Fixer | 0 | 28 | 32 | 96 | 3
1190 | 1.2.4.4.1.5.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1186,1187,1188,1189 |  | - | - | 0 | Admin | 0 | 88 | 20 | 83 | 51
1191 | 1.2.4.4.1.5.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Timber Floorer | 0 | 93 | 11 | 57 | 9
1192 | 1.2.4.4.1.5.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1193 | - | - | 0 | Painter | 0 | 59 | 27 | 36 | 33
1193 | 1.2.4.4.1.5.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1192 | 1194 | - | - | 0 | Subcontractor | 0 | 79 | 35 | 49 | 48
1194 | 1.2.4.4.1.5.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1193 | 1195 | - | - | 0 | Surveyor | 0 | 35 | 15 | 95 | 45
1195 | 1.2.4.4.1.5.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1194 | 1196 | - | - | 0 | Landscaper | 0 | 94 | 11 | 74 | 29
1196 | 1.2.4.4.1.5.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1195 | 1197 | - | - | 0 | Concretor | 0 | 86 | 19 | 3 | 2
1197 | 1.2.4.4.1.5.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1196 | 1198 | - | - | 0 | Foreman | 0 | 72 | 25 | 19 | 34
1198 | 1.2.4.4.1.5.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1197 | 1199 | - | - | 0 | Stone Mason | 0 | 97 | 33 | 48 | 22
1199 | 1.2.4.4.1.5.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1198 | 1200,1201,1202,1203 | - | - | 0 | Head Contractor | 0 | 11 | 31 | 22 | 45
1200 | 1.2.4.4.1.5.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Surveyor | 0 | 44 | 31 | 56 | 4
1201 | 1.2.4.4.1.5.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Project Manager | 0 | 42 | 34 | 54 | 11
1202 | 1.2.4.4.1.5.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Waterproofer | 0 | 59 | 13 | 94 | 23
1203 | 1.2.4.4.1.5.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Concretor | 0 | 78 | 26 | 49 | 3
1204 | 1.2.4.4.1.5.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1200,1201,1202,1203 |  | - | - | 0 | Post Tension | 0 | 59 | 24 | 84 | 27
1205 | 1.2.4.4.1.5.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | - | - | 0 | Mechanical | 0 | 25 | 33 | 53 | 4
1206 | 1.2.4.4.1.5.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1134 | 1207 | - | - | 0 | Excavation | 0 | 69 | 30 | 67 | 45
1207 | 1.2.4.4.1.5.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1206 |  | - | - | 0 | Reinforcement Fixer | 0 | 27 | 31 | 42 | 23
1208 | 1.2.4.4.1.5.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1143 | 1211 | - | - | 0 | Renderer | 0 | 19 | 10 | 2 | 32
1209 | 1.2.4.4.1.5.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1142 | 1211 | - | - | 0 | Joiner | 0 | 98 | 34 | 97 | 5
1210 | 1.2.4.4.1.5.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1139 | 1211 | - | - | 0 | Contract Administrator | 0 | 20 | 25 | 61 | 2
1211 | 1.2.4.4.1.5.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1208,1209,1210 | 1212 | - | - | 0 | Tiler | 0 | 38 | 26 | 4 | 34
1212 | 1.2.4.4.1.5.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1211 | 1213 | - | - | 0 | Mechanical | 0 | 46 | 14 | 30 | 3
1213 | 1.2.4.4.1.5.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1212 | 1214 | - | - | 0 | Site Manager | 0 | 42 | 32 | 33 | 13
1214 | 1.2.4.4.1.5.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1213 | 1215 | - | - | 0 | Site Manager | 0 | 35 | 13 | 22 | 53
1215 | 1.2.4.4.1.5.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1214 | 1216 | - | - | 0 | Carpenter | 0 | 58 | 14 | 41 | 59
1216 | 1.2.4.4.1.5.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1215 | 1217 | - | - | 0 | Surveyor | 0 | 70 | 29 | 4 | 20
1217 | 1.2.4.4.1.5.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1216 | 1218 | - | - | 0 | Formworker | 0 | 59 | 30 | 32 | 38
1218 | 1.2.4.4.1.5.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1217 | 1219,1220,1221,1222 | - | - | 0 | Line Market | 0 | 30 | 18 | 6 | 6
1219 | 1.2.4.4.1.5.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Site Manager | 0 | 99 | 34 | 30 | 13
1220 | 1.2.4.4.1.5.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Landscaper | 0 | 40 | 15 | 9 | 51
1221 | 1.2.4.4.1.5.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Post Tension | 0 | 66 | 29 | 91 | 33
1222 | 1.2.4.4.1.5.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Metal Work | 0 | 34 | 27 | 83 | 15
1223 | 1.2.4.4.1.5.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1169,1170,1171,1172,1173 | 1224 | - | - | 0 | Window | 0 | 59 | 30 | 49 | 49
1224 | 1.2.4.4.1.5.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1223 | 1225 | - | - | 0 | Electrician | 0 | 85 | 29 | 44 | 19
1225 | 1.2.4.4.1.5.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1224 | 1226 | - | - | 0 | Excavation | 0 | 60 | 10 | 49 | 33
1226 | 1.2.4.4.1.5.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1225 |  | - | - | 0 | Surveyor | 0 | 36 | 19 | 33 | 24
1227 | 1.2.4.4.1.6 | Apartment B015 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | - | - | 0 | Window | 0 | 46 | 29 | 35 | 41
1228 | 1.2.4.4.1.6.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1229,1232,1233,1300 | - | - | 0 | Subcontractor | 0 | 23 | 25 | 76 | 23
1229 | 1.2.4.4.1.6.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1228 | 1231,1230 | - | - | 0 | Landscaper | 0 | 34 | 27 | 97 | 33
1230 | 1.2.4.4.1.6.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1229 |  | - | - | 0 | Painter | 0 | 25 | 22 | 12 | 59
1231 | 1.2.4.4.1.6.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1229 | 1234 | - | - | 0 | Site Manager | 0 | 29 | 10 | 59 | 28
1232 | 1.2.4.4.1.6.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1241 | - | - | 0 | Metal Work | 0 | 92 | 22 | 94 | 48
1233 | 1.2.4.4.1.6.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1304 | - | - | 0 | Head Contractor | 0 | 56 | 29 | 33 | 26
1234 | 1.2.4.4.1.6.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1231 | 1235,1236,1237,1238,1239 | - | - | 0 | Scaffolder | 0 | 12 | 19 | 38 | 57
1235 | 1.2.4.4.1.6.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239 | - | - | 0 | Window | 0 | 51 | 18 | 59 | 50
1236 | 1.2.4.4.1.6.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239,1303 | - | - | 0 | Development Manager | 0 | 10 | 16 | 52 | 36
1237 | 1.2.4.4.1.6.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1302 | - | - | 0 | Concretor | 0 | 31 | 32 | 69 | 17
1238 | 1.2.4.4.1.6.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 |  | - | - | 0 | Admin | 0 | 32 | 32 | 45 | 28
1239 | 1.2.4.4.1.6.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1234,1235,1236 | 1240 | - | - | 0 | Joiner | 0 | 64 | 29 | 44 | 20
1240 | 1.2.4.4.1.6.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1239 | 1241 | - | - | 0 | Stone Mason | 0 | 80 | 30 | 97 | 41
1241 | 1.2.4.4.1.6.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1232,1240 | 1242,1243,1244,1245,1247,1249 | - | - | 0 | Plumber | 0 | 13 | 26 | 17 | 12
1242 | 1.2.4.4.1.6.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1246,1249 | - | - | 0 | Stone Mason | 0 | 61 | 13 | 19 | 21
1243 | 1.2.4.4.1.6.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Carpet | 0 | 61 | 27 | 11 | 9
1244 | 1.2.4.4.1.6.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1248,1249 | - | - | 0 | Waterproofer | 0 | 99 | 10 | 98 | 19
1245 | 1.2.4.4.1.6.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Plumber | 0 | 92 | 33 | 40 | 39
1246 | 1.2.4.4.1.6.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1242 | 1249 | - | - | 0 | Project Manager | 0 | 96 | 14 | 51 | 3
1247 | 1.2.4.4.1.6.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Concretor | 0 | 99 | 18 | 83 | 2
1248 | 1.2.4.4.1.6.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1244 | 1249 | - | - | 0 | Cleaner | 0 | 17 | 28 | 20 | 42
1249 | 1.2.4.4.1.6.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1241,1242,1243,1244,1245,1246,1247,1248 | 1250 | - | - | 0 | Tiler | 0 | 41 | 35 | 90 | 19
1250 | 1.2.4.4.1.6.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1249 | 1251 | - | - | 0 | Hoarding | 0 | 86 | 27 | 25 | 50
1251 | 1.2.4.4.1.6.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1250 | 1252,1269,1286 | - | - | 0 | Surveyor | 0 | 84 | 20 | 84 | 8
1252 | 1.2.4.4.1.6.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1253 | - | - | 0 | Post Tension | 0 | 71 | 24 | 55 | 50
1253 | 1.2.4.4.1.6.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1252 | 1254 | - | - | 0 | Site Manager | 0 | 72 | 25 | 45 | 43
1254 | 1.2.4.4.1.6.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1253 | 1255 | - | - | 0 | Foreman | 0 | 72 | 28 | 94 | 59
1255 | 1.2.4.4.1.6.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1254 | 1256 | - | - | 0 | Joiner | 0 | 67 | 34 | 51 | 34
1256 | 1.2.4.4.1.6.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1255 | 1257,1258 | - | - | 0 | Contract Administrator | 0 | 42 | 34 | 97 | 6
1257 | 1.2.4.4.1.6.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1256 | 1261 | - | - | 0 | Joiner | 0 | 10 | 35 | 91 | 5
1258 | 1.2.4.4.1.6.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1256 | 1259 | - | - | 0 | Post Tension | 0 | 100 | 23 | 87 | 51
1259 | 1.2.4.4.1.6.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1258 | 1260 | - | - | 0 | Renderer | 0 | 16 | 16 | 70 | 21
1260 | 1.2.4.4.1.6.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1259 |  | - | - | 0 | Scaffolder | 0 | 42 | 23 | 62 | 57
1261 | 1.2.4.4.1.6.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1257 | 1262,1263,1264,1265,1266 | - | - | 0 | Joiner | 0 | 40 | 24 | 37 | 32
1262 | 1.2.4.4.1.6.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1261 |  | - | - | 0 | Line Market | 0 | 11 | 28 | 5 | 36
1263 | 1.2.4.4.1.6.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Tiler | 0 | 27 | 30 | 68 | 39
1264 | 1.2.4.4.1.6.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Post Tension | 0 | 74 | 11 | 22 | 48
1265 | 1.2.4.4.1.6.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Admin | 0 | 93 | 14 | 85 | 33
1266 | 1.2.4.4.1.6.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Metal Work | 0 | 21 | 15 | 57 | 24
1267 | 1.2.4.4.1.6.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1317 | - | - | 0 | Post Tension | 0 | 68 | 32 | 77 | 19
1268 | 1.2.4.4.1.6.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 45 | 19 | 8 | 20
1269 | 1.2.4.4.1.6.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1270 | - | - | 0 | Excavation | 0 | 38 | 12 | 2 | 50
1270 | 1.2.4.4.1.6.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1269 | 1271 | - | - | 0 | Project Manager | 0 | 34 | 21 | 76 | 16
1271 | 1.2.4.4.1.6.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1270 | 1272 | - | - | 0 | Development Manager | 0 | 85 | 31 | 87 | 36
1272 | 1.2.4.4.1.6.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1271 | 1273 | - | - | 0 | Renderer | 0 | 14 | 19 | 70 | 30
1273 | 1.2.4.4.1.6.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1272 | 1274 | - | - | 0 | Foreman | 0 | 69 | 34 | 0 | 20
1274 | 1.2.4.4.1.6.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1273 | 1275 | - | - | 0 | Floor Sealer | 0 | 93 | 25 | 73 | 20
1275 | 1.2.4.4.1.6.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1274 | 1276 | - | - | 0 | Surveyor | 0 | 30 | 22 | 15 | 2
1276 | 1.2.4.4.1.6.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1275 | 1277 | - | - | 0 | Subcontractor | 0 | 39 | 32 | 46 | 4
1277 | 1.2.4.4.1.6.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1276 | 1278 | - | - | 0 | Line Market | 0 | 66 | 11 | 68 | 32
1278 | 1.2.4.4.1.6.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1277 | 1279 | - | - | 0 | Stone Mason | 0 | 12 | 20 | 100 | 15
1279 | 1.2.4.4.1.6.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1278 | 1280 | - | - | 0 | Carpet | 0 | 55 | 13 | 81 | 32
1280 | 1.2.4.4.1.6.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1279 | 1284,1281,1282,1283 | - | - | 0 | Admin | 0 | 63 | 29 | 91 | 5
1281 | 1.2.4.4.1.6.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Scaffolder | 0 | 80 | 35 | 40 | 44
1282 | 1.2.4.4.1.6.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Landscaper | 0 | 97 | 12 | 99 | 57
1283 | 1.2.4.4.1.6.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Landscaper | 0 | 49 | 17 | 95 | 3
1284 | 1.2.4.4.1.6.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1280,1281,1282,1283 |  | - | - | 0 | Subcontractor | 0 | 42 | 33 | 15 | 7
1285 | 1.2.4.4.1.6.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 80 | 18 | 2 | 60
1286 | 1.2.4.4.1.6.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1287 | - | - | 0 | Concretor | 0 | 59 | 15 | 35 | 50
1287 | 1.2.4.4.1.6.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1286 | 1288 | - | - | 0 | Timber Floorer | 0 | 37 | 28 | 2 | 20
1288 | 1.2.4.4.1.6.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1287 | 1289 | - | - | 0 | Waterproofer | 0 | 67 | 32 | 72 | 29
1289 | 1.2.4.4.1.6.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1288 | 1290 | - | - | 0 | Head Contractor | 0 | 44 | 12 | 20 | 28
1290 | 1.2.4.4.1.6.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1289 | 1291 | - | - | 0 | Landscaper | 0 | 64 | 20 | 6 | 14
1291 | 1.2.4.4.1.6.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1290 | 1292 | - | - | 0 | Development Manager | 0 | 87 | 32 | 87 | 33
1292 | 1.2.4.4.1.6.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1291 | 1293 | - | - | 0 | Metal Work | 0 | 49 | 18 | 98 | 43
1293 | 1.2.4.4.1.6.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1292 | 1294,1295,1296,1297 | - | - | 0 | Stone Mason | 0 | 64 | 12 | 32 | 49
1294 | 1.2.4.4.1.6.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Plasterboarder | 0 | 81 | 14 | 50 | 18
1295 | 1.2.4.4.1.6.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Post Tension | 0 | 89 | 30 | 46 | 11
1296 | 1.2.4.4.1.6.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Scaffolder | 0 | 34 | 33 | 89 | 12
1297 | 1.2.4.4.1.6.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Contract Administrator | 0 | 84 | 35 | 28 | 46
1298 | 1.2.4.4.1.6.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1294,1295,1296,1297 |  | - | - | 0 | Renderer | 0 | 14 | 35 | 10 | 22
1299 | 1.2.4.4.1.6.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 50 | 24 | 38 | 54
1300 | 1.2.4.4.1.6.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1228 | 1301 | - | - | 0 | Landscaper | 0 | 47 | 27 | 31 | 29
1301 | 1.2.4.4.1.6.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1300 |  | - | - | 0 | Concretor | 0 | 61 | 33 | 36 | 31
1302 | 1.2.4.4.1.6.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1237 | 1305 | - | - | 0 | Formworker | 0 | 64 | 17 | 71 | 13
1303 | 1.2.4.4.1.6.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1236 | 1305 | - | - | 0 | Waterproofer | 0 | 78 | 17 | 90 | 44
1304 | 1.2.4.4.1.6.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1233 | 1305 | - | - | 0 | Painter | 0 | 75 | 20 | 10 | 6
1305 | 1.2.4.4.1.6.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1302,1303,1304 | 1306 | - | - | 0 | Carpenter | 0 | 50 | 27 | 95 | 27
1306 | 1.2.4.4.1.6.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1305 | 1307 | - | - | 0 | Post Tension | 0 | 19 | 22 | 85 | 3
1307 | 1.2.4.4.1.6.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1306 | 1308 | - | - | 0 | Concretor | 0 | 94 | 28 | 17 | 46
1308 | 1.2.4.4.1.6.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1307 | 1309 | - | - | 0 | Mechanical | 0 | 26 | 34 | 54 | 28
1309 | 1.2.4.4.1.6.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1308 | 1310 | - | - | 0 | Development Manager | 0 | 45 | 21 | 46 | 60
1310 | 1.2.4.4.1.6.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1309 | 1311 | - | - | 0 | Hoarding | 0 | 56 | 25 | 19 | 7
1311 | 1.2.4.4.1.6.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1310 | 1312 | - | - | 0 | Subcontractor | 0 | 88 | 23 | 3 | 50
1312 | 1.2.4.4.1.6.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1311 | 1313,1314,1315,1316 | - | - | 0 | Plasterboarder | 0 | 37 | 32 | 12 | 57
1313 | 1.2.4.4.1.6.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Plumber | 0 | 38 | 11 | 76 | 44
1314 | 1.2.4.4.1.6.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Mechanical | 0 | 28 | 13 | 26 | 23
1315 | 1.2.4.4.1.6.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Electrician | 0 | 21 | 22 | 15 | 42
1316 | 1.2.4.4.1.6.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Plumber | 0 | 34 | 14 | 12 | 38
1317 | 1.2.4.4.1.6.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1263,1264,1265,1266,1267 | 1318 | - | - | 0 | Timber Floorer | 0 | 89 | 27 | 100 | 53
1318 | 1.2.4.4.1.6.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1317 | 1319 | - | - | 0 | Excavation | 0 | 53 | 11 | 26 | 51
1319 | 1.2.4.4.1.6.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1318 | 1320 | - | - | 0 | Project Manager | 0 | 46 | 29 | 2 | 59
1320 | 1.2.4.4.1.6.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1319 |  | - | - | 0 | Reinforcement Fixer | 0 | 99 | 35 | 4 | 22
1321 | 1.2.4.4.1.7 | Apartment B016 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Floor Sealer | 0 | 37 | 17 | 59 | 20
1322 | 1.2.4.4.1.7.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1323,1326,1327,1394 | - | - | 0 | Window | 0 | 98 | 14 | 12 | 35
1323 | 1.2.4.4.1.7.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1322 | 1325,1324 | - | - | 0 | Electrician | 0 | 74 | 11 | 78 | 22
1324 | 1.2.4.4.1.7.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1323 |  | - | - | 0 | Subcontractor | 0 | 73 | 35 | 87 | 22
1325 | 1.2.4.4.1.7.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1323 | 1328 | - | - | 0 | Mechanical | 0 | 10 | 12 | 56 | 31
1326 | 1.2.4.4.1.7.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1335 | - | - | 0 | Scaffolder | 0 | 82 | 17 | 39 | 56
1327 | 1.2.4.4.1.7.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1398 | - | - | 0 | Tiler | 0 | 54 | 11 | 91 | 19
1328 | 1.2.4.4.1.7.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1325 | 1329,1330,1331,1332,1333 | - | - | 0 | Post Tension | 0 | 95 | 31 | 11 | 28
1329 | 1.2.4.4.1.7.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333 | - | - | 0 | Timber Floorer | 0 | 40 | 11 | 11 | 48
1330 | 1.2.4.4.1.7.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333,1397 | - | - | 0 | Joiner | 0 | 28 | 21 | 28 | 30
1331 | 1.2.4.4.1.7.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1396 | - | - | 0 | Excavation | 0 | 55 | 16 | 45 | 21
1332 | 1.2.4.4.1.7.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 |  | - | - | 0 | Line Market | 0 | 51 | 20 | 49 | 12
1333 | 1.2.4.4.1.7.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1328,1329,1330 | 1334 | - | - | 0 | Metal Work | 0 | 20 | 10 | 100 | 14
1334 | 1.2.4.4.1.7.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1333 | 1335 | - | - | 0 | Hoarding | 0 | 81 | 16 | 18 | 30
1335 | 1.2.4.4.1.7.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1326,1334 | 1336,1337,1338,1339,1341,1343 | - | - | 0 | Carpet | 0 | 75 | 23 | 69 | 7
1336 | 1.2.4.4.1.7.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1340,1343 | - | - | 0 | Subcontractor | 0 | 32 | 27 | 3 | 10
1337 | 1.2.4.4.1.7.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Subcontractor | 0 | 100 | 27 | 47 | 2
1338 | 1.2.4.4.1.7.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1342,1343 | - | - | 0 | Hoarding | 0 | 59 | 13 | 97 | 4
1339 | 1.2.4.4.1.7.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Excavation | 0 | 43 | 24 | 53 | 24
1340 | 1.2.4.4.1.7.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1336 | 1343 | - | - | 0 | Tiler | 0 | 77 | 33 | 22 | 51
1341 | 1.2.4.4.1.7.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Post Tension | 0 | 97 | 35 | 87 | 6
1342 | 1.2.4.4.1.7.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1338 | 1343 | - | - | 0 | Formworker | 0 | 90 | 10 | 46 | 36
1343 | 1.2.4.4.1.7.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1335,1336,1337,1338,1339,1340,1341,1342 | 1344 | - | - | 0 | Site Manager | 0 | 32 | 16 | 21 | 6
1344 | 1.2.4.4.1.7.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1343 | 1345 | - | - | 0 | Site Manager | 0 | 84 | 20 | 3 | 15
1345 | 1.2.4.4.1.7.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1344 | 1346,1363,1380 | - | - | 0 | Mechanical | 0 | 36 | 32 | 54 | 19
1346 | 1.2.4.4.1.7.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1347 | - | - | 0 | Reinforcement Fixer | 0 | 50 | 35 | 77 | 54
1347 | 1.2.4.4.1.7.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1346 | 1348 | - | - | 0 | Window | 0 | 18 | 13 | 52 | 27
1348 | 1.2.4.4.1.7.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1347 | 1349 | - | - | 0 | Hoarding | 0 | 51 | 28 | 12 | 15
1349 | 1.2.4.4.1.7.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1348 | 1350 | - | - | 0 | Joiner | 0 | 40 | 19 | 90 | 32
1350 | 1.2.4.4.1.7.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1349 | 1351,1352 | - | - | 0 | Excavation | 0 | 38 | 23 | 47 | 31
1351 | 1.2.4.4.1.7.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1350 | 1355 | - | - | 0 | Contract Administrator | 0 | 74 | 15 | 49 | 13
1352 | 1.2.4.4.1.7.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1350 | 1353 | - | - | 0 | Foreman | 0 | 67 | 28 | 19 | 23
1353 | 1.2.4.4.1.7.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1352 | 1354 | - | - | 0 | Site Manager | 0 | 45 | 18 | 0 | 5
1354 | 1.2.4.4.1.7.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1353 |  | - | - | 0 | Plasterboarder | 0 | 29 | 19 | 40 | 51
1355 | 1.2.4.4.1.7.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1351 | 1356,1357,1358,1359,1360 | - | - | 0 | Painter | 0 | 91 | 22 | 70 | 41
1356 | 1.2.4.4.1.7.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1355 |  | - | - | 0 | Landscaper | 0 | 79 | 27 | 25 | 9
1357 | 1.2.4.4.1.7.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Tiler | 0 | 76 | 17 | 78 | 5
1358 | 1.2.4.4.1.7.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Electrician | 0 | 18 | 31 | 99 | 27
1359 | 1.2.4.4.1.7.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Contract Administrator | 0 | 20 | 11 | 66 | 27
1360 | 1.2.4.4.1.7.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Joiner | 0 | 88 | 15 | 36 | 26
1361 | 1.2.4.4.1.7.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1411 | - | - | 0 | Foreman | 0 | 54 | 20 | 41 | 25
1362 | 1.2.4.4.1.7.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 55 | 27 | 89 | 36
1363 | 1.2.4.4.1.7.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1364 | - | - | 0 | Joiner | 0 | 64 | 28 | 59 | 43
1364 | 1.2.4.4.1.7.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1363 | 1365 | - | - | 0 | Project Manager | 0 | 82 | 34 | 43 | 36
1365 | 1.2.4.4.1.7.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1364 | 1366 | - | - | 0 | Landscaper | 0 | 70 | 24 | 29 | 19
1366 | 1.2.4.4.1.7.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1365 | 1367 | - | - | 0 | Hoarding | 0 | 67 | 23 | 43 | 58
1367 | 1.2.4.4.1.7.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1366 | 1368 | - | - | 0 | Contract Administrator | 0 | 31 | 16 | 14 | 43
1368 | 1.2.4.4.1.7.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1367 | 1369 | - | - | 0 | Line Market | 0 | 44 | 12 | 69 | 33
1369 | 1.2.4.4.1.7.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1368 | 1370 | - | - | 0 | Hoarding | 0 | 59 | 21 | 10 | 53
1370 | 1.2.4.4.1.7.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1369 | 1371 | - | - | 0 | Hoarding | 0 | 90 | 29 | 79 | 35
1371 | 1.2.4.4.1.7.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1370 | 1372 | - | - | 0 | Tiler | 0 | 59 | 14 | 62 | 16
1372 | 1.2.4.4.1.7.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1371 | 1373 | - | - | 0 | Line Market | 0 | 86 | 27 | 86 | 13
1373 | 1.2.4.4.1.7.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1372 | 1374 | - | - | 0 | Electrician | 0 | 66 | 35 | 1 | 23
1374 | 1.2.4.4.1.7.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1373 | 1378,1375,1376,1377 | - | - | 0 | Development Manager | 0 | 96 | 30 | 78 | 52
1375 | 1.2.4.4.1.7.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Project Manager | 0 | 90 | 34 | 51 | 14
1376 | 1.2.4.4.1.7.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Site Manager | 0 | 46 | 21 | 6 | 46
1377 | 1.2.4.4.1.7.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Joiner | 0 | 31 | 22 | 59 | 40
1378 | 1.2.4.4.1.7.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1374,1375,1376,1377 |  | - | - | 0 | Admin | 0 | 27 | 33 | 39 | 37
1379 | 1.2.4.4.1.7.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Electrician | 0 | 20 | 13 | 51 | 37
1380 | 1.2.4.4.1.7.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1381 | - | - | 0 | Subcontractor | 0 | 78 | 34 | 19 | 3
1381 | 1.2.4.4.1.7.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1380 | 1382 | - | - | 0 | Painter | 0 | 52 | 34 | 97 | 2
1382 | 1.2.4.4.1.7.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1381 | 1383 | - | - | 0 | Metal Work | 0 | 24 | 28 | 62 | 59
1383 | 1.2.4.4.1.7.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1382 | 1384 | - | - | 0 | Post Tension | 0 | 26 | 29 | 14 | 11
1384 | 1.2.4.4.1.7.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1383 | 1385 | - | - | 0 | Landscaper | 0 | 98 | 35 | 58 | 39
1385 | 1.2.4.4.1.7.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1384 | 1386 | - | - | 0 | Electrician | 0 | 78 | 14 | 55 | 39
1386 | 1.2.4.4.1.7.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1385 | 1387 | - | - | 0 | Scaffolder | 0 | 69 | 34 | 66 | 27
1387 | 1.2.4.4.1.7.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1386 | 1388,1389,1390,1391 | - | - | 0 | Floor Sealer | 0 | 89 | 34 | 62 | 42
1388 | 1.2.4.4.1.7.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Head Contractor | 0 | 56 | 21 | 28 | 35
1389 | 1.2.4.4.1.7.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Carpet | 0 | 60 | 28 | 4 | 21
1390 | 1.2.4.4.1.7.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Scaffolder | 0 | 25 | 30 | 45 | 30
1391 | 1.2.4.4.1.7.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Carpet | 0 | 22 | 18 | 22 | 39
1392 | 1.2.4.4.1.7.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1388,1389,1390,1391 |  | - | - | 0 | Tiler | 0 | 68 | 18 | 100 | 57
1393 | 1.2.4.4.1.7.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | - | - | 0 | Excavation | 0 | 53 | 22 | 49 | 2
1394 | 1.2.4.4.1.7.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1322 | 1395 | - | - | 0 | Scaffolder | 0 | 62 | 30 | 48 | 8
1395 | 1.2.4.4.1.7.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1394 |  | - | - | 0 | Tiler | 0 | 29 | 15 | 35 | 4
1396 | 1.2.4.4.1.7.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1331 | 1399 | - | - | 0 | Surveyor | 0 | 74 | 35 | 19 | 48
1397 | 1.2.4.4.1.7.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1330 | 1399 | - | - | 0 | Plasterboarder | 0 | 17 | 15 | 40 | 57
1398 | 1.2.4.4.1.7.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1327 | 1399 | - | - | 0 | Line Market | 0 | 81 | 21 | 84 | 42
1399 | 1.2.4.4.1.7.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1396,1397,1398 | 1400 | - | - | 0 | Hoarding | 0 | 37 | 21 | 90 | 53
1400 | 1.2.4.4.1.7.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1399 | 1401 | - | - | 0 | Contract Administrator | 0 | 66 | 35 | 53 | 39
1401 | 1.2.4.4.1.7.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1400 | 1402 | - | - | 0 | Project Manager | 0 | 23 | 13 | 43 | 50
1402 | 1.2.4.4.1.7.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1401 | 1403 | - | - | 0 | Waterproofer | 0 | 76 | 19 | 57 | 26
1403 | 1.2.4.4.1.7.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1402 | 1404 | - | - | 0 | Line Market | 0 | 83 | 19 | 41 | 22
1404 | 1.2.4.4.1.7.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1403 | 1405 | - | - | 0 | Tiler | 0 | 47 | 29 | 37 | 7
1405 | 1.2.4.4.1.7.41.12 | Grout | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1404 | 1406 | - | - | 0 | Cleaner | 0 | 11 | 21 | 26 | 44
1406 | 1.2.4.4.1.7.41.13 | Paint/Cladding | 3 | 14 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1405 | 1407,1408,1409,1410 | - | - | 0 | Landscaper | 0 | 44 | 35 | 49 | 58
1407 | 1.2.4.4.1.7.41.14 | Silicone | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Reinforcement Fixer | 0 | 51 | 26 | 75 | 24
1408 | 1.2.4.4.1.7.41.15 | Hydraulic Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Subcontractor | 0 | 17 | 30 | 14 | 22
1409 | 1.2.4.4.1.7.41.16 | Electrical Fit Off | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Development Manager | 0 | 83 | 30 | 51 | 15
1410 | 1.2.4.4.1.7.41.17 | Fit Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Waterproofer | 0 | 83 | 16 | 100 | 22
1411 | 1.2.4.4.1.7.42 | Carpet Install | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1357,1358,1359,1360,1361 | 1412 | - | - | 0 | Admin | 0 | 100 | 26 | 97 | 41
1412 | 1.2.4.4.1.7.43 | Paint (FINAL Coat) | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1411 | 1413 | - | - | 0 | Carpenter | 0 | 75 | 26 | 74 | 7
1413 | 1.2.4.4.1.7.44 | FINAL CLEAN | 1 | 11 December 2024 8:00 AM | 11 December 2024 5:00 PM | 1412 | 1414 | - | - | 0 | Site Manager | 0 | 51 | 18 | 17 | 46
1414 | 1.2.4.4.1.7.45 | UNIT LOCKED | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 1413 |  | - | - | 0 | Subcontractor | 0 | 64 | 14 | 63 | 54
1415 | 1.2.4.4.1.8 | Apartment B017 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Post Tension | 0 | 12 | 30 | 70 | 37
1416 | 1.2.4.4.1.8.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1417,1420,1421,1488 | - | - | 0 | Surveyor | 0 | 46 | 20 | 32 | 26
1417 | 1.2.4.4.1.8.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1416 | 1419,1418 | - | - | 0 | Waterproofer | 0 | 95 | 18 | 10 | 50
1418 | 1.2.4.4.1.8.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1417 |  | - | - | 0 | Tiler | 0 | 49 | 19 | 91 | 39
1419 | 1.2.4.4.1.8.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1417 | 1422 | - | - | 0 | Cleaner | 0 | 24 | 34 | 87 | 38
1420 | 1.2.4.4.1.8.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1429 | - | - | 0 | Site Manager | 0 | 76 | 29 | 83 | 39
1421 | 1.2.4.4.1.8.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1492 | - | - | 0 | Formworker | 0 | 44 | 27 | 13 | 32
1422 | 1.2.4.4.1.8.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1419 | 1423,1424,1425,1426,1427 | - | - | 0 | Formworker | 0 | 62 | 11 | 56 | 34
1423 | 1.2.4.4.1.8.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427 | - | - | 0 | Formworker | 0 | 27 | 26 | 33 | 18
1424 | 1.2.4.4.1.8.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427,1491 | - | - | 0 | Post Tension | 0 | 21 | 15 | 52 | 22
1425 | 1.2.4.4.1.8.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1490 | - | - | 0 | Fire | 0 | 21 | 35 | 89 | 30
1426 | 1.2.4.4.1.8.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 |  | - | - | 0 | Carpet | 0 | 36 | 35 | 11 | 54
1427 | 1.2.4.4.1.8.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1422,1423,1424 | 1428 | - | - | 0 | Formworker | 0 | 64 | 24 | 29 | 8
1428 | 1.2.4.4.1.8.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1427 | 1429 | - | - | 0 | Plasterboarder | 0 | 76 | 14 | 55 | 15
1429 | 1.2.4.4.1.8.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1420,1428 | 1430,1431,1432,1433,1435,1437 | - | - | 0 | Metal Work | 0 | 11 | 27 | 91 | 45
1430 | 1.2.4.4.1.8.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1434,1437 | - | - | 0 | Hoarding | 0 | 50 | 33 | 56 | 40
1431 | 1.2.4.4.1.8.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Carpet | 0 | 33 | 34 | 29 | 31
1432 | 1.2.4.4.1.8.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1436,1437 | - | - | 0 | Stone Mason | 0 | 73 | 31 | 54 | 19
1433 | 1.2.4.4.1.8.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Renderer | 0 | 95 | 19 | 48 | 8
1434 | 1.2.4.4.1.8.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1430 | 1437 | - | - | 0 | Foreman | 0 | 28 | 24 | 43 | 50
1435 | 1.2.4.4.1.8.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Tiler | 0 | 39 | 30 | 8 | 8
1436 | 1.2.4.4.1.8.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1432 | 1437 | - | - | 0 | Timber Floorer | 0 | 80 | 25 | 83 | 58
1437 | 1.2.4.4.1.8.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1429,1430,1431,1432,1433,1434,1435,1436 | 1438 | - | - | 0 | Mechanical | 0 | 64 | 21 | 98 | 23
1438 | 1.2.4.4.1.8.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1437 | 1439 | - | - | 0 | Stone Mason | 0 | 83 | 28 | 42 | 4
1439 | 1.2.4.4.1.8.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1438 | 1440,1457,1474 | - | - | 0 | Foreman | 0 | 42 | 32 | 97 | 37
1440 | 1.2.4.4.1.8.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1441 | - | - | 0 | Contract Administrator | 0 | 56 | 25 | 62 | 31
1441 | 1.2.4.4.1.8.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1440 | 1442 | - | - | 0 | Carpet | 0 | 43 | 30 | 66 | 57
1442 | 1.2.4.4.1.8.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1441 | 1443 | - | - | 0 | Floor Sealer | 0 | 11 | 17 | 80 | 17
1443 | 1.2.4.4.1.8.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1442 | 1444 | - | - | 0 | Reinforcement Fixer | 0 | 39 | 25 | 10 | 58
1444 | 1.2.4.4.1.8.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1443 | 1445,1446 | - | - | 0 | Line Market | 0 | 47 | 26 | 15 | 35
1445 | 1.2.4.4.1.8.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1444 | 1449 | - | - | 0 | Hoarding | 0 | 95 | 31 | 28 | 17
1446 | 1.2.4.4.1.8.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1444 | 1447 | - | - | 0 | Development Manager | 0 | 80 | 16 | 18 | 5
1447 | 1.2.4.4.1.8.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1446 | 1448 | - | - | 0 | Head Contractor | 0 | 45 | 30 | 41 | 56
1448 | 1.2.4.4.1.8.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1447 |  | - | - | 0 | Renderer | 0 | 15 | 18 | 80 | 50
1449 | 1.2.4.4.1.8.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1445 | 1450,1451,1452,1453,1454 | - | - | 0 | Surveyor | 0 | 91 | 28 | 80 | 51
1450 | 1.2.4.4.1.8.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1449 |  | - | - | 0 | Cleaner | 0 | 24 | 27 | 94 | 15
1451 | 1.2.4.4.1.8.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Floor Sealer | 0 | 15 | 18 | 98 | 11
1452 | 1.2.4.4.1.8.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Subcontractor | 0 | 62 | 20 | 89 | 45
1453 | 1.2.4.4.1.8.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Renderer | 0 | 54 | 33 | 34 | 36
1454 | 1.2.4.4.1.8.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Cleaner | 0 | 92 | 22 | 79 | 19
1455 | 1.2.4.4.1.8.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1505 | - | - | 0 | Mechanical | 0 | 97 | 15 | 23 | 48
1456 | 1.2.4.4.1.8.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 70 | 26 | 87 | 54
1457 | 1.2.4.4.1.8.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1458 | - | - | 0 | Mechanical | 0 | 36 | 27 | 5 | 34
1458 | 1.2.4.4.1.8.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1457 | 1459 | - | - | 0 | Foreman | 0 | 15 | 33 | 9 | 8
1459 | 1.2.4.4.1.8.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1458 | 1460 | - | - | 0 | Waterproofer | 0 | 34 | 17 | 34 | 32
1460 | 1.2.4.4.1.8.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1459 | 1461 | - | - | 0 | Project Manager | 0 | 86 | 31 | 34 | 21
1461 | 1.2.4.4.1.8.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1460 | 1462 | - | - | 0 | Carpet | 0 | 11 | 18 | 71 | 39
1462 | 1.2.4.4.1.8.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1461 | 1463 | - | - | 0 | Admin | 0 | 87 | 10 | 72 | 34
1463 | 1.2.4.4.1.8.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1462 | 1464 | - | - | 0 | Scaffolder | 0 | 36 | 23 | 54 | 24
1464 | 1.2.4.4.1.8.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1463 | 1465 | - | - | 0 | Joiner | 0 | 11 | 32 | 15 | 49
1465 | 1.2.4.4.1.8.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1464 | 1466 | - | - | 0 | Painter | 0 | 98 | 24 | 73 | 27
1466 | 1.2.4.4.1.8.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1465 | 1467 | - | - | 0 | Foreman | 0 | 13 | 18 | 12 | 35
1467 | 1.2.4.4.1.8.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1466 | 1468 | - | - | 0 | Plasterboarder | 0 | 54 | 13 | 69 | 17
1468 | 1.2.4.4.1.8.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1467 | 1472,1469,1470,1471 | - | - | 0 | Plasterboarder | 0 | 71 | 19 | 11 | 33
1469 | 1.2.4.4.1.8.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Window | 0 | 15 | 30 | 98 | 49
1470 | 1.2.4.4.1.8.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Electrician | 0 | 10 | 15 | 69 | 48
1471 | 1.2.4.4.1.8.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Reinforcement Fixer | 0 | 41 | 11 | 54 | 54
1472 | 1.2.4.4.1.8.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1468,1469,1470,1471 |  | - | - | 0 | Carpenter | 0 | 72 | 17 | 87 | 41
1473 | 1.2.4.4.1.8.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Project Manager | 0 | 92 | 24 | 69 | 59
1474 | 1.2.4.4.1.8.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1475 | - | - | 0 | Metal Work | 0 | 61 | 23 | 53 | 9
1475 | 1.2.4.4.1.8.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1474 | 1476 | - | - | 0 | Formworker | 0 | 12 | 25 | 65 | 34
1476 | 1.2.4.4.1.8.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1475 | 1477 | - | - | 0 | Landscaper | 0 | 59 | 33 | 26 | 23
1477 | 1.2.4.4.1.8.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1476 | 1478 | - | - | 0 | Fire | 0 | 64 | 31 | 27 | 12
1478 | 1.2.4.4.1.8.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1477 | 1479 | - | - | 0 | Head Contractor | 0 | 42 | 33 | 82 | 56
1479 | 1.2.4.4.1.8.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1478 | 1480 | - | - | 0 | Contract Administrator | 0 | 66 | 28 | 67 | 51
1480 | 1.2.4.4.1.8.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1479 | 1481 | - | - | 0 | Project Manager | 0 | 52 | 12 | 49 | 16
1481 | 1.2.4.4.1.8.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1480 | 1482,1483,1484,1485 | - | - | 0 | Window | 0 | 41 | 33 | 15 | 7
1482 | 1.2.4.4.1.8.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Timber Floorer | 0 | 20 | 27 | 10 | 8
1483 | 1.2.4.4.1.8.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Renderer | 0 | 81 | 14 | 37 | 6
1484 | 1.2.4.4.1.8.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Painter | 0 | 16 | 30 | 64 | 37
1485 | 1.2.4.4.1.8.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Plasterboarder | 0 | 59 | 29 | 91 | 10
1486 | 1.2.4.4.1.8.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1482,1483,1484,1485 |  | - | - | 0 | Project Manager | 0 | 62 | 33 | 86 | 23
1487 | 1.2.4.4.1.8.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 48 | 26 | 37 | 20
1488 | 1.2.4.4.1.8.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1416 | 1489 | - | - | 0 | Floor Sealer | 0 | 51 | 16 | 32 | 56
1489 | 1.2.4.4.1.8.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1488 |  | - | - | 0 | Joiner | 0 | 50 | 21 | 65 | 53
1490 | 1.2.4.4.1.8.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1425 | 1493 | - | - | 0 | Admin | 0 | 24 | 26 | 85 | 48
1491 | 1.2.4.4.1.8.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1424 | 1493 | - | - | 0 | Line Market | 0 | 79 | 11 | 90 | 30
1492 | 1.2.4.4.1.8.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1421 | 1493 | - | - | 0 | Scaffolder | 0 | 31 | 12 | 80 | 59
1493 | 1.2.4.4.1.8.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1490,1491,1492 | 1494 | - | - | 0 | Surveyor | 0 | 63 | 24 | 38 | 55
1494 | 1.2.4.4.1.8.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1493 | 1495 | - | - | 0 | Concretor | 0 | 73 | 22 | 82 | 44
1495 | 1.2.4.4.1.8.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1494 | 1496 | - | - | 0 | Waterproofer | 0 | 99 | 25 | 9 | 24
1496 | 1.2.4.4.1.8.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1495 | 1497 | - | - | 0 | Development Manager | 0 | 13 | 35 | 65 | 56
1497 | 1.2.4.4.1.8.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1496 | 1498 | - | - | 0 | Scaffolder | 0 | 28 | 19 | 44 | 15
1498 | 1.2.4.4.1.8.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1497 | 1499 | - | - | 0 | Surveyor | 0 | 86 | 31 | 94 | 60

## Progress 35%
ID | Outline_Number | Name | Duration | Start_Date | Finish_Date | Predecessors | Successors | Actual_Start | Actual_End | Delay | Trade | Progress | Worker_Score | Temp | Rain_Probability | Wind_Speed
2 | 1.1 | MILESTONES / KEY DATES | 633 | 17 April 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 17 April 2023 7:00 AM | - | 0 |  | 35.1471 | 35 | 21 | 37 | 7
3 | 1.1.1 | Site Establishment | 0 | 5 June 2023 7:00 AM | 5 June 2023 7:00 AM |  | 25SS | 5 June 2023 7:00 AM | 2023-06-05 07:00 | 0 | Plasterboarder | 100 | 33 | 30 | 69 | 19
4 | 1.1.2 | Basement Completed (B2) | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 88 |  | 2 May 2024 5:00 PM | 2024-05-02 17:00 | 0 | Timber Floorer | 100 | 93 | 24 | 2 | 16
5 | 1.1.3 | Building A Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 444,753,746,714 | 3466,9 | 5 May 2025 5:00 PM | 2025-05-05 17:00 | 0 | Floor Sealer | 100 | 72 | 30 | 36 | 57
6 | 1.1.4 | Building B Complete | 0 | 29 March 2025 5:00 PM | 29 March 2025 5:00 PM | 228,482,306,1737 | 3466,9 | 29 March 2025 5:00 PM | 2025-03-29 17:00 | 0 | Scaffolder | 100 | 89 | 22 | 78 | 33
7 | 1.1.5 | Building C Complete | 0 | 16 April 2025 5:00 PM | 16 April 2025 5:00 PM | 306,360,503,3169 | 3466,9 | 16 April 2025 5:00 PM | 2025-04-16 17:00 | 0 | Painter | 100 | 19 | 14 | 44 | 60
8 | 1.1.6 | Building D Complete | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 360,396,519,3439 | 3466,9 | 17 April 2025 5:00 PM | 2025-04-17 17:00 | 0 | Post Tension | 100 | 72 | 18 | 31 | 43
9 | 1.1.7 | Practical Completion (Net) | 0 | 28 May 2025 5:00 PM | 28 May 2025 5:00 PM | 3465,3440,5,3460,6,7,8 |  | 28 May 2025 5:00 PM | 2025-05-28 17:00 | 0 | Admin | 100 | 56 | 30 | 35 | 39
10 | 1.1.8 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | 28 July 2023 8:00 AM | 2023-08-15 17:00 | 0 | Plasterboarder | 100 | 34 | 14 | 40 | 35
11 | 1.1.9 | Inclement Weatherallowed (Spent) | 19 | 29 May 2025 8:00 AM | 21 June 2025 5:00 PM | 3466 | 12 | 29 May 2025 8:00 AM | 2025-06-23 17:00 | 2 | Subcontractor | 100 | 15 | 12 | 75 | 32
12 | 1.1.10 | Inclement Weatherallowed (Remaining) | 1 | 23 June 2025 8:00 AM | 23 June 2025 5:00 PM | 11 | 3469 | 23 June 2025 8:00 AM | 2025-06-23 17:00 | 0 | Painter | 100 | 50 | 33 | 73 | 35
13 | 1.1.11 | Practical Completion (Gross) - Building Handover | 0 | 23 June 2025 5:00 PM | 23 June 2025 5:00 PM | 3469 |  | 23 June 2025 5:00 PM | 2025-06-23 17:00 | 0 | Contract Administrator | 100 | 88 | 22 | 67 | 45
14 | 1.1.12 | PRE CONSTRUCTION WORKS | 210.13 | 17 April 2023 7:00 AM | 16 January 2024 5:00 PM |  |  | 17 April 2023 7:00 AM | 2024-01-16 17:00 | 0 | Stone Mason | 100 | 70 | 22 | 98 | 35
15 | 1.1.12.1 | Authority Approvals, (Access Deeds by Client etc (Ultra to assist in coordination) These are qualifying causes of delay resulting in EOT time & costs) | 372 | 17 April 2023 7:00 AM | 1 August 2024 5:00 PM |  |  | 17 April 2023 7:00 AM | 2024-08-04 17:00 | 3 | Scaffolder | 100 | 19 | 24 | 60 | 26
16 | 1.1.12.1.1 | Section 73 - BPA Design & Stormwater Works | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Mechanical | 100 | 85 | 35 | 39 | 22
17 | 1.1.12.1.2 | Rail Approval | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Scaffolder | 100 | 63 | 17 | 5 | 5
18 | 1.1.12.1.3 | CC1 - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  | 25,19 | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Electrician | 100 | 93 | 19 | 7 | 35
19 | 1.1.12.1.4 | CC1a - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM | 18 | 25,20 | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Post Tension | 100 | 60 | 35 | 80 | 46
20 | 1.1.12.1.5 | CC2 - Structure (SoG - Podium) | 120 | 17 April 2023 8:00 AM | 12 September 2023 5:00 PM | 19 | 21 | 17 April 2023 8:00 AM | 2023-09-13 17:00 | 1 | Floor Sealer | 100 | 75 | 15 | 51 | 10
21 | 1.1.12.1.6 | CC3 - Structure (Podium - Roof) + Facade | 156 | 13 September 2023 8:00 AM | 8 April 2024 5:00 PM | 20 | 22 | 13 September 2023 8:00 AM | 2024-04-13 17:00 | 5 | Window | 100 | 13 | 24 | 47 | 16
22 | 1.1.12.1.7 | CC4 - Services & Fit Out | 60 | 9 April 2024 8:00 AM | 20 June 2024 5:00 PM | 21 | 23 | 9 April 2024 8:00 AM | 2024-06-21 17:00 | 1 | Plumber | 100 | 71 | 25 | 85 | 39
23 | 1.1.12.1.8 | CC5 - External Works and Public Domain | 36 | 21 June 2024 8:00 AM | 1 August 2024 5:00 PM | 22 |  | 21 June 2024 8:00 AM | 2024-08-04 17:00 | 3 | Development Manager | 100 | 46 | 24 | 87 | 24
24 | 1.1.12.2 | SITE ESTABLISHMENT | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM |  |  | 26 June 2023 8:00 AM | 2023-06-30 17:00 | 0 | Head Contractor | 100 | 85 | 10 | 99 | 53
25 | 1.1.12.2.1 | Site Establishment, Enviro Protection, Survey Set out & Hoardings | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM | 18,3SS,19 | 28 | 26 June 2023 8:00 AM | 2023-06-30 17:00 | 0 | Painter | 100 | 22 | 30 | 48 | 39
26 | 1.2 | CONSTRUCTION WORKS | 571 | 3 July 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 3 July 2023 7:00 AM | 2025-06-24 17:00 | 1 | Mechanical | 100 | 65 | 11 | 2 | 33
27 | 1.2.1 | EARTHWORKS, PILING - BASEMENT | 234 | 3 July 2023 7:00 AM | 2 May 2024 5:00 PM |  |  | 3 July 2023 7:00 AM | 2024-05-06 17:00 | 4 | Contract Administrator | 100 | 25 | 23 | 51 | 8
28 | 1.2.1.1 | Demolition, Clear & Cut/Level Site | 6 | 3 July 2023 7:00 AM | 8 July 2023 5:00 PM | 25 | 10SS,29SS | 3 July 2023 7:00 AM | 2023-07-08 17:00 | 0 | Plasterboarder | 100 | 22 | 25 | 82 | 58
29 | 1.2.1.2 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | 28 July 2023 8:00 AM | 2023-08-15 17:00 | 0 | Head Contractor | 100 | 26 | 29 | 29 | 19
30 | 1.2.1.3 | Install Piling Matt | 12 | 16 August 2023 8:00 AM | 30 August 2023 5:00 PM | 10,29 | 34FS-6d | 16 August 2023 8:00 AM | 2023-09-03 17:00 | 4 | Tiler | 100 | 11 | 21 | 74 | 41
31 | 1.2.1.4 | Crane Base Ex, Piles & FRP | 8 | 18 December 2023 8:00 AM | 5 January 2024 5:00 PM | 53 | 3442FS+8d | 18 December 2023 8:00 AM | 2024-01-08 17:00 | 3 | Cleaner | 100 | 44 | 29 | 28 | 18
32 | 1.2.1.5 | Piling and Capping Beam | 58 | 28 August 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | 28 August 2023 8:00 AM | 2023-11-13 17:00 | 4 | Concretor | 100 | 14 | 26 | 34 | 47
33 | 1.2.1.5.1 | Buildings A | 28 | 28 August 2023 8:00 AM | 3 October 2023 5:00 PM |  |  | 28 August 2023 8:00 AM | 2023-10-03 17:00 | 0 | Formworker | 100 | 45 | 22 | 36 | 9
34 | 1.2.1.5.1.1 | Perimeter Piling (75 Piles) | 16 | 28 August 2023 8:00 AM | 15 September 2023 5:00 PM | 30FS-6d | 35FS-6d,37,46 | 28 August 2023 8:00 AM | 2023-09-20 17:00 | 5 | Electrician | 100 | 54 | 20 | 97 | 34
35 | 1.2.1.5.1.2 | Capping Beam - Detailed Excavation & FRP | 18 | 9 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34FS-6d |  | 9 September 2023 8:00 AM | 2023-10-06 17:00 | 3 | Metal Work | 100 | 74 | 14 | 48 | 11
36 | 1.2.1.5.2 | Buildings B | 24 | 16 September 2023 8:00 AM | 17 October 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-10-21 17:00 | 4 | Renderer | 100 | 40 | 32 | 55 | 50
37 | 1.2.1.5.2.1 | Perimeter Piling (56 Piles) | 12 | 16 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34 | 38FS-6d,40 | 16 September 2023 8:00 AM | 2023-10-08 17:00 | 5 | Carpenter | 100 | 71 | 11 | 93 | 37
38 | 1.2.1.5.2.2 | Capping Beam - Detailed Excavation & FRP | 18 | 25 September 2023 8:00 AM | 17 October 2023 5:00 PM | 37FS-6d | 56 | 25 September 2023 8:00 AM | 2023-10-22 17:00 | 5 | Development Manager | 100 | 88 | 10 | 11 | 60
39 | 1.2.1.5.3 | Buildings C & D | 30 | 4 October 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | 4 October 2023 8:00 AM | 2023-11-09 17:00 | 0 | Foreman | 100 | 16 | 11 | 37 | 11
40 | 1.2.1.5.3.1 | Foundation Piling (Gnd Lvl) - (17 Piles) | 6 | 4 October 2023 8:00 AM | 10 October 2023 5:00 PM | 37 | 41 | 4 October 2023 8:00 AM | 2023-10-10 17:00 | 0 | Cleaner | 100 | 70 | 34 | 70 | 4
41 | 1.2.1.5.3.2 | Perimeter Piling (82 Piles) | 18 | 11 October 2023 8:00 AM | 1 November 2023 5:00 PM | 40 | 42FS-6d | 11 October 2023 8:00 AM | 2023-11-03 17:00 | 2 | Reinforcement Fixer | 100 | 79 | 19 | 79 | 48
42 | 1.2.1.5.3.3 | Capping Beam - Detailed Excavation & FRP | 12 | 26 October 2023 8:00 AM | 9 November 2023 5:00 PM | 41FS-6d | 66 | 26 October 2023 8:00 AM | 2023-11-10 17:00 | 1 | Excavation | 100 | 30 | 35 | 30 | 58
43 | 1.2.1.6 | Bulk Excavation & Shotcrete | 142 | 16 September 2023 8:00 AM | 22 March 2024 5:00 PM |  |  | 16 September 2023 8:00 AM | 2024-03-22 17:00 | 0 | Reinforcement Fixer | 100 | 32 | 10 | 20 | 3
44 | 1.2.1.6.1 | Building A | 70 | 16 September 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-12-16 17:00 | 0 | Carpet | 100 | 47 | 27 | 11 | 3
45 | 1.2.1.6.1.1 | Excavate - Gnd - B1 | 57 | 16 September 2023 8:00 AM | 28 November 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-11-28 17:00 | 0 | Hoarding | 100 | 31 | 18 | 47 | 57
46 | 1.2.1.6.1.1.1 | Excavation | 21 | 16 September 2023 8:00 AM | 13 October 2023 5:00 PM | 34 | 47,56,51,71 | 16 September 2023 8:00 AM | 2023-10-18 17:00 | 5 | Carpet | 100 | 94 | 28 | 49 | 30
47 | 1.2.1.6.1.1.2 | Installation of Anchors | 8 | 20 October 2023 8:00 AM | 30 October 2023 5:00 PM | 46 | 48,49SS+11d | 20 October 2023 8:00 AM | 2023-11-01 17:00 | 2 | Plumber | 100 | 37 | 26 | 54 | 53
48 | 1.2.1.6.1.1.3 | Install Bracing | 4 | 31 October 2023 8:00 AM | 3 November 2023 5:00 PM | 47 |  | 31 October 2023 8:00 AM | 2023-11-03 17:00 | 0 | Project Manager | 100 | 95 | 14 | 28 | 46
49 | 1.2.1.6.1.1.4 | Shotcrete | 20 | 3 November 2023 8:00 AM | 28 November 2023 5:00 PM | 47SS+11d |  | 3 November 2023 8:00 AM | 2023-11-28 17:00 | 0 | Painter | 100 | 29 | 12 | 72 | 3
50 | 1.2.1.6.1.2 | Excavate - B1-B2 | 44 | 20 October 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | 20 October 2023 8:00 AM | 2023-12-16 17:00 | 0 | Carpet | 100 | 28 | 16 | 21 | 7
51 | 1.2.1.6.1.2.1 | Excavation | 14 | 20 October 2023 8:00 AM | 7 November 2023 5:00 PM | 46 | 52,53,56,71 | 20 October 2023 8:00 AM | 2023-11-10 17:00 | 3 | Electrician | 100 | 77 | 15 | 71 | 59
52 | 1.2.1.6.1.2.2 | Shotcrete | 16 | 15 November 2023 8:00 AM | 7 December 2023 5:00 PM | 51 | 53 | 15 November 2023 8:00 AM | 2023-12-12 17:00 | 5 | Fire | 100 | 45 | 28 | 74 | 4
53 | 1.2.1.6.1.2.3 | Foundation Piling (Basement 2 Lvl) - (35 Piles) | 8 | 8 December 2023 8:00 AM | 16 December 2023 5:00 PM | 51,52 | 63,31 | 8 December 2023 8:00 AM | 2023-12-16 17:00 | 0 | Formworker | 100 | 71 | 27 | 59 | 40
54 | 1.2.1.6.2 | Building B | 66 | 15 November 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | 15 November 2023 8:00 AM | 2024-02-16 17:00 | 0 | Site Manager | 100 | 77 | 28 | 81 | 47
55 | 1.2.1.6.2.1 | Excavate - Gnd - B1 | 46 | 15 November 2023 8:00 AM | 22 January 2024 5:00 PM |  |  | 15 November 2023 8:00 AM | 2024-01-26 17:00 | 4 | Plumber | 100 | 34 | 23 | 60 | 57
56 | 1.2.1.6.2.1.1 | Excavation | 22 | 15 November 2023 8:00 AM | 14 December 2023 5:00 PM | 38,46,51 | 57,59,61,71 | 15 November 2023 8:00 AM | 2023-12-16 17:00 | 2 | Excavation | 100 | 69 | 18 | 68 | 16
57 | 1.2.1.6.2.1.2 | Installation of Anchors | 8 | 20 December 2023 8:00 AM | 8 January 2024 5:00 PM | 56 | 58 | 20 December 2023 8:00 AM | 2024-01-09 17:00 | 1 | Cleaner | 100 | 62 | 31 | 70 | 45
58 | 1.2.1.6.2.1.3 | Install Bracing | 4 | 9 January 2024 8:00 AM | 12 January 2024 5:00 PM | 57 | 59 | 9 January 2024 8:00 AM | 2024-01-12 17:00 | 0 | Head Contractor | 100 | 21 | 14 | 72 | 38
59 | 1.2.1.6.2.1.4 | Shotcrete | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,58 | 61 | 20 December 2023 8:00 AM | 2024-01-23 17:00 | 1 | Floor Sealer | 100 | 52 | 13 | 62 | 23
60 | 1.2.1.6.2.2 | Excavate - B1-B2 | 40 | 20 December 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | 20 December 2023 8:00 AM | 2024-02-20 17:00 | 4 | Fire | 100 | 61 | 24 | 64 | 15
61 | 1.2.1.6.2.2.1 | Excavation | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,59 | 66,63,71,62 | 20 December 2023 8:00 AM | 2024-01-27 17:00 | 5 | Metal Work | 100 | 66 | 19 | 85 | 18
62 | 1.2.1.6.2.2.2 | Shotcrete | 10 | 1 February 2024 8:00 AM | 12 February 2024 5:00 PM | 61 | 63 | 1 February 2024 8:00 AM | 2024-02-12 17:00 | 0 | Contract Administrator | 100 | 56 | 26 | 17 | 44
63 | 1.2.1.6.2.2.3 | Foundation Piling (Basement 2 Lvl) - (23 Piles) | 4 | 13 February 2024 8:00 AM | 16 February 2024 5:00 PM | 61,53,62 | 74 | 13 February 2024 8:00 AM | 2024-02-16 17:00 | 0 | Stone Mason | 100 | 88 | 13 | 37 | 14
64 | 1.2.1.6.3 | Buildings C & D | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | 23 January 2024 8:00 AM | 2024-03-22 17:00 | 0 | Mechanical | 100 | 61 | 21 | 14 | 43
65 | 1.2.1.6.3.1 | Excavate - Gnd - B2 | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | 23 January 2024 8:00 AM | 2024-03-27 17:00 | 5 | Foreman | 100 | 20 | 13 | 44 | 37
66 | 1.2.1.6.3.1.1 | Excavation | 30 | 23 January 2024 8:00 AM | 28 February 2024 5:00 PM | 42,61 | 67,71 | 23 January 2024 8:00 AM | 2024-03-01 17:00 | 2 | Plumber | 100 | 61 | 32 | 20 | 2
67 | 1.2.1.6.3.1.2 | Installation of Anchors | 8 | 29 February 2024 8:00 AM | 8 March 2024 5:00 PM | 66 | 68 | 29 February 2024 8:00 AM | 2024-03-08 17:00 | 0 | Site Manager | 100 | 84 | 28 | 71 | 35
68 | 1.2.1.6.3.1.3 | Install Bracing | 4 | 9 March 2024 8:00 AM | 13 March 2024 5:00 PM | 67 | 69 | 9 March 2024 8:00 AM | 2024-03-13 17:00 | 0 | Fire | 100 | 64 | 12 | 34 | 26
69 | 1.2.1.6.3.1.4 | Shotcrete | 6 | 14 March 2024 8:00 AM | 20 March 2024 5:00 PM | 68 | 70,84 | 14 March 2024 8:00 AM | 2024-03-20 17:00 | 0 | Contract Administrator | 100 | 83 | 31 | 66 | 32
70 | 1.2.1.6.3.1.5 | Foundation Piling (Basement 2 Lvl) - (5 Piles) | 2 | 21 March 2024 8:00 AM | 22 March 2024 5:00 PM | 69 | 86 | 21 March 2024 8:00 AM | 2024-03-22 17:00 | 0 | Mechanical | 100 | 46 | 14 | 21 | 20
71 | 1.2.1.6.4 | Complete Bulk Exacavation | 0 | 28 February 2024 5:00 PM | 28 February 2024 5:00 PM | 46,51,56,61,66 |  | 28 February 2024 5:00 PM | 2024-02-28 17:00 | 0 | Admin | 100 | 78 | 19 | 72 | 21
72 | 1.2.1.7 | Detail Excavation, Services & Base course | 61 | 17 February 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | 17 February 2024 8:00 AM | 2024-05-07 17:00 | 5 | Window | 100 | 97 | 11 | 6 | 28
73 | 1.2.1.7.1 | Stage 1 (Building A) | 32 | 17 February 2024 8:00 AM | 25 March 2024 5:00 PM |  |  | 17 February 2024 8:00 AM | 2024-03-29 17:00 | 4 | Concretor | 100 | 46 | 20 | 55 | 55
74 | 1.2.1.7.1.1 | Detailed Excavation | 11 | 17 February 2024 8:00 AM | 29 February 2024 5:00 PM | 63 | 75,79 | 17 February 2024 8:00 AM | 2024-03-02 17:00 | 2 | Formworker | 100 | 63 | 10 | 29 | 2
75 | 1.2.1.7.1.2 | In-Ground Services | 8 | 1 March 2024 8:00 AM | 9 March 2024 5:00 PM | 74 | 76 | 1 March 2024 8:00 AM | 2024-03-12 17:00 | 3 | Plumber | 100 | 63 | 27 | 4 | 44
76 | 1.2.1.7.1.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 11 March 2024 8:00 AM | 15 March 2024 5:00 PM | 75 | 77 | 11 March 2024 8:00 AM | 2024-03-15 17:00 | 0 | Foreman | 100 | 66 | 35 | 9 | 4
77 | 1.2.1.7.1.4 | Base Course to Basement | 8 | 16 March 2024 8:00 AM | 25 March 2024 5:00 PM | 76 | 88 | 16 March 2024 8:00 AM | 2024-03-25 17:00 | 0 | Metal Work | 100 | 99 | 31 | 70 | 35
78 | 1.2.1.7.2 | Stage 2 (Building B) | 32 | 1 March 2024 8:00 AM | 10 April 2024 5:00 PM |  |  | 1 March 2024 8:00 AM | 2024-04-15 17:00 | 5 | Reinforcement Fixer | 100 | 81 | 25 | 57 | 46
79 | 1.2.1.7.2.1 | Detailed Excavation | 12 | 1 March 2024 8:00 AM | 14 March 2024 5:00 PM | 74 | 80 | 1 March 2024 8:00 AM | 2024-03-17 17:00 | 3 | Surveyor | 100 | 75 | 13 | 36 | 59
80 | 1.2.1.7.2.2 | In-Ground Services | 9 | 15 March 2024 8:00 AM | 25 March 2024 5:00 PM | 79 | 81 | 15 March 2024 8:00 AM | 2024-03-27 17:00 | 2 | Surveyor | 100 | 57 | 16 | 68 | 31
81 | 1.2.1.7.2.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 6 | 26 March 2024 8:00 AM | 4 April 2024 5:00 PM | 80 | 82 | 26 March 2024 8:00 AM | 2024-04-05 17:00 | 1 | Metal Work | 100 | 84 | 33 | 87 | 55
82 | 1.2.1.7.2.4 | Base Course to Basement | 5 | 5 April 2024 8:00 AM | 10 April 2024 5:00 PM | 81 | 93 | 5 April 2024 8:00 AM | 2024-04-10 17:00 | 0 | Window | 100 | 74 | 23 | 47 | 26
83 | 1.2.1.7.3 | Stage 3 (Buildings C&D) | 33 | 21 March 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | 21 March 2024 8:00 AM | 2024-05-03 17:00 | 1 | Development Manager | 100 | 58 | 16 | 40 | 18
84 | 1.2.1.7.3.1 | Detailed Excavation | 12 | 21 March 2024 8:00 AM | 6 April 2024 5:00 PM | 69 | 85 | 21 March 2024 8:00 AM | 2024-04-09 17:00 | 3 | Floor Sealer | 100 | 83 | 24 | 55 | 42
85 | 1.2.1.7.3.2 | In-Ground Services | 8 | 8 April 2024 8:00 AM | 16 April 2024 5:00 PM | 84 | 86 | 8 April 2024 8:00 AM | 2024-04-16 17:00 | 0 | Carpenter | 100 | 49 | 29 | 96 | 44
86 | 1.2.1.7.3.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 17 April 2024 8:00 AM | 22 April 2024 5:00 PM | 85,70 | 87 | 17 April 2024 8:00 AM | 2024-04-22 17:00 | 0 | Line Market | 100 | 56 | 21 | 86 | 21
87 | 1.2.1.7.3.4 | Base Course to Basement | 8 | 23 April 2024 8:00 AM | 2 May 2024 5:00 PM | 86 | 88 | 23 April 2024 8:00 AM | 2024-05-04 17:00 | 2 | Painter | 100 | 69 | 24 | 95 | 20
88 | 1.2.1.7.4 | Basement Earthworks and Piling Complete | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 87,77 | 122,4 | 2 May 2024 5:00 PM | 2024-05-02 17:00 | 0 | Concretor | 100 | 33 | 29 | 65 | 33
89 | 1.2.2 | STRUCTURE WORKS | 217 | 11 April 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 11 April 2024 8:00 AM | 2025-01-04 17:00 | 1 | Metal Work | 100 | 93 | 29 | 22 | 38
90 | 1.2.2.1 | CC2 - Basement to Podium L1 - A, B, C, D | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  |  | 11 April 2024 8:00 AM | 2024-10-04 17:00 | 4 | Line Market | 100 | 70 | 28 | 43 | 3
91 | 1.2.2.1.1 | Basement to Podium (Level 1 - A & B ) | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | 11 April 2024 8:00 AM | 2024-10-01 17:00 | 1 | Development Manager | 100 | 91 | 25 | 80 | 35
92 | 1.2.2.1.1.1 | Basement 2 - FRP - SoG | 23 | 11 April 2024 8:00 AM | 8 May 2024 5:00 PM |  |  | 11 April 2024 8:00 AM | 2024-05-11 17:00 | 3 | Cleaner | 100 | 34 | 10 | 40 | 32
93 | 1.2.2.1.1.1.1 | Reinforcement Fix | 13 | 11 April 2024 8:00 AM | 26 April 2024 5:00 PM | 82 | 94 | 11 April 2024 8:00 AM | 2024-04-27 17:00 | 1 | Plumber | 100 | 37 | 26 | 87 | 37
94 | 1.2.2.1.1.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 9 | 27 April 2024 8:00 AM | 7 May 2024 5:00 PM | 93 | 95 | 27 April 2024 8:00 AM | 2024-05-07 17:00 | 0 | Stone Mason | 100 | 60 | 20 | 3 | 24
95 | 1.2.2.1.1.1.3 | Pour | 1 | 8 May 2024 8:00 AM | 8 May 2024 5:00 PM | 94 | 97 | 8 May 2024 8:00 AM | 2024-05-08 17:00 | 0 | Landscaper | 100 | 98 | 22 | 82 | 45
96 | 1.2.2.1.1.2 | Basement 1 - FRP - Suspended Slab | 25 | 9 May 2024 8:00 AM | 6 June 2024 5:00 PM |  |  | 9 May 2024 8:00 AM | 2024-06-07 17:00 | 1 | Hoarding | 100 | 75 | 17 | 82 | 59
97 | 1.2.2.1.1.2.1 | Scaffold Stair Removal/Adjustment | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 95 | 98SS | 9 May 2024 8:00 AM | 2024-05-10 17:00 | 0 | Subcontractor | 100 | 51 | 34 | 11 | 7
98 | 1.2.2.1.1.2.2 | Setout and Install Lift/Stair Formwork | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 97SS | 99 | 9 May 2024 8:00 AM | 2024-05-10 17:00 | 0 | Plasterboarder | 100 | 96 | 21 | 14 | 41
99 | 1.2.2.1.1.2.3 | Formworker setout, drop material and 80% Deck | 9 | 11 May 2024 8:00 AM | 21 May 2024 5:00 PM | 98 | 100FS-1d,101 | 11 May 2024 8:00 AM | 2024-05-21 17:00 | 0 | Formworker | 100 | 12 | 19 | 62 | 33
100 | 1.2.2.1.1.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 21 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99FS-1d | 102,103 | 21 May 2024 8:00 AM | 2024-05-24 17:00 | 0 | Plumber | 100 | 10 | 19 | 40 | 37
101 | 1.2.2.1.1.2.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 22 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99 |  | 22 May 2024 8:00 AM | 2024-05-24 17:00 | 0 | Painter | 100 | 61 | 13 | 13 | 59
102 | 1.2.2.1.1.2.6 | Services | 4 | 25 May 2024 8:00 AM | 29 May 2024 5:00 PM | 100 | 104FS-1d | 25 May 2024 8:00 AM | 2024-05-29 17:00 | 0 | Reinforcement Fixer | 100 | 88 | 28 | 69 | 29
103 | 1.2.2.1.1.2.7 | Post Tension | 3 | 25 May 2024 8:00 AM | 28 May 2024 5:00 PM | 100 | 104FS-1d | 25 May 2024 8:00 AM | 2024-05-28 17:00 | 0 | Plasterboarder | 100 | 79 | 33 | 69 | 19
104 | 1.2.2.1.1.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 29 May 2024 8:00 AM | 31 May 2024 5:00 PM | 102FS-1d,103FS-1d | 105 | 29 May 2024 8:00 AM | 2024-05-31 17:00 | 0 | Admin | 100 | 45 | 32 | 46 | 47
105 | 1.2.2.1.1.2.9 | Formworker setdowns and edge boards | 4 | 1 June 2024 8:00 AM | 5 June 2024 5:00 PM | 104 | 106 | 1 June 2024 8:00 AM | 2024-06-05 17:00 | 0 | Window | 100 | 27 | 12 | 89 | 21
106 | 1.2.2.1.1.2.10 | Pour | 1 | 6 June 2024 8:00 AM | 6 June 2024 5:00 PM | 105 | 109 | 6 June 2024 8:00 AM | 2024-06-06 17:00 | 0 | Mechanical | 100 | 99 | 23 | 73 | 48
107 | 1.2.2.1.1.3 | Strip Formwork - Basement 1 | 5 | 7 September 2024 8:00 AM | 12 September 2024 5:00 PM | 161FS+5d | 522 | 7 September 2024 8:00 AM | 2024-09-12 17:00 | 0 | Contract Administrator | 100 | 99 | 26 | 5 | 2
108 | 1.2.2.1.1.4 | Lvl 1 - FRP - Suspended Slab | 28 | 7 June 2024 8:00 AM | 11 July 2024 5:00 PM |  |  | 7 June 2024 8:00 AM | 2024-07-14 17:00 | 3 | Plasterboarder | 100 | 26 | 32 | 4 | 10
109 | 1.2.2.1.1.4.1 | Scaffold Stair Removal/Adjustment | 1 | 7 June 2024 8:00 AM | 7 June 2024 5:00 PM | 106 | 110SS | 7 June 2024 8:00 AM | 2024-06-07 17:00 | 0 | Surveyor | 100 | 68 | 27 | 6 | 52
110 | 1.2.2.1.1.4.2 | Setout and Install Lift/Stair Formwork | 3 | 7 June 2024 8:00 AM | 12 June 2024 5:00 PM | 109SS | 111 | 7 June 2024 8:00 AM | 2024-06-12 17:00 | 0 | Metal Work | 100 | 36 | 18 | 80 | 49
111 | 1.2.2.1.1.4.3 | Formworker setout, drop material and 80% Deck | 10 | 13 June 2024 8:00 AM | 24 June 2024 5:00 PM | 110 | 112FS-1d,113,128 | 13 June 2024 8:00 AM | 2024-06-24 17:00 | 0 | Project Manager | 100 | 24 | 10 | 65 | 53
112 | 1.2.2.1.1.4.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 6 | 24 June 2024 8:00 AM | 29 June 2024 5:00 PM | 111FS-1d | 114,115 | 24 June 2024 8:00 AM | 2024-06-29 17:00 | 0 | Renderer | 100 | 24 | 12 | 4 | 18
113 | 1.2.2.1.1.4.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 25 June 2024 8:00 AM | 28 June 2024 5:00 PM | 111 | 118 | 25 June 2024 8:00 AM | 2024-06-28 17:00 | 0 | Tiler | 100 | 77 | 13 | 3 | 4
114 | 1.2.2.1.1.4.6 | Services | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 112 | 116FS-1d | 1 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Carpet | 100 | 45 | 11 | 23 | 33
115 | 1.2.2.1.1.4.7 | Post Tension | 4 | 1 July 2024 8:00 AM | 4 July 2024 5:00 PM | 112 | 116FS-1d | 1 July 2024 8:00 AM | 2024-07-04 17:00 | 0 | Reinforcement Fixer | 100 | 69 | 14 | 14 | 45
116 | 1.2.2.1.1.4.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 114FS-1d,115FS-1d | 117,401FS+5d | 4 July 2024 8:00 AM | 2024-07-06 17:00 | 0 | Carpet | 100 | 54 | 32 | 56 | 47
117 | 1.2.2.1.1.4.9 | Formworker setdowns and edge boards | 3 | 8 July 2024 8:00 AM | 10 July 2024 5:00 PM | 116 | 118 | 8 July 2024 8:00 AM | 2024-07-10 17:00 | 0 | Carpenter | 100 | 47 | 27 | 60 | 5
118 | 1.2.2.1.1.4.10 | Pour | 1 | 11 July 2024 8:00 AM | 11 July 2024 5:00 PM | 117,113 | 140 | 11 July 2024 8:00 AM | 2024-07-11 17:00 | 0 | Carpet | 100 | 52 | 13 | 56 | 16
119 | 1.2.2.1.1.5 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d | 535 | 25 September 2024 8:00 AM | 2024-09-30 17:00 | 0 | Painter | 100 | 99 | 22 | 40 | 25
120 | 1.2.2.1.2 | Basement to Podium (Level 1 - C & D) | 127 | 3 May 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | 3 May 2024 8:00 AM | 2024-10-03 17:00 | 3 | Concretor | 100 | 80 | 34 | 63 | 14
121 | 1.2.2.1.2.1 | Basement 2 - FRP - SoG | 12 | 3 May 2024 8:00 AM | 16 May 2024 5:00 PM |  |  | 3 May 2024 8:00 AM | 2024-05-19 17:00 | 3 | Subcontractor | 100 | 28 | 23 | 64 | 48
122 | 1.2.2.1.2.1.1 | Reinforcement Fix | 6 | 3 May 2024 8:00 AM | 9 May 2024 5:00 PM | 88 | 123 | 3 May 2024 8:00 AM | 2024-05-09 17:00 | 0 | Cleaner | 100 | 44 | 26 | 11 | 5
123 | 1.2.2.1.2.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 5 | 10 May 2024 8:00 AM | 15 May 2024 5:00 PM | 122 | 124 | 10 May 2024 8:00 AM | 2024-05-15 17:00 | 0 | Line Market | 100 | 53 | 21 | 24 | 48
124 | 1.2.2.1.2.1.3 | Pour | 1 | 16 May 2024 8:00 AM | 16 May 2024 5:00 PM | 123 | 126 | 16 May 2024 8:00 AM | 2024-05-16 17:00 | 0 | Stone Mason | 100 | 39 | 27 | 43 | 48
125 | 1.2.2.1.2.2 | Lvl 1 - FRP - Suspended Slab | 48 | 17 May 2024 8:00 AM | 13 July 2024 5:00 PM |  |  | 17 May 2024 8:00 AM | 2024-07-13 17:00 | 0 | Plasterboarder | 100 | 18 | 25 | 20 | 29
126 | 1.2.2.1.2.2.1 | Scaffold Stair Removal/Adjustment | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 124 | 127SS | 17 May 2024 8:00 AM | 2024-05-17 17:00 | 0 | Foreman | 100 | 82 | 25 | 6 | 25
127 | 1.2.2.1.2.2.2 | Setout and Install Lift/Stair Formwork | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 126SS | 128 | 17 May 2024 8:00 AM | 2024-05-17 17:00 | 0 | Plasterboarder | 100 | 82 | 10 | 14 | 31
128 | 1.2.2.1.2.2.3 | Formworker setout, drop material and 80% Deck | 6 | 25 June 2024 8:00 AM | 1 July 2024 5:00 PM | 127,111 | 129FS-1d,130 | 25 June 2024 8:00 AM | 2024-07-01 17:00 | 0 | Electrician | 100 | 13 | 32 | 94 | 17
129 | 1.2.2.1.2.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128FS-1d | 131,132 | 1 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Project Manager | 100 | 63 | 18 | 49 | 36
130 | 1.2.2.1.2.2.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128 |  | 2 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Waterproofer | 100 | 37 | 23 | 9 | 37
131 | 1.2.2.1.2.2.6 | Services | 2 | 4 July 2024 8:00 AM | 5 July 2024 5:00 PM | 129 | 133FS-1d | 4 July 2024 8:00 AM | 2024-07-05 17:00 | 0 | Window | 100 | 26 | 32 | 43 | 18
132 | 1.2.2.1.2.2.7 | Post Tension | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 129 | 133FS-1d | 4 July 2024 8:00 AM | 2024-07-06 17:00 | 0 | Line Market | 100 | 31 | 29 | 60 | 39
133 | 1.2.2.1.2.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 6 July 2024 8:00 AM | 9 July 2024 5:00 PM | 131FS-1d,132FS-1d | 134 | 6 July 2024 8:00 AM | 2024-07-09 17:00 | 0 | Line Market | 100 | 24 | 13 | 97 | 51
134 | 1.2.2.1.2.2.9 | Formworker setdowns and edge boards | 3 | 10 July 2024 8:00 AM | 12 July 2024 5:00 PM | 133 | 135 | 10 July 2024 8:00 AM | 2024-07-12 17:00 | 0 | Concretor | 100 | 76 | 31 | 78 | 40
135 | 1.2.2.1.2.2.10 | Pour | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 134 | 309,233 | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Cleaner | 100 | 60 | 25 | 97 | 51
136 | 1.2.2.1.2.3 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d |  | 25 September 2024 8:00 AM | 2024-09-30 17:00 | 0 | Mechanical | 100 | 87 | 20 | 70 | 35
137 | 1.2.2.2 | CC3 - Remainder of Structure | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 12 July 2024 8:00 AM | 2025-01-06 17:00 | 3 | Head Contractor | 100 | 11 | 12 | 74 | 43
138 | 1.2.2.2.1 | Building A | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | 12 July 2024 8:00 AM | 2025-01-07 17:00 | 4 | Landscaper | 100 | 73 | 35 | 83 | 56
139 | 1.2.2.2.1.1 | Lvl 2 - FRP - Suspended Slab | 26 | 12 July 2024 8:00 AM | 10 August 2024 5:00 PM |  |  | 12 July 2024 8:00 AM | 2024-08-14 17:00 | 4 | Reinforcement Fixer | 100 | 12 | 14 | 16 | 47
140 | 1.2.2.2.1.1.1 | Scaffold Perimeter Protection | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 118 | 141SS | 12 July 2024 8:00 AM | 2024-07-16 17:00 | 0 | Tiler | 100 | 71 | 20 | 3 | 30
141 | 1.2.2.2.1.1.2 | Setout and Install Lift/Stair Formwork | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 140SS | 142 | 12 July 2024 8:00 AM | 2024-07-16 17:00 | 0 | Reinforcement Fixer | 100 | 14 | 28 | 59 | 28
142 | 1.2.2.2.1.1.3 | Formworker setout, drop material and 80% Deck | 6 | 17 July 2024 8:00 AM | 23 July 2024 5:00 PM | 141 | 143FS-1d,144 | 17 July 2024 8:00 AM | 2024-07-23 17:00 | 0 | Painter | 100 | 95 | 28 | 48 | 32
143 | 1.2.2.2.1.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 23 July 2024 8:00 AM | 26 July 2024 5:00 PM | 142FS-1d | 145,146 | 23 July 2024 8:00 AM | 2024-07-26 17:00 | 0 | Window | 100 | 44 | 17 | 30 | 18
144 | 1.2.2.2.1.1.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 24 July 2024 8:00 AM | 27 July 2024 5:00 PM | 142 | 146 | 24 July 2024 8:00 AM | 2024-07-27 17:00 | 0 | Post Tension | 100 | 33 | 15 | 46 | 15
145 | 1.2.2.2.1.1.6 | Services | 3 | 27 July 2024 8:00 AM | 30 July 2024 5:00 PM | 143 | 147FS-1d | 27 July 2024 8:00 AM | 2024-07-30 17:00 | 0 | Painter | 100 | 53 | 18 | 21 | 10
146 | 1.2.2.2.1.1.7 | Post Tension | 3 | 29 July 2024 8:00 AM | 31 July 2024 5:00 PM | 143,144 | 147FS-1d | 29 July 2024 8:00 AM | 2024-07-31 17:00 | 0 | Window | 100 | 84 | 29 | 22 | 37
147 | 1.2.2.2.1.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 5 | 31 July 2024 8:00 AM | 5 August 2024 5:00 PM | 145FS-1d,146FS-1d | 148 | 31 July 2024 8:00 AM | 2024-08-05 17:00 | 0 | Foreman | 100 | 72 | 23 | 63 | 47
148 | 1.2.2.2.1.1.9 | Formworker setdowns and edge boards | 4 | 6 August 2024 8:00 AM | 9 August 2024 5:00 PM | 147 | 149 | 6 August 2024 8:00 AM | 2024-08-09 17:00 | 0 | Excavation | 100 | 16 | 12 | 86 | 43
149 | 1.2.2.2.1.1.10 | Pour | 1 | 10 August 2024 8:00 AM | 10 August 2024 5:00 PM | 148 | 152,407FS+5d | 10 August 2024 8:00 AM | 2024-08-10 17:00 | 0 | Fire | 100 | 26 | 31 | 7 | 44
150 | 1.2.2.2.1.2 | Strip Formwork - Lvl 2 | 5 | 15 October 2024 8:00 AM | 19 October 2024 5:00 PM | 185FS+5d | 577,550,409FS-10d | 15 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Window | 100 | 21 | 32 | 33 | 50
151 | 1.2.2.2.1.3 | Lvl 3 - FRP - Suspended Slab | 18 | 12 August 2024 8:00 AM | 31 August 2024 5:00 PM |  |  | 12 August 2024 8:00 AM | 2024-09-03 17:00 | 3 | Hoarding | 100 | 54 | 21 | 84 | 43
152 | 1.2.2.2.1.3.1 | Scaffold Perimeter Protection | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 149 | 153SS | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 0 | Project Manager | 100 | 73 | 26 | 14 | 53
153 | 1.2.2.2.1.3.2 | Setout and Install Lift/Stair Formwork | 1 | 12 August 2024 8:00 AM | 12 August 2024 5:00 PM | 152SS | 154 | 12 August 2024 8:00 AM | 2024-08-12 17:00 | 0 | Waterproofer | 100 | 58 | 15 | 65 | 49
154 | 1.2.2.2.1.3.3 | Formworker setout, drop material and 80% Deck | 6 | 13 August 2024 8:00 AM | 19 August 2024 5:00 PM | 153 | 155FS-1d,156 | 13 August 2024 8:00 AM | 2024-08-19 17:00 | 0 | Formworker | 100 | 67 | 27 | 20 | 11
155 | 1.2.2.2.1.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 19 August 2024 8:00 AM | 22 August 2024 5:00 PM | 154FS-1d | 157,158 | 19 August 2024 8:00 AM | 2024-08-22 17:00 | 0 | Tiler | 100 | 53 | 28 | 80 | 13
156 | 1.2.2.2.1.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 August 2024 8:00 AM | 21 August 2024 5:00 PM | 154 |  | 20 August 2024 8:00 AM | 2024-08-21 17:00 | 0 | Hoarding | 100 | 21 | 13 | 70 | 55
157 | 1.2.2.2.1.3.6 | Services | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | 23 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Mechanical | 100 | 92 | 26 | 26 | 24
158 | 1.2.2.2.1.3.7 | Post Tension | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | 23 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Development Manager | 100 | 15 | 22 | 3 | 14
159 | 1.2.2.2.1.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 24 August 2024 8:00 AM | 27 August 2024 5:00 PM | 157FS-1d,158FS-1d | 160 | 24 August 2024 8:00 AM | 2024-08-27 17:00 | 0 | Cleaner | 100 | 66 | 20 | 3 | 40
160 | 1.2.2.2.1.3.9 | Formworker setdowns and edge boards | 3 | 28 August 2024 8:00 AM | 30 August 2024 5:00 PM | 159 | 161 | 28 August 2024 8:00 AM | 2024-08-30 17:00 | 0 | Electrician | 100 | 93 | 10 | 18 | 18
161 | 1.2.2.2.1.3.10 | Pour | 1 | 31 August 2024 8:00 AM | 31 August 2024 5:00 PM | 160 | 164,3445,107FS+5d | 31 August 2024 8:00 AM | 2024-08-31 17:00 | 0 | Floor Sealer | 100 | 31 | 34 | 93 | 35
162 | 1.2.2.2.1.4 | Strip Formwork - Lvl 3 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d |  | 19 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Timber Floorer | 100 | 39 | 21 | 97 | 12
163 | 1.2.2.2.1.5 | Lvl 4 - FRP - Suspended Slab | 15 | 2 September 2024 8:00 AM | 18 September 2024 5:00 PM |  |  | 2 September 2024 8:00 AM | 2024-09-19 17:00 | 1 | Window | 100 | 68 | 18 | 31 | 45
164 | 1.2.2.2.1.5.1 | Scaffold Perimeter Protection | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 161 | 165SS | 2 September 2024 8:00 AM | 2024-09-02 17:00 | 0 | Joiner | 100 | 10 | 20 | 38 | 32
165 | 1.2.2.2.1.5.2 | Setout and Install Lift/Stair Formwork | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 164SS | 166FS-1d | 2 September 2024 8:00 AM | 2024-09-02 17:00 | 0 | Foreman | 100 | 66 | 15 | 38 | 18
166 | 1.2.2.2.1.5.3 | Formworker setout, drop material and 80% Deck | 6 | 2 September 2024 8:00 AM | 7 September 2024 5:00 PM | 165FS-1d | 167FS-1d,168 | 2 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Head Contractor | 100 | 58 | 28 | 78 | 49
167 | 1.2.2.2.1.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 7 September 2024 8:00 AM | 11 September 2024 5:00 PM | 166FS-1d | 169,170 | 7 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Landscaper | 100 | 76 | 13 | 63 | 35
168 | 1.2.2.2.1.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 9 September 2024 8:00 AM | 10 September 2024 5:00 PM | 166 |  | 9 September 2024 8:00 AM | 2024-09-10 17:00 | 0 | Timber Floorer | 100 | 98 | 12 | 53 | 38
169 | 1.2.2.2.1.5.6 | Services | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | 12 September 2024 8:00 AM | 2024-09-13 17:00 | 0 | Surveyor | 100 | 17 | 11 | 21 | 54
170 | 1.2.2.2.1.5.7 | Post Tension | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | 12 September 2024 8:00 AM | 2024-09-13 17:00 | 0 | Reinforcement Fixer | 100 | 25 | 20 | 49 | 38
171 | 1.2.2.2.1.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 13 September 2024 8:00 AM | 14 September 2024 5:00 PM | 169FS-1d,170FS-1d | 172 | 13 September 2024 8:00 AM | 2024-09-14 17:00 | 0 | Fire | 100 | 35 | 30 | 29 | 49
172 | 1.2.2.2.1.5.9 | Formworker setdowns and edge boards | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 171 | 173 | 16 September 2024 8:00 AM | 2024-09-17 17:00 | 0 | Floor Sealer | 100 | 27 | 30 | 28 | 15
173 | 1.2.2.2.1.5.10 | Pour | 1 | 18 September 2024 8:00 AM | 18 September 2024 5:00 PM | 172 | 176,119FS+5d,136FS+5d | 18 September 2024 8:00 AM | 2024-09-18 17:00 | 0 | Surveyor | 100 | 57 | 28 | 17 | 22
174 | 1.2.2.2.1.6 | Strip Formwork - Lvl 4 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d | 413FS+5d,604,415FS-10d | 19 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Window | 100 | 35 | 12 | 75 | 30
175 | 1.2.2.2.1.7 | Lvl 5 - FRP - Suspended Slab | 15 | 19 September 2024 8:00 AM | 8 October 2024 5:00 PM |  |  | 19 September 2024 8:00 AM | 2024-10-11 17:00 | 3 | Site Manager | 100 | 26 | 15 | 40 | 9
176 | 1.2.2.2.1.7.1 | Scaffold Perimeter Protection | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 173 | 177SS | 19 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Joiner | 100 | 73 | 35 | 64 | 7
177 | 1.2.2.2.1.7.2 | Setout and Install Lift/Stair Formwork | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 176SS | 178FS-1d | 19 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Tiler | 100 | 57 | 35 | 77 | 60
178 | 1.2.2.2.1.7.3 | Formworker setout, drop material and 80% Deck | 6 | 19 September 2024 8:00 AM | 25 September 2024 5:00 PM | 177FS-1d | 179FS-1d,180 | 19 September 2024 8:00 AM | 2024-09-25 17:00 | 0 | Post Tension | 100 | 69 | 28 | 4 | 37
179 | 1.2.2.2.1.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 25 September 2024 8:00 AM | 28 September 2024 5:00 PM | 178FS-1d | 181,182 | 25 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Tiler | 100 | 82 | 23 | 80 | 49
180 | 1.2.2.2.1.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 26 September 2024 8:00 AM | 27 September 2024 5:00 PM | 178 |  | 26 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Floor Sealer | 100 | 20 | 20 | 13 | 34
181 | 1.2.2.2.1.7.6 | Services | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | 30 September 2024 8:00 AM | 2024-10-01 17:00 | 0 | Landscaper | 100 | 68 | 32 | 14 | 18
182 | 1.2.2.2.1.7.7 | Post Tension | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | 30 September 2024 8:00 AM | 2024-10-01 17:00 | 0 | Electrician | 100 | 47 | 25 | 79 | 6
183 | 1.2.2.2.1.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 1 October 2024 8:00 AM | 2 October 2024 5:00 PM | 181FS-1d,182FS-1d | 184 | 1 October 2024 8:00 AM | 2024-10-02 17:00 | 0 | Painter | 100 | 57 | 35 | 71 | 3
184 | 1.2.2.2.1.7.9 | Formworker setdowns and edge boards | 2 | 3 October 2024 8:00 AM | 4 October 2024 5:00 PM | 183 | 185 | 3 October 2024 8:00 AM | 2024-10-04 17:00 | 0 | Concretor | 100 | 44 | 21 | 46 | 43
185 | 1.2.2.2.1.7.10 | Pour | 1 | 8 October 2024 8:00 AM | 8 October 2024 5:00 PM | 184 | 188,150FS+5d | 8 October 2024 8:00 AM | 2024-10-08 17:00 | 0 | Subcontractor | 100 | 40 | 28 | 7 | 21
186 | 1.2.2.2.1.8 | Strip Formwork - Lvl 5 | 5 | 5 December 2024 8:00 AM | 10 December 2024 5:00 PM | 221FS+5d | 631,421FS-10d,419FS+5d | 5 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Carpet | 100 | 89 | 33 | 25 | 12
187 | 1.2.2.2.1.9 | Lvl 6 - FRP - Suspended Slab | 15 | 9 October 2024 8:00 AM | 25 October 2024 5:00 PM |  |  | 9 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Carpet | 100 | 76 | 24 | 22 | 41
188 | 1.2.2.2.1.9.1 | Scaffold Perimeter Protection | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 185 | 189SS | 9 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Contract Administrator | 100 | 80 | 11 | 28 | 60
189 | 1.2.2.2.1.9.2 | Setout and Install Lift/Stair Formwork | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 188SS | 190FS-1d | 9 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Mechanical | 100 | 34 | 19 | 68 | 34
190 | 1.2.2.2.1.9.3 | Formworker setout, drop material and 80% Deck | 6 | 9 October 2024 8:00 AM | 15 October 2024 5:00 PM | 189FS-1d | 191FS-1d,192 | 9 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Concretor | 100 | 84 | 24 | 74 | 20
191 | 1.2.2.2.1.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 October 2024 8:00 AM | 18 October 2024 5:00 PM | 190FS-1d | 193,194 | 15 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Carpenter | 100 | 24 | 23 | 15 | 58
192 | 1.2.2.2.1.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 190 |  | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Waterproofer | 100 | 80 | 33 | 92 | 10
193 | 1.2.2.2.1.9.6 | Services | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Floor Sealer | 100 | 62 | 13 | 93 | 12
194 | 1.2.2.2.1.9.7 | Post Tension | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Landscaper | 100 | 10 | 13 | 44 | 45
195 | 1.2.2.2.1.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 193FS-1d,194FS-1d | 196 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Contract Administrator | 100 | 62 | 20 | 76 | 15
196 | 1.2.2.2.1.9.9 | Formworker setdowns and edge boards | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 195 | 197 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Reinforcement Fixer | 100 | 79 | 25 | 61 | 55
197 | 1.2.2.2.1.9.10 | Pour | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 196 | 200 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Electrician | 100 | 11 | 23 | 50 | 58
198 | 1.2.2.2.1.10 | Strip Formwork - Lvl 6 | 5 | 6 December 2024 8:00 AM | 11 December 2024 5:00 PM | 225 | 657,425FS+5d,427FS-10d | 6 December 2024 8:00 AM | 2024-12-11 17:00 | 0 | Hoarding | 100 | 71 | 25 | 70 | 38
199 | 1.2.2.2.1.11 | Lvl 7 - FRP - Suspended Slab | 15 | 26 October 2024 8:00 AM | 12 November 2024 5:00 PM |  |  | 26 October 2024 8:00 AM | 2024-11-16 17:00 | 4 | Subcontractor | 100 | 19 | 30 | 10 | 19
200 | 1.2.2.2.1.11.1 | Scaffold Perimeter Protection | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 197 | 201SS | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Metal Work | 100 | 36 | 21 | 71 | 55
201 | 1.2.2.2.1.11.2 | Setout and Install Lift/Stair Formwork | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 200SS | 202FS-1d | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Concretor | 100 | 62 | 30 | 36 | 14
202 | 1.2.2.2.1.11.3 | Formworker setout, drop material and 80% Deck | 6 | 26 October 2024 8:00 AM | 1 November 2024 5:00 PM | 201FS-1d | 203FS-1d,204 | 26 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Concretor | 100 | 93 | 27 | 83 | 45
203 | 1.2.2.2.1.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 1 November 2024 8:00 AM | 5 November 2024 5:00 PM | 202FS-1d | 205,206 | 1 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Project Manager | 100 | 20 | 35 | 85 | 35
204 | 1.2.2.2.1.11.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 202 |  | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Painter | 100 | 59 | 20 | 40 | 17
205 | 1.2.2.2.1.11.6 | Services | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Plasterboarder | 100 | 67 | 31 | 58 | 14
206 | 1.2.2.2.1.11.7 | Post Tension | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Admin | 100 | 58 | 31 | 82 | 23
207 | 1.2.2.2.1.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 205FS-1d,206FS-1d | 208 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Excavation | 100 | 100 | 17 | 22 | 16
208 | 1.2.2.2.1.11.9 | Formworker setdowns and edge boards | 2 | 9 November 2024 8:00 AM | 11 November 2024 5:00 PM | 207 | 209 | 9 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Subcontractor | 100 | 11 | 14 | 24 | 9
209 | 1.2.2.2.1.11.10 | Pour | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 208 | 212,162FS+5d,174FS+5d,431FS+5d | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Carpenter | 100 | 31 | 22 | 62 | 46
210 | 1.2.2.2.1.12 | Strip Formwork - Lvl 7 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 225FS+5d | 690,432FS-10d | 12 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Concretor | 100 | 70 | 20 | 35 | 15
211 | 1.2.2.2.1.13 | Lvl 8 (Roof) - FRP - Suspended Slab | 14 | 13 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | 13 November 2024 8:00 AM | 2024-12-01 17:00 | 3 | Formworker | 100 | 56 | 10 | 95 | 37
212 | 1.2.2.2.1.13.1 | Scaffold Perimeter Protection | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 209 | 213SS | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Electrician | 100 | 10 | 17 | 73 | 54
213 | 1.2.2.2.1.13.2 | Setout and Install Lift/Stair Formwork | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 212SS | 214FS-1d | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Joiner | 100 | 50 | 21 | 64 | 35
214 | 1.2.2.2.1.13.3 | Formworker setout, drop material and 80% Deck | 6 | 13 November 2024 8:00 AM | 19 November 2024 5:00 PM | 213FS-1d | 215FS-1d,216 | 13 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Cleaner | 100 | 85 | 11 | 3 | 54
215 | 1.2.2.2.1.13.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214FS-1d | 217,218 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Timber Floorer | 100 | 10 | 22 | 18 | 31
216 | 1.2.2.2.1.13.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214 |  | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Mechanical | 100 | 47 | 25 | 6 | 48
217 | 1.2.2.2.1.13.6 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Contract Administrator | 100 | 90 | 13 | 59 | 43
218 | 1.2.2.2.1.13.7 | Post Tension | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Stone Mason | 100 | 87 | 12 | 15 | 58
219 | 1.2.2.2.1.13.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 217FS-1d,218FS-1d | 220 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Surveyor | 100 | 68 | 28 | 31 | 3
220 | 1.2.2.2.1.13.9 | Formworker setdowns and edge boards | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 219 | 221 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Renderer | 100 | 36 | 10 | 44 | 53
221 | 1.2.2.2.1.13.10 | Pour - Structure Top Out | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 220 | 223FS+12d,222,225,186FS+5d,437FS+5d | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Admin | 100 | 50 | 23 | 37 | 5
222 | 1.2.2.2.1.13.11 | Structure Top Out | 0 | 28 November 2024 5:00 PM | 28 November 2024 5:00 PM | 221 |  | 28 November 2024 5:00 PM | 2024-11-28 17:00 | 0 | Head Contractor | 100 | 92 | 22 | 2 | 16
223 | 1.2.2.2.1.14 | Strip Formwork - Lvl 8 | 4 | 13 December 2024 8:00 AM | 17 December 2024 5:00 PM | 221FS+12d | 716,439FS+10d | 13 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Development Manager | 100 | 46 | 11 | 45 | 57
224 | 1.2.2.2.1.15 | Lift Shaft | 23 | 29 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 29 November 2024 8:00 AM | 2025-01-08 17:00 | 5 | Plasterboarder | 100 | 69 | 14 | 89 | 28
225 | 1.2.2.2.1.15.1 | FRP Lift Over-run | 6 | 29 November 2024 8:00 AM | 5 December 2024 5:00 PM | 221 | 226FS+5d,228,198,210FS+5d | 29 November 2024 8:00 AM | 2024-12-08 17:00 | 3 | Cleaner | 100 | 88 | 16 | 77 | 14
226 | 1.2.2.2.1.15.2 | Strip Lift Shaft Formwork | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 225FS+5d | 227 | 12 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Contract Administrator | 100 | 31 | 32 | 89 | 37
227 | 1.2.2.2.1.15.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 17 December 2024 8:00 AM | 3 January 2025 5:00 PM | 226 | 3451 | 17 December 2024 8:00 AM | 2025-01-05 17:00 | 2 | Timber Floorer | 100 | 84 | 21 | 61 | 25
228 | 1.2.2.2.1.15.4 | Building A Structure Complete | 0 | 5 December 2024 5:00 PM | 5 December 2024 5:00 PM | 225 | 6 | 5 December 2024 5:00 PM | 2024-12-05 17:00 | 0 | Reinforcement Fixer | 100 | 25 | 33 | 88 | 26
229 | 1.2.2.2.2 | Building B | 119 | 13 July 2024 8:00 AM | 30 November 2024 5:00 PM |  | 397 | 13 July 2024 8:00 AM | 2024-11-30 17:00 | 0 | Head Contractor | 100 | 77 | 13 | 22 | 10
230 | 1.2.2.2.2.1 | Lvl 2 - FRP - Suspended Slab | 18 | 13 July 2024 8:00 AM | 2 August 2024 5:00 PM |  |  | 13 July 2024 8:00 AM | 2024-08-02 17:00 | 0 | Plumber | 100 | 87 | 16 | 16 | 19
231 | 1.2.2.2.2.1.1 | Scaffold Perimeter Protection | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 232SS |  | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Window | 100 | 85 | 14 | 22 | 16
232 | 1.2.2.2.2.1.2 | Setout and Install Lift/Stair Formwork | 1 | 13 July 2024 8:00 AM | 15 July 2024 8:00 AM | 233SF | 231SS | 13 July 2024 8:00 AM | 2024-07-15 08:00 | 0 | Plumber | 100 | 42 | 23 | 34 | 45
233 | 1.2.2.2.2.1.3 | Formworker setout, drop material and 80% Deck | 6 | 15 July 2024 8:00 AM | 20 July 2024 5:00 PM | 135 | 234FS-1d,235,232SF | 15 July 2024 8:00 AM | 2024-07-20 17:00 | 0 | Joiner | 100 | 74 | 21 | 8 | 18
234 | 1.2.2.2.2.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 20 July 2024 8:00 AM | 24 July 2024 5:00 PM | 233FS-1d | 236,237 | 20 July 2024 8:00 AM | 2024-07-24 17:00 | 0 | Subcontractor | 100 | 14 | 23 | 99 | 27
235 | 1.2.2.2.2.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 22 July 2024 8:00 AM | 23 July 2024 5:00 PM | 233 |  | 22 July 2024 8:00 AM | 2024-07-23 17:00 | 0 | Floor Sealer | 100 | 86 | 32 | 8 | 43
236 | 1.2.2.2.2.1.6 | Services | 2 | 25 July 2024 8:00 AM | 26 July 2024 5:00 PM | 234 | 238FS-1d | 25 July 2024 8:00 AM | 2024-07-26 17:00 | 0 | Excavation | 100 | 81 | 28 | 46 | 3
237 | 1.2.2.2.2.1.7 | Post Tension | 3 | 25 July 2024 8:00 AM | 27 July 2024 5:00 PM | 234 | 238FS-1d | 25 July 2024 8:00 AM | 2024-07-27 17:00 | 0 | Floor Sealer | 100 | 16 | 12 | 9 | 57
238 | 1.2.2.2.2.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 27 July 2024 8:00 AM | 29 July 2024 5:00 PM | 236FS-1d,237FS-1d | 239 | 27 July 2024 8:00 AM | 2024-07-29 17:00 | 0 | Plumber | 100 | 18 | 35 | 80 | 35
239 | 1.2.2.2.2.1.9 | Formworker setdowns and edge boards | 3 | 30 July 2024 8:00 AM | 1 August 2024 5:00 PM | 238 | 240 | 30 July 2024 8:00 AM | 2024-08-01 17:00 | 0 | Hoarding | 100 | 71 | 33 | 37 | 2
240 | 1.2.2.2.2.1.10 | Pour | 1 | 2 August 2024 8:00 AM | 2 August 2024 5:00 PM | 239 | 243,309FS+30d | 2 August 2024 8:00 AM | 2024-08-02 17:00 | 0 | Hoarding | 100 | 51 | 13 | 53 | 60
241 | 1.2.2.2.2.2 | Strip Formwork - Lvl 2 | 5 | 28 September 2024 8:00 AM | 3 October 2024 5:00 PM | 276 | 447 | 28 September 2024 8:00 AM | 2024-10-03 17:00 | 0 | Excavation | 100 | 46 | 22 | 79 | 17
242 | 1.2.2.2.2.3 | Lvl 3 - FRP - Suspended Slab | 18 | 3 August 2024 8:00 AM | 23 August 2024 5:00 PM |  |  | 3 August 2024 8:00 AM | 2024-08-24 17:00 | 1 | Head Contractor | 100 | 29 | 17 | 51 | 21
243 | 1.2.2.2.2.3.1 | Scaffold Perimeter Protection | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 240 | 244SS | 3 August 2024 8:00 AM | 2024-08-03 17:00 | 0 | Concretor | 100 | 80 | 10 | 4 | 48
244 | 1.2.2.2.2.3.2 | Setout and Install Lift/Stair Formwork | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 243SS | 245 | 3 August 2024 8:00 AM | 2024-08-03 17:00 | 0 | Surveyor | 100 | 66 | 32 | 67 | 54
245 | 1.2.2.2.2.3.3 | Formworker setout, drop material and 80% Deck | 6 | 5 August 2024 8:00 AM | 10 August 2024 5:00 PM | 244 | 246FS-1d,247 | 5 August 2024 8:00 AM | 2024-08-12 17:00 | 2 | Admin | 100 | 79 | 17 | 61 | 51
246 | 1.2.2.2.2.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 10 August 2024 8:00 AM | 14 August 2024 5:00 PM | 245FS-1d | 248,249 | 10 August 2024 8:00 AM | 2024-08-14 17:00 | 0 | Carpenter | 100 | 11 | 32 | 17 | 27
247 | 1.2.2.2.2.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 245 |  | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 0 | Floor Sealer | 100 | 96 | 23 | 80 | 13
248 | 1.2.2.2.2.3.6 | Services | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | 15 August 2024 8:00 AM | 2024-08-16 17:00 | 0 | Carpet | 100 | 11 | 12 | 82 | 25
249 | 1.2.2.2.2.3.7 | Post Tension | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | 15 August 2024 8:00 AM | 2024-08-16 17:00 | 0 | Concretor | 100 | 11 | 13 | 70 | 46
250 | 1.2.2.2.2.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 16 August 2024 8:00 AM | 19 August 2024 5:00 PM | 248FS-1d,249FS-1d | 251 | 16 August 2024 8:00 AM | 2024-08-19 17:00 | 0 | Admin | 100 | 89 | 25 | 72 | 5
251 | 1.2.2.2.2.3.9 | Formworker setdowns and edge boards | 3 | 20 August 2024 8:00 AM | 22 August 2024 5:00 PM | 250 | 252 | 20 August 2024 8:00 AM | 2024-08-22 17:00 | 0 | Plumber | 100 | 62 | 24 | 40 | 50
252 | 1.2.2.2.2.3.10 | Pour | 1 | 23 August 2024 8:00 AM | 23 August 2024 5:00 PM | 251 | 255,3447 | 23 August 2024 8:00 AM | 2024-08-23 17:00 | 0 | Fire | 100 | 61 | 12 | 16 | 54
253 | 1.2.2.2.2.4 | Strip Formwork - Lvl 3 | 5 | 21 October 2024 8:00 AM | 25 October 2024 5:00 PM | 288 | 453,1605 | 21 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Scaffolder | 100 | 77 | 24 | 57 | 27
254 | 1.2.2.2.2.5 | Lvl 4 - FRP - Suspended Slab | 15 | 24 August 2024 8:00 AM | 10 September 2024 5:00 PM |  |  | 24 August 2024 8:00 AM | 2024-09-15 17:00 | 5 | Metal Work | 100 | 12 | 14 | 47 | 13
255 | 1.2.2.2.2.5.1 | Scaffold Perimeter Protection | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 252 | 256SS | 24 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Foreman | 100 | 89 | 31 | 19 | 29
256 | 1.2.2.2.2.5.2 | Setout and Install Lift/Stair Formwork | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 255SS | 257FS-1d | 24 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Project Manager | 100 | 10 | 25 | 31 | 6
257 | 1.2.2.2.2.5.3 | Formworker setout, drop material and 80% Deck | 6 | 24 August 2024 8:00 AM | 30 August 2024 5:00 PM | 256FS-1d | 258FS-1d,259 | 24 August 2024 8:00 AM | 2024-09-01 17:00 | 2 | Excavation | 100 | 85 | 19 | 29 | 5
258 | 1.2.2.2.2.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 30 August 2024 8:00 AM | 3 September 2024 5:00 PM | 257FS-1d | 260,261 | 30 August 2024 8:00 AM | 2024-09-03 17:00 | 0 | Fire | 100 | 29 | 11 | 0 | 12
259 | 1.2.2.2.2.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 31 August 2024 8:00 AM | 2 September 2024 5:00 PM | 257 |  | 31 August 2024 8:00 AM | 2024-09-02 17:00 | 0 | Plumber | 100 | 50 | 33 | 57 | 59
260 | 1.2.2.2.2.5.6 | Services | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | 4 September 2024 8:00 AM | 2024-09-05 17:00 | 0 | Foreman | 100 | 27 | 10 | 80 | 55
261 | 1.2.2.2.2.5.7 | Post Tension | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | 4 September 2024 8:00 AM | 2024-09-05 17:00 | 0 | Waterproofer | 100 | 44 | 23 | 67 | 32
262 | 1.2.2.2.2.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 5 September 2024 8:00 AM | 6 September 2024 5:00 PM | 260FS-1d,261FS-1d | 263 | 5 September 2024 8:00 AM | 2024-09-06 17:00 | 0 | Admin | 100 | 23 | 10 | 1 | 20
263 | 1.2.2.2.2.5.9 | Formworker setdowns and edge boards | 2 | 7 September 2024 8:00 AM | 9 September 2024 5:00 PM | 262 | 264 | 7 September 2024 8:00 AM | 2024-09-09 17:00 | 0 | Window | 100 | 27 | 14 | 19 | 15
264 | 1.2.2.2.2.5.10 | Pour | 1 | 10 September 2024 8:00 AM | 10 September 2024 5:00 PM | 263 | 267 | 10 September 2024 8:00 AM | 2024-09-10 17:00 | 0 | Plasterboarder | 100 | 30 | 26 | 100 | 18
265 | 1.2.2.2.2.6 | Strip Formwork - Lvl 4 | 5 | 11 November 2024 8:00 AM | 15 November 2024 5:00 PM | 300 | 459,1632 | 11 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Carpet | 100 | 55 | 27 | 95 | 24
266 | 1.2.2.2.2.7 | Lvl 5 - FRP - Suspended Slab | 15 | 11 September 2024 8:00 AM | 27 September 2024 5:00 PM |  |  | 11 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Plasterboarder | 100 | 41 | 16 | 55 | 29
267 | 1.2.2.2.2.7.1 | Scaffold Perimeter Protection | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 264 | 268SS | 11 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Carpet | 100 | 81 | 28 | 82 | 12
268 | 1.2.2.2.2.7.2 | Setout and Install Lift/Stair Formwork | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 267SS | 269FS-1d | 11 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Floor Sealer | 100 | 80 | 28 | 59 | 25
269 | 1.2.2.2.2.7.3 | Formworker setout, drop material and 80% Deck | 6 | 11 September 2024 8:00 AM | 17 September 2024 5:00 PM | 268FS-1d | 270FS-1d,271 | 11 September 2024 8:00 AM | 2024-09-18 17:00 | 1 | Excavation | 100 | 78 | 21 | 94 | 36
270 | 1.2.2.2.2.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 17 September 2024 8:00 AM | 20 September 2024 5:00 PM | 269FS-1d | 272,273 | 17 September 2024 8:00 AM | 2024-09-20 17:00 | 0 | Floor Sealer | 100 | 97 | 13 | 12 | 11
271 | 1.2.2.2.2.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 18 September 2024 8:00 AM | 19 September 2024 5:00 PM | 269 |  | 18 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Line Market | 100 | 16 | 21 | 10 | 43
272 | 1.2.2.2.2.7.6 | Services | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Carpenter | 100 | 30 | 17 | 80 | 15
273 | 1.2.2.2.2.7.7 | Post Tension | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Admin | 100 | 41 | 29 | 5 | 11
274 | 1.2.2.2.2.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 September 2024 8:00 AM | 24 September 2024 5:00 PM | 272FS-1d,273FS-1d | 275 | 23 September 2024 8:00 AM | 2024-09-24 17:00 | 0 | Plumber | 100 | 92 | 22 | 98 | 18
275 | 1.2.2.2.2.7.9 | Formworker setdowns and edge boards | 2 | 25 September 2024 8:00 AM | 26 September 2024 5:00 PM | 274 | 276 | 25 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Timber Floorer | 100 | 78 | 16 | 63 | 34
276 | 1.2.2.2.2.7.10 | Pour | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 275 | 279,241 | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Site Manager | 100 | 89 | 22 | 17 | 56
277 | 1.2.2.2.2.8 | Strip Formwork - Lvl 5 | 5 | 18 November 2024 8:00 AM | 22 November 2024 5:00 PM | 303 | 465,1659 | 18 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Hoarding | 100 | 38 | 13 | 66 | 5
278 | 1.2.2.2.2.9 | Lvl 6 - FRP - Suspended Slab | 17 | 28 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | 28 September 2024 8:00 AM | 2024-10-22 17:00 | 3 | Joiner | 100 | 28 | 29 | 86 | 2
279 | 1.2.2.2.2.9.1 | Scaffold Perimeter Protection | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 276 | 280SS | 28 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Post Tension | 100 | 70 | 24 | 6 | 18
280 | 1.2.2.2.2.9.2 | Setout and Install Lift/Stair Formwork | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 279SS | 281FS-1d | 28 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Electrician | 100 | 19 | 31 | 15 | 47
281 | 1.2.2.2.2.9.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 280FS-1d | 282FS-1d,283 | 28 September 2024 8:00 AM | 2024-10-05 17:00 | 1 | Site Manager | 100 | 31 | 12 | 42 | 51
282 | 1.2.2.2.2.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 281FS-1d | 284,285 | 4 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Cleaner | 100 | 42 | 28 | 32 | 26
283 | 1.2.2.2.2.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 281 |  | 8 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Admin | 100 | 47 | 10 | 55 | 40
284 | 1.2.2.2.2.9.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Concretor | 100 | 63 | 32 | 3 | 58
285 | 1.2.2.2.2.9.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Mechanical | 100 | 80 | 33 | 84 | 46
286 | 1.2.2.2.2.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 284FS-1d,285FS-1d | 287 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Development Manager | 100 | 99 | 27 | 100 | 60
287 | 1.2.2.2.2.9.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 286 | 288 | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Concretor | 100 | 37 | 21 | 13 | 42
288 | 1.2.2.2.2.9.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 287 | 291,253 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Head Contractor | 100 | 87 | 13 | 86 | 53
289 | 1.2.2.2.2.10 | Strip Formwork - Lvl 6 | 5 | 20 November 2024 8:00 AM | 25 November 2024 5:00 PM | 300FS+8d | 657,471,1686 | 20 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Window | 100 | 26 | 23 | 2 | 29
290 | 1.2.2.2.2.11 | Lvl 7 (Roof) - FRP - Suspended Slab | 18 | 21 October 2024 8:00 AM | 9 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-13 17:00 | 4 | Stone Mason | 100 | 35 | 25 | 64 | 32
291 | 1.2.2.2.2.11.1 | Scaffold Perimeter Protection | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 288 | 292SS | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Surveyor | 100 | 44 | 26 | 32 | 29
292 | 1.2.2.2.2.11.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 291SS | 293FS-1d | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Carpenter | 100 | 23 | 12 | 54 | 58
293 | 1.2.2.2.2.11.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 292FS-1d | 294FS-1d,295 | 21 October 2024 8:00 AM | 2024-10-27 17:00 | 1 | Fire | 100 | 37 | 13 | 35 | 6
294 | 1.2.2.2.2.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293FS-1d | 296,297 | 26 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Foreman | 100 | 78 | 32 | 87 | 51
295 | 1.2.2.2.2.11.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 28 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293 |  | 28 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Plasterboarder | 100 | 96 | 29 | 13 | 42
296 | 1.2.2.2.2.11.6 | Services | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Formworker | 100 | 17 | 19 | 46 | 16
297 | 1.2.2.2.2.11.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Line Market | 100 | 25 | 30 | 95 | 16
298 | 1.2.2.2.2.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 296FS-1d,297FS-1d | 299 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Plasterboarder | 100 | 91 | 18 | 39 | 11
299 | 1.2.2.2.2.11.9 | Formworker setdowns and edge boards | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 298 | 300 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Electrician | 100 | 60 | 22 | 61 | 28
300 | 1.2.2.2.2.11.10 | Pour | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 299 | 303,289FS+8d,301FS+12d,1739FS+24d,265 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Carpenter | 100 | 47 | 13 | 42 | 57
301 | 1.2.2.2.2.12 | Strip Formwork - Lvl 7 | 5 | 25 November 2024 8:00 AM | 29 November 2024 5:00 PM | 300FS+12d | 716,748FS+24d,477,1713 | 25 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Head Contractor | 100 | 73 | 12 | 92 | 46
302 | 1.2.2.2.2.13 | Lift Shaft | 18 | 11 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 11 November 2024 8:00 AM | 2024-12-04 17:00 | 4 | Electrician | 100 | 28 | 12 | 83 | 39
303 | 1.2.2.2.2.13.1 | FRP Lift Over-run | 6 | 11 November 2024 8:00 AM | 16 November 2024 5:00 PM | 300 | 304,277 | 11 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Carpet | 100 | 25 | 12 | 12 | 19
304 | 1.2.2.2.2.13.2 | Strip Lift Shaft Formwork | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 303 | 305 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Waterproofer | 100 | 100 | 10 | 61 | 48
305 | 1.2.2.2.2.13.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 304 | 3452,306 | 22 November 2024 8:00 AM | 2024-12-02 17:00 | 2 | Post Tension | 100 | 30 | 12 | 4 | 34
306 | 1.2.2.2.2.13.4 | Building B Structure Complete | 0 | 30 November 2024 5:00 PM | 30 November 2024 5:00 PM | 305 | 7,6 | 30 November 2024 5:00 PM | 2024-11-30 17:00 | 0 | Electrician | 100 | 15 | 19 | 24 | 31
307 | 1.2.2.2.3 | Building C | 90 | 7 September 2024 8:00 AM | 23 December 2024 5:00 PM |  | 397 | 7 September 2024 8:00 AM | 2024-12-27 17:00 | 4 | Metal Work | 100 | 12 | 25 | 39 | 11
308 | 1.2.2.2.3.1 | Lvl 2 - FRP - Suspended Slab | 17 | 7 September 2024 8:00 AM | 26 September 2024 5:00 PM |  |  | 7 September 2024 8:00 AM | 2024-09-29 17:00 | 3 | Joiner | 100 | 25 | 33 | 86 | 59
309 | 1.2.2.2.3.1.1 | Scaffold Stair Removal/Adjustment | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 135,240FS+30d | 310SS | 7 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Line Market | 100 | 67 | 31 | 25 | 59
310 | 1.2.2.2.3.1.2 | Setout and Install Lift/Stair Formwork | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 309SS | 311 | 7 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Plasterboarder | 100 | 56 | 13 | 4 | 45
311 | 1.2.2.2.3.1.3 | Formworker setout, drop material and 80% Deck | 6 | 9 September 2024 8:00 AM | 14 September 2024 5:00 PM | 310 | 312FS-1d,313,365FS+10d | 9 September 2024 8:00 AM | 2024-09-14 17:00 | 0 | Plasterboarder | 100 | 78 | 29 | 77 | 3
312 | 1.2.2.2.3.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 14 September 2024 8:00 AM | 18 September 2024 5:00 PM | 311FS-1d | 314,315 | 14 September 2024 8:00 AM | 2024-09-18 17:00 | 0 | Excavation | 100 | 12 | 13 | 66 | 25
313 | 1.2.2.2.3.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 311 |  | 16 September 2024 8:00 AM | 2024-09-17 17:00 | 0 | Development Manager | 100 | 31 | 33 | 72 | 21
314 | 1.2.2.2.3.1.6 | Services | 2 | 19 September 2024 8:00 AM | 20 September 2024 5:00 PM | 312 | 316FS-1d | 19 September 2024 8:00 AM | 2024-09-20 17:00 | 0 | Carpet | 100 | 48 | 22 | 4 | 24
315 | 1.2.2.2.3.1.7 | Post Tension | 3 | 19 September 2024 8:00 AM | 21 September 2024 5:00 PM | 312 | 316FS-1d | 19 September 2024 8:00 AM | 2024-09-21 17:00 | 0 | Project Manager | 100 | 13 | 11 | 9 | 49
316 | 1.2.2.2.3.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 314FS-1d,315FS-1d | 317 | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Project Manager | 100 | 18 | 24 | 94 | 28
317 | 1.2.2.2.3.1.9 | Formworker setdowns and edge boards | 2 | 24 September 2024 8:00 AM | 25 September 2024 5:00 PM | 316 | 318 | 24 September 2024 8:00 AM | 2024-09-25 17:00 | 0 | Stone Mason | 100 | 11 | 16 | 64 | 18
318 | 1.2.2.2.3.1.10 | Pour | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 317 | 321 | 26 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Head Contractor | 100 | 75 | 29 | 52 | 48
319 | 1.2.2.2.3.2 | Strip Formwork - Lvl 2 | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 354 | 331FS+5d | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Carpet | 100 | 57 | 31 | 81 | 35
320 | 1.2.2.2.3.3 | Lvl 3 - FRP - Suspended Slab | 17 | 27 September 2024 8:00 AM | 18 October 2024 5:00 PM |  |  | 27 September 2024 8:00 AM | 2024-10-21 17:00 | 3 | Surveyor | 100 | 28 | 17 | 25 | 10
321 | 1.2.2.2.3.3.1 | Scaffold Stair Removal/Adjustment | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 318 | 322SS | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Post Tension | 100 | 42 | 35 | 66 | 28
322 | 1.2.2.2.3.3.2 | Setout and Install Lift/Stair Formwork | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 321SS | 323 | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Timber Floorer | 100 | 10 | 33 | 88 | 5
323 | 1.2.2.2.3.3.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 322 | 324FS-1d,325 | 28 September 2024 8:00 AM | 2024-10-08 17:00 | 4 | Post Tension | 100 | 56 | 31 | 18 | 40
324 | 1.2.2.2.3.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 323FS-1d | 326,327 | 4 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Plasterboarder | 100 | 27 | 33 | 100 | 40
325 | 1.2.2.2.3.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 323 |  | 8 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Formworker | 100 | 89 | 12 | 11 | 50
326 | 1.2.2.2.3.3.6 | Services | 2 | 11 October 2024 8:00 AM | 12 October 2024 5:00 PM | 324 | 328FS-1d | 11 October 2024 8:00 AM | 2024-10-12 17:00 | 0 | Line Market | 100 | 100 | 35 | 91 | 46
327 | 1.2.2.2.3.3.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 324 | 328FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Reinforcement Fixer | 100 | 80 | 23 | 63 | 58
328 | 1.2.2.2.3.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 326FS-1d,327FS-1d | 329 | 14 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Metal Work | 100 | 48 | 31 | 80 | 56
329 | 1.2.2.2.3.3.9 | Formworker setdowns and edge boards | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 328 | 330 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Waterproofer | 100 | 24 | 22 | 11 | 24
330 | 1.2.2.2.3.3.10 | Pour | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 329 | 333 | 18 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Excavation | 100 | 99 | 16 | 69 | 16
331 | 1.2.2.2.3.4 | Strip Formwork - Lvl 3 | 5 | 10 December 2024 8:00 AM | 14 December 2024 5:00 PM | 319FS+5d | 490,1748,2151,1774,2177FS+5d | 10 December 2024 8:00 AM | 2024-12-14 17:00 | 0 | Line Market | 100 | 53 | 10 | 24 | 52
332 | 1.2.2.2.3.5 | Lvl 4 - FRP - Suspended Slab | 17 | 19 October 2024 8:00 AM | 7 November 2024 5:00 PM |  |  | 19 October 2024 8:00 AM | 2024-11-08 17:00 | 1 | Hoarding | 100 | 20 | 20 | 8 | 48
333 | 1.2.2.2.3.5.1 | Scaffold Stair Removal/Adjustment | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 330 | 334SS | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Contract Administrator | 100 | 86 | 10 | 45 | 39
334 | 1.2.2.2.3.5.2 | Setout and Install Lift/Stair Formwork | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 333SS | 335 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Site Manager | 100 | 55 | 27 | 13 | 30
335 | 1.2.2.2.3.5.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 334 | 336FS-1d,337 | 21 October 2024 8:00 AM | 2024-10-29 17:00 | 3 | Cleaner | 100 | 78 | 27 | 31 | 53
336 | 1.2.2.2.3.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 335FS-1d | 338,339 | 26 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Plumber | 100 | 66 | 24 | 13 | 2
337 | 1.2.2.2.3.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 335 |  | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Project Manager | 100 | 37 | 16 | 2 | 25
338 | 1.2.2.2.3.5.6 | Services | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 336 | 340FS-1d | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Concretor | 100 | 54 | 11 | 23 | 48
339 | 1.2.2.2.3.5.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 336 | 340FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Carpenter | 100 | 34 | 30 | 11 | 31
340 | 1.2.2.2.3.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 338FS-1d,339FS-1d | 341 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Head Contractor | 100 | 24 | 22 | 94 | 59
341 | 1.2.2.2.3.5.9 | Formworker setdowns and edge boards | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 340 | 342 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Mechanical | 100 | 20 | 28 | 46 | 30
342 | 1.2.2.2.3.5.10 | Pour | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 341 | 345 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Surveyor | 100 | 13 | 27 | 50 | 2
343 | 1.2.2.2.3.6 | Strip Formwork - Lvl 4 | 5 | 16 December 2024 8:00 AM | 20 December 2024 5:00 PM | 354FS+15d | 495,2648,2674FS+5d | 16 December 2024 8:00 AM | 2024-12-20 17:00 | 0 | Plasterboarder | 100 | 44 | 25 | 20 | 49
344 | 1.2.2.2.3.7 | Lvl 5 (Roof) - FRP - Suspended Slab | 17 | 8 November 2024 8:00 AM | 27 November 2024 5:00 PM |  |  | 8 November 2024 8:00 AM | 2024-11-29 17:00 | 2 | Hoarding | 100 | 41 | 16 | 65 | 59
345 | 1.2.2.2.3.7.1 | Scaffold Stair Removal/Adjustment | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 342 | 346SS | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Waterproofer | 100 | 94 | 20 | 29 | 45
346 | 1.2.2.2.3.7.2 | Setout and Install Lift/Stair Formwork | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 345SS | 347 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Renderer | 100 | 45 | 13 | 45 | 15
347 | 1.2.2.2.3.7.3 | Formworker setout, drop material and 80% Deck | 6 | 9 November 2024 8:00 AM | 15 November 2024 5:00 PM | 346 | 348FS-1d,349 | 9 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Excavation | 100 | 86 | 23 | 90 | 17
348 | 1.2.2.2.3.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 November 2024 8:00 AM | 19 November 2024 5:00 PM | 347FS-1d | 350,351 | 15 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Carpet | 100 | 62 | 31 | 0 | 48
349 | 1.2.2.2.3.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 347 |  | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Timber Floorer | 100 | 50 | 33 | 21 | 58
350 | 1.2.2.2.3.7.6 | Services | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 348 | 352FS-1d | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 100 | 48 | 23 | 91 | 43
351 | 1.2.2.2.3.7.7 | Post Tension | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 348 | 352FS-1d | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Carpet | 100 | 15 | 16 | 45 | 5
352 | 1.2.2.2.3.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 350FS-1d,351FS-1d | 353 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Fire | 100 | 81 | 25 | 7 | 10
353 | 1.2.2.2.3.7.9 | Formworker setdowns and edge boards | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 352 | 354 | 25 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Contract Administrator | 100 | 62 | 14 | 26 | 39
354 | 1.2.2.2.3.7.10 | Pour | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 353 | 357,355FS+12d,343FS+15d,360,319 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Admin | 100 | 90 | 32 | 90 | 5
355 | 1.2.2.2.3.8 | Strip Formwork - Lvl 5 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 354FS+12d | 500,3145,3171FS+5d | 12 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Renderer | 100 | 77 | 28 | 95 | 22
356 | 1.2.2.2.3.9 | Lift Shaft | 22 | 28 November 2024 8:00 AM | 23 December 2024 5:00 PM |  |  | 28 November 2024 8:00 AM | 2024-12-24 17:00 | 1 | Plasterboarder | 100 | 76 | 18 | 87 | 33
357 | 1.2.2.2.3.9.1 | FRP Lift Over-run | 10 | 28 November 2024 8:00 AM | 9 December 2024 5:00 PM | 354 | 358 | 28 November 2024 8:00 AM | 2024-12-13 17:00 | 4 | Plumber | 100 | 87 | 34 | 41 | 50
358 | 1.2.2.2.3.9.2 | Strip Lift Shaft Formwork | 4 | 10 December 2024 8:00 AM | 13 December 2024 5:00 PM | 357 | 359 | 10 December 2024 8:00 AM | 2024-12-13 17:00 | 0 | Project Manager | 100 | 64 | 22 | 33 | 50
359 | 1.2.2.2.3.9.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 14 December 2024 8:00 AM | 23 December 2024 5:00 PM | 358 | 3453,360 | 14 December 2024 8:00 AM | 2024-12-25 17:00 | 2 | Head Contractor | 100 | 79 | 31 | 19 | 15
360 | 1.2.2.2.3.10 | Building C Structure Complete | 0 | 23 December 2024 5:00 PM | 23 December 2024 5:00 PM | 354,359 | 8,7 | 23 December 2024 5:00 PM | 2024-12-23 17:00 | 0 | Excavation | 100 | 42 | 15 | 38 | 18
361 | 1.2.2.2.4 | Building D | 76 | 26 September 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | 26 September 2024 8:00 AM | 2025-01-06 17:00 | 3 | Landscaper | 100 | 21 | 24 | 58 | 35
362 | 1.2.2.2.4.1 | Lvl 2 - FRP - Suspended Slab | 19 | 26 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | 26 September 2024 8:00 AM | 2024-10-23 17:00 | 4 | Joiner | 100 | 75 | 22 | 86 | 50
363 | 1.2.2.2.4.1.1 | Scaffold Stair Removal/Adjustment | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 364SS |  | 26 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Tiler | 100 | 57 | 12 | 77 | 24
364 | 1.2.2.2.4.1.2 | Setout and Install Lift/Stair Formwork | 1 | 26 September 2024 8:00 AM | 27 September 2024 8:00 AM | 365SF | 363SS | 26 September 2024 8:00 AM | 2024-09-27 08:00 | 0 | Fire | 100 | 28 | 15 | 96 | 13
365 | 1.2.2.2.4.1.3 | Formworker setout, drop material and 80% Deck | 6 | 27 September 2024 8:00 AM | 3 October 2024 5:00 PM | 311FS+10d | 366FS-1d,367,364SF | 27 September 2024 8:00 AM | 2024-10-04 17:00 | 1 | Cleaner | 100 | 68 | 23 | 31 | 35
366 | 1.2.2.2.4.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 3 October 2024 8:00 AM | 10 October 2024 5:00 PM | 365FS-1d | 368,369 | 3 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Joiner | 100 | 54 | 19 | 41 | 54
367 | 1.2.2.2.4.1.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 4 October 2024 8:00 AM | 9 October 2024 5:00 PM | 365 |  | 4 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Head Contractor | 100 | 59 | 15 | 80 | 12
368 | 1.2.2.2.4.1.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Line Market | 100 | 49 | 32 | 36 | 58
369 | 1.2.2.2.4.1.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Admin | 100 | 49 | 26 | 41 | 31
370 | 1.2.2.2.4.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 368FS-1d,369FS-1d | 371 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Formworker | 100 | 82 | 14 | 37 | 43
371 | 1.2.2.2.4.1.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 370 | 372 | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Site Manager | 100 | 83 | 26 | 63 | 13
372 | 1.2.2.2.4.1.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 371 | 375 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Post Tension | 100 | 88 | 25 | 45 | 5
373 | 1.2.2.2.4.2 | Strip Formwork - Lvl 2 | 5 | 21 November 2024 8:00 AM | 26 November 2024 5:00 PM | 384FS+8d | 485,506 | 21 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Tiler | 100 | 100 | 17 | 91 | 44
374 | 1.2.2.2.4.3 | Lvl 3 - FRP - Suspended Slab | 19 | 21 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-16 17:00 | 5 | Timber Floorer | 100 | 38 | 15 | 46 | 60
375 | 1.2.2.2.4.3.1 | Scaffold Stair Removal/Adjustment | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 372 | 376SS | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Foreman | 100 | 88 | 14 | 31 | 6
376 | 1.2.2.2.4.3.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 375SS | 377 | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Project Manager | 100 | 22 | 14 | 84 | 29
377 | 1.2.2.2.4.3.3 | Formworker setout, drop material and 80% Deck | 6 | 22 October 2024 8:00 AM | 28 October 2024 5:00 PM | 376 | 378FS-1d,379 | 22 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Fire | 100 | 18 | 29 | 29 | 52
378 | 1.2.2.2.4.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 377FS-1d | 380,381 | 28 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Contract Administrator | 100 | 24 | 35 | 11 | 26
379 | 1.2.2.2.4.3.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 29 October 2024 8:00 AM | 31 October 2024 5:00 PM | 377 |  | 29 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Formworker | 100 | 54 | 33 | 68 | 59
380 | 1.2.2.2.4.3.6 | Services | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Project Manager | 100 | 25 | 32 | 83 | 57
381 | 1.2.2.2.4.3.7 | Post Tension | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Development Manager | 100 | 13 | 10 | 64 | 18
382 | 1.2.2.2.4.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 5 November 2024 8:00 AM | 7 November 2024 5:00 PM | 380FS-1d,381FS-1d | 383 | 5 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Electrician | 100 | 20 | 28 | 19 | 23
383 | 1.2.2.2.4.3.9 | Formworker setdowns and edge boards | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 382 | 384 | 8 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Electrician | 100 | 63 | 25 | 29 | 19
384 | 1.2.2.2.4.3.10 | Pour | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 383 | 385FS+12d,373FS+8d,387 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Contract Administrator | 100 | 62 | 22 | 84 | 16
385 | 1.2.2.2.4.4 | Strip Formwork - Lvl 3 | 5 | 26 November 2024 8:00 AM | 30 November 2024 5:00 PM | 384FS+12d | 511 | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Plasterboarder | 100 | 62 | 21 | 100 | 9
386 | 1.2.2.2.4.5 | L4 Strucutral Steel Roof | 38 | 12 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 12 November 2024 8:00 AM | 2025-01-08 17:00 | 5 | Electrician | 100 | 77 | 15 | 39 | 7
387 | 1.2.2.2.4.5.1 | Scaffold Perimeter Protection | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 384 | 388SS | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Window | 100 | 52 | 23 | 73 | 38
388 | 1.2.2.2.4.5.2 | Setout | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 387SS | 389 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Metal Work | 100 | 48 | 13 | 47 | 47
389 | 1.2.2.2.4.5.3 | Formworker setout, drop material and 80% Walls | 5 | 14 November 2024 8:00 AM | 19 November 2024 5:00 PM | 388 | 390FS-1d | 14 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Line Market | 100 | 21 | 16 | 11 | 22
390 | 1.2.2.2.4.5.4 | Steel Fixer - Walls | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 389FS-1d | 391 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Cleaner | 100 | 63 | 13 | 28 | 24
391 | 1.2.2.2.4.5.5 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 390 | 392 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Floor Sealer | 100 | 18 | 16 | 48 | 13
392 | 1.2.2.2.4.5.6 | Pour | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 391 | 393 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Renderer | 100 | 13 | 14 | 42 | 34
393 | 1.2.2.2.4.5.7 | Strip Formwork | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 392 | 394 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Carpenter | 100 | 17 | 22 | 28 | 56
394 | 1.2.2.2.4.5.8 | Structural Steel Setout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 393 | 395 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Timber Floorer | 100 | 19 | 10 | 30 | 43
395 | 1.2.2.2.4.5.9 | Install Structural Steel | 8 | 29 November 2024 8:00 AM | 7 December 2024 5:00 PM | 394 | 396 | 29 November 2024 8:00 AM | 2024-12-09 17:00 | 2 | Subcontractor | 100 | 57 | 15 | 78 | 52
396 | 1.2.2.2.4.5.10 | Install Metal Deck Roofing | 15 | 9 December 2024 8:00 AM | 3 January 2025 5:00 PM | 395 | 516,8 | 9 December 2024 8:00 AM | 2025-01-08 17:00 | 5 | Joiner | 100 | 13 | 15 | 19 | 29
397 | 1.2.2.3 | Structural Works Complete | 0 | 3 January 2025 5:00 PM | 3 January 2025 5:00 PM | 120,307,361,91,138,229 |  | 3 January 2025 5:00 PM | 2025-01-03 17:00 | 0 | Subcontractor | 100 | 80 | 10 | 40 | 9
398 | 1.2.3 | FAÇADE WORKS | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | 13 July 2024 8:00 AM | 2025-03-23 17:00 | 1 | Landscaper | 100 | 91 | 30 | 47 | 7
399 | 1.2.3.1 | Building A | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | 13 July 2024 8:00 AM | 2025-03-24 17:00 | 2 | Contract Administrator | 100 | 79 | 31 | 16 | 54
400 | 1.2.3.1.1 | Lvl 1 | 44 | 13 July 2024 8:00 AM | 2 September 2024 5:00 PM |  |  | 13 July 2024 8:00 AM | 2024-09-04 17:00 | 2 | Joiner | 100 | 76 | 30 | 37 | 33
401 | 1.2.3.1.1.1 | Survey & Setout | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 116FS+5d | 402 | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Surveyor | 100 | 27 | 20 | 0 | 53
402 | 1.2.3.1.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 15 July 2024 8:00 AM | 19 July 2024 5:00 PM | 401 | 403 | 15 July 2024 8:00 AM | 2024-07-19 17:00 | 0 | Concretor | 100 | 69 | 29 | 46 | 39
403 | 1.2.3.1.1.3 | Façade & External Walls | 20 | 20 July 2024 8:00 AM | 12 August 2024 5:00 PM | 402 | 404 | 20 July 2024 8:00 AM | 2024-08-17 17:00 | 5 | Cleaner | 100 | 33 | 10 | 87 | 8
404 | 1.2.3.1.1.4 | Windows Install | 18 | 13 August 2024 8:00 AM | 2 September 2024 5:00 PM | 403 | 405,411 | 13 August 2024 8:00 AM | 2024-09-04 17:00 | 2 | Subcontractor | 100 | 96 | 15 | 65 | 15
405 | 1.2.3.1.1.5 | Level 1 Weathertight | 0 | 2 September 2024 5:00 PM | 2 September 2024 5:00 PM | 404 | 558 | 2 September 2024 5:00 PM | 2024-09-02 17:00 | 0 | Electrician | 100 | 91 | 19 | 14 | 34
406 | 1.2.3.1.2 | Lvl 2 | 83 | 17 August 2024 8:00 AM | 23 November 2024 5:00 PM |  |  | 17 August 2024 8:00 AM | 2024-11-24 17:00 | 1 | Concretor | 100 | 23 | 10 | 64 | 51
407 | 1.2.3.1.2.1 | Survey & Setout | 1 | 17 August 2024 8:00 AM | 17 August 2024 5:00 PM | 149FS+5d | 408 | 17 August 2024 8:00 AM | 2024-08-17 17:00 | 0 | Concretor | 100 | 57 | 15 | 97 | 38
408 | 1.2.3.1.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 19 August 2024 8:00 AM | 23 August 2024 5:00 PM | 407 | 577 | 19 August 2024 8:00 AM | 2024-08-23 17:00 | 0 | Reinforcement Fixer | 100 | 67 | 16 | 10 | 3
409 | 1.2.3.1.2.3 | Façade & External Walls | 22 | 9 October 2024 8:00 AM | 2 November 2024 5:00 PM | 150FS-10d | 410 | 9 October 2024 8:00 AM | 2024-11-04 17:00 | 2 | Metal Work | 100 | 98 | 22 | 20 | 50
410 | 1.2.3.1.2.4 | Windows Install | 18 | 4 November 2024 8:00 AM | 23 November 2024 5:00 PM | 409 | 411 | 4 November 2024 8:00 AM | 2024-11-25 17:00 | 2 | Painter | 100 | 77 | 31 | 94 | 37
411 | 1.2.3.1.2.5 | Level 2 Weathertight | 0 | 23 November 2024 5:00 PM | 23 November 2024 5:00 PM | 404,410 | 585 | 23 November 2024 5:00 PM | 2024-11-23 17:00 | 0 | Electrician | 100 | 96 | 27 | 20 | 55
412 | 1.2.3.1.3 | Lvl 3 | 40 | 13 November 2024 8:00 AM | 7 January 2025 5:00 PM |  |  | 13 November 2024 8:00 AM | 2025-01-08 17:00 | 1 | Metal Work | 100 | 59 | 24 | 27 | 46
413 | 1.2.3.1.3.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 174FS+5d | 414FS-1d | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Renderer | 100 | 12 | 10 | 90 | 39
414 | 1.2.3.1.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 413FS-1d |  | 30 November 2024 8:00 AM | 2024-12-04 17:00 | 0 | Tiler | 100 | 91 | 14 | 53 | 19
415 | 1.2.3.1.3.3 | Façade & External Walls | 22 | 13 November 2024 8:00 AM | 7 December 2024 5:00 PM | 174FS-10d | 416 | 13 November 2024 8:00 AM | 2024-12-12 17:00 | 5 | Stone Mason | 100 | 37 | 18 | 39 | 29
416 | 1.2.3.1.3.4 | Windows Install | 18 | 9 December 2024 8:00 AM | 7 January 2025 5:00 PM | 415 | 610FS-6d,417 | 9 December 2024 8:00 AM | 2025-01-07 17:00 | 0 | Excavation | 100 | 34 | 14 | 73 | 27
417 | 1.2.3.1.3.5 | Level 3 Weathertight | 0 | 7 January 2025 5:00 PM | 7 January 2025 5:00 PM | 416 | 612,444 | 7 January 2025 5:00 PM | 2025-01-07 17:00 | 0 | Waterproofer | 100 | 96 | 19 | 62 | 46
418 | 1.2.3.1.4 | Lvl 4 | 44 | 17 December 2024 8:00 AM | 15 February 2025 5:00 PM |  |  | 17 December 2024 8:00 AM | - | 0 | Site Manager | 75 | 74 | 12 | 20 | 55
419 | 1.2.3.1.4.1 | Survey & Setout | 1 | 17 December 2024 8:00 AM | 17 December 2024 5:00 PM | 186FS+5d | 420FS-1d | 17 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Waterproofer | 100 | 67 | 22 | 67 | 7
420 | 1.2.3.1.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 17 December 2024 8:00 AM | 20 December 2024 5:00 PM | 419FS-1d | 421 | 17 December 2024 8:00 AM | 2024-12-20 17:00 | 0 | Project Manager | 100 | 29 | 14 | 43 | 31
421 | 1.2.3.1.4.3 | Façade & External Walls | 22 | 21 December 2024 8:00 AM | 24 January 2025 5:00 PM | 186FS-10d,420 | 422 | 21 December 2024 8:00 AM | 2025-01-24 17:00 | 0 | Mechanical | 100 | 14 | 33 | 78 | 2
422 | 1.2.3.1.4.4 | Windows Install | 18 | 27 January 2025 8:00 AM | 15 February 2025 5:00 PM | 421 | 637FS-6d,423 | 27 January 2025 8:00 AM | - | 0 | Plasterboarder | 75 | 66 | 11 | 41 | 13
423 | 1.2.3.1.4.5 | Level 4 Weathertight | 0 | 15 February 2025 5:00 PM | 15 February 2025 5:00 PM | 422 | 639,444 | - | - | 0 | Landscaper | 0 | 83 | 33 | 19 | 8
424 | 1.2.3.1.5 | Lvl 5 | 40 | 30 November 2024 8:00 AM | 24 January 2025 5:00 PM |  |  | 30 November 2024 8:00 AM | - | 0 | Electrician | 75 | 98 | 28 | 100 | 16
425 | 1.2.3.1.5.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 198FS+5d | 426FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Contract Administrator | 100 | 40 | 14 | 30 | 12
426 | 1.2.3.1.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 425FS-1d | 663 | 18 December 2024 8:00 AM | - | 0 | Stone Mason | 95 | 19 | 21 | 28 | 56
427 | 1.2.3.1.5.3 | Façade & External Walls | 22 | 30 November 2024 8:00 AM | 3 January 2025 5:00 PM | 198FS-10d | 428 | 30 November 2024 8:00 AM | - | 0 | Site Manager | 50 | 67 | 31 | 12 | 56
428 | 1.2.3.1.5.4 | Windows Install | 18 | 4 January 2025 8:00 AM | 24 January 2025 5:00 PM | 427 | 669FS-6d,429,444 | 4 January 2025 8:00 AM | - | 0 | Surveyor | 50 | 61 | 19 | 96 | 54
429 | 1.2.3.1.5.5 | Level 5 Weathertight | 0 | 24 January 2025 5:00 PM | 24 January 2025 5:00 PM | 428 | 671 | 24 January 2025 5:00 PM | 2025-01-24 17:00 | 0 | Timber Floorer | 100 | 21 | 14 | 65 | 18
430 | 1.2.3.1.6 | Lvl 6 | 59 | 19 November 2024 8:00 AM | 5 February 2025 5:00 PM |  |  | 19 November 2024 8:00 AM | - | 0 | Timber Floorer | 25 | 75 | 31 | 91 | 33
431 | 1.2.3.1.6.1 | Survey & Setout | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 209FS+5d | 432 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Admin | 100 | 80 | 18 | 56 | 36
432 | 1.2.3.1.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 6 December 2024 8:00 AM | 10 December 2024 5:00 PM | 210FS-10d,431 | 433,690 | 6 December 2024 8:00 AM | - | 0 | Tiler | 25 | 17 | 15 | 95 | 46
433 | 1.2.3.1.6.3 | Façade & External Walls | 22 | 11 December 2024 8:00 AM | 14 January 2025 5:00 PM | 432 | 434 | 11 December 2024 8:00 AM | - | 0 | Scaffolder | 25 | 96 | 35 | 91 | 32
434 | 1.2.3.1.6.4 | Windows Install | 18 | 15 January 2025 8:00 AM | 5 February 2025 5:00 PM | 433 | 696FS-6d,435 | - | - | 0 | Contract Administrator | 25 | 87 | 15 | 50 | 22
435 | 1.2.3.1.6.5 | Level 6 Weathertight | 0 | 5 February 2025 5:00 PM | 5 February 2025 5:00 PM | 434 | 698,444 | - | - | 0 | Floor Sealer | 0 | 79 | 32 | 11 | 36
436 | 1.2.3.1.7 | Lvl 7 | 59 | 5 December 2024 8:00 AM | 21 February 2025 5:00 PM |  |  | 5 December 2024 8:00 AM | - | 0 | Post Tension | 25 | 27 | 26 | 42 | 43
437 | 1.2.3.1.7.1 | Survey & Setout | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 221FS+5d | 438FS-1d | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Metal Work | 100 | 26 | 27 | 61 | 28
438 | 1.2.3.1.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 5 December 2024 8:00 AM | 9 December 2024 5:00 PM | 437FS-1d | 722 | 5 December 2024 8:00 AM | 2024-12-09 17:00 | 0 | Metal Work | 100 | 94 | 31 | 77 | 46
439 | 1.2.3.1.7.3 | Façade & External Walls | 22 | 8 January 2025 8:00 AM | 3 February 2025 5:00 PM | 223FS+10d | 440 | 8 January 2025 8:00 AM | - | 0 | Plasterboarder | 25 | 74 | 29 | 65 | 40
440 | 1.2.3.1.7.4 | Windows Install | 16 | 4 February 2025 8:00 AM | 21 February 2025 5:00 PM | 439 | 728FS-6d,441,3446FS-5d |  | - | 0 | Tiler | 0 | 51 | 20 | 13 | 53
441 | 1.2.3.1.7.5 | Level 7 Weathertight | 0 | 21 February 2025 5:00 PM | 21 February 2025 5:00 PM | 440 | 730,442 |  | - | 0 | Floor Sealer | 0 | 82 | 28 | 52 | 10
442 | 1.2.3.1.8 | Defect Rectification | 15 | 22 February 2025 8:00 AM | 11 March 2025 5:00 PM | 441 | 443 |  | - | 0 | Subcontractor | 0 | 53 | 17 | 30 | 56
443 | 1.2.3.1.9 | Strip Scaffold | 10 | 12 March 2025 8:00 AM | 22 March 2025 5:00 PM | 442 | 444,3456 |  | - | 0 | Reinforcement Fixer | 0 | 74 | 19 | 1 | 11
444 | 1.2.3.1.10 | Building A Façade Complete | 0 | 22 March 2025 5:00 PM | 22 March 2025 5:00 PM | 443,435,428,423,417 | 5 |  | - | 0 | Electrician | 0 | 38 | 11 | 61 | 40
445 | 1.2.3.2 | Building B | 89 | 4 October 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | 4 October 2024 8:00 AM | 2025-02-01 17:00 | 4 | Admin | 100 | 45 | 27 | 52 | 17
446 | 1.2.3.2.1 | Lvl 1 | 44 | 4 October 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 4 October 2024 8:00 AM | 2024-11-30 17:00 | 4 | Window | 100 | 62 | 25 | 58 | 11
447 | 1.2.3.2.1.1 | Survey & Setout | 1 | 4 October 2024 8:00 AM | 4 October 2024 5:00 PM | 241 | 448 | 4 October 2024 8:00 AM | 2024-10-04 17:00 | 0 | Window | 100 | 48 | 20 | 10 | 2
448 | 1.2.3.2.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 8 October 2024 8:00 AM | 12 October 2024 5:00 PM | 447 | 449,758,852,1322FS+6d,1510FS+6d,1416FS+6d,946FS+2d,1040FS+2d,1134FS+4d,1228FS+4d | 8 October 2024 8:00 AM | 2024-10-12 17:00 | 0 | Reinforcement Fixer | 100 | 39 | 11 | 83 | 58
449 | 1.2.3.2.1.3 | Façade & External Walls | 20 | 14 October 2024 8:00 AM | 5 November 2024 5:00 PM | 448 | 450 | 14 October 2024 8:00 AM | 2024-11-10 17:00 | 5 | Project Manager | 100 | 87 | 23 | 59 | 30
450 | 1.2.3.2.1.4 | Windows Install | 18 | 6 November 2024 8:00 AM | 26 November 2024 5:00 PM | 449 | 451 | 6 November 2024 8:00 AM | 2024-11-29 17:00 | 3 | Plumber | 100 | 89 | 22 | 82 | 38
451 | 1.2.3.2.1.5 | Level 1 Weathertight | 0 | 26 November 2024 5:00 PM | 26 November 2024 5:00 PM | 450 | 1640 | 26 November 2024 5:00 PM | 2024-11-26 17:00 | 0 | Electrician | 100 | 75 | 13 | 15 | 59
452 | 1.2.3.2.2 | Lvl 2 | 42 | 26 October 2024 8:00 AM | 13 December 2024 5:00 PM |  |  | 26 October 2024 8:00 AM | 2024-12-14 17:00 | 1 | Concretor | 100 | 31 | 28 | 24 | 10
453 | 1.2.3.2.2.1 | Survey & Setout | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 253 | 454 | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Window | 100 | 33 | 31 | 79 | 40
454 | 1.2.3.2.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 453 | 455 | 28 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Head Contractor | 100 | 16 | 10 | 12 | 59
455 | 1.2.3.2.2.3 | Façade & External Walls | 20 | 2 November 2024 8:00 AM | 25 November 2024 5:00 PM | 454 | 456 | 2 November 2024 8:00 AM | 2024-11-29 17:00 | 4 | Painter | 100 | 10 | 29 | 31 | 8
456 | 1.2.3.2.2.4 | Windows Install | 16 | 26 November 2024 8:00 AM | 13 December 2024 5:00 PM | 455 | 457 | 26 November 2024 8:00 AM | 2024-12-17 17:00 | 4 | Mechanical | 100 | 98 | 30 | 18 | 36
457 | 1.2.3.2.2.5 | Level 2 Weathertight | 0 | 13 December 2024 5:00 PM | 13 December 2024 5:00 PM | 456 |  | 13 December 2024 5:00 PM | 2024-12-13 17:00 | 0 | Excavation | 100 | 64 | 29 | 0 | 22
458 | 1.2.3.2.3 | Lvl 3 | 43 | 16 November 2024 8:00 AM | 14 January 2025 5:00 PM |  |  | 16 November 2024 8:00 AM | 2025-01-15 17:00 | 1 | Renderer | 100 | 61 | 35 | 2 | 14
459 | 1.2.3.2.3.1 | Survey & Setout | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 265 | 460 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Joiner | 100 | 82 | 35 | 42 | 13
460 | 1.2.3.2.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 459 | 461 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 100 | 73 | 11 | 23 | 51
461 | 1.2.3.2.3.3 | Façade & External Walls | 20 | 22 November 2024 8:00 AM | 14 December 2024 5:00 PM | 460 | 462 | 22 November 2024 8:00 AM | 2024-12-15 17:00 | 1 | Contract Administrator | 100 | 10 | 27 | 47 | 3
462 | 1.2.3.2.3.4 | Windows Install | 18 | 16 December 2024 8:00 AM | 14 January 2025 5:00 PM | 461 | 1638FS-6d,463 | 16 December 2024 8:00 AM | 2025-01-19 17:00 | 5 | Reinforcement Fixer | 100 | 56 | 20 | 94 | 39
463 | 1.2.3.2.3.5 | Level 3 Weathertight | 0 | 14 January 2025 5:00 PM | 14 January 2025 5:00 PM | 462 | 1640 | 14 January 2025 5:00 PM | 2025-01-14 17:00 | 0 | Admin | 100 | 88 | 34 | 32 | 37
464 | 1.2.3.2.4 | Lvl 4 | 42 | 23 November 2024 8:00 AM | 20 January 2025 5:00 PM |  |  | 23 November 2024 8:00 AM | 2025-01-23 17:00 | 3 | Formworker | 100 | 10 | 28 | 85 | 56
465 | 1.2.3.2.4.1 | Survey & Setout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 277 | 466FS-1d | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Metal Work | 100 | 67 | 10 | 83 | 24
466 | 1.2.3.2.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 23 November 2024 8:00 AM | 27 November 2024 5:00 PM | 465FS-1d | 467 | 23 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Landscaper | 100 | 16 | 28 | 32 | 10
467 | 1.2.3.2.4.3 | Façade & External Walls | 20 | 28 November 2024 8:00 AM | 20 December 2024 5:00 PM | 466 | 468 | 28 November 2024 8:00 AM | 2024-12-24 17:00 | 4 | Line Market | 100 | 82 | 15 | 4 | 34
468 | 1.2.3.2.4.4 | Windows Install | 18 | 21 December 2024 8:00 AM | 20 January 2025 5:00 PM | 467 | 1665FS-6d,469 | 21 December 2024 8:00 AM | 2025-01-24 17:00 | 4 | Landscaper | 100 | 84 | 31 | 84 | 37
469 | 1.2.3.2.4.5 | Level 4 Weathertight | 0 | 20 January 2025 5:00 PM | 20 January 2025 5:00 PM | 468 | 1665FS-6d | 20 January 2025 5:00 PM | 2025-01-20 17:00 | 0 | Carpet | 100 | 64 | 17 | 59 | 54
470 | 1.2.3.2.5 | Lvl 5 | 42 | 26 November 2024 8:00 AM | 22 January 2025 5:00 PM |  |  | 26 November 2024 8:00 AM | 2025-01-26 17:00 | 4 | Head Contractor | 100 | 18 | 13 | 15 | 57
471 | 1.2.3.2.5.1 | Survey & Setout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 289 | 472FS-1d | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Subcontractor | 100 | 73 | 18 | 44 | 21
472 | 1.2.3.2.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 26 November 2024 8:00 AM | 29 November 2024 5:00 PM | 471FS-1d | 473 | 26 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Window | 100 | 33 | 16 | 0 | 18
473 | 1.2.3.2.5.3 | Façade & External Walls | 20 | 30 November 2024 8:00 AM | 23 December 2024 5:00 PM | 472 | 474 | 30 November 2024 8:00 AM | 2024-12-28 17:00 | 5 | Timber Floorer | 100 | 100 | 35 | 16 | 11
474 | 1.2.3.2.5.4 | Windows Install | 18 | 24 December 2024 8:00 AM | 22 January 2025 5:00 PM | 473 | 475 | 24 December 2024 8:00 AM | 2025-01-27 17:00 | 5 | Surveyor | 100 | 94 | 16 | 53 | 13
475 | 1.2.3.2.5.5 | Level 5 Weathertight | 0 | 22 January 2025 5:00 PM | 22 January 2025 5:00 PM | 474 | 1692FS-4d | 22 January 2025 5:00 PM | 2025-01-22 17:00 | 0 | Foreman | 100 | 67 | 33 | 38 | 8
476 | 1.2.3.2.6 | Lvl 6 | 42 | 30 November 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | 30 November 2024 8:00 AM | - | 0 | Renderer | 95 | 37 | 25 | 13 | 3
477 | 1.2.3.2.6.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 301 | 478FS-1d | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Concretor | 100 | 77 | 27 | 46 | 8
478 | 1.2.3.2.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 477FS-1d | 479 | 30 November 2024 8:00 AM | 2024-12-04 17:00 | 0 | Fire | 100 | 57 | 14 | 10 | 17
479 | 1.2.3.2.6.3 | Façade & External Walls | 20 | 5 December 2024 8:00 AM | 6 January 2025 5:00 PM | 478 | 480 | 5 December 2024 8:00 AM | 2025-01-10 17:00 | 4 | Window | 100 | 26 | 30 | 99 | 52
480 | 1.2.3.2.6.4 | Windows Install | 18 | 7 January 2025 8:00 AM | 28 January 2025 5:00 PM | 479 | 481 | 7 January 2025 8:00 AM | - | 0 | Painter | 95 | 46 | 22 | 90 | 44
481 | 1.2.3.2.6.5 | Level 6 Weathertight | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 480 | 1719FS-6d,482 | 28 January 2025 5:00 PM | - | 0 | Excavation | 0 | 63 | 14 | 80 | 9
482 | 1.2.3.2.6.6 | Building B Façade Complete | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 481 | 6 | 28 January 2025 5:00 PM | - | 0 | Landscaper | 0 | 59 | 23 | 12 | 56
483 | 1.2.3.3 | Building C | 63 | 27 November 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | - | 0 | Formworker | 50 | 52 | 24 | 76 | 2
484 | 1.2.3.3.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | - | 0 | Site Manager | 75 | 51 | 22 | 13 | 7
485 | 1.2.3.3.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 486 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Timber Floorer | 100 | 30 | 24 | 84 | 51
486 | 1.2.3.3.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 485 | 487 | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Timber Floorer | 100 | 68 | 32 | 57 | 34
487 | 1.2.3.3.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 486 | 488 | 4 December 2024 8:00 AM | 2025-01-06 17:00 | 2 | Joiner | 100 | 75 | 21 | 52 | 7
488 | 1.2.3.3.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 487 |  | 6 January 2025 8:00 AM | 2025-02-01 17:00 | 5 | Floor Sealer | 95 | 27 | 21 | 33 | 29
489 | 1.2.3.3.2 | Lvl 2 | 44 | 16 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | 16 December 2024 8:00 AM | - | 0 | Project Manager | 50 | 40 | 22 | 72 | 57
490 | 1.2.3.3.2.1 | Survey & Setout | 1 | 16 December 2024 8:00 AM | 16 December 2024 5:00 PM | 331 | 491 | 16 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Hoarding | 100 | 46 | 20 | 49 | 11
491 | 1.2.3.3.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 17 December 2024 8:00 AM | 21 December 2024 5:00 PM | 490 | 492 | 17 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Electrician | 100 | 55 | 31 | 23 | 14
492 | 1.2.3.3.2.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 491 | 493 | 23 December 2024 8:00 AM | 2025-01-26 17:00 | 3 | Tiler | 100 | 49 | 27 | 33 | 47
493 | 1.2.3.3.2.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 492 |  | 24 January 2025 8:00 AM | - | 0 | Window | 50 | 35 | 35 | 100 | 52
494 | 1.2.3.3.3 | Lvl 3 | 42 | 21 December 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | 21 December 2024 8:00 AM | - | 0 | Waterproofer | 50 | 66 | 14 | 80 | 32
495 | 1.2.3.3.3.1 | Survey & Setout | 1 | 21 December 2024 8:00 AM | 21 December 2024 5:00 PM | 343 | 496FS-1d | 21 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Excavation | 100 | 50 | 14 | 72 | 14
496 | 1.2.3.3.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 21 December 2024 8:00 AM | 3 January 2025 5:00 PM | 495FS-1d | 497 | 21 December 2024 8:00 AM | 2025-01-03 17:00 | 0 | Stone Mason | 100 | 90 | 22 | 53 | 3
497 | 1.2.3.3.3.3 | Façade & External Walls | 20 | 4 January 2025 8:00 AM | 28 January 2025 5:00 PM | 496 | 498 | 4 January 2025 8:00 AM | 2025-01-30 17:00 | 2 | Waterproofer | 95 | 12 | 29 | 40 | 4
498 | 1.2.3.3.3.4 | Windows Install | 18 | 29 January 2025 8:00 AM | 18 February 2025 5:00 PM | 497 | 2654FS-6d | 29 January 2025 8:00 AM | - | 0 | Tiler | 25 | 82 | 24 | 98 | 38
499 | 1.2.3.3.4 | Lvl 4 | 42 | 18 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | - | 0 | Admin | 50 | 56 | 13 | 19 | 58
500 | 1.2.3.3.4.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 355 | 501FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Carpenter | 100 | 80 | 33 | 92 | 50
501 | 1.2.3.3.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 500FS-1d | 502 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Timber Floorer | 100 | 17 | 33 | 94 | 51
502 | 1.2.3.3.4.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 501 | 503 | 23 December 2024 8:00 AM | 2025-01-26 17:00 | 3 | Development Manager | 100 | 56 | 35 | 78 | 59
503 | 1.2.3.3.4.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 502 | 3151FS-6d,7 | 24 January 2025 8:00 AM | - | 0 | Cleaner | 25 | 10 | 26 | 50 | 22
504 | 1.2.3.4 | Building D | 62 | 27 November 2024 8:00 AM | 17 February 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | - | 0 | Landscaper | 50 | 67 | 12 | 11 | 54
505 | 1.2.3.4.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-01-29 17:00 | 2 | Electrician | 95 | 74 | 21 | 86 | 30
506 | 1.2.3.4.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 507 | 27 November 2024 8:00 AM | - | 0 | Mechanical | 0 | 66 | 24 | 83 | 49
507 | 1.2.3.4.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 506 | 508,3361 | 28 November 2024 8:00 AM | - | 0 | Stone Mason | 0 | 76 | 13 | 96 | 10
508 | 1.2.3.4.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 507 | 509 | 4 December 2024 8:00 AM | 2025-01-05 17:00 | 1 | Electrician | 100 | 66 | 16 | 70 | 26
509 | 1.2.3.4.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 508 |  | 6 January 2025 8:00 AM | 2025-01-30 17:00 | 3 | Tiler | 95 | 14 | 19 | 78 | 58
510 | 1.2.3.4.2 | Lvl 2 | 44 | 2 December 2024 8:00 AM | 31 January 2025 5:00 PM |  |  | 2 December 2024 8:00 AM | - | 0 | Admin | 75 | 20 | 30 | 80 | 28
511 | 1.2.3.4.2.1 | Survey & Setout | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 385 | 512 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Cleaner | 100 | 18 | 11 | 72 | 41
512 | 1.2.3.4.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 3 December 2024 8:00 AM | 7 December 2024 5:00 PM | 511 | 513,3388 | 3 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Tiler | 100 | 21 | 11 | 94 | 35
513 | 1.2.3.4.2.3 | Façade & External Walls | 20 | 9 December 2024 8:00 AM | 9 January 2025 5:00 PM | 512 | 514 | 9 December 2024 8:00 AM | 2025-01-13 17:00 | 4 | Subcontractor | 100 | 67 | 16 | 12 | 3
514 | 1.2.3.4.2.4 | Windows Install | 18 | 10 January 2025 8:00 AM | 31 January 2025 5:00 PM | 513 |  | 10 January 2025 8:00 AM | - | 0 | Mechanical | 75 | 91 | 20 | 6 | 26
515 | 1.2.3.4.3 | Lvl 3 | 37 | 4 January 2025 8:00 AM | 17 February 2025 5:00 PM |  |  | 4 January 2025 8:00 AM | - | 0 | Fire | 25 | 49 | 16 | 38 | 19
516 | 1.2.3.4.3.1 | Survey & Setout | 1 | 4 January 2025 8:00 AM | 4 January 2025 5:00 PM | 396 | 517FS-1d | 4 January 2025 8:00 AM | 2025-01-04 17:00 | 0 | Development Manager | 100 | 44 | 15 | 71 | 31
517 | 1.2.3.4.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 3 | 4 January 2025 8:00 AM | 7 January 2025 5:00 PM | 516FS-1d | 518,3415 | 4 January 2025 8:00 AM | 2025-01-07 17:00 | 0 | Hoarding | 100 | 47 | 28 | 91 | 6
518 | 1.2.3.4.3.3 | Façade & External Walls | 18 | 8 January 2025 8:00 AM | 29 January 2025 5:00 PM | 517 | 519 | 8 January 2025 8:00 AM | - | 0 | Excavation | 75 | 71 | 16 | 93 | 52
519 | 1.2.3.4.3.4 | Windows Install | 16 | 30 January 2025 8:00 AM | 17 February 2025 5:00 PM | 518 | 3421FS-6d,8 | 30 January 2025 8:00 AM | - | 0 | Carpenter | 0 | 85 | 28 | 29 | 43
520 | 1.2.4 | FIT-OUT WORKS | 185 | 13 September 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 13 September 2024 8:00 AM | - | 0 | Hoarding | 50 | 11 | 17 | 61 | 51
521 | 1.2.4.1 | Basement 2 - Services & Fitoff | 140 | 13 September 2024 8:00 AM | 7 March 2025 5:00 PM |  |  | 13 September 2024 8:00 AM | - | 0 | Landscaper | 75 | 43 | 27 | 67 | 13
522 | 1.2.4.1.1 | Services rough in | 60 | 13 September 2024 8:00 AM | 23 November 2024 5:00 PM | 107 | 523 | 13 September 2024 8:00 AM | 2024-11-23 17:00 | 0 | Plumber | 100 | 58 | 33 | 81 | 31
523 | 1.2.4.1.2 | Block walls (Metal Door Frames) | 6 | 25 November 2024 8:00 AM | 30 November 2024 5:00 PM | 522 | 524,525 | 25 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Window | 100 | 57 | 31 | 65 | 10
524 | 1.2.4.1.3 | Render works as specified | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 527 | 2 December 2024 8:00 AM | 2024-12-19 17:00 | 5 | Reinforcement Fixer | 100 | 39 | 27 | 92 | 16
525 | 1.2.4.1.4 | Carpentry fitoff | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 526 | 2 December 2024 8:00 AM | 2024-12-18 17:00 | 4 | Painter | 100 | 79 | 13 | 2 | 50
526 | 1.2.4.1.5 | Services Plant & Equipment Install | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 525 |  | 16 December 2024 8:00 AM | 2025-01-11 17:00 | 4 | Post Tension | 100 | 54 | 24 | 59 | 3
527 | 1.2.4.1.6 | Doors & Hardware | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 524 | 528 | 16 December 2024 8:00 AM | 2025-01-11 17:00 | 4 | Carpet | 100 | 34 | 34 | 93 | 12
528 | 1.2.4.1.7 | Services Fitoff | 12 | 8 January 2025 8:00 AM | 21 January 2025 5:00 PM | 527 | 529 | 8 January 2025 8:00 AM | 2025-01-25 17:00 | 4 | Carpet | 100 | 11 | 35 | 69 | 33
529 | 1.2.4.1.8 | Finishes & Painting | 12 | 22 January 2025 8:00 AM | 5 February 2025 5:00 PM | 528 | 530 | 22 January 2025 8:00 AM | - | 0 | Carpet | 25 | 81 | 23 | 76 | 58
530 | 1.2.4.1.9 | Metalwork Items | 8 | 6 February 2025 8:00 AM | 14 February 2025 5:00 PM | 529 | 531 |  | - | 0 | Carpet | 0 | 27 | 26 | 22 | 18
531 | 1.2.4.1.10 | Builders Clean | 6 | 15 February 2025 8:00 AM | 21 February 2025 5:00 PM | 530 | 532 |  | - | 0 | Painter | 0 | 61 | 20 | 60 | 9
532 | 1.2.4.1.11 | Car Park Clean, Patch and Floor Sealer | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 531 | 533 |  | - | 0 | Waterproofer | 0 | 72 | 31 | 23 | 38
533 | 1.2.4.1.12 | Line Marking | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 532 |  |  | - | 0 | Excavation | 0 | 93 | 31 | 3 | 27
534 | 1.2.4.2 | Basement 1 - Services & Fitoff | 140 | 1 October 2024 8:00 AM | 25 March 2025 5:00 PM |  |  | 1 October 2024 8:00 AM | - | 0 | Painter | 50 | 47 | 22 | 79 | 3
535 | 1.2.4.2.1 | Services rough in | 60 | 1 October 2024 8:00 AM | 11 December 2024 5:00 PM | 119 | 536 | 1 October 2024 8:00 AM | 2024-12-11 17:00 | 0 | Electrician | 100 | 89 | 18 | 24 | 34
536 | 1.2.4.2.2 | Block walls (Metal Door Frames) | 6 | 12 December 2024 8:00 AM | 18 December 2024 5:00 PM | 535 | 537,538 | 12 December 2024 8:00 AM | 2024-12-20 17:00 | 2 | Plasterboarder | 100 | 81 | 24 | 44 | 31
537 | 1.2.4.2.3 | Render works as specified | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 540 | 19 December 2024 8:00 AM | 2025-01-13 17:00 | 3 | Carpet | 100 | 40 | 20 | 22 | 15
538 | 1.2.4.2.4 | Carpentry fitoff | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 539 | 19 December 2024 8:00 AM | 2025-01-14 17:00 | 4 | Timber Floorer | 100 | 46 | 22 | 0 | 41
539 | 1.2.4.2.5 | Services Plant & Equipment Install | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 538 |  | 11 January 2025 8:00 AM | - | 0 | Subcontractor | 95 | 67 | 16 | 77 | 36
540 | 1.2.4.2.6 | Doors & Hardware | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 537 | 541 | 11 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Joiner | 100 | 83 | 32 | 11 | 27
541 | 1.2.4.2.7 | Services Fitoff | 12 | 27 January 2025 8:00 AM | 8 February 2025 5:00 PM | 540 | 542 | 27 January 2025 8:00 AM | - | 0 | Hoarding | 50 | 92 | 14 | 63 | 43
542 | 1.2.4.2.8 | Finishes & Painting | 12 | 10 February 2025 8:00 AM | 22 February 2025 5:00 PM | 541 | 543 |  | - | 0 | Head Contractor | 0 | 59 | 22 | 30 | 11
543 | 1.2.4.2.9 | Metalwork Items | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 542 | 544 |  | - | 0 | Concretor | 0 | 100 | 19 | 7 | 53
544 | 1.2.4.2.10 | Builders Clean | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 543 | 545 |  | - | 0 | Reinforcement Fixer | 0 | 99 | 33 | 94 | 29
545 | 1.2.4.2.11 | Car Park Clean, Patch and Floor Sealer | 8 | 12 March 2025 8:00 AM | 20 March 2025 5:00 PM | 544 | 546 |  | - | 0 | Concretor | 0 | 93 | 33 | 72 | 28
546 | 1.2.4.2.12 | Line Marking | 4 | 21 March 2025 8:00 AM | 25 March 2025 5:00 PM | 545 |  |  | - | 0 | Electrician | 0 | 67 | 20 | 100 | 35
547 | 1.2.4.3 | Building A | 155 | 21 October 2024 8:00 AM | 5 May 2025 5:00 PM |  | 3440 | 21 October 2024 8:00 AM | - | 0 | Tiler | 50 | 83 | 19 | 61 | 32
548 | 1.2.4.3.1 | Lvl 1 - Services & Finishes | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | - | 0 | Metal Work | 50 | 73 | 13 | 48 | 17
549 | 1.2.4.3.1.1 | Internal Works | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | - | 0 | Scaffolder | 50 | 83 | 34 | 44 | 35
550 | 1.2.4.3.1.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 150 | 551FS-2d | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Site Manager | 100 | 59 | 35 | 31 | 51
551 | 1.2.4.3.1.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 550FS-2d | 552 | 21 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Landscaper | 100 | 75 | 12 | 67 | 49
552 | 1.2.4.3.1.1.3 | Internal Wall Framing | 10 | 1 November 2024 8:00 AM | 12 November 2024 5:00 PM | 551 | 554,553 | 1 November 2024 8:00 AM | 2024-11-16 17:00 | 4 | Floor Sealer | 100 | 22 | 22 | 76 | 45
553 | 1.2.4.3.1.1.4 | Sheet one side of walls | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 556,555 | 13 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Excavation | 100 | 53 | 28 | 29 | 24
554 | 1.2.4.3.1.1.5 | Service Rough-In | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 555 | 13 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Cleaner | 100 | 47 | 28 | 97 | 26
555 | 1.2.4.3.1.1.6 | ITP for services in the walls | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 553,554 | 556,562 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Reinforcement Fixer | 100 | 73 | 29 | 73 | 42
556 | 1.2.4.3.1.1.7 | Sheet other side of walls | 8 | 25 November 2024 8:00 AM | 3 December 2024 5:00 PM | 553,555 | 557 | 25 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Stone Mason | 100 | 70 | 15 | 12 | 40
557 | 1.2.4.3.1.1.8 | Frame & Sheet Ceilings | 8 | 4 December 2024 8:00 AM | 12 December 2024 5:00 PM | 556 | 558 | 4 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Excavation | 100 | 76 | 34 | 73 | 3
558 | 1.2.4.3.1.1.9 | Sheet, Set & Sand Ceilings | 8 | 13 December 2024 8:00 AM | 21 December 2024 5:00 PM | 557,405 | 559 | 13 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Formworker | 100 | 51 | 27 | 13 | 4
559 | 1.2.4.3.1.1.10 | Paint undercoat | 4 | 23 December 2024 8:00 AM | 4 January 2025 5:00 PM | 558 | 560 | 23 December 2024 8:00 AM | 2025-01-04 17:00 | 0 | Window | 100 | 84 | 27 | 82 | 10
560 | 1.2.4.3.1.1.11 | Floor Levelling and Floor Finish | 6 | 6 January 2025 8:00 AM | 11 January 2025 5:00 PM | 559 | 561 | 6 January 2025 8:00 AM | 2025-01-14 17:00 | 3 | Hoarding | 100 | 51 | 20 | 38 | 39
561 | 1.2.4.3.1.1.12 | Timber Flooring | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 560 | 567,568,563 | 13 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Line Market | 100 | 81 | 24 | 88 | 18
562 | 1.2.4.3.1.1.13 | Measure & Manufacture Joinery | 40 | 25 November 2024 8:00 AM | 18 January 2025 5:00 PM | 555 | 563 | 25 November 2024 8:00 AM | 2025-01-21 17:00 | 3 | Mechanical | 100 | 57 | 17 | 8 | 20
563 | 1.2.4.3.1.1.14 | Install Joinery | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 561,562 | 565 | 22 January 2025 8:00 AM | - | 0 | Cleaner | 50 | 91 | 27 | 64 | 6
564 | 1.2.4.3.1.1.15 | Measure & Manufacture Stone Benchtops | 12 | 17 January 2025 8:00 AM | 1 February 2025 8:00 AM | 565SF |  | 17 January 2025 8:00 AM | - | 0 | Project Manager | 50 | 59 | 16 | 15 | 52
565 | 1.2.4.3.1.1.16 | Install Stone Benchtops | 5 | 1 February 2025 8:00 AM | 6 February 2025 5:00 PM | 563 | 564SF,566 |  | - | 0 | Contract Administrator | 0 | 43 | 30 | 30 | 29
566 | 1.2.4.3.1.1.17 | Fixtures & Fittings Fit-off | 3 | 7 February 2025 8:00 AM | 10 February 2025 5:00 PM | 565 | 574 |  | - | 0 | Surveyor | 0 | 44 | 30 | 46 | 13
567 | 1.2.4.3.1.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 561 | 569 | 22 January 2025 8:00 AM | - | 0 | Cleaner | 95 | 83 | 15 | 32 | 27
568 | 1.2.4.3.1.1.19 | Lighting Fit-off | 3 | 22 January 2025 8:00 AM | 24 January 2025 5:00 PM | 561 | 569 | 22 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Site Manager | 100 | 35 | 23 | 18 | 57
569 | 1.2.4.3.1.1.20 | Setting Defects | 4 | 28 January 2025 8:00 AM | 31 January 2025 5:00 PM | 567,568 | 570 | 28 January 2025 8:00 AM | - | 0 | Landscaper | 75 | 90 | 31 | 80 | 7
570 | 1.2.4.3.1.1.21 | Paint Finish Coat | 4 | 1 February 2025 8:00 AM | 5 February 2025 5:00 PM | 569 | 573,571 | - | - | 0 | Development Manager | 0 | 16 | 34 | 94 | 22
571 | 1.2.4.3.1.1.22 | Carpet | 3 | 6 February 2025 8:00 AM | 8 February 2025 5:00 PM | 570 | 572 | - | - | 0 | Head Contractor | 0 | 26 | 29 | 74 | 55
572 | 1.2.4.3.1.1.23 | Final Clean & Commissioning | 4 | 10 February 2025 8:00 AM | 13 February 2025 5:00 PM | 571 |  | - | - | 0 | Cleaner | 0 | 23 | 31 | 0 | 10
573 | 1.2.4.3.1.1.24 | Defects Inspections & Rectifications | 6 | 6 February 2025 8:00 AM | 12 February 2025 5:00 PM | 570 | 574 | - | - | 0 | Carpenter | 0 | 48 | 15 | 56 | 10
574 | 1.2.4.3.1.2 | LVL 1 - FITOUT COMPLETE | 0 | 12 February 2025 5:00 PM | 12 February 2025 5:00 PM | 566,573 |  | - | - | 0 | Project Manager | 0 | 40 | 22 | 65 | 37
575 | 1.2.4.3.2 | Lvl 2 - Services & Finishes | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | - | - | 0 | Window | 0 | 18 | 28 | 79 | 12
576 | 1.2.4.3.2.1 | Internal Works | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | - | - | 0 | Plumber | 0 | 27 | 19 | 42 | 60
577 | 1.2.4.3.2.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 408,150 | 578FS-2d | - | - | 0 | Fire | 0 | 67 | 20 | 94 | 20
578 | 1.2.4.3.2.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 577FS-2d | 579 | - | - | 0 | Hoarding | 0 | 31 | 14 | 67 | 34
579 | 1.2.4.3.2.1.3 | Internal Wall Framing | 8 | 1 November 2024 8:00 AM | 9 November 2024 5:00 PM | 578 | 581,580 | - | - | 0 | Carpet | 0 | 79 | 19 | 63 | 33
580 | 1.2.4.3.2.1.4 | Sheet one side of walls | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 583,582 | - | - | 0 | Contract Administrator | 0 | 91 | 30 | 89 | 25
581 | 1.2.4.3.2.1.5 | Service Rough-In | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 582 | - | - | 0 | Carpenter | 0 | 73 | 12 | 13 | 40
582 | 1.2.4.3.2.1.6 | ITP for services in the walls | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 580,581 | 583,589 | - | - | 0 | Mechanical | 0 | 66 | 22 | 30 | 39
583 | 1.2.4.3.2.1.7 | Sheet other side of walls | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 580,582 | 584 | - | - | 0 | Contract Administrator | 0 | 66 | 34 | 18 | 45
584 | 1.2.4.3.2.1.8 | Frame & Sheet Ceilings | 8 | 2 December 2024 8:00 AM | 10 December 2024 5:00 PM | 583 | 585 | - | - | 0 | Head Contractor | 0 | 80 | 23 | 70 | 7
585 | 1.2.4.3.2.1.9 | Sheet, Set & Sand Ceilings | 8 | 11 December 2024 8:00 AM | 19 December 2024 5:00 PM | 584,411 | 586 | - | - | 0 | Line Market | 0 | 61 | 18 | 62 | 31
586 | 1.2.4.3.2.1.10 | Paint undercoat | 4 | 20 December 2024 8:00 AM | 24 December 2024 5:00 PM | 585 | 587 | - | - | 0 | Foreman | 0 | 80 | 12 | 26 | 8
587 | 1.2.4.3.2.1.11 | Floor Levelling and Floor Finish | 6 | 3 January 2025 8:00 AM | 9 January 2025 5:00 PM | 586 | 588 | - | - | 0 | Concretor | 0 | 72 | 30 | 38 | 38
588 | 1.2.4.3.2.1.12 | Timber Flooring | 6 | 10 January 2025 8:00 AM | 16 January 2025 5:00 PM | 587 | 594,595,590 | - | - | 0 | Head Contractor | 0 | 44 | 32 | 67 | 10
589 | 1.2.4.3.2.1.13 | Measure & Manufacture Joinery | 40 | 22 November 2024 8:00 AM | 16 January 2025 5:00 PM | 582 | 590 | - | - | 0 | Hoarding | 0 | 44 | 10 | 45 | 49
590 | 1.2.4.3.2.1.14 | Install Joinery | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 588,589 | 592 | - | - | 0 | Plumber | 0 | 25 | 29 | 85 | 19
591 | 1.2.4.3.2.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 January 2025 8:00 AM | 28 January 2025 8:00 AM | 592SF |  | - | - | 0 | Metal Work | 0 | 66 | 24 | 95 | 25
592 | 1.2.4.3.2.1.16 | Install Stone Benchtops | 5 | 28 January 2025 8:00 AM | 1 February 2025 5:00 PM | 590 | 591SF,593 | - | - | 0 | Concretor | 0 | 36 | 11 | 73 | 44
593 | 1.2.4.3.2.1.17 | Fixtures & Fittings Fit-off | 3 | 3 February 2025 8:00 AM | 5 February 2025 5:00 PM | 592 | 601 | - | - | 0 | Plumber | 0 | 59 | 22 | 44 | 18
594 | 1.2.4.3.2.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 17 January 2025 8:00 AM | 21 January 2025 5:00 PM | 588 | 596 | - | - | 0 | Formworker | 0 | 36 | 13 | 27 | 48
595 | 1.2.4.3.2.1.19 | Lighting Fit-off | 3 | 17 January 2025 8:00 AM | 20 January 2025 5:00 PM | 588 | 596 | - | - | 0 | Painter | 0 | 96 | 15 | 29 | 31
596 | 1.2.4.3.2.1.20 | Setting Defects | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 594,595 | 597 | - | - | 0 | Formworker | 0 | 33 | 33 | 86 | 9
597 | 1.2.4.3.2.1.21 | Paint Finish Coat | 3 | 28 January 2025 8:00 AM | 30 January 2025 5:00 PM | 596 | 600,598 | - | - | 0 | Electrician | 0 | 40 | 19 | 61 | 5
598 | 1.2.4.3.2.1.22 | Carpet | 2 | 31 January 2025 8:00 AM | 1 February 2025 5:00 PM | 597 | 599 | - | - | 0 | Post Tension | 0 | 58 | 20 | 17 | 47
599 | 1.2.4.3.2.1.23 | Final Clean & Commissioning | 4 | 3 February 2025 8:00 AM | 6 February 2025 5:00 PM | 598 |  | - | - | 0 | Waterproofer | 0 | 27 | 32 | 89 | 27
600 | 1.2.4.3.2.1.24 | Defects Inspections & Rectifications | 6 | 31 January 2025 8:00 AM | 6 February 2025 5:00 PM | 597 | 601 | - | - | 0 | Plasterboarder | 0 | 75 | 21 | 82 | 32
601 | 1.2.4.3.2.2 | LVL 2 - FITOUT COMPLETE | 0 | 6 February 2025 5:00 PM | 6 February 2025 5:00 PM | 593,600 |  | - | - | 0 | Carpenter | 0 | 92 | 34 | 14 | 53
602 | 1.2.4.3.3 | Lvl 3 - Services & Finishes | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | - | - | 0 | Scaffolder | 0 | 92 | 27 | 92 | 7
603 | 1.2.4.3.3.1 | Internal Works | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | - | - | 0 | Foreman | 0 | 24 | 27 | 76 | 22
604 | 1.2.4.3.3.1.1 | Pre-load Levels | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 174 | 605FS-2d | - | - | 0 | Carpenter | 0 | 70 | 21 | 11 | 60
605 | 1.2.4.3.3.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 25 November 2024 8:00 AM | 5 December 2024 5:00 PM | 604FS-2d | 606 | - | - | 0 | Stone Mason | 0 | 36 | 27 | 51 | 47
606 | 1.2.4.3.3.1.3 | Internal Wall Framing | 8 | 6 December 2024 8:00 AM | 14 December 2024 5:00 PM | 605 | 608,607 | - | - | 0 | Surveyor | 0 | 28 | 30 | 2 | 15
607 | 1.2.4.3.3.1.4 | Sheet one side of walls | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 610,609 | - | - | 0 | Renderer | 0 | 59 | 19 | 60 | 60
608 | 1.2.4.3.3.1.5 | Service Rough-In | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 609 | - | - | 0 | Carpet | 0 | 82 | 14 | 10 | 17
609 | 1.2.4.3.3.1.6 | ITP for services in the walls | 2 | 3 January 2025 8:00 AM | 4 January 2025 5:00 PM | 607,608 | 610,616 | - | - | 0 | Subcontractor | 0 | 85 | 15 | 41 | 46
610 | 1.2.4.3.3.1.7 | Sheet other side of walls | 8 | 6 January 2025 8:00 AM | 14 January 2025 5:00 PM | 607,609,416FS-6d | 611 | - | - | 0 | Fire | 0 | 97 | 19 | 28 | 22
611 | 1.2.4.3.3.1.8 | Frame & Sheet Ceilings | 8 | 15 January 2025 8:00 AM | 23 January 2025 5:00 PM | 610 | 612 | - | - | 0 | Reinforcement Fixer | 0 | 91 | 29 | 19 | 19
612 | 1.2.4.3.3.1.9 | Sheet, Set & Sand Ceilings | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 611,417 | 613 | - | - | 0 | Fire | 0 | 38 | 26 | 2 | 39
613 | 1.2.4.3.3.1.10 | Paint undercoat | 4 | 4 February 2025 8:00 AM | 7 February 2025 5:00 PM | 612 | 614 | - | - | 0 | Mechanical | 0 | 94 | 13 | 3 | 59
614 | 1.2.4.3.3.1.11 | Floor Levelling and Floor Finish | 7 | 8 February 2025 8:00 AM | 15 February 2025 5:00 PM | 613 | 615 | - | - | 0 | Surveyor | 0 | 80 | 34 | 75 | 48
615 | 1.2.4.3.3.1.12 | Timber Flooring | 6 | 17 February 2025 8:00 AM | 22 February 2025 5:00 PM | 614 | 621,622,617 | - | - | 0 | Plasterboarder | 0 | 63 | 24 | 42 | 51
616 | 1.2.4.3.3.1.13 | Measure & Manufacture Joinery | 40 | 6 January 2025 8:00 AM | 21 February 2025 5:00 PM | 609 | 617 | - | - | 0 | Metal Work | 0 | 91 | 11 | 40 | 36
617 | 1.2.4.3.3.1.14 | Install Joinery | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 615,616 | 619 | - | - | 0 | Renderer | 0 | 15 | 32 | 55 | 14
618 | 1.2.4.3.3.1.15 | Measure & Manufacture Stone Benchtops | 12 | 19 February 2025 8:00 AM | 5 March 2025 8:00 AM | 619SF |  | - | - | 0 | Carpet | 0 | 77 | 34 | 38 | 29
619 | 1.2.4.3.3.1.16 | Install Stone Benchtops | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 617 | 618SF,620 | - | - | 0 | Tiler | 0 | 99 | 31 | 51 | 44
620 | 1.2.4.3.3.1.17 | Fixtures & Fittings Fit-off | 3 | 12 March 2025 8:00 AM | 14 March 2025 5:00 PM | 619 | 628 | - | - | 0 | Foreman | 0 | 10 | 28 | 2 | 14
621 | 1.2.4.3.3.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 24 February 2025 8:00 AM | 27 February 2025 5:00 PM | 615 | 623 | - | - | 0 | Head Contractor | 0 | 15 | 16 | 80 | 23
622 | 1.2.4.3.3.1.19 | Lighting Fit-off | 3 | 24 February 2025 8:00 AM | 26 February 2025 5:00 PM | 615 | 623 | - | - | 0 | Formworker | 0 | 43 | 34 | 89 | 35
623 | 1.2.4.3.3.1.20 | Setting Defects | 4 | 28 February 2025 8:00 AM | 4 March 2025 5:00 PM | 621,622 | 624 | - | - | 0 | Concretor | 0 | 43 | 16 | 75 | 19
624 | 1.2.4.3.3.1.21 | Paint Finish Coat | 3 | 5 March 2025 8:00 AM | 7 March 2025 5:00 PM | 623 | 627,625 | - | - | 0 | Plasterboarder | 0 | 68 | 30 | 22 | 46
625 | 1.2.4.3.3.1.22 | Carpet | 2 | 8 March 2025 8:00 AM | 10 March 2025 5:00 PM | 624 | 626 | - | - | 0 | Plumber | 0 | 29 | 21 | 10 | 52
626 | 1.2.4.3.3.1.23 | Final Clean & Commissioning | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 625 |  | - | - | 0 | Hoarding | 0 | 50 | 11 | 93 | 48
627 | 1.2.4.3.3.1.24 | Defects Inspections & Rectifications | 8 | 8 March 2025 8:00 AM | 17 March 2025 5:00 PM | 624 | 628 | - | - | 0 | Head Contractor | 0 | 40 | 10 | 75 | 23
628 | 1.2.4.3.3.2 | LVL 3 - FITOUT COMPLETE | 0 | 17 March 2025 5:00 PM | 17 March 2025 5:00 PM | 620,627 | 753 | - | - | 0 | Project Manager | 0 | 24 | 13 | 28 | 40
629 | 1.2.4.3.4 | Lvl 4 - Services & Finishes | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 14 | 34 | 100 | 22
630 | 1.2.4.3.4.1 | Internal Works | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 82 | 18 | 41 | 26
631 | 1.2.4.3.4.1.1 | Pre-load Levels | 2 | 11 December 2024 8:00 AM | 12 December 2024 5:00 PM | 186 | 632FS-2d | - | - | 0 | Tiler | 0 | 13 | 31 | 12 | 31
632 | 1.2.4.3.4.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 11 December 2024 8:00 AM | 21 December 2024 5:00 PM | 631FS-2d | 633 | - | - | 0 | Renderer | 0 | 31 | 21 | 15 | 12
633 | 1.2.4.3.4.1.3 | Internal Wall Framing | 8 | 23 December 2024 8:00 AM | 9 January 2025 5:00 PM | 632 | 635,634 | - | - | 0 | Waterproofer | 0 | 64 | 33 | 14 | 24
634 | 1.2.4.3.4.1.4 | Sheet one side of walls | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 637,636 | - | - | 0 | Reinforcement Fixer | 0 | 98 | 18 | 56 | 44
635 | 1.2.4.3.4.1.5 | Service Rough-In | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 636 | - | - | 0 | Development Manager | 0 | 20 | 10 | 7 | 17
636 | 1.2.4.3.4.1.6 | ITP for services in the walls | 2 | 20 January 2025 8:00 AM | 21 January 2025 5:00 PM | 634,635 | 637,643 | - | - | 0 | Renderer | 0 | 23 | 28 | 56 | 25
637 | 1.2.4.3.4.1.7 | Sheet other side of walls | 8 | 10 February 2025 8:00 AM | 18 February 2025 5:00 PM | 634,636,422FS-6d | 638 | - | - | 0 | Concretor | 0 | 100 | 22 | 22 | 51
638 | 1.2.4.3.4.1.8 | Frame & Sheet Ceilings | 8 | 19 February 2025 8:00 AM | 27 February 2025 5:00 PM | 637 | 639 | - | - | 0 | Carpenter | 0 | 79 | 12 | 63 | 20
639 | 1.2.4.3.4.1.9 | Sheet, Set & Sand Ceilings | 8 | 28 February 2025 8:00 AM | 8 March 2025 5:00 PM | 638,423 | 640 | - | - | 0 | Timber Floorer | 0 | 25 | 16 | 9 | 38
640 | 1.2.4.3.4.1.10 | Paint undercoat | 4 | 10 March 2025 8:00 AM | 13 March 2025 5:00 PM | 639 | 641 | - | - | 0 | Tiler | 0 | 34 | 26 | 56 | 52
641 | 1.2.4.3.4.1.11 | Floor Levelling and Floor Finish | 6 | 14 March 2025 8:00 AM | 20 March 2025 5:00 PM | 640 | 642 | - | - | 0 | Post Tension | 0 | 70 | 28 | 21 | 49
642 | 1.2.4.3.4.1.12 | Timber Flooring | 6 | 21 March 2025 8:00 AM | 27 March 2025 5:00 PM | 641 | 648,649,644 | - | - | 0 | Electrician | 0 | 27 | 20 | 3 | 14
643 | 1.2.4.3.4.1.13 | Measure & Manufacture Joinery | 40 | 22 January 2025 8:00 AM | 10 March 2025 5:00 PM | 636 | 644 | - | - | 0 | Carpet | 0 | 26 | 30 | 28 | 29
644 | 1.2.4.3.4.1.14 | Install Joinery | 8 | 28 March 2025 8:00 AM | 5 April 2025 5:00 PM | 642,643 | 646 | - | - | 0 | Mechanical | 0 | 49 | 31 | 60 | 48
645 | 1.2.4.3.4.1.15 | Measure & Manufacture Stone Benchtops | 12 | 24 March 2025 8:00 AM | 7 April 2025 8:00 AM | 646SF |  | - | - | 0 | Development Manager | 0 | 17 | 34 | 30 | 47
646 | 1.2.4.3.4.1.16 | Install Stone Benchtops | 6 | 7 April 2025 8:00 AM | 12 April 2025 5:00 PM | 644 | 645SF,647 | - | - | 0 | Fire | 0 | 26 | 31 | 58 | 39
647 | 1.2.4.3.4.1.17 | Fixtures & Fittings Fit-off | 3 | 14 April 2025 8:00 AM | 16 April 2025 5:00 PM | 646 | 655 | - | - | 0 | Plumber | 0 | 55 | 19 | 34 | 25
648 | 1.2.4.3.4.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 28 March 2025 8:00 AM | 1 April 2025 5:00 PM | 642 | 650 | - | - | 0 | Metal Work | 0 | 59 | 17 | 67 | 54
649 | 1.2.4.3.4.1.19 | Lighting Fit-off | 3 | 28 March 2025 8:00 AM | 31 March 2025 5:00 PM | 642 | 650 | - | - | 0 | Electrician | 0 | 42 | 11 | 43 | 46
650 | 1.2.4.3.4.1.20 | Setting Defects | 4 | 2 April 2025 8:00 AM | 5 April 2025 5:00 PM | 648,649 | 651 | - | - | 0 | Plasterboarder | 0 | 19 | 28 | 75 | 54
651 | 1.2.4.3.4.1.21 | Paint Finish Coat | 3 | 7 April 2025 8:00 AM | 9 April 2025 5:00 PM | 650 | 654,652 | - | - | 0 | Subcontractor | 0 | 65 | 26 | 87 | 54
652 | 1.2.4.3.4.1.22 | Carpet | 2 | 10 April 2025 8:00 AM | 11 April 2025 5:00 PM | 651 | 653 | - | - | 0 | Cleaner | 0 | 77 | 11 | 66 | 5
653 | 1.2.4.3.4.1.23 | Final Clean & Commissioning | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 652 |  | - | - | 0 | Metal Work | 0 | 92 | 31 | 33 | 43
654 | 1.2.4.3.4.1.24 | Defects Inspections & Rectifications | 8 | 10 April 2025 8:00 AM | 22 April 2025 5:00 PM | 651 | 655 | - | - | 0 | Concretor | 0 | 68 | 19 | 96 | 23
655 | 1.2.4.3.4.2 | LVL 4 - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 647,654 | 753 | - | - | 0 | Timber Floorer | 0 | 13 | 30 | 94 | 45
656 | 1.2.4.3.5 | Lvl 5 - Services & Finishes | 100 | 12 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | - | - | 0 | Development Manager | 0 | 70 | 19 | 59 | 10
657 | 1.2.4.3.5.1 | Survey & Setout | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 289,198 | 658FS-1d | - | - | 0 | Landscaper | 0 | 95 | 16 | 42 | 25
658 | 1.2.4.3.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 657FS-1d | 660,663 | - | - | 0 | Scaffolder | 0 | 57 | 13 | 46 | 39
659 | 1.2.4.3.5.3 | External Works | 34 | 17 December 2024 8:00 AM | 4 February 2025 5:00 PM |  |  | - | - | 0 | Project Manager | 0 | 45 | 13 | 9 | 23
660 | 1.2.4.3.5.3.1 | Façade & External Walls | 18 | 17 December 2024 8:00 AM | 15 January 2025 5:00 PM | 658 | 661 | - | - | 0 | Electrician | 0 | 89 | 18 | 89 | 35
661 | 1.2.4.3.5.3.2 | Windows Install | 16 | 16 January 2025 8:00 AM | 4 February 2025 5:00 PM | 660 | 669FS-6d | - | - | 0 | Surveyor | 0 | 91 | 24 | 92 | 50
662 | 1.2.4.3.5.4 | Internal Works | 91 | 23 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | - | - | 0 | Painter | 0 | 10 | 26 | 28 | 39
663 | 1.2.4.3.5.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 658,426 | 664FS-2d | - | - | 0 | Project Manager | 0 | 25 | 25 | 33 | 17
664 | 1.2.4.3.5.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 663FS-2d | 665 | - | - | 0 | Joiner | 0 | 95 | 23 | 52 | 17
665 | 1.2.4.3.5.4.3 | Internal Wall Framing | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 664 | 667,666 | - | - | 0 | Mechanical | 0 | 25 | 17 | 54 | 3
666 | 1.2.4.3.5.4.4 | Sheet one side of walls | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 669,668 | - | - | 0 | Window | 0 | 48 | 33 | 18 | 58
667 | 1.2.4.3.5.4.5 | Service Rough-In | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 668 | - | - | 0 | Landscaper | 0 | 26 | 20 | 86 | 54
668 | 1.2.4.3.5.4.6 | ITP for services in the walls | 2 | 1 February 2025 8:00 AM | 3 February 2025 5:00 PM | 666,667 | 669,675 | - | - | 0 | Cleaner | 0 | 32 | 24 | 85 | 55
669 | 1.2.4.3.5.4.7 | Sheet other side of walls | 8 | 4 February 2025 8:00 AM | 12 February 2025 5:00 PM | 661FS-6d,666,668,428FS-6d | 670 | - | - | 0 | Stone Mason | 0 | 98 | 28 | 22 | 31
670 | 1.2.4.3.5.4.8 | Frame & Sheet Ceilings | 8 | 13 February 2025 8:00 AM | 21 February 2025 5:00 PM | 669 | 671 | - | - | 0 | Hoarding | 0 | 72 | 33 | 21 | 18
671 | 1.2.4.3.5.4.9 | Sheet, Set & Sand Ceilings | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 670,429 | 672 | - | - | 0 | Waterproofer | 0 | 94 | 28 | 34 | 18
672 | 1.2.4.3.5.4.10 | Paint undercoat | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 671 | 673 | - | - | 0 | Renderer | 0 | 56 | 12 | 56 | 51
673 | 1.2.4.3.5.4.11 | Floor Levelling and Floor Finish | 6 | 8 March 2025 8:00 AM | 14 March 2025 5:00 PM | 672 | 674 | - | - | 0 | Excavation | 0 | 36 | 22 | 100 | 60
674 | 1.2.4.3.5.4.12 | Timber Flooring | 6 | 15 March 2025 8:00 AM | 21 March 2025 5:00 PM | 673 | 680,681,676 | - | - | 0 | Plumber | 0 | 72 | 35 | 60 | 40
675 | 1.2.4.3.5.4.13 | Measure & Manufacture Joinery | 40 | 4 February 2025 8:00 AM | 21 March 2025 5:00 PM | 668 | 676 | - | - | 0 | Window | 0 | 27 | 15 | 20 | 5
676 | 1.2.4.3.5.4.14 | Install Joinery | 8 | 22 March 2025 8:00 AM | 31 March 2025 5:00 PM | 674,675 | 678 | - | - | 0 | Site Manager | 0 | 93 | 10 | 6 | 26
677 | 1.2.4.3.5.4.15 | Measure & Manufacture Stone Benchtops | 15 | 14 March 2025 8:00 AM | 1 April 2025 8:00 AM | 678SF | 687 | - | - | 0 | Foreman | 0 | 22 | 28 | 88 | 43
678 | 1.2.4.3.5.4.16 | Install Stone Benchtops | 6 | 1 April 2025 8:00 AM | 7 April 2025 5:00 PM | 676 | 677SF,679 | - | - | 0 | Scaffolder | 0 | 77 | 11 | 97 | 41
679 | 1.2.4.3.5.4.17 | Fixtures & Fittings Fit-off | 8 | 8 April 2025 8:00 AM | 16 April 2025 5:00 PM | 678 | 687 | - | - | 0 | Head Contractor | 0 | 20 | 32 | 99 | 3
680 | 1.2.4.3.5.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 674 | 682 | - | - | 0 | Waterproofer | 0 | 93 | 21 | 9 | 37
681 | 1.2.4.3.5.4.19 | Lighting Fit-off | 3 | 22 March 2025 8:00 AM | 25 March 2025 5:00 PM | 674 | 682 | - | - | 0 | Contract Administrator | 0 | 26 | 19 | 42 | 28
682 | 1.2.4.3.5.4.20 | Setting Defects | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 680,681 | 683 | - | - | 0 | Tiler | 0 | 60 | 32 | 59 | 17
683 | 1.2.4.3.5.4.21 | Paint Finish Coat | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 682 | 686,684 | - | - | 0 | Painter | 0 | 58 | 24 | 14 | 36
684 | 1.2.4.3.5.4.22 | Carpet | 2 | 4 April 2025 8:00 AM | 5 April 2025 5:00 PM | 683 | 685 | - | - | 0 | Head Contractor | 0 | 51 | 13 | 28 | 38
685 | 1.2.4.3.5.4.23 | Final Clean & Commissioning | 10 | 7 April 2025 8:00 AM | 17 April 2025 5:00 PM | 684 | 687 | - | - | 0 | Plasterboarder | 0 | 76 | 32 | 42 | 13
686 | 1.2.4.3.5.4.24 | Defects Inspections & Rectifications | 8 | 4 April 2025 8:00 AM | 12 April 2025 5:00 PM | 683 | 687 | - | - | 0 | Waterproofer | 0 | 12 | 34 | 47 | 13
687 | 1.2.4.3.5.5 | LVL 5 - FITOUT COMPLETE | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 679,686,685,677 |  | - | - | 0 | Site Manager | 0 | 58 | 34 | 96 | 20
688 | 1.2.4.3.6 | Lvl 6 - Services & Finishes | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 75 | 26 | 38 | 12
689 | 1.2.4.3.6.1 | Internal Works | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | - | - | 0 | Excavation | 0 | 50 | 11 | 43 | 24
690 | 1.2.4.3.6.1.1 | Pre-load Levels | 2 | 18 December 2024 8:00 AM | 19 December 2024 5:00 PM | 432,210 | 691FS-2d | - | - | 0 | Project Manager | 0 | 11 | 11 | 31 | 44
691 | 1.2.4.3.6.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 18 December 2024 8:00 AM | 7 January 2025 5:00 PM | 690FS-2d | 692 | - | - | 0 | Carpet | 0 | 59 | 20 | 63 | 37
692 | 1.2.4.3.6.1.3 | Internal Wall Framing | 8 | 8 January 2025 8:00 AM | 16 January 2025 5:00 PM | 691 | 694,693 | - | - | 0 | Plumber | 0 | 67 | 29 | 3 | 59
693 | 1.2.4.3.6.1.4 | Sheet one side of walls | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 696,695 | - | - | 0 | Subcontractor | 0 | 17 | 16 | 36 | 24
694 | 1.2.4.3.6.1.5 | Service Rough-In | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 695 | - | - | 0 | Waterproofer | 0 | 56 | 33 | 28 | 49
695 | 1.2.4.3.6.1.6 | ITP for services in the walls | 2 | 28 January 2025 8:00 AM | 29 January 2025 5:00 PM | 693,694 | 696,702 | - | - | 0 | Foreman | 0 | 82 | 22 | 59 | 46
696 | 1.2.4.3.6.1.7 | Sheet other side of walls | 8 | 30 January 2025 8:00 AM | 7 February 2025 5:00 PM | 693,695,434FS-6d | 697 | - | - | 0 | Subcontractor | 0 | 39 | 13 | 97 | 6
697 | 1.2.4.3.6.1.8 | Frame & Sheet Ceilings | 8 | 8 February 2025 8:00 AM | 17 February 2025 5:00 PM | 696 | 698 | - | - | 0 | Scaffolder | 0 | 33 | 20 | 78 | 15
698 | 1.2.4.3.6.1.9 | Sheet, Set & Sand Ceilings | 8 | 18 February 2025 8:00 AM | 26 February 2025 5:00 PM | 697,435 | 699 | - | - | 0 | Stone Mason | 0 | 59 | 16 | 74 | 48
699 | 1.2.4.3.6.1.10 | Paint undercoat | 4 | 27 February 2025 8:00 AM | 3 March 2025 5:00 PM | 698 | 700 | - | - | 0 | Floor Sealer | 0 | 86 | 17 | 47 | 59
700 | 1.2.4.3.6.1.11 | Floor Levelling and Floor Finish | 6 | 4 March 2025 8:00 AM | 10 March 2025 5:00 PM | 699 | 701 | - | - | 0 | Renderer | 0 | 86 | 20 | 62 | 39
701 | 1.2.4.3.6.1.12 | Timber Flooring | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 700 | 707,708,703 | - | - | 0 | Carpet | 0 | 18 | 30 | 38 | 34
702 | 1.2.4.3.6.1.13 | Measure & Manufacture Joinery | 40 | 30 January 2025 8:00 AM | 17 March 2025 5:00 PM | 695 | 703 | - | - | 0 | Project Manager | 0 | 17 | 30 | 51 | 11
703 | 1.2.4.3.6.1.14 | Install Joinery | 8 | 18 March 2025 8:00 AM | 26 March 2025 5:00 PM | 701,702 | 705 | - | - | 0 | Metal Work | 0 | 22 | 25 | 29 | 58
704 | 1.2.4.3.6.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 March 2025 8:00 AM | 27 March 2025 8:00 AM | 705SF |  | - | - | 0 | Reinforcement Fixer | 0 | 49 | 18 | 92 | 14
705 | 1.2.4.3.6.1.16 | Install Stone Benchtops | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 703 | 704SF,706 | - | - | 0 | Metal Work | 0 | 35 | 13 | 97 | 55
706 | 1.2.4.3.6.1.17 | Fixtures & Fittings Fit-off | 7 | 3 April 2025 8:00 AM | 10 April 2025 5:00 PM | 705 | 714 | - | - | 0 | Formworker | 0 | 18 | 26 | 72 | 56
707 | 1.2.4.3.6.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 18 March 2025 8:00 AM | 21 March 2025 5:00 PM | 701 | 709 | - | - | 0 | Post Tension | 0 | 49 | 24 | 9 | 8
708 | 1.2.4.3.6.1.19 | Lighting Fit-off | 3 | 18 March 2025 8:00 AM | 20 March 2025 5:00 PM | 701 | 709 | - | - | 0 | Development Manager | 0 | 63 | 24 | 48 | 24
709 | 1.2.4.3.6.1.20 | Setting Defects | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 707,708 | 710 | - | - | 0 | Waterproofer | 0 | 42 | 10 | 85 | 34
710 | 1.2.4.3.6.1.21 | Paint Finish Coat | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 709 | 713,711 | - | - | 0 | Subcontractor | 0 | 50 | 14 | 7 | 10
711 | 1.2.4.3.6.1.22 | Carpet | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 710 | 712 | - | - | 0 | Admin | 0 | 30 | 13 | 22 | 28
712 | 1.2.4.3.6.1.23 | Final Clean & Commissioning | 10 | 4 April 2025 8:00 AM | 15 April 2025 5:00 PM | 711 |  | - | - | 0 | Development Manager | 0 | 94 | 12 | 39 | 9
713 | 1.2.4.3.6.1.24 | Defects Inspections & Rectifications | 8 | 1 April 2025 8:00 AM | 9 April 2025 5:00 PM | 710 | 714 | - | - | 0 | Waterproofer | 0 | 76 | 24 | 75 | 35
714 | 1.2.4.3.6.2 | LVL 6 - FITOUT COMPLETE | 0 | 10 April 2025 5:00 PM | 10 April 2025 5:00 PM | 706,713 | 5 | - | - | 0 | Surveyor | 0 | 95 | 34 | 44 | 9
715 | 1.2.4.3.7 | Lvl 7 - Services & Finishes | 105 | 18 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | - | - | 0 | Development Manager | 0 | 69 | 33 | 76 | 3
716 | 1.2.4.3.7.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 301,223 | 717FS-1d | - | - | 0 | Window | 0 | 34 | 23 | 7 | 12
717 | 1.2.4.3.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 716FS-1d | 719,722 | - | - | 0 | Plumber | 0 | 48 | 26 | 48 | 29
718 | 1.2.4.3.7.3 | External Works | 34 | 23 December 2024 8:00 AM | 10 February 2025 5:00 PM |  |  | - | - | 0 | Site Manager | 0 | 96 | 31 | 23 | 51
719 | 1.2.4.3.7.3.1 | Façade & External Walls | 18 | 23 December 2024 8:00 AM | 21 January 2025 5:00 PM | 717 | 720 | - | - | 0 | Metal Work | 0 | 96 | 27 | 72 | 51
720 | 1.2.4.3.7.3.2 | Windows Install | 16 | 22 January 2025 8:00 AM | 10 February 2025 5:00 PM | 719 | 728FS-6d | - | - | 0 | Window | 0 | 70 | 30 | 88 | 53
721 | 1.2.4.3.7.4 | Internal Works | 101 | 23 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 32 | 14 | 26 | 58
722 | 1.2.4.3.7.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 717,438 | 723FS-2d | - | - | 0 | Reinforcement Fixer | 0 | 77 | 20 | 86 | 58
723 | 1.2.4.3.7.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 722FS-2d | 724 | - | - | 0 | Carpet | 0 | 81 | 18 | 41 | 60
724 | 1.2.4.3.7.4.3 | Internal Wall Framing | 10 | 13 January 2025 8:00 AM | 23 January 2025 5:00 PM | 723 | 726,725 | - | - | 0 | Foreman | 0 | 30 | 12 | 89 | 43
725 | 1.2.4.3.7.4.4 | Sheet one side of walls | 9 | 24 January 2025 8:00 AM | 4 February 2025 5:00 PM | 724 | 728,727 | - | - | 0 | Head Contractor | 0 | 37 | 18 | 82 | 13
726 | 1.2.4.3.7.4.5 | Service Rough-In | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 724 | 727 | - | - | 0 | Stone Mason | 0 | 50 | 24 | 18 | 56
727 | 1.2.4.3.7.4.6 | ITP for services in the walls | 2 | 5 February 2025 8:00 AM | 6 February 2025 5:00 PM | 725,726 | 728,734 | - | - | 0 | Painter | 0 | 77 | 17 | 86 | 47
728 | 1.2.4.3.7.4.7 | Sheet other side of walls | 8 | 15 February 2025 8:00 AM | 24 February 2025 5:00 PM | 720FS-6d,725,727,440FS-6d | 729 | - | - | 0 | Metal Work | 0 | 57 | 17 | 25 | 58
729 | 1.2.4.3.7.4.8 | Frame & Sheet Ceilings | 8 | 25 February 2025 8:00 AM | 5 March 2025 5:00 PM | 728 | 730 | - | - | 0 | Tiler | 0 | 50 | 19 | 25 | 51
730 | 1.2.4.3.7.4.9 | Sheet, Set & Sand Ceilings | 8 | 6 March 2025 8:00 AM | 14 March 2025 5:00 PM | 729,441 | 731 | - | - | 0 | Concretor | 0 | 91 | 33 | 1 | 57
731 | 1.2.4.3.7.4.10 | Paint undercoat | 4 | 15 March 2025 8:00 AM | 19 March 2025 5:00 PM | 730 | 732 | - | - | 0 | Tiler | 0 | 31 | 27 | 87 | 30
732 | 1.2.4.3.7.4.11 | Floor Levelling and Floor Finish | 6 | 20 March 2025 8:00 AM | 26 March 2025 5:00 PM | 731 | 733 | - | - | 0 | Stone Mason | 0 | 11 | 17 | 42 | 35
733 | 1.2.4.3.7.4.12 | Timber Flooring | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 732 | 739,740,735 | - | - | 0 | Subcontractor | 0 | 38 | 17 | 63 | 56
734 | 1.2.4.3.7.4.13 | Measure & Manufacture Joinery | 40 | 7 February 2025 8:00 AM | 25 March 2025 5:00 PM | 727 | 735 | - | - | 0 | Surveyor | 0 | 47 | 18 | 68 | 3
735 | 1.2.4.3.7.4.14 | Install Joinery | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733,734 | 737 | - | - | 0 | Metal Work | 0 | 64 | 34 | 18 | 26
736 | 1.2.4.3.7.4.15 | Measure & Manufacture Stone Benchtops | 12 | 29 March 2025 8:00 AM | 12 April 2025 8:00 AM | 737SF | 746 | - | - | 0 | Contract Administrator | 0 | 29 | 17 | 24 | 36
737 | 1.2.4.3.7.4.16 | Install Stone Benchtops | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 735 | 736SF,738 | - | - | 0 | Renderer | 0 | 98 | 34 | 94 | 13
738 | 1.2.4.3.7.4.17 | Fixtures & Fittings Fit-off | 7 | 23 April 2025 8:00 AM | 2 May 2025 5:00 PM | 737 | 746 | - | - | 0 | Foreman | 0 | 18 | 26 | 40 | 24
739 | 1.2.4.3.7.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733 | 741 | - | - | 0 | Mechanical | 0 | 32 | 34 | 96 | 55
740 | 1.2.4.3.7.4.19 | Lighting Fit-off | 5 | 3 April 2025 8:00 AM | 8 April 2025 5:00 PM | 733 | 741 | - | - | 0 | Hoarding | 0 | 41 | 27 | 65 | 20
741 | 1.2.4.3.7.4.20 | Setting Defects | 4 | 12 April 2025 8:00 AM | 16 April 2025 5:00 PM | 739,740 | 742 | - | - | 0 | Cleaner | 0 | 46 | 27 | 81 | 59
742 | 1.2.4.3.7.4.21 | Paint Finish Coat | 4 | 17 April 2025 8:00 AM | 24 April 2025 5:00 PM | 741 | 745,743 | - | - | 0 | Cleaner | 0 | 40 | 31 | 56 | 23
743 | 1.2.4.3.7.4.22 | Carpet | 3 | 28 April 2025 8:00 AM | 30 April 2025 5:00 PM | 742 | 744 | - | - | 0 | Contract Administrator | 0 | 60 | 24 | 92 | 22
744 | 1.2.4.3.7.4.23 | Final Clean & Commissioning | 4 | 1 May 2025 8:00 AM | 5 May 2025 5:00 PM | 743 | 746 | - | - | 0 | Painter | 0 | 21 | 14 | 10 | 5
745 | 1.2.4.3.7.4.24 | Defects Inspections & Rectifications | 6 | 28 April 2025 8:00 AM | 3 May 2025 5:00 PM | 742 | 746 | - | - | 0 | Window | 0 | 75 | 11 | 92 | 36
746 | 1.2.4.3.7.5 | LVL 7 - FITOUT COMPLETE | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 738,745,744,736 | 5,754 | - | - | 0 | Tiler | 0 | 91 | 16 | 37 | 46
747 | 1.2.4.3.8 | Lvl 8 (Roof) - Services | 96 | 7 January 2025 8:00 AM | 5 May 2025 5:00 PM |  |  | - | - | 0 | Concretor | 0 | 62 | 35 | 34 | 55
748 | 1.2.4.3.8.1 | Survey & Setout | 1 | 7 January 2025 8:00 AM | 7 January 2025 5:00 PM | 301FS+24d | 749FS-1d | - | - | 0 | Tiler | 0 | 41 | 11 | 98 | 58
749 | 1.2.4.3.8.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 7 January 2025 8:00 AM | 10 January 2025 5:00 PM | 748FS-1d | 751 | - | - | 0 | Plasterboarder | 0 | 65 | 17 | 27 | 3
750 | 1.2.4.3.8.3 | External Services (Plant) | 56 | 11 January 2025 8:00 AM | 18 March 2025 5:00 PM |  |  | - | - | 0 | Excavation | 0 | 60 | 26 | 27 | 19
751 | 1.2.4.3.8.3.1 | Heat Pumps & Associated Services | 32 | 11 January 2025 8:00 AM | 18 February 2025 5:00 PM | 749 | 752 | - | - | 0 | Reinforcement Fixer | 0 | 95 | 29 | 53 | 54
752 | 1.2.4.3.8.3.2 | Louvres, Balustrades & Roof Safety System | 24 | 19 February 2025 8:00 AM | 18 March 2025 5:00 PM | 751 | 753 | - | - | 0 | Subcontractor | 0 | 31 | 25 | 38 | 47
753 | 1.2.4.3.8.4 | LVL 8 (ROOF) - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 752,655,628 | 5,754 | - | - | 0 | Fire | 0 | 33 | 19 | 1 | 35
754 | 1.2.4.3.8.5 | Building A Fitout Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 753,746 |  | - | - | 0 | Head Contractor | 0 | 97 | 13 | 52 | 6
755 | 1.2.4.4 | Building B | 135 | 14 October 2024 8:00 AM | 29 March 2025 5:00 PM |  | 3440 | - | - | 0 | Stone Mason | 0 | 13 | 24 | 92 | 10
756 | 1.2.4.4.1 | Level 1 | 52 | 14 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 66 | 33 | 49 | 52
757 | 1.2.4.4.1.1 | Apartment B010 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 32 | 12 | 22 | 36
758 | 1.2.4.4.1.1.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 759,762,763,830 | - | - | 0 | Electrician | 0 | 85 | 16 | 54 | 39
759 | 1.2.4.4.1.1.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 758 | 761,760 | - | - | 0 | Painter | 0 | 87 | 11 | 1 | 41
760 | 1.2.4.4.1.1.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 759 |  | - | - | 0 | Metal Work | 0 | 92 | 18 | 75 | 46
761 | 1.2.4.4.1.1.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 759 | 764 | - | - | 0 | Project Manager | 0 | 99 | 19 | 12 | 8
762 | 1.2.4.4.1.1.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 771 | - | - | 0 | Carpenter | 0 | 22 | 27 | 2 | 16
763 | 1.2.4.4.1.1.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 834 | - | - | 0 | Development Manager | 0 | 30 | 21 | 82 | 25
764 | 1.2.4.4.1.1.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 761 | 765,766,767,768,769 | - | - | 0 | Contract Administrator | 0 | 38 | 31 | 91 | 7
765 | 1.2.4.4.1.1.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769 | - | - | 0 | Development Manager | 0 | 68 | 30 | 71 | 34
766 | 1.2.4.4.1.1.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769,833 | - | - | 0 | Timber Floorer | 0 | 18 | 29 | 92 | 18
767 | 1.2.4.4.1.1.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 832 | - | - | 0 | Foreman | 0 | 14 | 23 | 47 | 25
768 | 1.2.4.4.1.1.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 |  | - | - | 0 | Waterproofer | 0 | 27 | 21 | 49 | 51
769 | 1.2.4.4.1.1.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 764,765,766 | 770 | - | - | 0 | Timber Floorer | 0 | 78 | 23 | 87 | 16
770 | 1.2.4.4.1.1.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 769 | 771 | - | - | 0 | Tiler | 0 | 44 | 10 | 63 | 44
771 | 1.2.4.4.1.1.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 762,770 | 772,773,774,775,777,779 | - | - | 0 | Contract Administrator | 0 | 29 | 13 | 81 | 33
772 | 1.2.4.4.1.1.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 776,779 | - | - | 0 | Stone Mason | 0 | 92 | 20 | 44 | 19
773 | 1.2.4.4.1.1.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 779 | - | - | 0 | Scaffolder | 0 | 99 | 32 | 73 | 32
774 | 1.2.4.4.1.1.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 778,779 | - | - | 0 | Foreman | 0 | 65 | 11 | 81 | 18
775 | 1.2.4.4.1.1.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | - | - | 0 | Surveyor | 0 | 21 | 26 | 49 | 39
776 | 1.2.4.4.1.1.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 772 | 779 | - | - | 0 | Cleaner | 0 | 14 | 29 | 62 | 24
777 | 1.2.4.4.1.1.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | - | - | 0 | Fire | 0 | 31 | 28 | 89 | 18
778 | 1.2.4.4.1.1.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 774 | 779 | - | - | 0 | Foreman | 0 | 81 | 12 | 96 | 15
779 | 1.2.4.4.1.1.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 771,772,773,774,775,776,777,778 | 780 | - | - | 0 | Post Tension | 0 | 90 | 14 | 88 | 32
780 | 1.2.4.4.1.1.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 779 | 781 | - | - | 0 | Joiner | 0 | 38 | 24 | 55 | 48
781 | 1.2.4.4.1.1.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 780 | 782,799,816 | - | - | 0 | Floor Sealer | 0 | 22 | 30 | 15 | 33
782 | 1.2.4.4.1.1.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 783 | - | - | 0 | Waterproofer | 0 | 77 | 25 | 2 | 58
783 | 1.2.4.4.1.1.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 782 | 784 | - | - | 0 | Head Contractor | 0 | 62 | 35 | 25 | 13
784 | 1.2.4.4.1.1.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 783 | 785 | - | - | 0 | Carpet | 0 | 68 | 22 | 63 | 56
785 | 1.2.4.4.1.1.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 784 | 786 | - | - | 0 | Hoarding | 0 | 23 | 11 | 97 | 19
786 | 1.2.4.4.1.1.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 785 | 787,788 | - | - | 0 | Landscaper | 0 | 54 | 31 | 76 | 3
787 | 1.2.4.4.1.1.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 786 | 791 | - | - | 0 | Window | 0 | 81 | 20 | 66 | 18
788 | 1.2.4.4.1.1.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 786 | 789 | - | - | 0 | Metal Work | 0 | 41 | 24 | 2 | 57
789 | 1.2.4.4.1.1.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 788 | 790 | - | - | 0 | Painter | 0 | 10 | 26 | 55 | 60
790 | 1.2.4.4.1.1.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 789 |  | - | - | 0 | Development Manager | 0 | 92 | 26 | 36 | 21
791 | 1.2.4.4.1.1.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 787 | 792,793,794,795,796 | - | - | 0 | Site Manager | 0 | 46 | 15 | 77 | 46
792 | 1.2.4.4.1.1.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 791 |  | - | - | 0 | Renderer | 0 | 93 | 30 | 80 | 45
793 | 1.2.4.4.1.1.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Plumber | 0 | 71 | 24 | 58 | 5
794 | 1.2.4.4.1.1.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Floor Sealer | 0 | 100 | 23 | 41 | 4
795 | 1.2.4.4.1.1.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Waterproofer | 0 | 80 | 13 | 16 | 58
796 | 1.2.4.4.1.1.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Stone Mason | 0 | 36 | 14 | 99 | 23
797 | 1.2.4.4.1.1.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 847 | - | - | 0 | Electrician | 0 | 25 | 35 | 34 | 36
798 | 1.2.4.4.1.1.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 90 | 28 | 90 | 32
799 | 1.2.4.4.1.1.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 800 | - | - | 0 | Window | 0 | 97 | 27 | 14 | 10
800 | 1.2.4.4.1.1.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 799 | 801 | - | - | 0 | Concretor | 0 | 15 | 24 | 52 | 9
801 | 1.2.4.4.1.1.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 800 | 802 | - | - | 0 | Mechanical | 0 | 67 | 19 | 84 | 29
802 | 1.2.4.4.1.1.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 801 | 803 | - | - | 0 | Scaffolder | 0 | 13 | 27 | 48 | 47
803 | 1.2.4.4.1.1.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 802 | 804 | - | - | 0 | Excavation | 0 | 10 | 19 | 19 | 26
804 | 1.2.4.4.1.1.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 803 | 805 | - | - | 0 | Plumber | 0 | 26 | 15 | 76 | 17
805 | 1.2.4.4.1.1.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 804 | 806 | - | - | 0 | Waterproofer | 0 | 58 | 24 | 36 | 46
806 | 1.2.4.4.1.1.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 805 | 807 | - | - | 0 | Window | 0 | 35 | 20 | 92 | 7
807 | 1.2.4.4.1.1.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 806 | 808 | - | - | 0 | Tiler | 0 | 70 | 19 | 69 | 51
808 | 1.2.4.4.1.1.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 807 | 809 | - | - | 0 | Timber Floorer | 0 | 72 | 30 | 56 | 15
809 | 1.2.4.4.1.1.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 808 | 810 | - | - | 0 | Project Manager | 0 | 50 | 27 | 44 | 11
810 | 1.2.4.4.1.1.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 809 | 814,811,812,813 | - | - | 0 | Landscaper | 0 | 83 | 22 | 90 | 7
811 | 1.2.4.4.1.1.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | - | - | 0 | Plumber | 0 | 97 | 29 | 7 | 5
812 | 1.2.4.4.1.1.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | - | - | 0 | Admin | 0 | 72 | 29 | 94 | 42
813 | 1.2.4.4.1.1.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | - | - | 0 | Excavation | 0 | 40 | 15 | 83 | 22
814 | 1.2.4.4.1.1.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 810,811,812,813 |  | - | - | 0 | Hoarding | 0 | 12 | 14 | 17 | 51
815 | 1.2.4.4.1.1.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 13 | 25 | 64 | 40
816 | 1.2.4.4.1.1.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 817 | - | - | 0 | Hoarding | 0 | 31 | 19 | 79 | 54
817 | 1.2.4.4.1.1.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 816 | 818 | - | - | 0 | Development Manager | 0 | 15 | 25 | 4 | 49
818 | 1.2.4.4.1.1.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 817 | 819 | - | - | 0 | Waterproofer | 0 | 64 | 34 | 24 | 34
819 | 1.2.4.4.1.1.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 818 | 820 | - | - | 0 | Reinforcement Fixer | 0 | 55 | 22 | 68 | 14
820 | 1.2.4.4.1.1.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 819 | 821 | - | - | 0 | Window | 0 | 84 | 18 | 61 | 58
821 | 1.2.4.4.1.1.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 820 | 822 | - | - | 0 | Site Manager | 0 | 16 | 25 | 74 | 46
822 | 1.2.4.4.1.1.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 821 | 823 | - | - | 0 | Floor Sealer | 0 | 18 | 26 | 65 | 32
823 | 1.2.4.4.1.1.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 822 | 824,825,826,827 | - | - | 0 | Mechanical | 0 | 56 | 22 | 1 | 25
824 | 1.2.4.4.1.1.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Tiler | 0 | 43 | 24 | 42 | 50
825 | 1.2.4.4.1.1.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Concretor | 0 | 100 | 10 | 96 | 49
826 | 1.2.4.4.1.1.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Head Contractor | 0 | 54 | 34 | 25 | 17
827 | 1.2.4.4.1.1.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Carpenter | 0 | 92 | 27 | 75 | 43
828 | 1.2.4.4.1.1.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 824,825,826,827 |  | - | - | 0 | Cleaner | 0 | 70 | 14 | 96 | 27
829 | 1.2.4.4.1.1.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 59 | 11 | 42 | 28
830 | 1.2.4.4.1.1.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 758 | 831 | - | - | 0 | Contract Administrator | 0 | 41 | 27 | 76 | 31
831 | 1.2.4.4.1.1.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 830 |  | - | - | 0 | Site Manager | 0 | 78 | 29 | 100 | 6
832 | 1.2.4.4.1.1.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 767 | 835 | - | - | 0 | Stone Mason | 0 | 12 | 24 | 2 | 60
833 | 1.2.4.4.1.1.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 766 | 835 | - | - | 0 | Contract Administrator | 0 | 21 | 28 | 24 | 57
834 | 1.2.4.4.1.1.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 763 | 835 | - | - | 0 | Renderer | 0 | 83 | 35 | 56 | 23
835 | 1.2.4.4.1.1.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 832,833,834 | 836 | - | - | 0 | Fire | 0 | 82 | 18 | 43 | 25
836 | 1.2.4.4.1.1.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 835 | 837 | - | - | 0 | Admin | 0 | 84 | 14 | 34 | 28
837 | 1.2.4.4.1.1.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 836 | 838 | - | - | 0 | Line Market | 0 | 84 | 23 | 79 | 51
838 | 1.2.4.4.1.1.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 837 | 839 | - | - | 0 | Contract Administrator | 0 | 52 | 32 | 36 | 27
839 | 1.2.4.4.1.1.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 838 | 840 | - | - | 0 | Scaffolder | 0 | 78 | 26 | 17 | 18
840 | 1.2.4.4.1.1.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 839 | 841 | - | - | 0 | Window | 0 | 26 | 35 | 87 | 41
841 | 1.2.4.4.1.1.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 840 | 842 | - | - | 0 | Formworker | 0 | 32 | 32 | 93 | 41
842 | 1.2.4.4.1.1.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 841 | 843,844,845,846 | - | - | 0 | Renderer | 0 | 23 | 17 | 93 | 13
843 | 1.2.4.4.1.1.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Stone Mason | 0 | 83 | 18 | 41 | 35
844 | 1.2.4.4.1.1.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Carpet | 0 | 12 | 24 | 34 | 7
845 | 1.2.4.4.1.1.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Stone Mason | 0 | 81 | 29 | 7 | 24
846 | 1.2.4.4.1.1.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Timber Floorer | 0 | 89 | 10 | 58 | 49
847 | 1.2.4.4.1.1.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 793,794,795,796,797 | 848 | - | - | 0 | Plumber | 0 | 26 | 20 | 23 | 22
848 | 1.2.4.4.1.1.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 847 | 849 | - | - | 0 | Foreman | 0 | 67 | 20 | 68 | 55
849 | 1.2.4.4.1.1.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 848 | 850 | - | - | 0 | Fire | 0 | 18 | 30 | 34 | 29
850 | 1.2.4.4.1.1.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 849 |  | - | - | 0 | Plasterboarder | 0 | 22 | 11 | 71 | 18
851 | 1.2.4.4.1.2 | Apartment B011 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 42 | 30 | 68 | 27
852 | 1.2.4.4.1.2.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 853,856,857,924 | - | - | 0 | Subcontractor | 0 | 73 | 33 | 49 | 59
853 | 1.2.4.4.1.2.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 852 | 855,854 | - | - | 0 | Line Market | 0 | 34 | 16 | 57 | 25
854 | 1.2.4.4.1.2.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 853 |  | - | - | 0 | Formworker | 0 | 72 | 14 | 22 | 9
855 | 1.2.4.4.1.2.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 853 | 858 | - | - | 0 | Development Manager | 0 | 50 | 24 | 19 | 48
856 | 1.2.4.4.1.2.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 865 | - | - | 0 | Post Tension | 0 | 26 | 26 | 19 | 44
857 | 1.2.4.4.1.2.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 928 | - | - | 0 | Subcontractor | 0 | 71 | 10 | 26 | 20
858 | 1.2.4.4.1.2.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 855 | 859,860,861,862,863 | - | - | 0 | Landscaper | 0 | 10 | 35 | 1 | 45
859 | 1.2.4.4.1.2.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863 | - | - | 0 | Carpet | 0 | 86 | 13 | 34 | 25
860 | 1.2.4.4.1.2.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863,927 | - | - | 0 | Line Market | 0 | 34 | 35 | 73 | 22
861 | 1.2.4.4.1.2.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 926 | - | - | 0 | Site Manager | 0 | 34 | 17 | 74 | 28
862 | 1.2.4.4.1.2.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 |  | - | - | 0 | Surveyor | 0 | 42 | 28 | 68 | 39
863 | 1.2.4.4.1.2.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 858,859,860 | 864 | - | - | 0 | Project Manager | 0 | 47 | 15 | 21 | 2
864 | 1.2.4.4.1.2.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 863 | 865 | - | - | 0 | Site Manager | 0 | 53 | 11 | 99 | 41
865 | 1.2.4.4.1.2.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 856,864 | 866,867,868,869,871,873 | - | - | 0 | Hoarding | 0 | 87 | 12 | 46 | 36
866 | 1.2.4.4.1.2.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 870,873 | - | - | 0 | Admin | 0 | 68 | 35 | 73 | 4
867 | 1.2.4.4.1.2.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 873 | - | - | 0 | Plasterboarder | 0 | 28 | 20 | 20 | 3
868 | 1.2.4.4.1.2.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 872,873 | - | - | 0 | Stone Mason | 0 | 18 | 21 | 37 | 39
869 | 1.2.4.4.1.2.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | - | - | 0 | Waterproofer | 0 | 91 | 17 | 7 | 45
870 | 1.2.4.4.1.2.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 866 | 873 | - | - | 0 | Scaffolder | 0 | 13 | 24 | 8 | 3
871 | 1.2.4.4.1.2.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | - | - | 0 | Waterproofer | 0 | 83 | 16 | 76 | 25
872 | 1.2.4.4.1.2.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 868 | 873 | - | - | 0 | Surveyor | 0 | 84 | 11 | 12 | 24
873 | 1.2.4.4.1.2.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 865,866,867,868,869,870,871,872 | 874 | - | - | 0 | Hoarding | 0 | 100 | 33 | 18 | 27
874 | 1.2.4.4.1.2.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 873 | 875 | - | - | 0 | Contract Administrator | 0 | 95 | 28 | 85 | 32
875 | 1.2.4.4.1.2.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 874 | 876,893,910 | - | - | 0 | Fire | 0 | 92 | 14 | 100 | 23
876 | 1.2.4.4.1.2.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 877 | - | - | 0 | Excavation | 0 | 35 | 14 | 60 | 38
877 | 1.2.4.4.1.2.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 876 | 878 | - | - | 0 | Development Manager | 0 | 40 | 24 | 95 | 24
878 | 1.2.4.4.1.2.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 877 | 879 | - | - | 0 | Fire | 0 | 60 | 24 | 8 | 8
879 | 1.2.4.4.1.2.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 878 | 880 | - | - | 0 | Head Contractor | 0 | 44 | 15 | 34 | 24
880 | 1.2.4.4.1.2.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 879 | 881,882 | - | - | 0 | Stone Mason | 0 | 78 | 22 | 87 | 58
881 | 1.2.4.4.1.2.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 880 | 885 | - | - | 0 | Post Tension | 0 | 24 | 14 | 81 | 17
882 | 1.2.4.4.1.2.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 880 | 883 | - | - | 0 | Plumber | 0 | 96 | 14 | 63 | 58
883 | 1.2.4.4.1.2.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 882 | 884 | - | - | 0 | Waterproofer | 0 | 91 | 27 | 11 | 3
884 | 1.2.4.4.1.2.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 883 |  | - | - | 0 | Reinforcement Fixer | 0 | 57 | 16 | 97 | 17
885 | 1.2.4.4.1.2.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 881 | 886,887,888,889,890 | - | - | 0 | Head Contractor | 0 | 34 | 13 | 67 | 52
886 | 1.2.4.4.1.2.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 885 |  | - | - | 0 | Hoarding | 0 | 36 | 11 | 70 | 6
887 | 1.2.4.4.1.2.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Tiler | 0 | 68 | 22 | 70 | 37
888 | 1.2.4.4.1.2.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Surveyor | 0 | 28 | 31 | 30 | 40
889 | 1.2.4.4.1.2.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Site Manager | 0 | 48 | 24 | 66 | 6
890 | 1.2.4.4.1.2.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Renderer | 0 | 67 | 33 | 28 | 22
891 | 1.2.4.4.1.2.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 941 | - | - | 0 | Carpenter | 0 | 81 | 23 | 75 | 50
892 | 1.2.4.4.1.2.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Floor Sealer | 0 | 27 | 26 | 71 | 7
893 | 1.2.4.4.1.2.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 894 | - | - | 0 | Contract Administrator | 0 | 29 | 11 | 93 | 22
894 | 1.2.4.4.1.2.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 893 | 895 | - | - | 0 | Site Manager | 0 | 45 | 26 | 28 | 12
895 | 1.2.4.4.1.2.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 894 | 896 | - | - | 0 | Foreman | 0 | 55 | 20 | 92 | 58
896 | 1.2.4.4.1.2.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 895 | 897 | - | - | 0 | Scaffolder | 0 | 88 | 25 | 20 | 19
897 | 1.2.4.4.1.2.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 896 | 898 | - | - | 0 | Development Manager | 0 | 52 | 18 | 18 | 6
898 | 1.2.4.4.1.2.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 897 | 899 | - | - | 0 | Project Manager | 0 | 27 | 21 | 24 | 41
899 | 1.2.4.4.1.2.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 898 | 900 | - | - | 0 | Plumber | 0 | 41 | 14 | 79 | 10
900 | 1.2.4.4.1.2.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 899 | 901 | - | - | 0 | Head Contractor | 0 | 46 | 11 | 89 | 52
901 | 1.2.4.4.1.2.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 900 | 902 | - | - | 0 | Hoarding | 0 | 30 | 25 | 35 | 3
902 | 1.2.4.4.1.2.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 901 | 903 | - | - | 0 | Electrician | 0 | 53 | 18 | 44 | 36
903 | 1.2.4.4.1.2.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 902 | 904 | - | - | 0 | Carpet | 0 | 66 | 13 | 94 | 40
904 | 1.2.4.4.1.2.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 903 | 908,905,906,907 | - | - | 0 | Landscaper | 0 | 46 | 17 | 65 | 50
905 | 1.2.4.4.1.2.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | - | - | 0 | Scaffolder | 0 | 78 | 24 | 14 | 14
906 | 1.2.4.4.1.2.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | - | - | 0 | Stone Mason | 0 | 38 | 24 | 8 | 37
907 | 1.2.4.4.1.2.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | - | - | 0 | Painter | 0 | 57 | 16 | 10 | 41
908 | 1.2.4.4.1.2.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 904,905,906,907 |  | - | - | 0 | Line Market | 0 | 94 | 26 | 8 | 53
909 | 1.2.4.4.1.2.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | - | - | 0 | Mechanical | 0 | 96 | 15 | 31 | 42
910 | 1.2.4.4.1.2.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 911 | - | - | 0 | Scaffolder | 0 | 70 | 34 | 81 | 27
911 | 1.2.4.4.1.2.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 910 | 912 | - | - | 0 | Line Market | 0 | 10 | 31 | 53 | 46
912 | 1.2.4.4.1.2.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 911 | 913 | - | - | 0 | Joiner | 0 | 19 | 34 | 27 | 60
913 | 1.2.4.4.1.2.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 912 | 914 | - | - | 0 | Line Market | 0 | 14 | 28 | 65 | 48
914 | 1.2.4.4.1.2.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 913 | 915 | - | - | 0 | Surveyor | 0 | 33 | 24 | 0 | 14
915 | 1.2.4.4.1.2.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 914 | 916 | - | - | 0 | Renderer | 0 | 54 | 12 | 75 | 30
916 | 1.2.4.4.1.2.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 915 | 917 | - | - | 0 | Carpet | 0 | 17 | 19 | 39 | 56
917 | 1.2.4.4.1.2.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 916 | 918,919,920,921 | - | - | 0 | Cleaner | 0 | 48 | 12 | 41 | 33
918 | 1.2.4.4.1.2.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Tiler | 0 | 81 | 16 | 67 | 53
919 | 1.2.4.4.1.2.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Surveyor | 0 | 51 | 16 | 8 | 28
920 | 1.2.4.4.1.2.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Tiler | 0 | 11 | 10 | 62 | 10
921 | 1.2.4.4.1.2.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Reinforcement Fixer | 0 | 48 | 17 | 82 | 26
922 | 1.2.4.4.1.2.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 918,919,920,921 |  | - | - | 0 | Stone Mason | 0 | 33 | 10 | 88 | 60
923 | 1.2.4.4.1.2.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | - | - | 0 | Project Manager | 0 | 48 | 32 | 94 | 30
924 | 1.2.4.4.1.2.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 852 | 925 | - | - | 0 | Plasterboarder | 0 | 23 | 20 | 13 | 57
925 | 1.2.4.4.1.2.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 924 |  | - | - | 0 | Formworker | 0 | 98 | 30 | 88 | 14
926 | 1.2.4.4.1.2.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 861 | 929 | - | - | 0 | Renderer | 0 | 75 | 27 | 60 | 44
927 | 1.2.4.4.1.2.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 860 | 929 | - | - | 0 | Carpenter | 0 | 71 | 35 | 79 | 42
928 | 1.2.4.4.1.2.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 857 | 929 | - | - | 0 | Timber Floorer | 0 | 92 | 19 | 28 | 36
929 | 1.2.4.4.1.2.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 926,927,928 | 930 | - | - | 0 | Line Market | 0 | 38 | 11 | 62 | 50
930 | 1.2.4.4.1.2.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 929 | 931 | - | - | 0 | Joiner | 0 | 15 | 24 | 65 | 6
931 | 1.2.4.4.1.2.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 930 | 932 | - | - | 0 | Concretor | 0 | 26 | 29 | 74 | 12
932 | 1.2.4.4.1.2.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 931 | 933 | - | - | 0 | Timber Floorer | 0 | 45 | 21 | 28 | 38
933 | 1.2.4.4.1.2.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 932 | 934 | - | - | 0 | Stone Mason | 0 | 38 | 18 | 1 | 55
934 | 1.2.4.4.1.2.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 933 | 935 | - | - | 0 | Development Manager | 0 | 16 | 10 | 47 | 29
935 | 1.2.4.4.1.2.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 934 | 936 | - | - | 0 | Floor Sealer | 0 | 27 | 33 | 98 | 6
936 | 1.2.4.4.1.2.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 935 | 937,938,939,940 | - | - | 0 | Hoarding | 0 | 50 | 29 | 24 | 15
937 | 1.2.4.4.1.2.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Formworker | 0 | 67 | 16 | 6 | 31
938 | 1.2.4.4.1.2.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Hoarding | 0 | 37 | 14 | 59 | 10
939 | 1.2.4.4.1.2.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Concretor | 0 | 37 | 20 | 91 | 6
940 | 1.2.4.4.1.2.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Joiner | 0 | 20 | 33 | 64 | 19
941 | 1.2.4.4.1.2.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 887,888,889,890,891 | 942 | - | - | 0 | Timber Floorer | 0 | 87 | 16 | 30 | 44
942 | 1.2.4.4.1.2.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 941 | 943 | - | - | 0 | Tiler | 0 | 48 | 26 | 45 | 7
943 | 1.2.4.4.1.2.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 942 | 944 | - | - | 0 | Renderer | 0 | 89 | 14 | 34 | 15
944 | 1.2.4.4.1.2.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 943 |  | - | - | 0 | Contract Administrator | 0 | 42 | 11 | 66 | 37
945 | 1.2.4.4.1.3 | Apartment B012 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Waterproofer | 0 | 77 | 14 | 33 | 17
946 | 1.2.4.4.1.3.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 947,950,951,1018 | - | - | 0 | Carpet | 0 | 26 | 25 | 71 | 49
947 | 1.2.4.4.1.3.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 946 | 949,948 | - | - | 0 | Waterproofer | 0 | 83 | 20 | 77 | 38
948 | 1.2.4.4.1.3.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 947 |  | - | - | 0 | Surveyor | 0 | 26 | 24 | 88 | 40
949 | 1.2.4.4.1.3.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 947 | 952 | - | - | 0 | Subcontractor | 0 | 42 | 31 | 97 | 4
950 | 1.2.4.4.1.3.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 959 | - | - | 0 | Scaffolder | 0 | 74 | 20 | 73 | 13
951 | 1.2.4.4.1.3.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 1022 | - | - | 0 | Electrician | 0 | 41 | 28 | 74 | 57
952 | 1.2.4.4.1.3.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 949 | 953,954,955,956,957 | - | - | 0 | Fire | 0 | 21 | 34 | 13 | 33
953 | 1.2.4.4.1.3.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957 | - | - | 0 | Landscaper | 0 | 86 | 24 | 38 | 21
954 | 1.2.4.4.1.3.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957,1021 | - | - | 0 | Electrician | 0 | 62 | 22 | 90 | 19
955 | 1.2.4.4.1.3.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 1020 | - | - | 0 | Landscaper | 0 | 37 | 19 | 2 | 56
956 | 1.2.4.4.1.3.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 |  | - | - | 0 | Line Market | 0 | 19 | 31 | 22 | 10
957 | 1.2.4.4.1.3.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 952,953,954 | 958 | - | - | 0 | Fire | 0 | 65 | 25 | 97 | 41
958 | 1.2.4.4.1.3.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 957 | 959 | - | - | 0 | Floor Sealer | 0 | 56 | 16 | 33 | 39
959 | 1.2.4.4.1.3.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 950,958 | 960,961,962,963,965,967 | - | - | 0 | Electrician | 0 | 72 | 31 | 25 | 45
960 | 1.2.4.4.1.3.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 964,967 | - | - | 0 | Line Market | 0 | 86 | 29 | 14 | 30
961 | 1.2.4.4.1.3.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 967 | - | - | 0 | Admin | 0 | 34 | 29 | 43 | 10
962 | 1.2.4.4.1.3.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 966,967 | - | - | 0 | Electrician | 0 | 99 | 13 | 39 | 9
963 | 1.2.4.4.1.3.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | - | - | 0 | Plasterboarder | 0 | 46 | 13 | 61 | 13
964 | 1.2.4.4.1.3.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 960 | 967 | - | - | 0 | Reinforcement Fixer | 0 | 84 | 13 | 66 | 56
965 | 1.2.4.4.1.3.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | - | - | 0 | Scaffolder | 0 | 32 | 12 | 34 | 23
966 | 1.2.4.4.1.3.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 962 | 967 | - | - | 0 | Concretor | 0 | 42 | 35 | 81 | 34
967 | 1.2.4.4.1.3.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 959,960,961,962,963,964,965,966 | 968 | - | - | 0 | Hoarding | 0 | 64 | 33 | 76 | 17
968 | 1.2.4.4.1.3.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 967 | 969 | - | - | 0 | Site Manager | 0 | 94 | 33 | 88 | 22
969 | 1.2.4.4.1.3.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 968 | 970,987,1004 | - | - | 0 | Cleaner | 0 | 75 | 29 | 17 | 18
970 | 1.2.4.4.1.3.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 971 | - | - | 0 | Tiler | 0 | 66 | 14 | 42 | 42
971 | 1.2.4.4.1.3.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 970 | 972 | - | - | 0 | Subcontractor | 0 | 49 | 14 | 46 | 58
972 | 1.2.4.4.1.3.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 971 | 973 | - | - | 0 | Plasterboarder | 0 | 56 | 10 | 68 | 6
973 | 1.2.4.4.1.3.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 972 | 974 | - | - | 0 | Excavation | 0 | 34 | 20 | 30 | 46
974 | 1.2.4.4.1.3.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 973 | 975,976 | - | - | 0 | Mechanical | 0 | 16 | 32 | 93 | 55
975 | 1.2.4.4.1.3.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 974 | 979 | - | - | 0 | Fire | 0 | 42 | 34 | 39 | 55
976 | 1.2.4.4.1.3.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 974 | 977 | - | - | 0 | Timber Floorer | 0 | 52 | 10 | 86 | 20
977 | 1.2.4.4.1.3.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 976 | 978 | - | - | 0 | Subcontractor | 0 | 59 | 29 | 16 | 25
978 | 1.2.4.4.1.3.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 977 |  | - | - | 0 | Excavation | 0 | 91 | 27 | 49 | 5
979 | 1.2.4.4.1.3.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 975 | 980,981,982,983,984 | - | - | 0 | Metal Work | 0 | 86 | 33 | 75 | 41
980 | 1.2.4.4.1.3.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 979 |  | - | - | 0 | Carpenter | 0 | 37 | 26 | 4 | 8
981 | 1.2.4.4.1.3.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Contract Administrator | 0 | 44 | 28 | 75 | 7
982 | 1.2.4.4.1.3.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Carpet | 0 | 43 | 17 | 41 | 50
983 | 1.2.4.4.1.3.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Concretor | 0 | 74 | 35 | 45 | 59
984 | 1.2.4.4.1.3.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Carpet | 0 | 91 | 15 | 98 | 28
985 | 1.2.4.4.1.3.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1035 | - | - | 0 | Waterproofer | 0 | 29 | 29 | 71 | 27
986 | 1.2.4.4.1.3.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 40 | 27 | 69 | 55
987 | 1.2.4.4.1.3.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 988 | - | - | 0 | Site Manager | 0 | 16 | 11 | 14 | 21
988 | 1.2.4.4.1.3.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 987 | 989 | - | - | 0 | Admin | 0 | 81 | 25 | 75 | 27
989 | 1.2.4.4.1.3.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 988 | 990 | - | - | 0 | Foreman | 0 | 75 | 12 | 26 | 60
990 | 1.2.4.4.1.3.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 989 | 991 | - | - | 0 | Formworker | 0 | 12 | 31 | 40 | 41
991 | 1.2.4.4.1.3.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 990 | 992 | - | - | 0 | Formworker | 0 | 53 | 17 | 68 | 19
992 | 1.2.4.4.1.3.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 991 | 993 | - | - | 0 | Subcontractor | 0 | 77 | 31 | 35 | 56
993 | 1.2.4.4.1.3.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 992 | 994 | - | - | 0 | Timber Floorer | 0 | 38 | 35 | 61 | 43
994 | 1.2.4.4.1.3.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 993 | 995 | - | - | 0 | Concretor | 0 | 41 | 24 | 10 | 28
995 | 1.2.4.4.1.3.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 994 | 996 | - | - | 0 | Metal Work | 0 | 22 | 18 | 14 | 50
996 | 1.2.4.4.1.3.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 995 | 997 | - | - | 0 | Joiner | 0 | 61 | 27 | 31 | 30
997 | 1.2.4.4.1.3.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 996 | 998 | - | - | 0 | Post Tension | 0 | 33 | 25 | 7 | 5
998 | 1.2.4.4.1.3.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 997 | 1002,999,1000,1001 | - | - | 0 | Subcontractor | 0 | 78 | 27 | 97 | 52
999 | 1.2.4.4.1.3.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | - | - | 0 | Timber Floorer | 0 | 57 | 35 | 11 | 42
1000 | 1.2.4.4.1.3.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | - | - | 0 | Mechanical | 0 | 24 | 10 | 62 | 56
1001 | 1.2.4.4.1.3.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | - | - | 0 | Reinforcement Fixer | 0 | 77 | 18 | 100 | 6
1002 | 1.2.4.4.1.3.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 998,999,1000,1001 |  | - | - | 0 | Cleaner | 0 | 86 | 35 | 71 | 50
1003 | 1.2.4.4.1.3.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | - | - | 0 | Fire | 0 | 56 | 12 | 79 | 18
1004 | 1.2.4.4.1.3.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 1005 | - | - | 0 | Admin | 0 | 39 | 25 | 66 | 31
1005 | 1.2.4.4.1.3.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1004 | 1006 | - | - | 0 | Admin | 0 | 96 | 28 | 85 | 29
1006 | 1.2.4.4.1.3.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1005 | 1007 | - | - | 0 | Mechanical | 0 | 56 | 29 | 32 | 39
1007 | 1.2.4.4.1.3.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1006 | 1008 | - | - | 0 | Excavation | 0 | 30 | 27 | 31 | 43
1008 | 1.2.4.4.1.3.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1007 | 1009 | - | - | 0 | Contract Administrator | 0 | 24 | 13 | 84 | 38
1009 | 1.2.4.4.1.3.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1008 | 1010 | - | - | 0 | Floor Sealer | 0 | 77 | 21 | 92 | 11
1010 | 1.2.4.4.1.3.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1009 | 1011 | - | - | 0 | Electrician | 0 | 88 | 28 | 70 | 30
1011 | 1.2.4.4.1.3.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1010 | 1012,1013,1014,1015 | - | - | 0 | Development Manager | 0 | 27 | 32 | 28 | 26
1012 | 1.2.4.4.1.3.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Subcontractor | 0 | 93 | 13 | 29 | 6
1013 | 1.2.4.4.1.3.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Reinforcement Fixer | 0 | 40 | 15 | 48 | 52
1014 | 1.2.4.4.1.3.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Head Contractor | 0 | 27 | 21 | 14 | 9
1015 | 1.2.4.4.1.3.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Painter | 0 | 28 | 34 | 94 | 24
1016 | 1.2.4.4.1.3.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1012,1013,1014,1015 |  | - | - | 0 | Renderer | 0 | 67 | 32 | 97 | 32
1017 | 1.2.4.4.1.3.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 80 | 10 | 26 | 46
1018 | 1.2.4.4.1.3.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 946 | 1019 | - | - | 0 | Carpenter | 0 | 44 | 17 | 93 | 31
1019 | 1.2.4.4.1.3.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1018 |  | - | - | 0 | Reinforcement Fixer | 0 | 53 | 28 | 21 | 13
1020 | 1.2.4.4.1.3.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 955 | 1023 | - | - | 0 | Site Manager | 0 | 72 | 13 | 58 | 3
1021 | 1.2.4.4.1.3.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 954 | 1023 | - | - | 0 | Site Manager | 0 | 20 | 23 | 35 | 8
1022 | 1.2.4.4.1.3.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 951 | 1023 | - | - | 0 | Floor Sealer | 0 | 60 | 32 | 27 | 46
1023 | 1.2.4.4.1.3.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1020,1021,1022 | 1024 | - | - | 0 | Post Tension | 0 | 91 | 16 | 21 | 22
1024 | 1.2.4.4.1.3.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1023 | 1025 | - | - | 0 | Joiner | 0 | 16 | 12 | 99 | 23
1025 | 1.2.4.4.1.3.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1024 | 1026 | - | - | 0 | Scaffolder | 0 | 38 | 10 | 96 | 18
1026 | 1.2.4.4.1.3.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1025 | 1027 | - | - | 0 | Contract Administrator | 0 | 100 | 27 | 17 | 21
1027 | 1.2.4.4.1.3.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1026 | 1028 | - | - | 0 | Stone Mason | 0 | 14 | 30 | 79 | 22
1028 | 1.2.4.4.1.3.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1027 | 1029 | - | - | 0 | Excavation | 0 | 69 | 17 | 77 | 11
1029 | 1.2.4.4.1.3.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1028 | 1030 | - | - | 0 | Line Market | 0 | 28 | 17 | 58 | 38
1030 | 1.2.4.4.1.3.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1029 | 1031,1032,1033,1034 | - | - | 0 | Concretor | 0 | 95 | 31 | 89 | 56
1031 | 1.2.4.4.1.3.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Concretor | 0 | 60 | 17 | 5 | 27
1032 | 1.2.4.4.1.3.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Landscaper | 0 | 83 | 18 | 86 | 60
1033 | 1.2.4.4.1.3.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Project Manager | 0 | 46 | 26 | 32 | 47
1034 | 1.2.4.4.1.3.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Stone Mason | 0 | 17 | 11 | 0 | 56
1035 | 1.2.4.4.1.3.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 981,982,983,984,985 | 1036 | - | - | 0 | Post Tension | 0 | 69 | 21 | 48 | 51
1036 | 1.2.4.4.1.3.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1035 | 1037 | - | - | 0 | Landscaper | 0 | 73 | 16 | 92 | 42
1037 | 1.2.4.4.1.3.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1036 | 1038 | - | - | 0 | Tiler | 0 | 19 | 20 | 54 | 45
1038 | 1.2.4.4.1.3.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1037 |  | - | - | 0 | Renderer | 0 | 55 | 18 | 47 | 13
1039 | 1.2.4.4.1.4 | Apartment B013 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 25 | 35 | 22 | 42
1040 | 1.2.4.4.1.4.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 1041,1044,1045,1112 | - | - | 0 | Fire | 0 | 85 | 34 | 10 | 12
1041 | 1.2.4.4.1.4.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 1040 | 1043,1042 | - | - | 0 | Contract Administrator | 0 | 95 | 16 | 54 | 23
1042 | 1.2.4.4.1.4.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1041 |  | - | - | 0 | Carpet | 0 | 79 | 11 | 96 | 54
1043 | 1.2.4.4.1.4.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1041 | 1046 | - | - | 0 | Joiner | 0 | 94 | 15 | 5 | 47
1044 | 1.2.4.4.1.4.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1053 | - | - | 0 | Reinforcement Fixer | 0 | 59 | 25 | 82 | 55
1045 | 1.2.4.4.1.4.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1116 | - | - | 0 | Surveyor | 0 | 57 | 18 | 84 | 19
1046 | 1.2.4.4.1.4.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1043 | 1047,1048,1049,1050,1051 | - | - | 0 | Carpenter | 0 | 49 | 13 | 8 | 41
1047 | 1.2.4.4.1.4.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051 | - | - | 0 | Development Manager | 0 | 47 | 20 | 61 | 45
1048 | 1.2.4.4.1.4.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051,1115 | - | - | 0 | Tiler | 0 | 20 | 23 | 75 | 33
1049 | 1.2.4.4.1.4.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1114 | - | - | 0 | Plumber | 0 | 78 | 15 | 66 | 28
1050 | 1.2.4.4.1.4.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 |  | - | - | 0 | Scaffolder | 0 | 38 | 32 | 6 | 45
1051 | 1.2.4.4.1.4.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1046,1047,1048 | 1052 | - | - | 0 | Carpet | 0 | 89 | 31 | 44 | 4
1052 | 1.2.4.4.1.4.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1051 | 1053 | - | - | 0 | Head Contractor | 0 | 96 | 12 | 16 | 38
1053 | 1.2.4.4.1.4.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1044,1052 | 1054,1055,1056,1057,1059,1061 | - | - | 0 | Carpet | 0 | 71 | 24 | 14 | 6
1054 | 1.2.4.4.1.4.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1058,1061 | - | - | 0 | Landscaper | 0 | 34 | 24 | 2 | 20
1055 | 1.2.4.4.1.4.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Contract Administrator | 0 | 67 | 18 | 58 | 27
1056 | 1.2.4.4.1.4.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1060,1061 | - | - | 0 | Metal Work | 0 | 93 | 13 | 70 | 36
1057 | 1.2.4.4.1.4.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Surveyor | 0 | 40 | 13 | 24 | 55
1058 | 1.2.4.4.1.4.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1054 | 1061 | - | - | 0 | Window | 0 | 52 | 24 | 89 | 46
1059 | 1.2.4.4.1.4.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Contract Administrator | 0 | 81 | 23 | 2 | 3
1060 | 1.2.4.4.1.4.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1056 | 1061 | - | - | 0 | Cleaner | 0 | 20 | 24 | 94 | 39
1061 | 1.2.4.4.1.4.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1053,1054,1055,1056,1057,1058,1059,1060 | 1062 | - | - | 0 | Reinforcement Fixer | 0 | 23 | 19 | 87 | 52
1062 | 1.2.4.4.1.4.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1061 | 1063 | - | - | 0 | Development Manager | 0 | 54 | 35 | 66 | 36
1063 | 1.2.4.4.1.4.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1062 | 1064,1081,1098 | - | - | 0 | Development Manager | 0 | 77 | 15 | 54 | 55
1064 | 1.2.4.4.1.4.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1065 | - | - | 0 | Renderer | 0 | 61 | 31 | 70 | 2
1065 | 1.2.4.4.1.4.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1064 | 1066 | - | - | 0 | Plasterboarder | 0 | 12 | 27 | 83 | 40
1066 | 1.2.4.4.1.4.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1065 | 1067 | - | - | 0 | Post Tension | 0 | 40 | 25 | 69 | 26
1067 | 1.2.4.4.1.4.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1066 | 1068 | - | - | 0 | Carpet | 0 | 16 | 20 | 20 | 45
1068 | 1.2.4.4.1.4.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1067 | 1069,1070 | - | - | 0 | Electrician | 0 | 68 | 17 | 82 | 60
1069 | 1.2.4.4.1.4.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1068 | 1073 | - | - | 0 | Joiner | 0 | 80 | 35 | 22 | 23
1070 | 1.2.4.4.1.4.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1068 | 1071 | - | - | 0 | Reinforcement Fixer | 0 | 40 | 17 | 31 | 24
1071 | 1.2.4.4.1.4.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1070 | 1072 | - | - | 0 | Waterproofer | 0 | 48 | 17 | 53 | 3
1072 | 1.2.4.4.1.4.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1071 |  | - | - | 0 | Window | 0 | 26 | 21 | 5 | 43
1073 | 1.2.4.4.1.4.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1069 | 1074,1075,1076,1077,1078 | - | - | 0 | Line Market | 0 | 54 | 33 | 90 | 35
1074 | 1.2.4.4.1.4.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1073 |  | - | - | 0 | Line Market | 0 | 79 | 11 | 13 | 37
1075 | 1.2.4.4.1.4.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Reinforcement Fixer | 0 | 49 | 24 | 92 | 33
1076 | 1.2.4.4.1.4.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Electrician | 0 | 44 | 27 | 41 | 53
1077 | 1.2.4.4.1.4.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Post Tension | 0 | 45 | 16 | 26 | 42
1078 | 1.2.4.4.1.4.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Plumber | 0 | 99 | 21 | 51 | 54
1079 | 1.2.4.4.1.4.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1129 | - | - | 0 | Floor Sealer | 0 | 89 | 35 | 46 | 12
1080 | 1.2.4.4.1.4.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Timber Floorer | 0 | 98 | 22 | 80 | 36
1081 | 1.2.4.4.1.4.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1082 | - | - | 0 | Admin | 0 | 92 | 14 | 0 | 53
1082 | 1.2.4.4.1.4.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1081 | 1083 | - | - | 0 | Line Market | 0 | 82 | 22 | 75 | 34
1083 | 1.2.4.4.1.4.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1082 | 1084 | - | - | 0 | Joiner | 0 | 17 | 13 | 98 | 24
1084 | 1.2.4.4.1.4.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1083 | 1085 | - | - | 0 | Waterproofer | 0 | 77 | 13 | 16 | 26
1085 | 1.2.4.4.1.4.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1084 | 1086 | - | - | 0 | Plasterboarder | 0 | 60 | 26 | 29 | 7
1086 | 1.2.4.4.1.4.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1085 | 1087 | - | - | 0 | Subcontractor | 0 | 48 | 33 | 62 | 17
1087 | 1.2.4.4.1.4.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1086 | 1088 | - | - | 0 | Metal Work | 0 | 13 | 32 | 71 | 13
1088 | 1.2.4.4.1.4.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1087 | 1089 | - | - | 0 | Renderer | 0 | 19 | 31 | 84 | 54
1089 | 1.2.4.4.1.4.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1088 | 1090 | - | - | 0 | Carpenter | 0 | 17 | 27 | 46 | 8
1090 | 1.2.4.4.1.4.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1089 | 1091 | - | - | 0 | Timber Floorer | 0 | 68 | 21 | 78 | 22
1091 | 1.2.4.4.1.4.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1090 | 1092 | - | - | 0 | Site Manager | 0 | 43 | 12 | 5 | 43
1092 | 1.2.4.4.1.4.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1091 | 1096,1093,1094,1095 | - | - | 0 | Head Contractor | 0 | 31 | 22 | 53 | 13
1093 | 1.2.4.4.1.4.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Admin | 0 | 27 | 27 | 54 | 10
1094 | 1.2.4.4.1.4.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Hoarding | 0 | 81 | 12 | 17 | 60
1095 | 1.2.4.4.1.4.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Window | 0 | 80 | 31 | 3 | 16
1096 | 1.2.4.4.1.4.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1092,1093,1094,1095 |  | - | - | 0 | Post Tension | 0 | 64 | 30 | 51 | 25
1097 | 1.2.4.4.1.4.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | - | - | 0 | Development Manager | 0 | 35 | 30 | 38 | 6
1098 | 1.2.4.4.1.4.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1099 | - | - | 0 | Tiler | 0 | 58 | 34 | 16 | 9
1099 | 1.2.4.4.1.4.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1098 | 1100 | - | - | 0 | Project Manager | 0 | 60 | 19 | 77 | 33
1100 | 1.2.4.4.1.4.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1099 | 1101 | - | - | 0 | Painter | 0 | 29 | 18 | 71 | 17
1101 | 1.2.4.4.1.4.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1100 | 1102 | - | - | 0 | Contract Administrator | 0 | 16 | 22 | 9 | 30
1102 | 1.2.4.4.1.4.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1101 | 1103 | - | - | 0 | Plumber | 0 | 12 | 33 | 61 | 17
1103 | 1.2.4.4.1.4.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1102 | 1104 | - | - | 0 | Stone Mason | 0 | 91 | 15 | 73 | 28
1104 | 1.2.4.4.1.4.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1103 | 1105 | - | - | 0 | Landscaper | 0 | 81 | 11 | 20 | 17
1105 | 1.2.4.4.1.4.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1104 | 1106,1107,1108,1109 | - | - | 0 | Foreman | 0 | 12 | 26 | 83 | 7
1106 | 1.2.4.4.1.4.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Post Tension | 0 | 62 | 20 | 33 | 29
1107 | 1.2.4.4.1.4.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Hoarding | 0 | 36 | 24 | 59 | 37
1108 | 1.2.4.4.1.4.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Excavation | 0 | 93 | 25 | 10 | 26
1109 | 1.2.4.4.1.4.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Painter | 0 | 19 | 30 | 94 | 7
1110 | 1.2.4.4.1.4.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1106,1107,1108,1109 |  | - | - | 0 | Development Manager | 0 | 81 | 14 | 45 | 10
1111 | 1.2.4.4.1.4.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | - | - | 0 | Landscaper | 0 | 92 | 35 | 4 | 10
1112 | 1.2.4.4.1.4.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 1040 | 1113 | - | - | 0 | Electrician | 0 | 51 | 30 | 80 | 10
1113 | 1.2.4.4.1.4.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1112 |  | - | - | 0 | Development Manager | 0 | 63 | 34 | 74 | 36
1114 | 1.2.4.4.1.4.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1049 | 1117 | - | - | 0 | Post Tension | 0 | 49 | 34 | 71 | 9
1115 | 1.2.4.4.1.4.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1048 | 1117 | - | - | 0 | Post Tension | 0 | 11 | 27 | 60 | 36
1116 | 1.2.4.4.1.4.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1045 | 1117 | - | - | 0 | Electrician | 0 | 45 | 18 | 38 | 12
1117 | 1.2.4.4.1.4.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1114,1115,1116 | 1118 | - | - | 0 | Surveyor | 0 | 59 | 22 | 65 | 24
1118 | 1.2.4.4.1.4.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1117 | 1119 | - | - | 0 | Renderer | 0 | 91 | 29 | 20 | 13
1119 | 1.2.4.4.1.4.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1118 | 1120 | - | - | 0 | Subcontractor | 0 | 60 | 26 | 97 | 60
1120 | 1.2.4.4.1.4.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1119 | 1121 | - | - | 0 | Post Tension | 0 | 57 | 29 | 2 | 32
1121 | 1.2.4.4.1.4.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1120 | 1122 | - | - | 0 | Plumber | 0 | 67 | 26 | 12 | 20
1122 | 1.2.4.4.1.4.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1121 | 1123 | - | - | 0 | Hoarding | 0 | 27 | 31 | 61 | 36
1123 | 1.2.4.4.1.4.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1122 | 1124 | - | - | 0 | Contract Administrator | 0 | 12 | 28 | 41 | 37
1124 | 1.2.4.4.1.4.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1123 | 1125,1126,1127,1128 | - | - | 0 | Floor Sealer | 0 | 33 | 34 | 34 | 18
1125 | 1.2.4.4.1.4.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Mechanical | 0 | 11 | 33 | 7 | 31
1126 | 1.2.4.4.1.4.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Window | 0 | 80 | 30 | 52 | 24
1127 | 1.2.4.4.1.4.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Painter | 0 | 22 | 23 | 79 | 3
1128 | 1.2.4.4.1.4.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Subcontractor | 0 | 70 | 31 | 6 | 60
1129 | 1.2.4.4.1.4.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1075,1076,1077,1078,1079 | 1130 | - | - | 0 | Plasterboarder | 0 | 72 | 23 | 81 | 39
1130 | 1.2.4.4.1.4.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1129 | 1131 | - | - | 0 | Renderer | 0 | 13 | 23 | 59 | 45
1131 | 1.2.4.4.1.4.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1130 | 1132 | - | - | 0 | Foreman | 0 | 17 | 20 | 100 | 21
1132 | 1.2.4.4.1.4.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1131 |  | - | - | 0 | Renderer | 0 | 75 | 14 | 23 | 50
1133 | 1.2.4.4.1.5 | Apartment B014 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | - | - | 0 | Joiner | 0 | 96 | 22 | 18 | 47
1134 | 1.2.4.4.1.5.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1135,1138,1139,1206 | - | - | 0 | Contract Administrator | 0 | 73 | 12 | 76 | 37
1135 | 1.2.4.4.1.5.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1134 | 1137,1136 | - | - | 0 | Formworker | 0 | 97 | 12 | 53 | 47
1136 | 1.2.4.4.1.5.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1135 |  | - | - | 0 | Project Manager | 0 | 17 | 10 | 54 | 29
1137 | 1.2.4.4.1.5.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1135 | 1140 | - | - | 0 | Line Market | 0 | 50 | 26 | 13 | 50
1138 | 1.2.4.4.1.5.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1147 | - | - | 0 | Reinforcement Fixer | 0 | 38 | 17 | 19 | 30
1139 | 1.2.4.4.1.5.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1210 | - | - | 0 | Site Manager | 0 | 45 | 18 | 63 | 37
1140 | 1.2.4.4.1.5.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1137 | 1141,1142,1143,1144,1145 | - | - | 0 | Renderer | 0 | 36 | 13 | 62 | 32
1141 | 1.2.4.4.1.5.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145 | - | - | 0 | Hoarding | 0 | 80 | 33 | 33 | 25
1142 | 1.2.4.4.1.5.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145,1209 | - | - | 0 | Project Manager | 0 | 47 | 20 | 87 | 48
1143 | 1.2.4.4.1.5.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1208 | - | - | 0 | Hoarding | 0 | 74 | 16 | 94 | 33
1144 | 1.2.4.4.1.5.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 |  | - | - | 0 | Scaffolder | 0 | 77 | 20 | 41 | 40
1145 | 1.2.4.4.1.5.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1140,1141,1142 | 1146 | - | - | 0 | Timber Floorer | 0 | 100 | 25 | 96 | 37
1146 | 1.2.4.4.1.5.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1145 | 1147 | - | - | 0 | Electrician | 0 | 54 | 29 | 33 | 48
1147 | 1.2.4.4.1.5.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1138,1146 | 1148,1149,1150,1151,1153,1155 | - | - | 0 | Cleaner | 0 | 56 | 17 | 58 | 41
1148 | 1.2.4.4.1.5.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1152,1155 | - | - | 0 | Site Manager | 0 | 59 | 13 | 30 | 18
1149 | 1.2.4.4.1.5.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Electrician | 0 | 44 | 25 | 20 | 20
1150 | 1.2.4.4.1.5.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1154,1155 | - | - | 0 | Project Manager | 0 | 84 | 17 | 5 | 56
1151 | 1.2.4.4.1.5.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Waterproofer | 0 | 24 | 32 | 34 | 29
1152 | 1.2.4.4.1.5.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1148 | 1155 | - | - | 0 | Plumber | 0 | 79 | 25 | 93 | 43
1153 | 1.2.4.4.1.5.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Stone Mason | 0 | 73 | 35 | 56 | 46
1154 | 1.2.4.4.1.5.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1150 | 1155 | - | - | 0 | Hoarding | 0 | 68 | 29 | 38 | 21
1155 | 1.2.4.4.1.5.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1147,1148,1149,1150,1151,1152,1153,1154 | 1156 | - | - | 0 | Waterproofer | 0 | 77 | 31 | 20 | 46
1156 | 1.2.4.4.1.5.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1155 | 1157 | - | - | 0 | Admin | 0 | 33 | 13 | 58 | 36
1157 | 1.2.4.4.1.5.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1156 | 1158,1175,1192 | - | - | 0 | Electrician | 0 | 97 | 21 | 26 | 45
1158 | 1.2.4.4.1.5.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1159 | - | - | 0 | Contract Administrator | 0 | 24 | 14 | 66 | 55
1159 | 1.2.4.4.1.5.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1158 | 1160 | - | - | 0 | Admin | 0 | 52 | 34 | 24 | 39
1160 | 1.2.4.4.1.5.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1159 | 1161 | - | - | 0 | Fire | 0 | 38 | 21 | 75 | 15
1161 | 1.2.4.4.1.5.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1160 | 1162 | - | - | 0 | Plasterboarder | 0 | 88 | 29 | 27 | 47
1162 | 1.2.4.4.1.5.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1161 | 1163,1164 | - | - | 0 | Formworker | 0 | 29 | 21 | 100 | 32
1163 | 1.2.4.4.1.5.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1162 | 1167 | - | - | 0 | Scaffolder | 0 | 49 | 14 | 83 | 19
1164 | 1.2.4.4.1.5.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1162 | 1165 | - | - | 0 | Contract Administrator | 0 | 98 | 30 | 15 | 39
1165 | 1.2.4.4.1.5.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1164 | 1166 | - | - | 0 | Development Manager | 0 | 71 | 30 | 37 | 23
1166 | 1.2.4.4.1.5.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1165 |  | - | - | 0 | Project Manager | 0 | 35 | 10 | 60 | 9
1167 | 1.2.4.4.1.5.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1163 | 1168,1169,1170,1171,1172 | - | - | 0 | Admin | 0 | 88 | 28 | 74 | 12
1168 | 1.2.4.4.1.5.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1167 |  | - | - | 0 | Admin | 0 | 55 | 29 | 3 | 37
1169 | 1.2.4.4.1.5.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Admin | 0 | 66 | 13 | 81 | 53
1170 | 1.2.4.4.1.5.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Joiner | 0 | 43 | 24 | 30 | 33
1171 | 1.2.4.4.1.5.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Cleaner | 0 | 35 | 14 | 73 | 8
1172 | 1.2.4.4.1.5.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Foreman | 0 | 99 | 14 | 72 | 55
1173 | 1.2.4.4.1.5.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1223 | - | - | 0 | Fire | 0 | 46 | 19 | 94 | 48
1174 | 1.2.4.4.1.5.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Plumber | 0 | 89 | 28 | 26 | 33
1175 | 1.2.4.4.1.5.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1176 | - | - | 0 | Renderer | 0 | 14 | 26 | 7 | 37
1176 | 1.2.4.4.1.5.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1175 | 1177 | - | - | 0 | Formworker | 0 | 88 | 11 | 22 | 3
1177 | 1.2.4.4.1.5.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1176 | 1178 | - | - | 0 | Plumber | 0 | 34 | 24 | 16 | 34
1178 | 1.2.4.4.1.5.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1177 | 1179 | - | - | 0 | Subcontractor | 0 | 77 | 26 | 71 | 3
1179 | 1.2.4.4.1.5.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1178 | 1180 | - | - | 0 | Carpenter | 0 | 87 | 30 | 35 | 51
1180 | 1.2.4.4.1.5.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1179 | 1181 | - | - | 0 | Timber Floorer | 0 | 68 | 30 | 93 | 48
1181 | 1.2.4.4.1.5.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1180 | 1182 | - | - | 0 | Carpenter | 0 | 56 | 29 | 80 | 42
1182 | 1.2.4.4.1.5.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1181 | 1183 | - | - | 0 | Renderer | 0 | 59 | 35 | 81 | 49
1183 | 1.2.4.4.1.5.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1182 | 1184 | - | - | 0 | Floor Sealer | 0 | 47 | 23 | 48 | 15
1184 | 1.2.4.4.1.5.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1183 | 1185 | - | - | 0 | Head Contractor | 0 | 29 | 23 | 45 | 8
1185 | 1.2.4.4.1.5.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1184 | 1186 | - | - | 0 | Development Manager | 0 | 86 | 27 | 28 | 9
1186 | 1.2.4.4.1.5.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1185 | 1190,1187,1188,1189 | - | - | 0 | Painter | 0 | 90 | 33 | 60 | 20
1187 | 1.2.4.4.1.5.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Development Manager | 0 | 87 | 13 | 81 | 34
1188 | 1.2.4.4.1.5.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Concretor | 0 | 39 | 14 | 73 | 15
1189 | 1.2.4.4.1.5.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Reinforcement Fixer | 0 | 28 | 32 | 96 | 3
1190 | 1.2.4.4.1.5.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1186,1187,1188,1189 |  | - | - | 0 | Admin | 0 | 88 | 20 | 83 | 51
1191 | 1.2.4.4.1.5.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Timber Floorer | 0 | 93 | 11 | 57 | 9
1192 | 1.2.4.4.1.5.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1193 | - | - | 0 | Painter | 0 | 59 | 27 | 36 | 33
1193 | 1.2.4.4.1.5.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1192 | 1194 | - | - | 0 | Subcontractor | 0 | 79 | 35 | 49 | 48
1194 | 1.2.4.4.1.5.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1193 | 1195 | - | - | 0 | Surveyor | 0 | 35 | 15 | 95 | 45
1195 | 1.2.4.4.1.5.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1194 | 1196 | - | - | 0 | Landscaper | 0 | 94 | 11 | 74 | 29
1196 | 1.2.4.4.1.5.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1195 | 1197 | - | - | 0 | Concretor | 0 | 86 | 19 | 3 | 2
1197 | 1.2.4.4.1.5.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1196 | 1198 | - | - | 0 | Foreman | 0 | 72 | 25 | 19 | 34
1198 | 1.2.4.4.1.5.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1197 | 1199 | - | - | 0 | Stone Mason | 0 | 97 | 33 | 48 | 22
1199 | 1.2.4.4.1.5.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1198 | 1200,1201,1202,1203 | - | - | 0 | Head Contractor | 0 | 11 | 31 | 22 | 45
1200 | 1.2.4.4.1.5.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Surveyor | 0 | 44 | 31 | 56 | 4
1201 | 1.2.4.4.1.5.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Project Manager | 0 | 42 | 34 | 54 | 11
1202 | 1.2.4.4.1.5.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Waterproofer | 0 | 59 | 13 | 94 | 23
1203 | 1.2.4.4.1.5.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Concretor | 0 | 78 | 26 | 49 | 3
1204 | 1.2.4.4.1.5.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1200,1201,1202,1203 |  | - | - | 0 | Post Tension | 0 | 59 | 24 | 84 | 27
1205 | 1.2.4.4.1.5.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | - | - | 0 | Mechanical | 0 | 25 | 33 | 53 | 4
1206 | 1.2.4.4.1.5.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1134 | 1207 | - | - | 0 | Excavation | 0 | 69 | 30 | 67 | 45
1207 | 1.2.4.4.1.5.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1206 |  | - | - | 0 | Reinforcement Fixer | 0 | 27 | 31 | 42 | 23
1208 | 1.2.4.4.1.5.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1143 | 1211 | - | - | 0 | Renderer | 0 | 19 | 10 | 2 | 32
1209 | 1.2.4.4.1.5.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1142 | 1211 | - | - | 0 | Joiner | 0 | 98 | 34 | 97 | 5
1210 | 1.2.4.4.1.5.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1139 | 1211 | - | - | 0 | Contract Administrator | 0 | 20 | 25 | 61 | 2
1211 | 1.2.4.4.1.5.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1208,1209,1210 | 1212 | - | - | 0 | Tiler | 0 | 38 | 26 | 4 | 34
1212 | 1.2.4.4.1.5.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1211 | 1213 | - | - | 0 | Mechanical | 0 | 46 | 14 | 30 | 3
1213 | 1.2.4.4.1.5.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1212 | 1214 | - | - | 0 | Site Manager | 0 | 42 | 32 | 33 | 13
1214 | 1.2.4.4.1.5.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1213 | 1215 | - | - | 0 | Site Manager | 0 | 35 | 13 | 22 | 53
1215 | 1.2.4.4.1.5.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1214 | 1216 | - | - | 0 | Carpenter | 0 | 58 | 14 | 41 | 59
1216 | 1.2.4.4.1.5.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1215 | 1217 | - | - | 0 | Surveyor | 0 | 70 | 29 | 4 | 20
1217 | 1.2.4.4.1.5.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1216 | 1218 | - | - | 0 | Formworker | 0 | 59 | 30 | 32 | 38
1218 | 1.2.4.4.1.5.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1217 | 1219,1220,1221,1222 | - | - | 0 | Line Market | 0 | 30 | 18 | 6 | 6
1219 | 1.2.4.4.1.5.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Site Manager | 0 | 99 | 34 | 30 | 13
1220 | 1.2.4.4.1.5.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Landscaper | 0 | 40 | 15 | 9 | 51
1221 | 1.2.4.4.1.5.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Post Tension | 0 | 66 | 29 | 91 | 33
1222 | 1.2.4.4.1.5.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Metal Work | 0 | 34 | 27 | 83 | 15
1223 | 1.2.4.4.1.5.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1169,1170,1171,1172,1173 | 1224 | - | - | 0 | Window | 0 | 59 | 30 | 49 | 49
1224 | 1.2.4.4.1.5.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1223 | 1225 | - | - | 0 | Electrician | 0 | 85 | 29 | 44 | 19
1225 | 1.2.4.4.1.5.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1224 | 1226 | - | - | 0 | Excavation | 0 | 60 | 10 | 49 | 33
1226 | 1.2.4.4.1.5.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1225 |  | - | - | 0 | Surveyor | 0 | 36 | 19 | 33 | 24
1227 | 1.2.4.4.1.6 | Apartment B015 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | - | - | 0 | Window | 0 | 46 | 29 | 35 | 41
1228 | 1.2.4.4.1.6.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1229,1232,1233,1300 | - | - | 0 | Subcontractor | 0 | 23 | 25 | 76 | 23
1229 | 1.2.4.4.1.6.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1228 | 1231,1230 | - | - | 0 | Landscaper | 0 | 34 | 27 | 97 | 33
1230 | 1.2.4.4.1.6.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1229 |  | - | - | 0 | Painter | 0 | 25 | 22 | 12 | 59
1231 | 1.2.4.4.1.6.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1229 | 1234 | - | - | 0 | Site Manager | 0 | 29 | 10 | 59 | 28
1232 | 1.2.4.4.1.6.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1241 | - | - | 0 | Metal Work | 0 | 92 | 22 | 94 | 48
1233 | 1.2.4.4.1.6.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1304 | - | - | 0 | Head Contractor | 0 | 56 | 29 | 33 | 26
1234 | 1.2.4.4.1.6.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1231 | 1235,1236,1237,1238,1239 | - | - | 0 | Scaffolder | 0 | 12 | 19 | 38 | 57
1235 | 1.2.4.4.1.6.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239 | - | - | 0 | Window | 0 | 51 | 18 | 59 | 50
1236 | 1.2.4.4.1.6.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239,1303 | - | - | 0 | Development Manager | 0 | 10 | 16 | 52 | 36
1237 | 1.2.4.4.1.6.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1302 | - | - | 0 | Concretor | 0 | 31 | 32 | 69 | 17
1238 | 1.2.4.4.1.6.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 |  | - | - | 0 | Admin | 0 | 32 | 32 | 45 | 28
1239 | 1.2.4.4.1.6.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1234,1235,1236 | 1240 | - | - | 0 | Joiner | 0 | 64 | 29 | 44 | 20
1240 | 1.2.4.4.1.6.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1239 | 1241 | - | - | 0 | Stone Mason | 0 | 80 | 30 | 97 | 41
1241 | 1.2.4.4.1.6.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1232,1240 | 1242,1243,1244,1245,1247,1249 | - | - | 0 | Plumber | 0 | 13 | 26 | 17 | 12
1242 | 1.2.4.4.1.6.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1246,1249 | - | - | 0 | Stone Mason | 0 | 61 | 13 | 19 | 21
1243 | 1.2.4.4.1.6.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Carpet | 0 | 61 | 27 | 11 | 9
1244 | 1.2.4.4.1.6.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1248,1249 | - | - | 0 | Waterproofer | 0 | 99 | 10 | 98 | 19
1245 | 1.2.4.4.1.6.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Plumber | 0 | 92 | 33 | 40 | 39
1246 | 1.2.4.4.1.6.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1242 | 1249 | - | - | 0 | Project Manager | 0 | 96 | 14 | 51 | 3
1247 | 1.2.4.4.1.6.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Concretor | 0 | 99 | 18 | 83 | 2
1248 | 1.2.4.4.1.6.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1244 | 1249 | - | - | 0 | Cleaner | 0 | 17 | 28 | 20 | 42
1249 | 1.2.4.4.1.6.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1241,1242,1243,1244,1245,1246,1247,1248 | 1250 | - | - | 0 | Tiler | 0 | 41 | 35 | 90 | 19
1250 | 1.2.4.4.1.6.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1249 | 1251 | - | - | 0 | Hoarding | 0 | 86 | 27 | 25 | 50
1251 | 1.2.4.4.1.6.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1250 | 1252,1269,1286 | - | - | 0 | Surveyor | 0 | 84 | 20 | 84 | 8
1252 | 1.2.4.4.1.6.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1253 | - | - | 0 | Post Tension | 0 | 71 | 24 | 55 | 50
1253 | 1.2.4.4.1.6.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1252 | 1254 | - | - | 0 | Site Manager | 0 | 72 | 25 | 45 | 43
1254 | 1.2.4.4.1.6.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1253 | 1255 | - | - | 0 | Foreman | 0 | 72 | 28 | 94 | 59
1255 | 1.2.4.4.1.6.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1254 | 1256 | - | - | 0 | Joiner | 0 | 67 | 34 | 51 | 34
1256 | 1.2.4.4.1.6.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1255 | 1257,1258 | - | - | 0 | Contract Administrator | 0 | 42 | 34 | 97 | 6
1257 | 1.2.4.4.1.6.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1256 | 1261 | - | - | 0 | Joiner | 0 | 10 | 35 | 91 | 5
1258 | 1.2.4.4.1.6.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1256 | 1259 | - | - | 0 | Post Tension | 0 | 100 | 23 | 87 | 51
1259 | 1.2.4.4.1.6.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1258 | 1260 | - | - | 0 | Renderer | 0 | 16 | 16 | 70 | 21
1260 | 1.2.4.4.1.6.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1259 |  | - | - | 0 | Scaffolder | 0 | 42 | 23 | 62 | 57
1261 | 1.2.4.4.1.6.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1257 | 1262,1263,1264,1265,1266 | - | - | 0 | Joiner | 0 | 40 | 24 | 37 | 32
1262 | 1.2.4.4.1.6.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1261 |  | - | - | 0 | Line Market | 0 | 11 | 28 | 5 | 36
1263 | 1.2.4.4.1.6.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Tiler | 0 | 27 | 30 | 68 | 39
1264 | 1.2.4.4.1.6.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Post Tension | 0 | 74 | 11 | 22 | 48
1265 | 1.2.4.4.1.6.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Admin | 0 | 93 | 14 | 85 | 33
1266 | 1.2.4.4.1.6.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Metal Work | 0 | 21 | 15 | 57 | 24
1267 | 1.2.4.4.1.6.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1317 | - | - | 0 | Post Tension | 0 | 68 | 32 | 77 | 19
1268 | 1.2.4.4.1.6.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 45 | 19 | 8 | 20
1269 | 1.2.4.4.1.6.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1270 | - | - | 0 | Excavation | 0 | 38 | 12 | 2 | 50
1270 | 1.2.4.4.1.6.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1269 | 1271 | - | - | 0 | Project Manager | 0 | 34 | 21 | 76 | 16
1271 | 1.2.4.4.1.6.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1270 | 1272 | - | - | 0 | Development Manager | 0 | 85 | 31 | 87 | 36
1272 | 1.2.4.4.1.6.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1271 | 1273 | - | - | 0 | Renderer | 0 | 14 | 19 | 70 | 30
1273 | 1.2.4.4.1.6.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1272 | 1274 | - | - | 0 | Foreman | 0 | 69 | 34 | 0 | 20
1274 | 1.2.4.4.1.6.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1273 | 1275 | - | - | 0 | Floor Sealer | 0 | 93 | 25 | 73 | 20
1275 | 1.2.4.4.1.6.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1274 | 1276 | - | - | 0 | Surveyor | 0 | 30 | 22 | 15 | 2
1276 | 1.2.4.4.1.6.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1275 | 1277 | - | - | 0 | Subcontractor | 0 | 39 | 32 | 46 | 4
1277 | 1.2.4.4.1.6.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1276 | 1278 | - | - | 0 | Line Market | 0 | 66 | 11 | 68 | 32
1278 | 1.2.4.4.1.6.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1277 | 1279 | - | - | 0 | Stone Mason | 0 | 12 | 20 | 100 | 15
1279 | 1.2.4.4.1.6.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1278 | 1280 | - | - | 0 | Carpet | 0 | 55 | 13 | 81 | 32
1280 | 1.2.4.4.1.6.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1279 | 1284,1281,1282,1283 | - | - | 0 | Admin | 0 | 63 | 29 | 91 | 5
1281 | 1.2.4.4.1.6.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Scaffolder | 0 | 80 | 35 | 40 | 44
1282 | 1.2.4.4.1.6.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Landscaper | 0 | 97 | 12 | 99 | 57
1283 | 1.2.4.4.1.6.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Landscaper | 0 | 49 | 17 | 95 | 3
1284 | 1.2.4.4.1.6.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1280,1281,1282,1283 |  | - | - | 0 | Subcontractor | 0 | 42 | 33 | 15 | 7
1285 | 1.2.4.4.1.6.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 80 | 18 | 2 | 60
1286 | 1.2.4.4.1.6.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1287 | - | - | 0 | Concretor | 0 | 59 | 15 | 35 | 50
1287 | 1.2.4.4.1.6.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1286 | 1288 | - | - | 0 | Timber Floorer | 0 | 37 | 28 | 2 | 20
1288 | 1.2.4.4.1.6.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1287 | 1289 | - | - | 0 | Waterproofer | 0 | 67 | 32 | 72 | 29
1289 | 1.2.4.4.1.6.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1288 | 1290 | - | - | 0 | Head Contractor | 0 | 44 | 12 | 20 | 28
1290 | 1.2.4.4.1.6.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1289 | 1291 | - | - | 0 | Landscaper | 0 | 64 | 20 | 6 | 14
1291 | 1.2.4.4.1.6.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1290 | 1292 | - | - | 0 | Development Manager | 0 | 87 | 32 | 87 | 33
1292 | 1.2.4.4.1.6.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1291 | 1293 | - | - | 0 | Metal Work | 0 | 49 | 18 | 98 | 43
1293 | 1.2.4.4.1.6.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1292 | 1294,1295,1296,1297 | - | - | 0 | Stone Mason | 0 | 64 | 12 | 32 | 49
1294 | 1.2.4.4.1.6.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Plasterboarder | 0 | 81 | 14 | 50 | 18
1295 | 1.2.4.4.1.6.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Post Tension | 0 | 89 | 30 | 46 | 11
1296 | 1.2.4.4.1.6.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Scaffolder | 0 | 34 | 33 | 89 | 12
1297 | 1.2.4.4.1.6.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Contract Administrator | 0 | 84 | 35 | 28 | 46
1298 | 1.2.4.4.1.6.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1294,1295,1296,1297 |  | - | - | 0 | Renderer | 0 | 14 | 35 | 10 | 22
1299 | 1.2.4.4.1.6.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 50 | 24 | 38 | 54
1300 | 1.2.4.4.1.6.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1228 | 1301 | - | - | 0 | Landscaper | 0 | 47 | 27 | 31 | 29
1301 | 1.2.4.4.1.6.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1300 |  | - | - | 0 | Concretor | 0 | 61 | 33 | 36 | 31
1302 | 1.2.4.4.1.6.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1237 | 1305 | - | - | 0 | Formworker | 0 | 64 | 17 | 71 | 13
1303 | 1.2.4.4.1.6.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1236 | 1305 | - | - | 0 | Waterproofer | 0 | 78 | 17 | 90 | 44
1304 | 1.2.4.4.1.6.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1233 | 1305 | - | - | 0 | Painter | 0 | 75 | 20 | 10 | 6
1305 | 1.2.4.4.1.6.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1302,1303,1304 | 1306 | - | - | 0 | Carpenter | 0 | 50 | 27 | 95 | 27
1306 | 1.2.4.4.1.6.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1305 | 1307 | - | - | 0 | Post Tension | 0 | 19 | 22 | 85 | 3
1307 | 1.2.4.4.1.6.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1306 | 1308 | - | - | 0 | Concretor | 0 | 94 | 28 | 17 | 46
1308 | 1.2.4.4.1.6.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1307 | 1309 | - | - | 0 | Mechanical | 0 | 26 | 34 | 54 | 28
1309 | 1.2.4.4.1.6.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1308 | 1310 | - | - | 0 | Development Manager | 0 | 45 | 21 | 46 | 60
1310 | 1.2.4.4.1.6.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1309 | 1311 | - | - | 0 | Hoarding | 0 | 56 | 25 | 19 | 7
1311 | 1.2.4.4.1.6.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1310 | 1312 | - | - | 0 | Subcontractor | 0 | 88 | 23 | 3 | 50
1312 | 1.2.4.4.1.6.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1311 | 1313,1314,1315,1316 | - | - | 0 | Plasterboarder | 0 | 37 | 32 | 12 | 57
1313 | 1.2.4.4.1.6.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Plumber | 0 | 38 | 11 | 76 | 44
1314 | 1.2.4.4.1.6.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Mechanical | 0 | 28 | 13 | 26 | 23
1315 | 1.2.4.4.1.6.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Electrician | 0 | 21 | 22 | 15 | 42
1316 | 1.2.4.4.1.6.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Plumber | 0 | 34 | 14 | 12 | 38
1317 | 1.2.4.4.1.6.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1263,1264,1265,1266,1267 | 1318 | - | - | 0 | Timber Floorer | 0 | 89 | 27 | 100 | 53
1318 | 1.2.4.4.1.6.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1317 | 1319 | - | - | 0 | Excavation | 0 | 53 | 11 | 26 | 51
1319 | 1.2.4.4.1.6.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1318 | 1320 | - | - | 0 | Project Manager | 0 | 46 | 29 | 2 | 59
1320 | 1.2.4.4.1.6.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1319 |  | - | - | 0 | Reinforcement Fixer | 0 | 99 | 35 | 4 | 22
1321 | 1.2.4.4.1.7 | Apartment B016 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Floor Sealer | 0 | 37 | 17 | 59 | 20
1322 | 1.2.4.4.1.7.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1323,1326,1327,1394 | - | - | 0 | Window | 0 | 98 | 14 | 12 | 35
1323 | 1.2.4.4.1.7.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1322 | 1325,1324 | - | - | 0 | Electrician | 0 | 74 | 11 | 78 | 22
1324 | 1.2.4.4.1.7.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1323 |  | - | - | 0 | Subcontractor | 0 | 73 | 35 | 87 | 22
1325 | 1.2.4.4.1.7.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1323 | 1328 | - | - | 0 | Mechanical | 0 | 10 | 12 | 56 | 31
1326 | 1.2.4.4.1.7.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1335 | - | - | 0 | Scaffolder | 0 | 82 | 17 | 39 | 56
1327 | 1.2.4.4.1.7.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1398 | - | - | 0 | Tiler | 0 | 54 | 11 | 91 | 19
1328 | 1.2.4.4.1.7.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1325 | 1329,1330,1331,1332,1333 | - | - | 0 | Post Tension | 0 | 95 | 31 | 11 | 28
1329 | 1.2.4.4.1.7.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333 | - | - | 0 | Timber Floorer | 0 | 40 | 11 | 11 | 48
1330 | 1.2.4.4.1.7.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333,1397 | - | - | 0 | Joiner | 0 | 28 | 21 | 28 | 30
1331 | 1.2.4.4.1.7.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1396 | - | - | 0 | Excavation | 0 | 55 | 16 | 45 | 21
1332 | 1.2.4.4.1.7.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 |  | - | - | 0 | Line Market | 0 | 51 | 20 | 49 | 12
1333 | 1.2.4.4.1.7.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1328,1329,1330 | 1334 | - | - | 0 | Metal Work | 0 | 20 | 10 | 100 | 14
1334 | 1.2.4.4.1.7.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1333 | 1335 | - | - | 0 | Hoarding | 0 | 81 | 16 | 18 | 30
1335 | 1.2.4.4.1.7.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1326,1334 | 1336,1337,1338,1339,1341,1343 | - | - | 0 | Carpet | 0 | 75 | 23 | 69 | 7
1336 | 1.2.4.4.1.7.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1340,1343 | - | - | 0 | Subcontractor | 0 | 32 | 27 | 3 | 10
1337 | 1.2.4.4.1.7.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Subcontractor | 0 | 100 | 27 | 47 | 2
1338 | 1.2.4.4.1.7.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1342,1343 | - | - | 0 | Hoarding | 0 | 59 | 13 | 97 | 4
1339 | 1.2.4.4.1.7.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Excavation | 0 | 43 | 24 | 53 | 24
1340 | 1.2.4.4.1.7.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1336 | 1343 | - | - | 0 | Tiler | 0 | 77 | 33 | 22 | 51
1341 | 1.2.4.4.1.7.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Post Tension | 0 | 97 | 35 | 87 | 6
1342 | 1.2.4.4.1.7.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1338 | 1343 | - | - | 0 | Formworker | 0 | 90 | 10 | 46 | 36
1343 | 1.2.4.4.1.7.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1335,1336,1337,1338,1339,1340,1341,1342 | 1344 | - | - | 0 | Site Manager | 0 | 32 | 16 | 21 | 6
1344 | 1.2.4.4.1.7.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1343 | 1345 | - | - | 0 | Site Manager | 0 | 84 | 20 | 3 | 15
1345 | 1.2.4.4.1.7.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1344 | 1346,1363,1380 | - | - | 0 | Mechanical | 0 | 36 | 32 | 54 | 19
1346 | 1.2.4.4.1.7.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1347 | - | - | 0 | Reinforcement Fixer | 0 | 50 | 35 | 77 | 54
1347 | 1.2.4.4.1.7.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1346 | 1348 | - | - | 0 | Window | 0 | 18 | 13 | 52 | 27
1348 | 1.2.4.4.1.7.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1347 | 1349 | - | - | 0 | Hoarding | 0 | 51 | 28 | 12 | 15
1349 | 1.2.4.4.1.7.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1348 | 1350 | - | - | 0 | Joiner | 0 | 40 | 19 | 90 | 32
1350 | 1.2.4.4.1.7.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1349 | 1351,1352 | - | - | 0 | Excavation | 0 | 38 | 23 | 47 | 31
1351 | 1.2.4.4.1.7.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1350 | 1355 | - | - | 0 | Contract Administrator | 0 | 74 | 15 | 49 | 13
1352 | 1.2.4.4.1.7.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1350 | 1353 | - | - | 0 | Foreman | 0 | 67 | 28 | 19 | 23
1353 | 1.2.4.4.1.7.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1352 | 1354 | - | - | 0 | Site Manager | 0 | 45 | 18 | 0 | 5
1354 | 1.2.4.4.1.7.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1353 |  | - | - | 0 | Plasterboarder | 0 | 29 | 19 | 40 | 51
1355 | 1.2.4.4.1.7.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1351 | 1356,1357,1358,1359,1360 | - | - | 0 | Painter | 0 | 91 | 22 | 70 | 41
1356 | 1.2.4.4.1.7.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1355 |  | - | - | 0 | Landscaper | 0 | 79 | 27 | 25 | 9
1357 | 1.2.4.4.1.7.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Tiler | 0 | 76 | 17 | 78 | 5
1358 | 1.2.4.4.1.7.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Electrician | 0 | 18 | 31 | 99 | 27
1359 | 1.2.4.4.1.7.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Contract Administrator | 0 | 20 | 11 | 66 | 27
1360 | 1.2.4.4.1.7.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Joiner | 0 | 88 | 15 | 36 | 26
1361 | 1.2.4.4.1.7.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1411 | - | - | 0 | Foreman | 0 | 54 | 20 | 41 | 25
1362 | 1.2.4.4.1.7.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 55 | 27 | 89 | 36
1363 | 1.2.4.4.1.7.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1364 | - | - | 0 | Joiner | 0 | 64 | 28 | 59 | 43
1364 | 1.2.4.4.1.7.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1363 | 1365 | - | - | 0 | Project Manager | 0 | 82 | 34 | 43 | 36
1365 | 1.2.4.4.1.7.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1364 | 1366 | - | - | 0 | Landscaper | 0 | 70 | 24 | 29 | 19
1366 | 1.2.4.4.1.7.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1365 | 1367 | - | - | 0 | Hoarding | 0 | 67 | 23 | 43 | 58
1367 | 1.2.4.4.1.7.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1366 | 1368 | - | - | 0 | Contract Administrator | 0 | 31 | 16 | 14 | 43
1368 | 1.2.4.4.1.7.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1367 | 1369 | - | - | 0 | Line Market | 0 | 44 | 12 | 69 | 33
1369 | 1.2.4.4.1.7.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1368 | 1370 | - | - | 0 | Hoarding | 0 | 59 | 21 | 10 | 53
1370 | 1.2.4.4.1.7.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1369 | 1371 | - | - | 0 | Hoarding | 0 | 90 | 29 | 79 | 35
1371 | 1.2.4.4.1.7.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1370 | 1372 | - | - | 0 | Tiler | 0 | 59 | 14 | 62 | 16
1372 | 1.2.4.4.1.7.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1371 | 1373 | - | - | 0 | Line Market | 0 | 86 | 27 | 86 | 13
1373 | 1.2.4.4.1.7.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1372 | 1374 | - | - | 0 | Electrician | 0 | 66 | 35 | 1 | 23
1374 | 1.2.4.4.1.7.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1373 | 1378,1375,1376,1377 | - | - | 0 | Development Manager | 0 | 96 | 30 | 78 | 52
1375 | 1.2.4.4.1.7.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Project Manager | 0 | 90 | 34 | 51 | 14
1376 | 1.2.4.4.1.7.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Site Manager | 0 | 46 | 21 | 6 | 46
1377 | 1.2.4.4.1.7.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Joiner | 0 | 31 | 22 | 59 | 40
1378 | 1.2.4.4.1.7.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1374,1375,1376,1377 |  | - | - | 0 | Admin | 0 | 27 | 33 | 39 | 37
1379 | 1.2.4.4.1.7.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Electrician | 0 | 20 | 13 | 51 | 37
1380 | 1.2.4.4.1.7.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1381 | - | - | 0 | Subcontractor | 0 | 78 | 34 | 19 | 3
1381 | 1.2.4.4.1.7.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1380 | 1382 | - | - | 0 | Painter | 0 | 52 | 34 | 97 | 2
1382 | 1.2.4.4.1.7.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1381 | 1383 | - | - | 0 | Metal Work | 0 | 24 | 28 | 62 | 59
1383 | 1.2.4.4.1.7.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1382 | 1384 | - | - | 0 | Post Tension | 0 | 26 | 29 | 14 | 11
1384 | 1.2.4.4.1.7.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1383 | 1385 | - | - | 0 | Landscaper | 0 | 98 | 35 | 58 | 39
1385 | 1.2.4.4.1.7.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1384 | 1386 | - | - | 0 | Electrician | 0 | 78 | 14 | 55 | 39
1386 | 1.2.4.4.1.7.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1385 | 1387 | - | - | 0 | Scaffolder | 0 | 69 | 34 | 66 | 27
1387 | 1.2.4.4.1.7.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1386 | 1388,1389,1390,1391 | - | - | 0 | Floor Sealer | 0 | 89 | 34 | 62 | 42
1388 | 1.2.4.4.1.7.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Head Contractor | 0 | 56 | 21 | 28 | 35
1389 | 1.2.4.4.1.7.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Carpet | 0 | 60 | 28 | 4 | 21
1390 | 1.2.4.4.1.7.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Scaffolder | 0 | 25 | 30 | 45 | 30
1391 | 1.2.4.4.1.7.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Carpet | 0 | 22 | 18 | 22 | 39
1392 | 1.2.4.4.1.7.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1388,1389,1390,1391 |  | - | - | 0 | Tiler | 0 | 68 | 18 | 100 | 57
1393 | 1.2.4.4.1.7.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | - | - | 0 | Excavation | 0 | 53 | 22 | 49 | 2
1394 | 1.2.4.4.1.7.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1322 | 1395 | - | - | 0 | Scaffolder | 0 | 62 | 30 | 48 | 8
1395 | 1.2.4.4.1.7.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1394 |  | - | - | 0 | Tiler | 0 | 29 | 15 | 35 | 4
1396 | 1.2.4.4.1.7.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1331 | 1399 | - | - | 0 | Surveyor | 0 | 74 | 35 | 19 | 48
1397 | 1.2.4.4.1.7.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1330 | 1399 | - | - | 0 | Plasterboarder | 0 | 17 | 15 | 40 | 57
1398 | 1.2.4.4.1.7.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1327 | 1399 | - | - | 0 | Line Market | 0 | 81 | 21 | 84 | 42
1399 | 1.2.4.4.1.7.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1396,1397,1398 | 1400 | - | - | 0 | Hoarding | 0 | 37 | 21 | 90 | 53
1400 | 1.2.4.4.1.7.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1399 | 1401 | - | - | 0 | Contract Administrator | 0 | 66 | 35 | 53 | 39
1401 | 1.2.4.4.1.7.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1400 | 1402 | - | - | 0 | Project Manager | 0 | 23 | 13 | 43 | 50
1402 | 1.2.4.4.1.7.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1401 | 1403 | - | - | 0 | Waterproofer | 0 | 76 | 19 | 57 | 26
1403 | 1.2.4.4.1.7.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1402 | 1404 | - | - | 0 | Line Market | 0 | 83 | 19 | 41 | 22
1404 | 1.2.4.4.1.7.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1403 | 1405 | - | - | 0 | Tiler | 0 | 47 | 29 | 37 | 7
1405 | 1.2.4.4.1.7.41.12 | Grout | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1404 | 1406 | - | - | 0 | Cleaner | 0 | 11 | 21 | 26 | 44
1406 | 1.2.4.4.1.7.41.13 | Paint/Cladding | 3 | 14 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1405 | 1407,1408,1409,1410 | - | - | 0 | Landscaper | 0 | 44 | 35 | 49 | 58
1407 | 1.2.4.4.1.7.41.14 | Silicone | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Reinforcement Fixer | 0 | 51 | 26 | 75 | 24
1408 | 1.2.4.4.1.7.41.15 | Hydraulic Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Subcontractor | 0 | 17 | 30 | 14 | 22
1409 | 1.2.4.4.1.7.41.16 | Electrical Fit Off | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Development Manager | 0 | 83 | 30 | 51 | 15
1410 | 1.2.4.4.1.7.41.17 | Fit Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Waterproofer | 0 | 83 | 16 | 100 | 22
1411 | 1.2.4.4.1.7.42 | Carpet Install | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1357,1358,1359,1360,1361 | 1412 | - | - | 0 | Admin | 0 | 100 | 26 | 97 | 41
1412 | 1.2.4.4.1.7.43 | Paint (FINAL Coat) | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1411 | 1413 | - | - | 0 | Carpenter | 0 | 75 | 26 | 74 | 7
1413 | 1.2.4.4.1.7.44 | FINAL CLEAN | 1 | 11 December 2024 8:00 AM | 11 December 2024 5:00 PM | 1412 | 1414 | - | - | 0 | Site Manager | 0 | 51 | 18 | 17 | 46
1414 | 1.2.4.4.1.7.45 | UNIT LOCKED | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 1413 |  | - | - | 0 | Subcontractor | 0 | 64 | 14 | 63 | 54
1415 | 1.2.4.4.1.8 | Apartment B017 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Post Tension | 0 | 12 | 30 | 70 | 37
1416 | 1.2.4.4.1.8.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1417,1420,1421,1488 | - | - | 0 | Surveyor | 0 | 46 | 20 | 32 | 26
1417 | 1.2.4.4.1.8.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1416 | 1419,1418 | - | - | 0 | Waterproofer | 0 | 95 | 18 | 10 | 50
1418 | 1.2.4.4.1.8.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1417 |  | - | - | 0 | Tiler | 0 | 49 | 19 | 91 | 39
1419 | 1.2.4.4.1.8.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1417 | 1422 | - | - | 0 | Cleaner | 0 | 24 | 34 | 87 | 38
1420 | 1.2.4.4.1.8.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1429 | - | - | 0 | Site Manager | 0 | 76 | 29 | 83 | 39
1421 | 1.2.4.4.1.8.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1492 | - | - | 0 | Formworker | 0 | 44 | 27 | 13 | 32
1422 | 1.2.4.4.1.8.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1419 | 1423,1424,1425,1426,1427 | - | - | 0 | Formworker | 0 | 62 | 11 | 56 | 34
1423 | 1.2.4.4.1.8.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427 | - | - | 0 | Formworker | 0 | 27 | 26 | 33 | 18
1424 | 1.2.4.4.1.8.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427,1491 | - | - | 0 | Post Tension | 0 | 21 | 15 | 52 | 22
1425 | 1.2.4.4.1.8.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1490 | - | - | 0 | Fire | 0 | 21 | 35 | 89 | 30
1426 | 1.2.4.4.1.8.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 |  | - | - | 0 | Carpet | 0 | 36 | 35 | 11 | 54
1427 | 1.2.4.4.1.8.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1422,1423,1424 | 1428 | - | - | 0 | Formworker | 0 | 64 | 24 | 29 | 8
1428 | 1.2.4.4.1.8.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1427 | 1429 | - | - | 0 | Plasterboarder | 0 | 76 | 14 | 55 | 15
1429 | 1.2.4.4.1.8.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1420,1428 | 1430,1431,1432,1433,1435,1437 | - | - | 0 | Metal Work | 0 | 11 | 27 | 91 | 45
1430 | 1.2.4.4.1.8.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1434,1437 | - | - | 0 | Hoarding | 0 | 50 | 33 | 56 | 40
1431 | 1.2.4.4.1.8.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Carpet | 0 | 33 | 34 | 29 | 31
1432 | 1.2.4.4.1.8.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1436,1437 | - | - | 0 | Stone Mason | 0 | 73 | 31 | 54 | 19
1433 | 1.2.4.4.1.8.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Renderer | 0 | 95 | 19 | 48 | 8
1434 | 1.2.4.4.1.8.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1430 | 1437 | - | - | 0 | Foreman | 0 | 28 | 24 | 43 | 50
1435 | 1.2.4.4.1.8.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Tiler | 0 | 39 | 30 | 8 | 8
1436 | 1.2.4.4.1.8.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1432 | 1437 | - | - | 0 | Timber Floorer | 0 | 80 | 25 | 83 | 58
1437 | 1.2.4.4.1.8.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1429,1430,1431,1432,1433,1434,1435,1436 | 1438 | - | - | 0 | Mechanical | 0 | 64 | 21 | 98 | 23
1438 | 1.2.4.4.1.8.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1437 | 1439 | - | - | 0 | Stone Mason | 0 | 83 | 28 | 42 | 4
1439 | 1.2.4.4.1.8.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1438 | 1440,1457,1474 | - | - | 0 | Foreman | 0 | 42 | 32 | 97 | 37
1440 | 1.2.4.4.1.8.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1441 | - | - | 0 | Contract Administrator | 0 | 56 | 25 | 62 | 31
1441 | 1.2.4.4.1.8.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1440 | 1442 | - | - | 0 | Carpet | 0 | 43 | 30 | 66 | 57
1442 | 1.2.4.4.1.8.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1441 | 1443 | - | - | 0 | Floor Sealer | 0 | 11 | 17 | 80 | 17
1443 | 1.2.4.4.1.8.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1442 | 1444 | - | - | 0 | Reinforcement Fixer | 0 | 39 | 25 | 10 | 58
1444 | 1.2.4.4.1.8.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1443 | 1445,1446 | - | - | 0 | Line Market | 0 | 47 | 26 | 15 | 35
1445 | 1.2.4.4.1.8.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1444 | 1449 | - | - | 0 | Hoarding | 0 | 95 | 31 | 28 | 17
1446 | 1.2.4.4.1.8.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1444 | 1447 | - | - | 0 | Development Manager | 0 | 80 | 16 | 18 | 5
1447 | 1.2.4.4.1.8.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1446 | 1448 | - | - | 0 | Head Contractor | 0 | 45 | 30 | 41 | 56
1448 | 1.2.4.4.1.8.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1447 |  | - | - | 0 | Renderer | 0 | 15 | 18 | 80 | 50
1449 | 1.2.4.4.1.8.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1445 | 1450,1451,1452,1453,1454 | - | - | 0 | Surveyor | 0 | 91 | 28 | 80 | 51
1450 | 1.2.4.4.1.8.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1449 |  | - | - | 0 | Cleaner | 0 | 24 | 27 | 94 | 15
1451 | 1.2.4.4.1.8.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Floor Sealer | 0 | 15 | 18 | 98 | 11
1452 | 1.2.4.4.1.8.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Subcontractor | 0 | 62 | 20 | 89 | 45
1453 | 1.2.4.4.1.8.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Renderer | 0 | 54 | 33 | 34 | 36
1454 | 1.2.4.4.1.8.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Cleaner | 0 | 92 | 22 | 79 | 19
1455 | 1.2.4.4.1.8.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1505 | - | - | 0 | Mechanical | 0 | 97 | 15 | 23 | 48
1456 | 1.2.4.4.1.8.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 70 | 26 | 87 | 54
1457 | 1.2.4.4.1.8.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1458 | - | - | 0 | Mechanical | 0 | 36 | 27 | 5 | 34
1458 | 1.2.4.4.1.8.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1457 | 1459 | - | - | 0 | Foreman | 0 | 15 | 33 | 9 | 8
1459 | 1.2.4.4.1.8.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1458 | 1460 | - | - | 0 | Waterproofer | 0 | 34 | 17 | 34 | 32
1460 | 1.2.4.4.1.8.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1459 | 1461 | - | - | 0 | Project Manager | 0 | 86 | 31 | 34 | 21
1461 | 1.2.4.4.1.8.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1460 | 1462 | - | - | 0 | Carpet | 0 | 11 | 18 | 71 | 39
1462 | 1.2.4.4.1.8.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1461 | 1463 | - | - | 0 | Admin | 0 | 87 | 10 | 72 | 34
1463 | 1.2.4.4.1.8.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1462 | 1464 | - | - | 0 | Scaffolder | 0 | 36 | 23 | 54 | 24
1464 | 1.2.4.4.1.8.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1463 | 1465 | - | - | 0 | Joiner | 0 | 11 | 32 | 15 | 49
1465 | 1.2.4.4.1.8.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1464 | 1466 | - | - | 0 | Painter | 0 | 98 | 24 | 73 | 27
1466 | 1.2.4.4.1.8.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1465 | 1467 | - | - | 0 | Foreman | 0 | 13 | 18 | 12 | 35
1467 | 1.2.4.4.1.8.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1466 | 1468 | - | - | 0 | Plasterboarder | 0 | 54 | 13 | 69 | 17
1468 | 1.2.4.4.1.8.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1467 | 1472,1469,1470,1471 | - | - | 0 | Plasterboarder | 0 | 71 | 19 | 11 | 33
1469 | 1.2.4.4.1.8.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Window | 0 | 15 | 30 | 98 | 49
1470 | 1.2.4.4.1.8.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Electrician | 0 | 10 | 15 | 69 | 48
1471 | 1.2.4.4.1.8.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Reinforcement Fixer | 0 | 41 | 11 | 54 | 54
1472 | 1.2.4.4.1.8.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1468,1469,1470,1471 |  | - | - | 0 | Carpenter | 0 | 72 | 17 | 87 | 41
1473 | 1.2.4.4.1.8.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Project Manager | 0 | 92 | 24 | 69 | 59
1474 | 1.2.4.4.1.8.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1475 | - | - | 0 | Metal Work | 0 | 61 | 23 | 53 | 9
1475 | 1.2.4.4.1.8.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1474 | 1476 | - | - | 0 | Formworker | 0 | 12 | 25 | 65 | 34
1476 | 1.2.4.4.1.8.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1475 | 1477 | - | - | 0 | Landscaper | 0 | 59 | 33 | 26 | 23
1477 | 1.2.4.4.1.8.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1476 | 1478 | - | - | 0 | Fire | 0 | 64 | 31 | 27 | 12
1478 | 1.2.4.4.1.8.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1477 | 1479 | - | - | 0 | Head Contractor | 0 | 42 | 33 | 82 | 56
1479 | 1.2.4.4.1.8.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1478 | 1480 | - | - | 0 | Contract Administrator | 0 | 66 | 28 | 67 | 51
1480 | 1.2.4.4.1.8.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1479 | 1481 | - | - | 0 | Project Manager | 0 | 52 | 12 | 49 | 16
1481 | 1.2.4.4.1.8.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1480 | 1482,1483,1484,1485 | - | - | 0 | Window | 0 | 41 | 33 | 15 | 7
1482 | 1.2.4.4.1.8.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Timber Floorer | 0 | 20 | 27 | 10 | 8
1483 | 1.2.4.4.1.8.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Renderer | 0 | 81 | 14 | 37 | 6
1484 | 1.2.4.4.1.8.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Painter | 0 | 16 | 30 | 64 | 37
1485 | 1.2.4.4.1.8.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Plasterboarder | 0 | 59 | 29 | 91 | 10
1486 | 1.2.4.4.1.8.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1482,1483,1484,1485 |  | - | - | 0 | Project Manager | 0 | 62 | 33 | 86 | 23
1487 | 1.2.4.4.1.8.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 48 | 26 | 37 | 20
1488 | 1.2.4.4.1.8.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1416 | 1489 | - | - | 0 | Floor Sealer | 0 | 51 | 16 | 32 | 56
1489 | 1.2.4.4.1.8.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1488 |  | - | - | 0 | Joiner | 0 | 50 | 21 | 65 | 53
1490 | 1.2.4.4.1.8.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1425 | 1493 | - | - | 0 | Admin | 0 | 24 | 26 | 85 | 48
1491 | 1.2.4.4.1.8.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1424 | 1493 | - | - | 0 | Line Market | 0 | 79 | 11 | 90 | 30
1492 | 1.2.4.4.1.8.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1421 | 1493 | - | - | 0 | Scaffolder | 0 | 31 | 12 | 80 | 59
1493 | 1.2.4.4.1.8.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1490,1491,1492 | 1494 | - | - | 0 | Surveyor | 0 | 63 | 24 | 38 | 55
1494 | 1.2.4.4.1.8.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1493 | 1495 | - | - | 0 | Concretor | 0 | 73 | 22 | 82 | 44
1495 | 1.2.4.4.1.8.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1494 | 1496 | - | - | 0 | Waterproofer | 0 | 99 | 25 | 9 | 24
1496 | 1.2.4.4.1.8.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1495 | 1497 | - | - | 0 | Development Manager | 0 | 13 | 35 | 65 | 56
1497 | 1.2.4.4.1.8.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1496 | 1498 | - | - | 0 | Scaffolder | 0 | 28 | 19 | 44 | 15
1498 | 1.2.4.4.1.8.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1497 | 1499 | - | - | 0 | Surveyor | 0 | 86 | 31 | 94 | 60

## Progress 50%
ID | Outline_Number | Name | Duration | Start_Date | Finish_Date | Predecessors | Successors | Actual_Start | Actual_End | Delay | Trade | Progress | Worker_Score | Temp | Rain_Probability | Wind_Speed
2 | 1.1 | MILESTONES / KEY DATES | 633 | 17 April 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 17 April 2023 7:00 AM | - | 0 |  | 49.893 | - | - | - | -
3 | 1.1.1 | Site Establishment | 0 | 5 June 2023 7:00 AM | 5 June 2023 7:00 AM |  | 25SS | 5 June 2023 7:00 AM | 2023-06-05 07:00 | 0 | Plasterboarder | 100 | 33 | 30 | 69 | 19
4 | 1.1.2 | Basement Completed (B2) | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 88 |  | 2 May 2024 5:00 PM | 2024-05-02 17:00 | 0 | Timber Floorer | 100 | 93 | 24 | 2 | 16
5 | 1.1.3 | Building A Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 444,753,746,714 | 3466,9 | 5 May 2025 5:00 PM | 2025-05-05 17:00 | 0 | Floor Sealer | 100 | 72 | 30 | 36 | 57
6 | 1.1.4 | Building B Complete | 0 | 29 March 2025 5:00 PM | 29 March 2025 5:00 PM | 228,482,306,1737 | 3466,9 | 29 March 2025 5:00 PM | 2025-03-29 17:00 | 0 | Scaffolder | 100 | 89 | 22 | 78 | 33
7 | 1.1.5 | Building C Complete | 0 | 16 April 2025 5:00 PM | 16 April 2025 5:00 PM | 306,360,503,3169 | 3466,9 | 16 April 2025 5:00 PM | 2025-04-16 17:00 | 0 | Painter | 100 | 19 | 14 | 44 | 60
8 | 1.1.6 | Building D Complete | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 360,396,519,3439 | 3466,9 | 17 April 2025 5:00 PM | 2025-04-17 17:00 | 0 | Post Tension | 100 | 72 | 18 | 31 | 43
9 | 1.1.7 | Practical Completion (Net) | 0 | 28 May 2025 5:00 PM | 28 May 2025 5:00 PM | 3465,3440,5,3460,6,7,8 |  | 28 May 2025 5:00 PM | 2025-05-28 17:00 | 0 | Admin | 100 | 56 | 30 | 35 | 39
10 | 1.1.8 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | 28 July 2023 8:00 AM | 2023-08-15 17:00 | 0 | Plasterboarder | 100 | 34 | 14 | 40 | 35
11 | 1.1.9 | Inclement Weatherallowed (Spent) | 19 | 29 May 2025 8:00 AM | 21 June 2025 5:00 PM | 3466 | 12 | 29 May 2025 8:00 AM | 2025-06-23 17:00 | 2 | Subcontractor | 100 | 15 | 12 | 75 | 32
12 | 1.1.10 | Inclement Weatherallowed (Remaining) | 1 | 23 June 2025 8:00 AM | 23 June 2025 5:00 PM | 11 | 3469 | 23 June 2025 8:00 AM | 2025-06-23 17:00 | 0 | Painter | 100 | 50 | 33 | 73 | 35
13 | 1.1.11 | Practical Completion (Gross) - Building Handover | 0 | 23 June 2025 5:00 PM | 23 June 2025 5:00 PM | 3469 |  | 23 June 2025 5:00 PM | 2025-06-23 17:00 | 0 | Contract Administrator | 100 | 88 | 22 | 67 | 45
14 | 1.1.12 | PRE CONSTRUCTION WORKS | 210.13 | 17 April 2023 7:00 AM | 16 January 2024 5:00 PM |  |  | 17 April 2023 7:00 AM | 2024-01-16 17:00 | 0 | Stone Mason | 100 | 70 | 22 | 98 | 35
15 | 1.1.12.1 | Authority Approvals, (Access Deeds by Client etc (Ultra to assist in coordination) These are qualifying causes of delay resulting in EOT time & costs) | 372 | 17 April 2023 7:00 AM | 1 August 2024 5:00 PM |  |  | 17 April 2023 7:00 AM | 2024-08-04 17:00 | 3 | Scaffolder | 100 | 19 | 24 | 60 | 26
16 | 1.1.12.1.1 | Section 73 - BPA Design & Stormwater Works | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Mechanical | 100 | 85 | 35 | 39 | 22
17 | 1.1.12.1.2 | Rail Approval | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Scaffolder | 100 | 63 | 17 | 5 | 5
18 | 1.1.12.1.3 | CC1 - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  | 25,19 | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Electrician | 100 | 93 | 19 | 7 | 35
19 | 1.1.12.1.4 | CC1a - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM | 18 | 25,20 | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Post Tension | 100 | 60 | 35 | 80 | 46
20 | 1.1.12.1.5 | CC2 - Structure (SoG - Podium) | 120 | 17 April 2023 8:00 AM | 12 September 2023 5:00 PM | 19 | 21 | 17 April 2023 8:00 AM | 2023-09-13 17:00 | 1 | Floor Sealer | 100 | 75 | 15 | 51 | 10
21 | 1.1.12.1.6 | CC3 - Structure (Podium - Roof) + Facade | 156 | 13 September 2023 8:00 AM | 8 April 2024 5:00 PM | 20 | 22 | 13 September 2023 8:00 AM | 2024-04-13 17:00 | 5 | Window | 100 | 13 | 24 | 47 | 16
22 | 1.1.12.1.7 | CC4 - Services & Fit Out | 60 | 9 April 2024 8:00 AM | 20 June 2024 5:00 PM | 21 | 23 | 9 April 2024 8:00 AM | 2024-06-21 17:00 | 1 | Plumber | 100 | 71 | 25 | 85 | 39
23 | 1.1.12.1.8 | CC5 - External Works and Public Domain | 36 | 21 June 2024 8:00 AM | 1 August 2024 5:00 PM | 22 |  | 21 June 2024 8:00 AM | 2024-08-04 17:00 | 3 | Development Manager | 100 | 46 | 24 | 87 | 24
24 | 1.1.12.2 | SITE ESTABLISHMENT | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM |  |  | 26 June 2023 8:00 AM | 2023-06-30 17:00 | 0 | Head Contractor | 100 | 85 | 10 | 99 | 53
25 | 1.1.12.2.1 | Site Establishment, Enviro Protection, Survey Set out & Hoardings | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM | 18,3SS,19 | 28 | 26 June 2023 8:00 AM | 2023-06-30 17:00 | 0 | Painter | 100 | 22 | 30 | 48 | 39
26 | 1.2 | CONSTRUCTION WORKS | 571 | 3 July 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 3 July 2023 7:00 AM | 2025-06-24 17:00 | 1 | Mechanical | 100 | 65 | 11 | 2 | 33
27 | 1.2.1 | EARTHWORKS, PILING - BASEMENT | 234 | 3 July 2023 7:00 AM | 2 May 2024 5:00 PM |  |  | 3 July 2023 7:00 AM | 2024-05-06 17:00 | 4 | Contract Administrator | 100 | 25 | 23 | 51 | 8
28 | 1.2.1.1 | Demolition, Clear & Cut/Level Site | 6 | 3 July 2023 7:00 AM | 8 July 2023 5:00 PM | 25 | 10SS,29SS | 3 July 2023 7:00 AM | 2023-07-08 17:00 | 0 | Plasterboarder | 100 | 22 | 25 | 82 | 58
29 | 1.2.1.2 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | 28 July 2023 8:00 AM | 2023-08-15 17:00 | 0 | Head Contractor | 100 | 26 | 29 | 29 | 19
30 | 1.2.1.3 | Install Piling Matt | 12 | 16 August 2023 8:00 AM | 30 August 2023 5:00 PM | 10,29 | 34FS-6d | 16 August 2023 8:00 AM | 2023-09-03 17:00 | 4 | Tiler | 100 | 11 | 21 | 74 | 41
31 | 1.2.1.4 | Crane Base Ex, Piles & FRP | 8 | 18 December 2023 8:00 AM | 5 January 2024 5:00 PM | 53 | 3442FS+8d | 18 December 2023 8:00 AM | 2024-01-08 17:00 | 3 | Cleaner | 100 | 44 | 29 | 28 | 18
32 | 1.2.1.5 | Piling and Capping Beam | 58 | 28 August 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | 28 August 2023 8:00 AM | 2023-11-13 17:00 | 4 | Concretor | 100 | 14 | 26 | 34 | 47
33 | 1.2.1.5.1 | Buildings A | 28 | 28 August 2023 8:00 AM | 3 October 2023 5:00 PM |  |  | 28 August 2023 8:00 AM | 2023-10-03 17:00 | 0 | Formworker | 100 | 45 | 22 | 36 | 9
34 | 1.2.1.5.1.1 | Perimeter Piling (75 Piles) | 16 | 28 August 2023 8:00 AM | 15 September 2023 5:00 PM | 30FS-6d | 35FS-6d,37,46 | 28 August 2023 8:00 AM | 2023-09-20 17:00 | 5 | Electrician | 100 | 54 | 20 | 97 | 34
35 | 1.2.1.5.1.2 | Capping Beam - Detailed Excavation & FRP | 18 | 9 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34FS-6d |  | 9 September 2023 8:00 AM | 2023-10-06 17:00 | 3 | Metal Work | 100 | 74 | 14 | 48 | 11
36 | 1.2.1.5.2 | Buildings B | 24 | 16 September 2023 8:00 AM | 17 October 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-10-21 17:00 | 4 | Renderer | 100 | 40 | 32 | 55 | 50
37 | 1.2.1.5.2.1 | Perimeter Piling (56 Piles) | 12 | 16 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34 | 38FS-6d,40 | 16 September 2023 8:00 AM | 2023-10-08 17:00 | 5 | Carpenter | 100 | 71 | 11 | 93 | 37
38 | 1.2.1.5.2.2 | Capping Beam - Detailed Excavation & FRP | 18 | 25 September 2023 8:00 AM | 17 October 2023 5:00 PM | 37FS-6d | 56 | 25 September 2023 8:00 AM | 2023-10-22 17:00 | 5 | Development Manager | 100 | 88 | 10 | 11 | 60
39 | 1.2.1.5.3 | Buildings C & D | 30 | 4 October 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | 4 October 2023 8:00 AM | 2023-11-09 17:00 | 0 | Foreman | 100 | 16 | 11 | 37 | 11
40 | 1.2.1.5.3.1 | Foundation Piling (Gnd Lvl) - (17 Piles) | 6 | 4 October 2023 8:00 AM | 10 October 2023 5:00 PM | 37 | 41 | 4 October 2023 8:00 AM | 2023-10-10 17:00 | 0 | Cleaner | 100 | 70 | 34 | 70 | 4
41 | 1.2.1.5.3.2 | Perimeter Piling (82 Piles) | 18 | 11 October 2023 8:00 AM | 1 November 2023 5:00 PM | 40 | 42FS-6d | 11 October 2023 8:00 AM | 2023-11-03 17:00 | 2 | Reinforcement Fixer | 100 | 79 | 19 | 79 | 48
42 | 1.2.1.5.3.3 | Capping Beam - Detailed Excavation & FRP | 12 | 26 October 2023 8:00 AM | 9 November 2023 5:00 PM | 41FS-6d | 66 | 26 October 2023 8:00 AM | 2023-11-10 17:00 | 1 | Excavation | 100 | 30 | 35 | 30 | 58
43 | 1.2.1.6 | Bulk Excavation & Shotcrete | 142 | 16 September 2023 8:00 AM | 22 March 2024 5:00 PM |  |  | 16 September 2023 8:00 AM | 2024-03-22 17:00 | 0 | Reinforcement Fixer | 100 | 32 | 10 | 20 | 3
44 | 1.2.1.6.1 | Building A | 70 | 16 September 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-12-16 17:00 | 0 | Carpet | 100 | 47 | 27 | 11 | 3
45 | 1.2.1.6.1.1 | Excavate - Gnd - B1 | 57 | 16 September 2023 8:00 AM | 28 November 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-11-28 17:00 | 0 | Hoarding | 100 | 31 | 18 | 47 | 57
46 | 1.2.1.6.1.1.1 | Excavation | 21 | 16 September 2023 8:00 AM | 13 October 2023 5:00 PM | 34 | 47,56,51,71 | 16 September 2023 8:00 AM | 2023-10-18 17:00 | 5 | Carpet | 100 | 94 | 28 | 49 | 30
47 | 1.2.1.6.1.1.2 | Installation of Anchors | 8 | 20 October 2023 8:00 AM | 30 October 2023 5:00 PM | 46 | 48,49SS+11d | 20 October 2023 8:00 AM | 2023-11-01 17:00 | 2 | Plumber | 100 | 37 | 26 | 54 | 53
48 | 1.2.1.6.1.1.3 | Install Bracing | 4 | 31 October 2023 8:00 AM | 3 November 2023 5:00 PM | 47 |  | 31 October 2023 8:00 AM | 2023-11-03 17:00 | 0 | Project Manager | 100 | 95 | 14 | 28 | 46
49 | 1.2.1.6.1.1.4 | Shotcrete | 20 | 3 November 2023 8:00 AM | 28 November 2023 5:00 PM | 47SS+11d |  | 3 November 2023 8:00 AM | 2023-11-28 17:00 | 0 | Painter | 100 | 29 | 12 | 72 | 3
50 | 1.2.1.6.1.2 | Excavate - B1-B2 | 44 | 20 October 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | 20 October 2023 8:00 AM | 2023-12-16 17:00 | 0 | Carpet | 100 | 28 | 16 | 21 | 7
51 | 1.2.1.6.1.2.1 | Excavation | 14 | 20 October 2023 8:00 AM | 7 November 2023 5:00 PM | 46 | 52,53,56,71 | 20 October 2023 8:00 AM | 2023-11-10 17:00 | 3 | Electrician | 100 | 77 | 15 | 71 | 59
52 | 1.2.1.6.1.2.2 | Shotcrete | 16 | 15 November 2023 8:00 AM | 7 December 2023 5:00 PM | 51 | 53 | 15 November 2023 8:00 AM | 2023-12-12 17:00 | 5 | Fire | 100 | 45 | 28 | 74 | 4
53 | 1.2.1.6.1.2.3 | Foundation Piling (Basement 2 Lvl) - (35 Piles) | 8 | 8 December 2023 8:00 AM | 16 December 2023 5:00 PM | 51,52 | 63,31 | 8 December 2023 8:00 AM | 2023-12-16 17:00 | 0 | Formworker | 100 | 71 | 27 | 59 | 40
54 | 1.2.1.6.2 | Building B | 66 | 15 November 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | 15 November 2023 8:00 AM | 2024-02-16 17:00 | 0 | Site Manager | 100 | 77 | 28 | 81 | 47
55 | 1.2.1.6.2.1 | Excavate - Gnd - B1 | 46 | 15 November 2023 8:00 AM | 22 January 2024 5:00 PM |  |  | 15 November 2023 8:00 AM | 2024-01-26 17:00 | 4 | Plumber | 100 | 34 | 23 | 60 | 57
56 | 1.2.1.6.2.1.1 | Excavation | 22 | 15 November 2023 8:00 AM | 14 December 2023 5:00 PM | 38,46,51 | 57,59,61,71 | 15 November 2023 8:00 AM | 2023-12-16 17:00 | 2 | Excavation | 100 | 69 | 18 | 68 | 16
57 | 1.2.1.6.2.1.2 | Installation of Anchors | 8 | 20 December 2023 8:00 AM | 8 January 2024 5:00 PM | 56 | 58 | 20 December 2023 8:00 AM | 2024-01-09 17:00 | 1 | Cleaner | 100 | 62 | 31 | 70 | 45
58 | 1.2.1.6.2.1.3 | Install Bracing | 4 | 9 January 2024 8:00 AM | 12 January 2024 5:00 PM | 57 | 59 | 9 January 2024 8:00 AM | 2024-01-12 17:00 | 0 | Head Contractor | 100 | 21 | 14 | 72 | 38
59 | 1.2.1.6.2.1.4 | Shotcrete | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,58 | 61 | 20 December 2023 8:00 AM | 2024-01-23 17:00 | 1 | Floor Sealer | 100 | 52 | 13 | 62 | 23
60 | 1.2.1.6.2.2 | Excavate - B1-B2 | 40 | 20 December 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | 20 December 2023 8:00 AM | 2024-02-20 17:00 | 4 | Fire | 100 | 61 | 24 | 64 | 15
61 | 1.2.1.6.2.2.1 | Excavation | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,59 | 66,63,71,62 | 20 December 2023 8:00 AM | 2024-01-27 17:00 | 5 | Metal Work | 100 | 66 | 19 | 85 | 18
62 | 1.2.1.6.2.2.2 | Shotcrete | 10 | 1 February 2024 8:00 AM | 12 February 2024 5:00 PM | 61 | 63 | 1 February 2024 8:00 AM | 2024-02-12 17:00 | 0 | Contract Administrator | 100 | 56 | 26 | 17 | 44
63 | 1.2.1.6.2.2.3 | Foundation Piling (Basement 2 Lvl) - (23 Piles) | 4 | 13 February 2024 8:00 AM | 16 February 2024 5:00 PM | 61,53,62 | 74 | 13 February 2024 8:00 AM | 2024-02-16 17:00 | 0 | Stone Mason | 100 | 88 | 13 | 37 | 14
64 | 1.2.1.6.3 | Buildings C & D | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | 23 January 2024 8:00 AM | 2024-03-22 17:00 | 0 | Mechanical | 100 | 61 | 21 | 14 | 43
65 | 1.2.1.6.3.1 | Excavate - Gnd - B2 | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | 23 January 2024 8:00 AM | 2024-03-27 17:00 | 5 | Foreman | 100 | 20 | 13 | 44 | 37
66 | 1.2.1.6.3.1.1 | Excavation | 30 | 23 January 2024 8:00 AM | 28 February 2024 5:00 PM | 42,61 | 67,71 | 23 January 2024 8:00 AM | 2024-03-01 17:00 | 2 | Plumber | 100 | 61 | 32 | 20 | 2
67 | 1.2.1.6.3.1.2 | Installation of Anchors | 8 | 29 February 2024 8:00 AM | 8 March 2024 5:00 PM | 66 | 68 | 29 February 2024 8:00 AM | 2024-03-08 17:00 | 0 | Site Manager | 100 | 84 | 28 | 71 | 35
68 | 1.2.1.6.3.1.3 | Install Bracing | 4 | 9 March 2024 8:00 AM | 13 March 2024 5:00 PM | 67 | 69 | 9 March 2024 8:00 AM | 2024-03-13 17:00 | 0 | Fire | 100 | 64 | 12 | 34 | 26
69 | 1.2.1.6.3.1.4 | Shotcrete | 6 | 14 March 2024 8:00 AM | 20 March 2024 5:00 PM | 68 | 70,84 | 14 March 2024 8:00 AM | 2024-03-20 17:00 | 0 | Contract Administrator | 100 | 83 | 31 | 66 | 32
70 | 1.2.1.6.3.1.5 | Foundation Piling (Basement 2 Lvl) - (5 Piles) | 2 | 21 March 2024 8:00 AM | 22 March 2024 5:00 PM | 69 | 86 | 21 March 2024 8:00 AM | 2024-03-22 17:00 | 0 | Mechanical | 100 | 46 | 14 | 21 | 20
71 | 1.2.1.6.4 | Complete Bulk Exacavation | 0 | 28 February 2024 5:00 PM | 28 February 2024 5:00 PM | 46,51,56,61,66 |  | 28 February 2024 5:00 PM | 2024-02-28 17:00 | 0 | Admin | 100 | 78 | 19 | 72 | 21
72 | 1.2.1.7 | Detail Excavation, Services & Base course | 61 | 17 February 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | 17 February 2024 8:00 AM | 2024-05-07 17:00 | 5 | Window | 100 | 97 | 11 | 6 | 28
73 | 1.2.1.7.1 | Stage 1 (Building A) | 32 | 17 February 2024 8:00 AM | 25 March 2024 5:00 PM |  |  | 17 February 2024 8:00 AM | 2024-03-29 17:00 | 4 | Concretor | 100 | 46 | 20 | 55 | 55
74 | 1.2.1.7.1.1 | Detailed Excavation | 11 | 17 February 2024 8:00 AM | 29 February 2024 5:00 PM | 63 | 75,79 | 17 February 2024 8:00 AM | 2024-03-02 17:00 | 2 | Formworker | 100 | 63 | 10 | 29 | 2
75 | 1.2.1.7.1.2 | In-Ground Services | 8 | 1 March 2024 8:00 AM | 9 March 2024 5:00 PM | 74 | 76 | 1 March 2024 8:00 AM | 2024-03-12 17:00 | 3 | Plumber | 100 | 63 | 27 | 4 | 44
76 | 1.2.1.7.1.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 11 March 2024 8:00 AM | 15 March 2024 5:00 PM | 75 | 77 | 11 March 2024 8:00 AM | 2024-03-15 17:00 | 0 | Foreman | 100 | 66 | 35 | 9 | 4
77 | 1.2.1.7.1.4 | Base Course to Basement | 8 | 16 March 2024 8:00 AM | 25 March 2024 5:00 PM | 76 | 88 | 16 March 2024 8:00 AM | 2024-03-25 17:00 | 0 | Metal Work | 100 | 99 | 31 | 70 | 35
78 | 1.2.1.7.2 | Stage 2 (Building B) | 32 | 1 March 2024 8:00 AM | 10 April 2024 5:00 PM |  |  | 1 March 2024 8:00 AM | 2024-04-15 17:00 | 5 | Reinforcement Fixer | 100 | 81 | 25 | 57 | 46
79 | 1.2.1.7.2.1 | Detailed Excavation | 12 | 1 March 2024 8:00 AM | 14 March 2024 5:00 PM | 74 | 80 | 1 March 2024 8:00 AM | 2024-03-17 17:00 | 3 | Surveyor | 100 | 75 | 13 | 36 | 59
80 | 1.2.1.7.2.2 | In-Ground Services | 9 | 15 March 2024 8:00 AM | 25 March 2024 5:00 PM | 79 | 81 | 15 March 2024 8:00 AM | 2024-03-27 17:00 | 2 | Surveyor | 100 | 57 | 16 | 68 | 31
81 | 1.2.1.7.2.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 6 | 26 March 2024 8:00 AM | 4 April 2024 5:00 PM | 80 | 82 | 26 March 2024 8:00 AM | 2024-04-05 17:00 | 1 | Metal Work | 100 | 84 | 33 | 87 | 55
82 | 1.2.1.7.2.4 | Base Course to Basement | 5 | 5 April 2024 8:00 AM | 10 April 2024 5:00 PM | 81 | 93 | 5 April 2024 8:00 AM | 2024-04-10 17:00 | 0 | Window | 100 | 74 | 23 | 47 | 26
83 | 1.2.1.7.3 | Stage 3 (Buildings C&D) | 33 | 21 March 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | 21 March 2024 8:00 AM | 2024-05-03 17:00 | 1 | Development Manager | 100 | 58 | 16 | 40 | 18
84 | 1.2.1.7.3.1 | Detailed Excavation | 12 | 21 March 2024 8:00 AM | 6 April 2024 5:00 PM | 69 | 85 | 21 March 2024 8:00 AM | 2024-04-09 17:00 | 3 | Floor Sealer | 100 | 83 | 24 | 55 | 42
85 | 1.2.1.7.3.2 | In-Ground Services | 8 | 8 April 2024 8:00 AM | 16 April 2024 5:00 PM | 84 | 86 | 8 April 2024 8:00 AM | 2024-04-16 17:00 | 0 | Carpenter | 100 | 49 | 29 | 96 | 44
86 | 1.2.1.7.3.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 17 April 2024 8:00 AM | 22 April 2024 5:00 PM | 85,70 | 87 | 17 April 2024 8:00 AM | 2024-04-22 17:00 | 0 | Line Market | 100 | 56 | 21 | 86 | 21
87 | 1.2.1.7.3.4 | Base Course to Basement | 8 | 23 April 2024 8:00 AM | 2 May 2024 5:00 PM | 86 | 88 | 23 April 2024 8:00 AM | 2024-05-04 17:00 | 2 | Painter | 100 | 69 | 24 | 95 | 20
88 | 1.2.1.7.4 | Basement Earthworks and Piling Complete | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 87,77 | 122,4 | 2 May 2024 5:00 PM | 2024-05-02 17:00 | 0 | Concretor | 100 | 33 | 29 | 65 | 33
89 | 1.2.2 | STRUCTURE WORKS | 217 | 11 April 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 11 April 2024 8:00 AM | 2025-01-04 17:00 | 1 | Metal Work | 100 | 93 | 29 | 22 | 38
90 | 1.2.2.1 | CC2 - Basement to Podium L1 - A, B, C, D | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  |  | 11 April 2024 8:00 AM | 2024-10-04 17:00 | 4 | Line Market | 100 | 70 | 28 | 43 | 3
91 | 1.2.2.1.1 | Basement to Podium (Level 1 - A & B ) | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | 11 April 2024 8:00 AM | 2024-10-01 17:00 | 1 | Development Manager | 100 | 91 | 25 | 80 | 35
92 | 1.2.2.1.1.1 | Basement 2 - FRP - SoG | 23 | 11 April 2024 8:00 AM | 8 May 2024 5:00 PM |  |  | 11 April 2024 8:00 AM | 2024-05-11 17:00 | 3 | Cleaner | 100 | 34 | 10 | 40 | 32
93 | 1.2.2.1.1.1.1 | Reinforcement Fix | 13 | 11 April 2024 8:00 AM | 26 April 2024 5:00 PM | 82 | 94 | 11 April 2024 8:00 AM | 2024-04-27 17:00 | 1 | Plumber | 100 | 37 | 26 | 87 | 37
94 | 1.2.2.1.1.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 9 | 27 April 2024 8:00 AM | 7 May 2024 5:00 PM | 93 | 95 | 27 April 2024 8:00 AM | 2024-05-07 17:00 | 0 | Stone Mason | 100 | 60 | 20 | 3 | 24
95 | 1.2.2.1.1.1.3 | Pour | 1 | 8 May 2024 8:00 AM | 8 May 2024 5:00 PM | 94 | 97 | 8 May 2024 8:00 AM | 2024-05-08 17:00 | 0 | Landscaper | 100 | 98 | 22 | 82 | 45
96 | 1.2.2.1.1.2 | Basement 1 - FRP - Suspended Slab | 25 | 9 May 2024 8:00 AM | 6 June 2024 5:00 PM |  |  | 9 May 2024 8:00 AM | 2024-06-07 17:00 | 1 | Hoarding | 100 | 75 | 17 | 82 | 59
97 | 1.2.2.1.1.2.1 | Scaffold Stair Removal/Adjustment | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 95 | 98SS | 9 May 2024 8:00 AM | 2024-05-10 17:00 | 0 | Subcontractor | 100 | 51 | 34 | 11 | 7
98 | 1.2.2.1.1.2.2 | Setout and Install Lift/Stair Formwork | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 97SS | 99 | 9 May 2024 8:00 AM | 2024-05-10 17:00 | 0 | Plasterboarder | 100 | 96 | 21 | 14 | 41
99 | 1.2.2.1.1.2.3 | Formworker setout, drop material and 80% Deck | 9 | 11 May 2024 8:00 AM | 21 May 2024 5:00 PM | 98 | 100FS-1d,101 | 11 May 2024 8:00 AM | 2024-05-21 17:00 | 0 | Formworker | 100 | 12 | 19 | 62 | 33
100 | 1.2.2.1.1.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 21 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99FS-1d | 102,103 | 21 May 2024 8:00 AM | 2024-05-24 17:00 | 0 | Plumber | 100 | 10 | 19 | 40 | 37
101 | 1.2.2.1.1.2.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 22 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99 |  | 22 May 2024 8:00 AM | 2024-05-24 17:00 | 0 | Painter | 100 | 61 | 13 | 13 | 59
102 | 1.2.2.1.1.2.6 | Services | 4 | 25 May 2024 8:00 AM | 29 May 2024 5:00 PM | 100 | 104FS-1d | 25 May 2024 8:00 AM | 2024-05-29 17:00 | 0 | Reinforcement Fixer | 100 | 88 | 28 | 69 | 29
103 | 1.2.2.1.1.2.7 | Post Tension | 3 | 25 May 2024 8:00 AM | 28 May 2024 5:00 PM | 100 | 104FS-1d | 25 May 2024 8:00 AM | 2024-05-28 17:00 | 0 | Plasterboarder | 100 | 79 | 33 | 69 | 19
104 | 1.2.2.1.1.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 29 May 2024 8:00 AM | 31 May 2024 5:00 PM | 102FS-1d,103FS-1d | 105 | 29 May 2024 8:00 AM | 2024-05-31 17:00 | 0 | Admin | 100 | 45 | 32 | 46 | 47
105 | 1.2.2.1.1.2.9 | Formworker setdowns and edge boards | 4 | 1 June 2024 8:00 AM | 5 June 2024 5:00 PM | 104 | 106 | 1 June 2024 8:00 AM | 2024-06-05 17:00 | 0 | Window | 100 | 27 | 12 | 89 | 21
106 | 1.2.2.1.1.2.10 | Pour | 1 | 6 June 2024 8:00 AM | 6 June 2024 5:00 PM | 105 | 109 | 6 June 2024 8:00 AM | 2024-06-06 17:00 | 0 | Mechanical | 100 | 99 | 23 | 73 | 48
107 | 1.2.2.1.1.3 | Strip Formwork - Basement 1 | 5 | 7 September 2024 8:00 AM | 12 September 2024 5:00 PM | 161FS+5d | 522 | 7 September 2024 8:00 AM | 2024-09-12 17:00 | 0 | Contract Administrator | 100 | 99 | 26 | 5 | 2
108 | 1.2.2.1.1.4 | Lvl 1 - FRP - Suspended Slab | 28 | 7 June 2024 8:00 AM | 11 July 2024 5:00 PM |  |  | 7 June 2024 8:00 AM | 2024-07-14 17:00 | 3 | Plasterboarder | 100 | 26 | 32 | 4 | 10
109 | 1.2.2.1.1.4.1 | Scaffold Stair Removal/Adjustment | 1 | 7 June 2024 8:00 AM | 7 June 2024 5:00 PM | 106 | 110SS | 7 June 2024 8:00 AM | 2024-06-07 17:00 | 0 | Surveyor | 100 | 68 | 27 | 6 | 52
110 | 1.2.2.1.1.4.2 | Setout and Install Lift/Stair Formwork | 3 | 7 June 2024 8:00 AM | 12 June 2024 5:00 PM | 109SS | 111 | 7 June 2024 8:00 AM | 2024-06-12 17:00 | 0 | Metal Work | 100 | 36 | 18 | 80 | 49
111 | 1.2.2.1.1.4.3 | Formworker setout, drop material and 80% Deck | 10 | 13 June 2024 8:00 AM | 24 June 2024 5:00 PM | 110 | 112FS-1d,113,128 | 13 June 2024 8:00 AM | 2024-06-24 17:00 | 0 | Project Manager | 100 | 24 | 10 | 65 | 53
112 | 1.2.2.1.1.4.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 6 | 24 June 2024 8:00 AM | 29 June 2024 5:00 PM | 111FS-1d | 114,115 | 24 June 2024 8:00 AM | 2024-06-29 17:00 | 0 | Renderer | 100 | 24 | 12 | 4 | 18
113 | 1.2.2.1.1.4.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 25 June 2024 8:00 AM | 28 June 2024 5:00 PM | 111 | 118 | 25 June 2024 8:00 AM | 2024-06-28 17:00 | 0 | Tiler | 100 | 77 | 13 | 3 | 4
114 | 1.2.2.1.1.4.6 | Services | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 112 | 116FS-1d | 1 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Carpet | 100 | 45 | 11 | 23 | 33
115 | 1.2.2.1.1.4.7 | Post Tension | 4 | 1 July 2024 8:00 AM | 4 July 2024 5:00 PM | 112 | 116FS-1d | 1 July 2024 8:00 AM | 2024-07-04 17:00 | 0 | Reinforcement Fixer | 100 | 69 | 14 | 14 | 45
116 | 1.2.2.1.1.4.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 114FS-1d,115FS-1d | 117,401FS+5d | 4 July 2024 8:00 AM | 2024-07-06 17:00 | 0 | Carpet | 100 | 54 | 32 | 56 | 47
117 | 1.2.2.1.1.4.9 | Formworker setdowns and edge boards | 3 | 8 July 2024 8:00 AM | 10 July 2024 5:00 PM | 116 | 118 | 8 July 2024 8:00 AM | 2024-07-10 17:00 | 0 | Carpenter | 100 | 47 | 27 | 60 | 5
118 | 1.2.2.1.1.4.10 | Pour | 1 | 11 July 2024 8:00 AM | 11 July 2024 5:00 PM | 117,113 | 140 | 11 July 2024 8:00 AM | 2024-07-11 17:00 | 0 | Carpet | 100 | 52 | 13 | 56 | 16
119 | 1.2.2.1.1.5 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d | 535 | 25 September 2024 8:00 AM | 2024-09-30 17:00 | 0 | Painter | 100 | 99 | 22 | 40 | 25
120 | 1.2.2.1.2 | Basement to Podium (Level 1 - C & D) | 127 | 3 May 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | 3 May 2024 8:00 AM | 2024-10-03 17:00 | 3 | Concretor | 100 | 80 | 34 | 63 | 14
121 | 1.2.2.1.2.1 | Basement 2 - FRP - SoG | 12 | 3 May 2024 8:00 AM | 16 May 2024 5:00 PM |  |  | 3 May 2024 8:00 AM | 2024-05-19 17:00 | 3 | Subcontractor | 100 | 28 | 23 | 64 | 48
122 | 1.2.2.1.2.1.1 | Reinforcement Fix | 6 | 3 May 2024 8:00 AM | 9 May 2024 5:00 PM | 88 | 123 | 3 May 2024 8:00 AM | 2024-05-09 17:00 | 0 | Cleaner | 100 | 44 | 26 | 11 | 5
123 | 1.2.2.1.2.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 5 | 10 May 2024 8:00 AM | 15 May 2024 5:00 PM | 122 | 124 | 10 May 2024 8:00 AM | 2024-05-15 17:00 | 0 | Line Market | 100 | 53 | 21 | 24 | 48
124 | 1.2.2.1.2.1.3 | Pour | 1 | 16 May 2024 8:00 AM | 16 May 2024 5:00 PM | 123 | 126 | 16 May 2024 8:00 AM | 2024-05-16 17:00 | 0 | Stone Mason | 100 | 39 | 27 | 43 | 48
125 | 1.2.2.1.2.2 | Lvl 1 - FRP - Suspended Slab | 48 | 17 May 2024 8:00 AM | 13 July 2024 5:00 PM |  |  | 17 May 2024 8:00 AM | 2024-07-13 17:00 | 0 | Plasterboarder | 100 | 18 | 25 | 20 | 29
126 | 1.2.2.1.2.2.1 | Scaffold Stair Removal/Adjustment | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 124 | 127SS | 17 May 2024 8:00 AM | 2024-05-17 17:00 | 0 | Foreman | 100 | 82 | 25 | 6 | 25
127 | 1.2.2.1.2.2.2 | Setout and Install Lift/Stair Formwork | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 126SS | 128 | 17 May 2024 8:00 AM | 2024-05-17 17:00 | 0 | Plasterboarder | 100 | 82 | 10 | 14 | 31
128 | 1.2.2.1.2.2.3 | Formworker setout, drop material and 80% Deck | 6 | 25 June 2024 8:00 AM | 1 July 2024 5:00 PM | 127,111 | 129FS-1d,130 | 25 June 2024 8:00 AM | 2024-07-01 17:00 | 0 | Electrician | 100 | 13 | 32 | 94 | 17
129 | 1.2.2.1.2.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128FS-1d | 131,132 | 1 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Project Manager | 100 | 63 | 18 | 49 | 36
130 | 1.2.2.1.2.2.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128 |  | 2 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Waterproofer | 100 | 37 | 23 | 9 | 37
131 | 1.2.2.1.2.2.6 | Services | 2 | 4 July 2024 8:00 AM | 5 July 2024 5:00 PM | 129 | 133FS-1d | 4 July 2024 8:00 AM | 2024-07-05 17:00 | 0 | Window | 100 | 26 | 32 | 43 | 18
132 | 1.2.2.1.2.2.7 | Post Tension | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 129 | 133FS-1d | 4 July 2024 8:00 AM | 2024-07-06 17:00 | 0 | Line Market | 100 | 31 | 29 | 60 | 39
133 | 1.2.2.1.2.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 6 July 2024 8:00 AM | 9 July 2024 5:00 PM | 131FS-1d,132FS-1d | 134 | 6 July 2024 8:00 AM | 2024-07-09 17:00 | 0 | Line Market | 100 | 24 | 13 | 97 | 51
134 | 1.2.2.1.2.2.9 | Formworker setdowns and edge boards | 3 | 10 July 2024 8:00 AM | 12 July 2024 5:00 PM | 133 | 135 | 10 July 2024 8:00 AM | 2024-07-12 17:00 | 0 | Concretor | 100 | 76 | 31 | 78 | 40
135 | 1.2.2.1.2.2.10 | Pour | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 134 | 309,233 | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Cleaner | 100 | 60 | 25 | 97 | 51
136 | 1.2.2.1.2.3 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d |  | 25 September 2024 8:00 AM | 2024-09-30 17:00 | 0 | Mechanical | 100 | 87 | 20 | 70 | 35
137 | 1.2.2.2 | CC3 - Remainder of Structure | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 12 July 2024 8:00 AM | 2025-01-06 17:00 | 3 | Head Contractor | 100 | 11 | 12 | 74 | 43
138 | 1.2.2.2.1 | Building A | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | 12 July 2024 8:00 AM | 2025-01-07 17:00 | 4 | Landscaper | 100 | 73 | 35 | 83 | 56
139 | 1.2.2.2.1.1 | Lvl 2 - FRP - Suspended Slab | 26 | 12 July 2024 8:00 AM | 10 August 2024 5:00 PM |  |  | 12 July 2024 8:00 AM | 2024-08-14 17:00 | 4 | Reinforcement Fixer | 100 | 12 | 14 | 16 | 47
140 | 1.2.2.2.1.1.1 | Scaffold Perimeter Protection | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 118 | 141SS | 12 July 2024 8:00 AM | 2024-07-16 17:00 | 0 | Tiler | 100 | 71 | 20 | 3 | 30
141 | 1.2.2.2.1.1.2 | Setout and Install Lift/Stair Formwork | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 140SS | 142 | 12 July 2024 8:00 AM | 2024-07-16 17:00 | 0 | Reinforcement Fixer | 100 | 14 | 28 | 59 | 28
142 | 1.2.2.2.1.1.3 | Formworker setout, drop material and 80% Deck | 6 | 17 July 2024 8:00 AM | 23 July 2024 5:00 PM | 141 | 143FS-1d,144 | 17 July 2024 8:00 AM | 2024-07-23 17:00 | 0 | Painter | 100 | 95 | 28 | 48 | 32
143 | 1.2.2.2.1.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 23 July 2024 8:00 AM | 26 July 2024 5:00 PM | 142FS-1d | 145,146 | 23 July 2024 8:00 AM | 2024-07-26 17:00 | 0 | Window | 100 | 44 | 17 | 30 | 18
144 | 1.2.2.2.1.1.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 24 July 2024 8:00 AM | 27 July 2024 5:00 PM | 142 | 146 | 24 July 2024 8:00 AM | 2024-07-27 17:00 | 0 | Post Tension | 100 | 33 | 15 | 46 | 15
145 | 1.2.2.2.1.1.6 | Services | 3 | 27 July 2024 8:00 AM | 30 July 2024 5:00 PM | 143 | 147FS-1d | 27 July 2024 8:00 AM | 2024-07-30 17:00 | 0 | Painter | 100 | 53 | 18 | 21 | 10
146 | 1.2.2.2.1.1.7 | Post Tension | 3 | 29 July 2024 8:00 AM | 31 July 2024 5:00 PM | 143,144 | 147FS-1d | 29 July 2024 8:00 AM | 2024-07-31 17:00 | 0 | Window | 100 | 84 | 29 | 22 | 37
147 | 1.2.2.2.1.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 5 | 31 July 2024 8:00 AM | 5 August 2024 5:00 PM | 145FS-1d,146FS-1d | 148 | 31 July 2024 8:00 AM | 2024-08-05 17:00 | 0 | Foreman | 100 | 72 | 23 | 63 | 47
148 | 1.2.2.2.1.1.9 | Formworker setdowns and edge boards | 4 | 6 August 2024 8:00 AM | 9 August 2024 5:00 PM | 147 | 149 | 6 August 2024 8:00 AM | 2024-08-09 17:00 | 0 | Excavation | 100 | 16 | 12 | 86 | 43
149 | 1.2.2.2.1.1.10 | Pour | 1 | 10 August 2024 8:00 AM | 10 August 2024 5:00 PM | 148 | 152,407FS+5d | 10 August 2024 8:00 AM | 2024-08-10 17:00 | 0 | Fire | 100 | 26 | 31 | 7 | 44
150 | 1.2.2.2.1.2 | Strip Formwork - Lvl 2 | 5 | 15 October 2024 8:00 AM | 19 October 2024 5:00 PM | 185FS+5d | 577,550,409FS-10d | 15 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Window | 100 | 21 | 32 | 33 | 50
151 | 1.2.2.2.1.3 | Lvl 3 - FRP - Suspended Slab | 18 | 12 August 2024 8:00 AM | 31 August 2024 5:00 PM |  |  | 12 August 2024 8:00 AM | 2024-09-03 17:00 | 3 | Hoarding | 100 | 54 | 21 | 84 | 43
152 | 1.2.2.2.1.3.1 | Scaffold Perimeter Protection | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 149 | 153SS | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 0 | Project Manager | 100 | 73 | 26 | 14 | 53
153 | 1.2.2.2.1.3.2 | Setout and Install Lift/Stair Formwork | 1 | 12 August 2024 8:00 AM | 12 August 2024 5:00 PM | 152SS | 154 | 12 August 2024 8:00 AM | 2024-08-12 17:00 | 0 | Waterproofer | 100 | 58 | 15 | 65 | 49
154 | 1.2.2.2.1.3.3 | Formworker setout, drop material and 80% Deck | 6 | 13 August 2024 8:00 AM | 19 August 2024 5:00 PM | 153 | 155FS-1d,156 | 13 August 2024 8:00 AM | 2024-08-19 17:00 | 0 | Formworker | 100 | 67 | 27 | 20 | 11
155 | 1.2.2.2.1.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 19 August 2024 8:00 AM | 22 August 2024 5:00 PM | 154FS-1d | 157,158 | 19 August 2024 8:00 AM | 2024-08-22 17:00 | 0 | Tiler | 100 | 53 | 28 | 80 | 13
156 | 1.2.2.2.1.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 August 2024 8:00 AM | 21 August 2024 5:00 PM | 154 |  | 20 August 2024 8:00 AM | 2024-08-21 17:00 | 0 | Hoarding | 100 | 21 | 13 | 70 | 55
157 | 1.2.2.2.1.3.6 | Services | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | 23 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Mechanical | 100 | 92 | 26 | 26 | 24
158 | 1.2.2.2.1.3.7 | Post Tension | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | 23 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Development Manager | 100 | 15 | 22 | 3 | 14
159 | 1.2.2.2.1.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 24 August 2024 8:00 AM | 27 August 2024 5:00 PM | 157FS-1d,158FS-1d | 160 | 24 August 2024 8:00 AM | 2024-08-27 17:00 | 0 | Cleaner | 100 | 66 | 20 | 3 | 40
160 | 1.2.2.2.1.3.9 | Formworker setdowns and edge boards | 3 | 28 August 2024 8:00 AM | 30 August 2024 5:00 PM | 159 | 161 | 28 August 2024 8:00 AM | 2024-08-30 17:00 | 0 | Electrician | 100 | 93 | 10 | 18 | 18
161 | 1.2.2.2.1.3.10 | Pour | 1 | 31 August 2024 8:00 AM | 31 August 2024 5:00 PM | 160 | 164,3445,107FS+5d | 31 August 2024 8:00 AM | 2024-08-31 17:00 | 0 | Floor Sealer | 100 | 31 | 34 | 93 | 35
162 | 1.2.2.2.1.4 | Strip Formwork - Lvl 3 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d |  | 19 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Timber Floorer | 100 | 39 | 21 | 97 | 12
163 | 1.2.2.2.1.5 | Lvl 4 - FRP - Suspended Slab | 15 | 2 September 2024 8:00 AM | 18 September 2024 5:00 PM |  |  | 2 September 2024 8:00 AM | 2024-09-19 17:00 | 1 | Window | 100 | 68 | 18 | 31 | 45
164 | 1.2.2.2.1.5.1 | Scaffold Perimeter Protection | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 161 | 165SS | 2 September 2024 8:00 AM | 2024-09-02 17:00 | 0 | Joiner | 100 | 10 | 20 | 38 | 32
165 | 1.2.2.2.1.5.2 | Setout and Install Lift/Stair Formwork | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 164SS | 166FS-1d | 2 September 2024 8:00 AM | 2024-09-02 17:00 | 0 | Foreman | 100 | 66 | 15 | 38 | 18
166 | 1.2.2.2.1.5.3 | Formworker setout, drop material and 80% Deck | 6 | 2 September 2024 8:00 AM | 7 September 2024 5:00 PM | 165FS-1d | 167FS-1d,168 | 2 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Head Contractor | 100 | 58 | 28 | 78 | 49
167 | 1.2.2.2.1.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 7 September 2024 8:00 AM | 11 September 2024 5:00 PM | 166FS-1d | 169,170 | 7 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Landscaper | 100 | 76 | 13 | 63 | 35
168 | 1.2.2.2.1.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 9 September 2024 8:00 AM | 10 September 2024 5:00 PM | 166 |  | 9 September 2024 8:00 AM | 2024-09-10 17:00 | 0 | Timber Floorer | 100 | 98 | 12 | 53 | 38
169 | 1.2.2.2.1.5.6 | Services | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | 12 September 2024 8:00 AM | 2024-09-13 17:00 | 0 | Surveyor | 100 | 17 | 11 | 21 | 54
170 | 1.2.2.2.1.5.7 | Post Tension | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | 12 September 2024 8:00 AM | 2024-09-13 17:00 | 0 | Reinforcement Fixer | 100 | 25 | 20 | 49 | 38
171 | 1.2.2.2.1.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 13 September 2024 8:00 AM | 14 September 2024 5:00 PM | 169FS-1d,170FS-1d | 172 | 13 September 2024 8:00 AM | 2024-09-14 17:00 | 0 | Fire | 100 | 35 | 30 | 29 | 49
172 | 1.2.2.2.1.5.9 | Formworker setdowns and edge boards | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 171 | 173 | 16 September 2024 8:00 AM | 2024-09-17 17:00 | 0 | Floor Sealer | 100 | 27 | 30 | 28 | 15
173 | 1.2.2.2.1.5.10 | Pour | 1 | 18 September 2024 8:00 AM | 18 September 2024 5:00 PM | 172 | 176,119FS+5d,136FS+5d | 18 September 2024 8:00 AM | 2024-09-18 17:00 | 0 | Surveyor | 100 | 57 | 28 | 17 | 22
174 | 1.2.2.2.1.6 | Strip Formwork - Lvl 4 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d | 413FS+5d,604,415FS-10d | 19 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Window | 100 | 35 | 12 | 75 | 30
175 | 1.2.2.2.1.7 | Lvl 5 - FRP - Suspended Slab | 15 | 19 September 2024 8:00 AM | 8 October 2024 5:00 PM |  |  | 19 September 2024 8:00 AM | 2024-10-11 17:00 | 3 | Site Manager | 100 | 26 | 15 | 40 | 9
176 | 1.2.2.2.1.7.1 | Scaffold Perimeter Protection | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 173 | 177SS | 19 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Joiner | 100 | 73 | 35 | 64 | 7
177 | 1.2.2.2.1.7.2 | Setout and Install Lift/Stair Formwork | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 176SS | 178FS-1d | 19 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Tiler | 100 | 57 | 35 | 77 | 60
178 | 1.2.2.2.1.7.3 | Formworker setout, drop material and 80% Deck | 6 | 19 September 2024 8:00 AM | 25 September 2024 5:00 PM | 177FS-1d | 179FS-1d,180 | 19 September 2024 8:00 AM | 2024-09-25 17:00 | 0 | Post Tension | 100 | 69 | 28 | 4 | 37
179 | 1.2.2.2.1.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 25 September 2024 8:00 AM | 28 September 2024 5:00 PM | 178FS-1d | 181,182 | 25 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Tiler | 100 | 82 | 23 | 80 | 49
180 | 1.2.2.2.1.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 26 September 2024 8:00 AM | 27 September 2024 5:00 PM | 178 |  | 26 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Floor Sealer | 100 | 20 | 20 | 13 | 34
181 | 1.2.2.2.1.7.6 | Services | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | 30 September 2024 8:00 AM | 2024-10-01 17:00 | 0 | Landscaper | 100 | 68 | 32 | 14 | 18
182 | 1.2.2.2.1.7.7 | Post Tension | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | 30 September 2024 8:00 AM | 2024-10-01 17:00 | 0 | Electrician | 100 | 47 | 25 | 79 | 6
183 | 1.2.2.2.1.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 1 October 2024 8:00 AM | 2 October 2024 5:00 PM | 181FS-1d,182FS-1d | 184 | 1 October 2024 8:00 AM | 2024-10-02 17:00 | 0 | Painter | 100 | 57 | 35 | 71 | 3
184 | 1.2.2.2.1.7.9 | Formworker setdowns and edge boards | 2 | 3 October 2024 8:00 AM | 4 October 2024 5:00 PM | 183 | 185 | 3 October 2024 8:00 AM | 2024-10-04 17:00 | 0 | Concretor | 100 | 44 | 21 | 46 | 43
185 | 1.2.2.2.1.7.10 | Pour | 1 | 8 October 2024 8:00 AM | 8 October 2024 5:00 PM | 184 | 188,150FS+5d | 8 October 2024 8:00 AM | 2024-10-08 17:00 | 0 | Subcontractor | 100 | 40 | 28 | 7 | 21
186 | 1.2.2.2.1.8 | Strip Formwork - Lvl 5 | 5 | 5 December 2024 8:00 AM | 10 December 2024 5:00 PM | 221FS+5d | 631,421FS-10d,419FS+5d | 5 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Carpet | 100 | 89 | 33 | 25 | 12
187 | 1.2.2.2.1.9 | Lvl 6 - FRP - Suspended Slab | 15 | 9 October 2024 8:00 AM | 25 October 2024 5:00 PM |  |  | 9 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Carpet | 100 | 76 | 24 | 22 | 41
188 | 1.2.2.2.1.9.1 | Scaffold Perimeter Protection | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 185 | 189SS | 9 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Contract Administrator | 100 | 80 | 11 | 28 | 60
189 | 1.2.2.2.1.9.2 | Setout and Install Lift/Stair Formwork | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 188SS | 190FS-1d | 9 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Mechanical | 100 | 34 | 19 | 68 | 34
190 | 1.2.2.2.1.9.3 | Formworker setout, drop material and 80% Deck | 6 | 9 October 2024 8:00 AM | 15 October 2024 5:00 PM | 189FS-1d | 191FS-1d,192 | 9 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Concretor | 100 | 84 | 24 | 74 | 20
191 | 1.2.2.2.1.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 October 2024 8:00 AM | 18 October 2024 5:00 PM | 190FS-1d | 193,194 | 15 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Carpenter | 100 | 24 | 23 | 15 | 58
192 | 1.2.2.2.1.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 190 |  | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Waterproofer | 100 | 80 | 33 | 92 | 10
193 | 1.2.2.2.1.9.6 | Services | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Floor Sealer | 100 | 62 | 13 | 93 | 12
194 | 1.2.2.2.1.9.7 | Post Tension | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Landscaper | 100 | 10 | 13 | 44 | 45
195 | 1.2.2.2.1.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 193FS-1d,194FS-1d | 196 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Contract Administrator | 100 | 62 | 20 | 76 | 15
196 | 1.2.2.2.1.9.9 | Formworker setdowns and edge boards | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 195 | 197 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Reinforcement Fixer | 100 | 79 | 25 | 61 | 55
197 | 1.2.2.2.1.9.10 | Pour | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 196 | 200 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Electrician | 100 | 11 | 23 | 50 | 58
198 | 1.2.2.2.1.10 | Strip Formwork - Lvl 6 | 5 | 6 December 2024 8:00 AM | 11 December 2024 5:00 PM | 225 | 657,425FS+5d,427FS-10d | 6 December 2024 8:00 AM | 2024-12-11 17:00 | 0 | Hoarding | 100 | 71 | 25 | 70 | 38
199 | 1.2.2.2.1.11 | Lvl 7 - FRP - Suspended Slab | 15 | 26 October 2024 8:00 AM | 12 November 2024 5:00 PM |  |  | 26 October 2024 8:00 AM | 2024-11-16 17:00 | 4 | Subcontractor | 100 | 19 | 30 | 10 | 19
200 | 1.2.2.2.1.11.1 | Scaffold Perimeter Protection | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 197 | 201SS | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Metal Work | 100 | 36 | 21 | 71 | 55
201 | 1.2.2.2.1.11.2 | Setout and Install Lift/Stair Formwork | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 200SS | 202FS-1d | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Concretor | 100 | 62 | 30 | 36 | 14
202 | 1.2.2.2.1.11.3 | Formworker setout, drop material and 80% Deck | 6 | 26 October 2024 8:00 AM | 1 November 2024 5:00 PM | 201FS-1d | 203FS-1d,204 | 26 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Concretor | 100 | 93 | 27 | 83 | 45
203 | 1.2.2.2.1.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 1 November 2024 8:00 AM | 5 November 2024 5:00 PM | 202FS-1d | 205,206 | 1 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Project Manager | 100 | 20 | 35 | 85 | 35
204 | 1.2.2.2.1.11.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 202 |  | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Painter | 100 | 59 | 20 | 40 | 17
205 | 1.2.2.2.1.11.6 | Services | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Plasterboarder | 100 | 67 | 31 | 58 | 14
206 | 1.2.2.2.1.11.7 | Post Tension | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Admin | 100 | 58 | 31 | 82 | 23
207 | 1.2.2.2.1.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 205FS-1d,206FS-1d | 208 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Excavation | 100 | 100 | 17 | 22 | 16
208 | 1.2.2.2.1.11.9 | Formworker setdowns and edge boards | 2 | 9 November 2024 8:00 AM | 11 November 2024 5:00 PM | 207 | 209 | 9 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Subcontractor | 100 | 11 | 14 | 24 | 9
209 | 1.2.2.2.1.11.10 | Pour | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 208 | 212,162FS+5d,174FS+5d,431FS+5d | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Carpenter | 100 | 31 | 22 | 62 | 46
210 | 1.2.2.2.1.12 | Strip Formwork - Lvl 7 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 225FS+5d | 690,432FS-10d | 12 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Concretor | 100 | 70 | 20 | 35 | 15
211 | 1.2.2.2.1.13 | Lvl 8 (Roof) - FRP - Suspended Slab | 14 | 13 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | 13 November 2024 8:00 AM | 2024-12-01 17:00 | 3 | Formworker | 100 | 56 | 10 | 95 | 37
212 | 1.2.2.2.1.13.1 | Scaffold Perimeter Protection | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 209 | 213SS | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Electrician | 100 | 10 | 17 | 73 | 54
213 | 1.2.2.2.1.13.2 | Setout and Install Lift/Stair Formwork | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 212SS | 214FS-1d | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Joiner | 100 | 50 | 21 | 64 | 35
214 | 1.2.2.2.1.13.3 | Formworker setout, drop material and 80% Deck | 6 | 13 November 2024 8:00 AM | 19 November 2024 5:00 PM | 213FS-1d | 215FS-1d,216 | 13 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Cleaner | 100 | 85 | 11 | 3 | 54
215 | 1.2.2.2.1.13.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214FS-1d | 217,218 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Timber Floorer | 100 | 10 | 22 | 18 | 31
216 | 1.2.2.2.1.13.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214 |  | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Mechanical | 100 | 47 | 25 | 6 | 48
217 | 1.2.2.2.1.13.6 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Contract Administrator | 100 | 90 | 13 | 59 | 43
218 | 1.2.2.2.1.13.7 | Post Tension | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Stone Mason | 100 | 87 | 12 | 15 | 58
219 | 1.2.2.2.1.13.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 217FS-1d,218FS-1d | 220 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Surveyor | 100 | 68 | 28 | 31 | 3
220 | 1.2.2.2.1.13.9 | Formworker setdowns and edge boards | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 219 | 221 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Renderer | 100 | 36 | 10 | 44 | 53
221 | 1.2.2.2.1.13.10 | Pour - Structure Top Out | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 220 | 223FS+12d,222,225,186FS+5d,437FS+5d | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Admin | 100 | 50 | 23 | 37 | 5
222 | 1.2.2.2.1.13.11 | Structure Top Out | 0 | 28 November 2024 5:00 PM | 28 November 2024 5:00 PM | 221 |  | 28 November 2024 5:00 PM | 2024-11-28 17:00 | 0 | Head Contractor | 100 | 92 | 22 | 2 | 16
223 | 1.2.2.2.1.14 | Strip Formwork - Lvl 8 | 4 | 13 December 2024 8:00 AM | 17 December 2024 5:00 PM | 221FS+12d | 716,439FS+10d | 13 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Development Manager | 100 | 46 | 11 | 45 | 57
224 | 1.2.2.2.1.15 | Lift Shaft | 23 | 29 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 29 November 2024 8:00 AM | 2025-01-08 17:00 | 5 | Plasterboarder | 100 | 69 | 14 | 89 | 28
225 | 1.2.2.2.1.15.1 | FRP Lift Over-run | 6 | 29 November 2024 8:00 AM | 5 December 2024 5:00 PM | 221 | 226FS+5d,228,198,210FS+5d | 29 November 2024 8:00 AM | 2024-12-08 17:00 | 3 | Cleaner | 100 | 88 | 16 | 77 | 14
226 | 1.2.2.2.1.15.2 | Strip Lift Shaft Formwork | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 225FS+5d | 227 | 12 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Contract Administrator | 100 | 31 | 32 | 89 | 37
227 | 1.2.2.2.1.15.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 17 December 2024 8:00 AM | 3 January 2025 5:00 PM | 226 | 3451 | 17 December 2024 8:00 AM | 2025-01-05 17:00 | 2 | Timber Floorer | 100 | 84 | 21 | 61 | 25
228 | 1.2.2.2.1.15.4 | Building A Structure Complete | 0 | 5 December 2024 5:00 PM | 5 December 2024 5:00 PM | 225 | 6 | 5 December 2024 5:00 PM | 2024-12-05 17:00 | 0 | Reinforcement Fixer | 100 | 25 | 33 | 88 | 26
229 | 1.2.2.2.2 | Building B | 119 | 13 July 2024 8:00 AM | 30 November 2024 5:00 PM |  | 397 | 13 July 2024 8:00 AM | 2024-11-30 17:00 | 0 | Head Contractor | 100 | 77 | 13 | 22 | 10
230 | 1.2.2.2.2.1 | Lvl 2 - FRP - Suspended Slab | 18 | 13 July 2024 8:00 AM | 2 August 2024 5:00 PM |  |  | 13 July 2024 8:00 AM | 2024-08-02 17:00 | 0 | Plumber | 100 | 87 | 16 | 16 | 19
231 | 1.2.2.2.2.1.1 | Scaffold Perimeter Protection | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 232SS |  | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Window | 100 | 85 | 14 | 22 | 16
232 | 1.2.2.2.2.1.2 | Setout and Install Lift/Stair Formwork | 1 | 13 July 2024 8:00 AM | 15 July 2024 8:00 AM | 233SF | 231SS | 13 July 2024 8:00 AM | 2024-07-15 08:00 | 0 | Plumber | 100 | 42 | 23 | 34 | 45
233 | 1.2.2.2.2.1.3 | Formworker setout, drop material and 80% Deck | 6 | 15 July 2024 8:00 AM | 20 July 2024 5:00 PM | 135 | 234FS-1d,235,232SF | 15 July 2024 8:00 AM | 2024-07-20 17:00 | 0 | Joiner | 100 | 74 | 21 | 8 | 18
234 | 1.2.2.2.2.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 20 July 2024 8:00 AM | 24 July 2024 5:00 PM | 233FS-1d | 236,237 | 20 July 2024 8:00 AM | 2024-07-24 17:00 | 0 | Subcontractor | 100 | 14 | 23 | 99 | 27
235 | 1.2.2.2.2.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 22 July 2024 8:00 AM | 23 July 2024 5:00 PM | 233 |  | 22 July 2024 8:00 AM | 2024-07-23 17:00 | 0 | Floor Sealer | 100 | 86 | 32 | 8 | 43
236 | 1.2.2.2.2.1.6 | Services | 2 | 25 July 2024 8:00 AM | 26 July 2024 5:00 PM | 234 | 238FS-1d | 25 July 2024 8:00 AM | 2024-07-26 17:00 | 0 | Excavation | 100 | 81 | 28 | 46 | 3
237 | 1.2.2.2.2.1.7 | Post Tension | 3 | 25 July 2024 8:00 AM | 27 July 2024 5:00 PM | 234 | 238FS-1d | 25 July 2024 8:00 AM | 2024-07-27 17:00 | 0 | Floor Sealer | 100 | 16 | 12 | 9 | 57
238 | 1.2.2.2.2.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 27 July 2024 8:00 AM | 29 July 2024 5:00 PM | 236FS-1d,237FS-1d | 239 | 27 July 2024 8:00 AM | 2024-07-29 17:00 | 0 | Plumber | 100 | 18 | 35 | 80 | 35
239 | 1.2.2.2.2.1.9 | Formworker setdowns and edge boards | 3 | 30 July 2024 8:00 AM | 1 August 2024 5:00 PM | 238 | 240 | 30 July 2024 8:00 AM | 2024-08-01 17:00 | 0 | Hoarding | 100 | 71 | 33 | 37 | 2
240 | 1.2.2.2.2.1.10 | Pour | 1 | 2 August 2024 8:00 AM | 2 August 2024 5:00 PM | 239 | 243,309FS+30d | 2 August 2024 8:00 AM | 2024-08-02 17:00 | 0 | Hoarding | 100 | 51 | 13 | 53 | 60
241 | 1.2.2.2.2.2 | Strip Formwork - Lvl 2 | 5 | 28 September 2024 8:00 AM | 3 October 2024 5:00 PM | 276 | 447 | 28 September 2024 8:00 AM | 2024-10-03 17:00 | 0 | Excavation | 100 | 46 | 22 | 79 | 17
242 | 1.2.2.2.2.3 | Lvl 3 - FRP - Suspended Slab | 18 | 3 August 2024 8:00 AM | 23 August 2024 5:00 PM |  |  | 3 August 2024 8:00 AM | 2024-08-24 17:00 | 1 | Head Contractor | 100 | 29 | 17 | 51 | 21
243 | 1.2.2.2.2.3.1 | Scaffold Perimeter Protection | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 240 | 244SS | 3 August 2024 8:00 AM | 2024-08-03 17:00 | 0 | Concretor | 100 | 80 | 10 | 4 | 48
244 | 1.2.2.2.2.3.2 | Setout and Install Lift/Stair Formwork | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 243SS | 245 | 3 August 2024 8:00 AM | 2024-08-03 17:00 | 0 | Surveyor | 100 | 66 | 32 | 67 | 54
245 | 1.2.2.2.2.3.3 | Formworker setout, drop material and 80% Deck | 6 | 5 August 2024 8:00 AM | 10 August 2024 5:00 PM | 244 | 246FS-1d,247 | 5 August 2024 8:00 AM | 2024-08-12 17:00 | 2 | Admin | 100 | 79 | 17 | 61 | 51
246 | 1.2.2.2.2.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 10 August 2024 8:00 AM | 14 August 2024 5:00 PM | 245FS-1d | 248,249 | 10 August 2024 8:00 AM | 2024-08-14 17:00 | 0 | Carpenter | 100 | 11 | 32 | 17 | 27
247 | 1.2.2.2.2.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 245 |  | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 0 | Floor Sealer | 100 | 96 | 23 | 80 | 13
248 | 1.2.2.2.2.3.6 | Services | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | 15 August 2024 8:00 AM | 2024-08-16 17:00 | 0 | Carpet | 100 | 11 | 12 | 82 | 25
249 | 1.2.2.2.2.3.7 | Post Tension | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | 15 August 2024 8:00 AM | 2024-08-16 17:00 | 0 | Concretor | 100 | 11 | 13 | 70 | 46
250 | 1.2.2.2.2.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 16 August 2024 8:00 AM | 19 August 2024 5:00 PM | 248FS-1d,249FS-1d | 251 | 16 August 2024 8:00 AM | 2024-08-19 17:00 | 0 | Admin | 100 | 89 | 25 | 72 | 5
251 | 1.2.2.2.2.3.9 | Formworker setdowns and edge boards | 3 | 20 August 2024 8:00 AM | 22 August 2024 5:00 PM | 250 | 252 | 20 August 2024 8:00 AM | 2024-08-22 17:00 | 0 | Plumber | 100 | 62 | 24 | 40 | 50
252 | 1.2.2.2.2.3.10 | Pour | 1 | 23 August 2024 8:00 AM | 23 August 2024 5:00 PM | 251 | 255,3447 | 23 August 2024 8:00 AM | 2024-08-23 17:00 | 0 | Fire | 100 | 61 | 12 | 16 | 54
253 | 1.2.2.2.2.4 | Strip Formwork - Lvl 3 | 5 | 21 October 2024 8:00 AM | 25 October 2024 5:00 PM | 288 | 453,1605 | 21 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Scaffolder | 100 | 77 | 24 | 57 | 27
254 | 1.2.2.2.2.5 | Lvl 4 - FRP - Suspended Slab | 15 | 24 August 2024 8:00 AM | 10 September 2024 5:00 PM |  |  | 24 August 2024 8:00 AM | 2024-09-15 17:00 | 5 | Metal Work | 100 | 12 | 14 | 47 | 13
255 | 1.2.2.2.2.5.1 | Scaffold Perimeter Protection | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 252 | 256SS | 24 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Foreman | 100 | 89 | 31 | 19 | 29
256 | 1.2.2.2.2.5.2 | Setout and Install Lift/Stair Formwork | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 255SS | 257FS-1d | 24 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Project Manager | 100 | 10 | 25 | 31 | 6
257 | 1.2.2.2.2.5.3 | Formworker setout, drop material and 80% Deck | 6 | 24 August 2024 8:00 AM | 30 August 2024 5:00 PM | 256FS-1d | 258FS-1d,259 | 24 August 2024 8:00 AM | 2024-09-01 17:00 | 2 | Excavation | 100 | 85 | 19 | 29 | 5
258 | 1.2.2.2.2.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 30 August 2024 8:00 AM | 3 September 2024 5:00 PM | 257FS-1d | 260,261 | 30 August 2024 8:00 AM | 2024-09-03 17:00 | 0 | Fire | 100 | 29 | 11 | 0 | 12
259 | 1.2.2.2.2.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 31 August 2024 8:00 AM | 2 September 2024 5:00 PM | 257 |  | 31 August 2024 8:00 AM | 2024-09-02 17:00 | 0 | Plumber | 100 | 50 | 33 | 57 | 59
260 | 1.2.2.2.2.5.6 | Services | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | 4 September 2024 8:00 AM | 2024-09-05 17:00 | 0 | Foreman | 100 | 27 | 10 | 80 | 55
261 | 1.2.2.2.2.5.7 | Post Tension | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | 4 September 2024 8:00 AM | 2024-09-05 17:00 | 0 | Waterproofer | 100 | 44 | 23 | 67 | 32
262 | 1.2.2.2.2.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 5 September 2024 8:00 AM | 6 September 2024 5:00 PM | 260FS-1d,261FS-1d | 263 | 5 September 2024 8:00 AM | 2024-09-06 17:00 | 0 | Admin | 100 | 23 | 10 | 1 | 20
263 | 1.2.2.2.2.5.9 | Formworker setdowns and edge boards | 2 | 7 September 2024 8:00 AM | 9 September 2024 5:00 PM | 262 | 264 | 7 September 2024 8:00 AM | 2024-09-09 17:00 | 0 | Window | 100 | 27 | 14 | 19 | 15
264 | 1.2.2.2.2.5.10 | Pour | 1 | 10 September 2024 8:00 AM | 10 September 2024 5:00 PM | 263 | 267 | 10 September 2024 8:00 AM | 2024-09-10 17:00 | 0 | Plasterboarder | 100 | 30 | 26 | 100 | 18
265 | 1.2.2.2.2.6 | Strip Formwork - Lvl 4 | 5 | 11 November 2024 8:00 AM | 15 November 2024 5:00 PM | 300 | 459,1632 | 11 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Carpet | 100 | 55 | 27 | 95 | 24
266 | 1.2.2.2.2.7 | Lvl 5 - FRP - Suspended Slab | 15 | 11 September 2024 8:00 AM | 27 September 2024 5:00 PM |  |  | 11 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Plasterboarder | 100 | 41 | 16 | 55 | 29
267 | 1.2.2.2.2.7.1 | Scaffold Perimeter Protection | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 264 | 268SS | 11 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Carpet | 100 | 81 | 28 | 82 | 12
268 | 1.2.2.2.2.7.2 | Setout and Install Lift/Stair Formwork | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 267SS | 269FS-1d | 11 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Floor Sealer | 100 | 80 | 28 | 59 | 25
269 | 1.2.2.2.2.7.3 | Formworker setout, drop material and 80% Deck | 6 | 11 September 2024 8:00 AM | 17 September 2024 5:00 PM | 268FS-1d | 270FS-1d,271 | 11 September 2024 8:00 AM | 2024-09-18 17:00 | 1 | Excavation | 100 | 78 | 21 | 94 | 36
270 | 1.2.2.2.2.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 17 September 2024 8:00 AM | 20 September 2024 5:00 PM | 269FS-1d | 272,273 | 17 September 2024 8:00 AM | 2024-09-20 17:00 | 0 | Floor Sealer | 100 | 97 | 13 | 12 | 11
271 | 1.2.2.2.2.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 18 September 2024 8:00 AM | 19 September 2024 5:00 PM | 269 |  | 18 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Line Market | 100 | 16 | 21 | 10 | 43
272 | 1.2.2.2.2.7.6 | Services | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Carpenter | 100 | 30 | 17 | 80 | 15
273 | 1.2.2.2.2.7.7 | Post Tension | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Admin | 100 | 41 | 29 | 5 | 11
274 | 1.2.2.2.2.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 September 2024 8:00 AM | 24 September 2024 5:00 PM | 272FS-1d,273FS-1d | 275 | 23 September 2024 8:00 AM | 2024-09-24 17:00 | 0 | Plumber | 100 | 92 | 22 | 98 | 18
275 | 1.2.2.2.2.7.9 | Formworker setdowns and edge boards | 2 | 25 September 2024 8:00 AM | 26 September 2024 5:00 PM | 274 | 276 | 25 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Timber Floorer | 100 | 78 | 16 | 63 | 34
276 | 1.2.2.2.2.7.10 | Pour | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 275 | 279,241 | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Site Manager | 100 | 89 | 22 | 17 | 56
277 | 1.2.2.2.2.8 | Strip Formwork - Lvl 5 | 5 | 18 November 2024 8:00 AM | 22 November 2024 5:00 PM | 303 | 465,1659 | 18 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Hoarding | 100 | 38 | 13 | 66 | 5
278 | 1.2.2.2.2.9 | Lvl 6 - FRP - Suspended Slab | 17 | 28 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | 28 September 2024 8:00 AM | 2024-10-22 17:00 | 3 | Joiner | 100 | 28 | 29 | 86 | 2
279 | 1.2.2.2.2.9.1 | Scaffold Perimeter Protection | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 276 | 280SS | 28 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Post Tension | 100 | 70 | 24 | 6 | 18
280 | 1.2.2.2.2.9.2 | Setout and Install Lift/Stair Formwork | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 279SS | 281FS-1d | 28 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Electrician | 100 | 19 | 31 | 15 | 47
281 | 1.2.2.2.2.9.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 280FS-1d | 282FS-1d,283 | 28 September 2024 8:00 AM | 2024-10-05 17:00 | 1 | Site Manager | 100 | 31 | 12 | 42 | 51
282 | 1.2.2.2.2.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 281FS-1d | 284,285 | 4 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Cleaner | 100 | 42 | 28 | 32 | 26
283 | 1.2.2.2.2.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 281 |  | 8 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Admin | 100 | 47 | 10 | 55 | 40
284 | 1.2.2.2.2.9.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Concretor | 100 | 63 | 32 | 3 | 58
285 | 1.2.2.2.2.9.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Mechanical | 100 | 80 | 33 | 84 | 46
286 | 1.2.2.2.2.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 284FS-1d,285FS-1d | 287 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Development Manager | 100 | 99 | 27 | 100 | 60
287 | 1.2.2.2.2.9.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 286 | 288 | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Concretor | 100 | 37 | 21 | 13 | 42
288 | 1.2.2.2.2.9.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 287 | 291,253 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Head Contractor | 100 | 87 | 13 | 86 | 53
289 | 1.2.2.2.2.10 | Strip Formwork - Lvl 6 | 5 | 20 November 2024 8:00 AM | 25 November 2024 5:00 PM | 300FS+8d | 657,471,1686 | 20 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Window | 100 | 26 | 23 | 2 | 29
290 | 1.2.2.2.2.11 | Lvl 7 (Roof) - FRP - Suspended Slab | 18 | 21 October 2024 8:00 AM | 9 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-13 17:00 | 4 | Stone Mason | 100 | 35 | 25 | 64 | 32
291 | 1.2.2.2.2.11.1 | Scaffold Perimeter Protection | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 288 | 292SS | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Surveyor | 100 | 44 | 26 | 32 | 29
292 | 1.2.2.2.2.11.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 291SS | 293FS-1d | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Carpenter | 100 | 23 | 12 | 54 | 58
293 | 1.2.2.2.2.11.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 292FS-1d | 294FS-1d,295 | 21 October 2024 8:00 AM | 2024-10-27 17:00 | 1 | Fire | 100 | 37 | 13 | 35 | 6
294 | 1.2.2.2.2.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293FS-1d | 296,297 | 26 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Foreman | 100 | 78 | 32 | 87 | 51
295 | 1.2.2.2.2.11.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 28 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293 |  | 28 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Plasterboarder | 100 | 96 | 29 | 13 | 42
296 | 1.2.2.2.2.11.6 | Services | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Formworker | 100 | 17 | 19 | 46 | 16
297 | 1.2.2.2.2.11.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Line Market | 100 | 25 | 30 | 95 | 16
298 | 1.2.2.2.2.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 296FS-1d,297FS-1d | 299 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Plasterboarder | 100 | 91 | 18 | 39 | 11
299 | 1.2.2.2.2.11.9 | Formworker setdowns and edge boards | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 298 | 300 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Electrician | 100 | 60 | 22 | 61 | 28
300 | 1.2.2.2.2.11.10 | Pour | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 299 | 303,289FS+8d,301FS+12d,1739FS+24d,265 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Carpenter | 100 | 47 | 13 | 42 | 57
301 | 1.2.2.2.2.12 | Strip Formwork - Lvl 7 | 5 | 25 November 2024 8:00 AM | 29 November 2024 5:00 PM | 300FS+12d | 716,748FS+24d,477,1713 | 25 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Head Contractor | 100 | 73 | 12 | 92 | 46
302 | 1.2.2.2.2.13 | Lift Shaft | 18 | 11 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 11 November 2024 8:00 AM | 2024-12-04 17:00 | 4 | Electrician | 100 | 28 | 12 | 83 | 39
303 | 1.2.2.2.2.13.1 | FRP Lift Over-run | 6 | 11 November 2024 8:00 AM | 16 November 2024 5:00 PM | 300 | 304,277 | 11 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Carpet | 100 | 25 | 12 | 12 | 19
304 | 1.2.2.2.2.13.2 | Strip Lift Shaft Formwork | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 303 | 305 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Waterproofer | 100 | 100 | 10 | 61 | 48
305 | 1.2.2.2.2.13.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 304 | 3452,306 | 22 November 2024 8:00 AM | 2024-12-02 17:00 | 2 | Post Tension | 100 | 30 | 12 | 4 | 34
306 | 1.2.2.2.2.13.4 | Building B Structure Complete | 0 | 30 November 2024 5:00 PM | 30 November 2024 5:00 PM | 305 | 7,6 | 30 November 2024 5:00 PM | 2024-11-30 17:00 | 0 | Electrician | 100 | 15 | 19 | 24 | 31
307 | 1.2.2.2.3 | Building C | 90 | 7 September 2024 8:00 AM | 23 December 2024 5:00 PM |  | 397 | 7 September 2024 8:00 AM | 2024-12-27 17:00 | 4 | Metal Work | 100 | 12 | 25 | 39 | 11
308 | 1.2.2.2.3.1 | Lvl 2 - FRP - Suspended Slab | 17 | 7 September 2024 8:00 AM | 26 September 2024 5:00 PM |  |  | 7 September 2024 8:00 AM | 2024-09-29 17:00 | 3 | Joiner | 100 | 25 | 33 | 86 | 59
309 | 1.2.2.2.3.1.1 | Scaffold Stair Removal/Adjustment | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 135,240FS+30d | 310SS | 7 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Line Market | 100 | 67 | 31 | 25 | 59
310 | 1.2.2.2.3.1.2 | Setout and Install Lift/Stair Formwork | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 309SS | 311 | 7 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Plasterboarder | 100 | 56 | 13 | 4 | 45
311 | 1.2.2.2.3.1.3 | Formworker setout, drop material and 80% Deck | 6 | 9 September 2024 8:00 AM | 14 September 2024 5:00 PM | 310 | 312FS-1d,313,365FS+10d | 9 September 2024 8:00 AM | 2024-09-14 17:00 | 0 | Plasterboarder | 100 | 78 | 29 | 77 | 3
312 | 1.2.2.2.3.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 14 September 2024 8:00 AM | 18 September 2024 5:00 PM | 311FS-1d | 314,315 | 14 September 2024 8:00 AM | 2024-09-18 17:00 | 0 | Excavation | 100 | 12 | 13 | 66 | 25
313 | 1.2.2.2.3.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 311 |  | 16 September 2024 8:00 AM | 2024-09-17 17:00 | 0 | Development Manager | 100 | 31 | 33 | 72 | 21
314 | 1.2.2.2.3.1.6 | Services | 2 | 19 September 2024 8:00 AM | 20 September 2024 5:00 PM | 312 | 316FS-1d | 19 September 2024 8:00 AM | 2024-09-20 17:00 | 0 | Carpet | 100 | 48 | 22 | 4 | 24
315 | 1.2.2.2.3.1.7 | Post Tension | 3 | 19 September 2024 8:00 AM | 21 September 2024 5:00 PM | 312 | 316FS-1d | 19 September 2024 8:00 AM | 2024-09-21 17:00 | 0 | Project Manager | 100 | 13 | 11 | 9 | 49
316 | 1.2.2.2.3.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 314FS-1d,315FS-1d | 317 | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Project Manager | 100 | 18 | 24 | 94 | 28
317 | 1.2.2.2.3.1.9 | Formworker setdowns and edge boards | 2 | 24 September 2024 8:00 AM | 25 September 2024 5:00 PM | 316 | 318 | 24 September 2024 8:00 AM | 2024-09-25 17:00 | 0 | Stone Mason | 100 | 11 | 16 | 64 | 18
318 | 1.2.2.2.3.1.10 | Pour | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 317 | 321 | 26 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Head Contractor | 100 | 75 | 29 | 52 | 48
319 | 1.2.2.2.3.2 | Strip Formwork - Lvl 2 | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 354 | 331FS+5d | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Carpet | 100 | 57 | 31 | 81 | 35
320 | 1.2.2.2.3.3 | Lvl 3 - FRP - Suspended Slab | 17 | 27 September 2024 8:00 AM | 18 October 2024 5:00 PM |  |  | 27 September 2024 8:00 AM | 2024-10-21 17:00 | 3 | Surveyor | 100 | 28 | 17 | 25 | 10
321 | 1.2.2.2.3.3.1 | Scaffold Stair Removal/Adjustment | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 318 | 322SS | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Post Tension | 100 | 42 | 35 | 66 | 28
322 | 1.2.2.2.3.3.2 | Setout and Install Lift/Stair Formwork | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 321SS | 323 | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Timber Floorer | 100 | 10 | 33 | 88 | 5
323 | 1.2.2.2.3.3.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 322 | 324FS-1d,325 | 28 September 2024 8:00 AM | 2024-10-08 17:00 | 4 | Post Tension | 100 | 56 | 31 | 18 | 40
324 | 1.2.2.2.3.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 323FS-1d | 326,327 | 4 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Plasterboarder | 100 | 27 | 33 | 100 | 40
325 | 1.2.2.2.3.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 323 |  | 8 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Formworker | 100 | 89 | 12 | 11 | 50
326 | 1.2.2.2.3.3.6 | Services | 2 | 11 October 2024 8:00 AM | 12 October 2024 5:00 PM | 324 | 328FS-1d | 11 October 2024 8:00 AM | 2024-10-12 17:00 | 0 | Line Market | 100 | 100 | 35 | 91 | 46
327 | 1.2.2.2.3.3.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 324 | 328FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Reinforcement Fixer | 100 | 80 | 23 | 63 | 58
328 | 1.2.2.2.3.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 326FS-1d,327FS-1d | 329 | 14 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Metal Work | 100 | 48 | 31 | 80 | 56
329 | 1.2.2.2.3.3.9 | Formworker setdowns and edge boards | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 328 | 330 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Waterproofer | 100 | 24 | 22 | 11 | 24
330 | 1.2.2.2.3.3.10 | Pour | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 329 | 333 | 18 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Excavation | 100 | 99 | 16 | 69 | 16
331 | 1.2.2.2.3.4 | Strip Formwork - Lvl 3 | 5 | 10 December 2024 8:00 AM | 14 December 2024 5:00 PM | 319FS+5d | 490,1748,2151,1774,2177FS+5d | 10 December 2024 8:00 AM | 2024-12-14 17:00 | 0 | Line Market | 100 | 53 | 10 | 24 | 52
332 | 1.2.2.2.3.5 | Lvl 4 - FRP - Suspended Slab | 17 | 19 October 2024 8:00 AM | 7 November 2024 5:00 PM |  |  | 19 October 2024 8:00 AM | 2024-11-08 17:00 | 1 | Hoarding | 100 | 20 | 20 | 8 | 48
333 | 1.2.2.2.3.5.1 | Scaffold Stair Removal/Adjustment | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 330 | 334SS | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Contract Administrator | 100 | 86 | 10 | 45 | 39
334 | 1.2.2.2.3.5.2 | Setout and Install Lift/Stair Formwork | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 333SS | 335 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Site Manager | 100 | 55 | 27 | 13 | 30
335 | 1.2.2.2.3.5.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 334 | 336FS-1d,337 | 21 October 2024 8:00 AM | 2024-10-29 17:00 | 3 | Cleaner | 100 | 78 | 27 | 31 | 53
336 | 1.2.2.2.3.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 335FS-1d | 338,339 | 26 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Plumber | 100 | 66 | 24 | 13 | 2
337 | 1.2.2.2.3.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 335 |  | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Project Manager | 100 | 37 | 16 | 2 | 25
338 | 1.2.2.2.3.5.6 | Services | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 336 | 340FS-1d | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Concretor | 100 | 54 | 11 | 23 | 48
339 | 1.2.2.2.3.5.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 336 | 340FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Carpenter | 100 | 34 | 30 | 11 | 31
340 | 1.2.2.2.3.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 338FS-1d,339FS-1d | 341 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Head Contractor | 100 | 24 | 22 | 94 | 59
341 | 1.2.2.2.3.5.9 | Formworker setdowns and edge boards | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 340 | 342 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Mechanical | 100 | 20 | 28 | 46 | 30
342 | 1.2.2.2.3.5.10 | Pour | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 341 | 345 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Surveyor | 100 | 13 | 27 | 50 | 2
343 | 1.2.2.2.3.6 | Strip Formwork - Lvl 4 | 5 | 16 December 2024 8:00 AM | 20 December 2024 5:00 PM | 354FS+15d | 495,2648,2674FS+5d | 16 December 2024 8:00 AM | 2024-12-20 17:00 | 0 | Plasterboarder | 100 | 44 | 25 | 20 | 49
344 | 1.2.2.2.3.7 | Lvl 5 (Roof) - FRP - Suspended Slab | 17 | 8 November 2024 8:00 AM | 27 November 2024 5:00 PM |  |  | 8 November 2024 8:00 AM | 2024-11-29 17:00 | 2 | Hoarding | 100 | 41 | 16 | 65 | 59
345 | 1.2.2.2.3.7.1 | Scaffold Stair Removal/Adjustment | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 342 | 346SS | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Waterproofer | 100 | 94 | 20 | 29 | 45
346 | 1.2.2.2.3.7.2 | Setout and Install Lift/Stair Formwork | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 345SS | 347 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Renderer | 100 | 45 | 13 | 45 | 15
347 | 1.2.2.2.3.7.3 | Formworker setout, drop material and 80% Deck | 6 | 9 November 2024 8:00 AM | 15 November 2024 5:00 PM | 346 | 348FS-1d,349 | 9 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Excavation | 100 | 86 | 23 | 90 | 17
348 | 1.2.2.2.3.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 November 2024 8:00 AM | 19 November 2024 5:00 PM | 347FS-1d | 350,351 | 15 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Carpet | 100 | 62 | 31 | 0 | 48
349 | 1.2.2.2.3.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 347 |  | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Timber Floorer | 100 | 50 | 33 | 21 | 58
350 | 1.2.2.2.3.7.6 | Services | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 348 | 352FS-1d | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 100 | 48 | 23 | 91 | 43
351 | 1.2.2.2.3.7.7 | Post Tension | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 348 | 352FS-1d | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Carpet | 100 | 15 | 16 | 45 | 5
352 | 1.2.2.2.3.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 350FS-1d,351FS-1d | 353 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Fire | 100 | 81 | 25 | 7 | 10
353 | 1.2.2.2.3.7.9 | Formworker setdowns and edge boards | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 352 | 354 | 25 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Contract Administrator | 100 | 62 | 14 | 26 | 39
354 | 1.2.2.2.3.7.10 | Pour | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 353 | 357,355FS+12d,343FS+15d,360,319 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Admin | 100 | 90 | 32 | 90 | 5
355 | 1.2.2.2.3.8 | Strip Formwork - Lvl 5 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 354FS+12d | 500,3145,3171FS+5d | 12 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Renderer | 100 | 77 | 28 | 95 | 22
356 | 1.2.2.2.3.9 | Lift Shaft | 22 | 28 November 2024 8:00 AM | 23 December 2024 5:00 PM |  |  | 28 November 2024 8:00 AM | 2024-12-24 17:00 | 1 | Plasterboarder | 100 | 76 | 18 | 87 | 33
357 | 1.2.2.2.3.9.1 | FRP Lift Over-run | 10 | 28 November 2024 8:00 AM | 9 December 2024 5:00 PM | 354 | 358 | 28 November 2024 8:00 AM | 2024-12-13 17:00 | 4 | Plumber | 100 | 87 | 34 | 41 | 50
358 | 1.2.2.2.3.9.2 | Strip Lift Shaft Formwork | 4 | 10 December 2024 8:00 AM | 13 December 2024 5:00 PM | 357 | 359 | 10 December 2024 8:00 AM | 2024-12-13 17:00 | 0 | Project Manager | 100 | 64 | 22 | 33 | 50
359 | 1.2.2.2.3.9.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 14 December 2024 8:00 AM | 23 December 2024 5:00 PM | 358 | 3453,360 | 14 December 2024 8:00 AM | 2024-12-25 17:00 | 2 | Head Contractor | 100 | 79 | 31 | 19 | 15
360 | 1.2.2.2.3.10 | Building C Structure Complete | 0 | 23 December 2024 5:00 PM | 23 December 2024 5:00 PM | 354,359 | 8,7 | 23 December 2024 5:00 PM | 2024-12-23 17:00 | 0 | Excavation | 100 | 42 | 15 | 38 | 18
361 | 1.2.2.2.4 | Building D | 76 | 26 September 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | 26 September 2024 8:00 AM | 2025-01-06 17:00 | 3 | Landscaper | 100 | 21 | 24 | 58 | 35
362 | 1.2.2.2.4.1 | Lvl 2 - FRP - Suspended Slab | 19 | 26 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | 26 September 2024 8:00 AM | 2024-10-23 17:00 | 4 | Joiner | 100 | 75 | 22 | 86 | 50
363 | 1.2.2.2.4.1.1 | Scaffold Stair Removal/Adjustment | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 364SS |  | 26 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Tiler | 100 | 57 | 12 | 77 | 24
364 | 1.2.2.2.4.1.2 | Setout and Install Lift/Stair Formwork | 1 | 26 September 2024 8:00 AM | 27 September 2024 8:00 AM | 365SF | 363SS | 26 September 2024 8:00 AM | 2024-09-27 08:00 | 0 | Fire | 100 | 28 | 15 | 96 | 13
365 | 1.2.2.2.4.1.3 | Formworker setout, drop material and 80% Deck | 6 | 27 September 2024 8:00 AM | 3 October 2024 5:00 PM | 311FS+10d | 366FS-1d,367,364SF | 27 September 2024 8:00 AM | 2024-10-04 17:00 | 1 | Cleaner | 100 | 68 | 23 | 31 | 35
366 | 1.2.2.2.4.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 3 October 2024 8:00 AM | 10 October 2024 5:00 PM | 365FS-1d | 368,369 | 3 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Joiner | 100 | 54 | 19 | 41 | 54
367 | 1.2.2.2.4.1.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 4 October 2024 8:00 AM | 9 October 2024 5:00 PM | 365 |  | 4 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Head Contractor | 100 | 59 | 15 | 80 | 12
368 | 1.2.2.2.4.1.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Line Market | 100 | 49 | 32 | 36 | 58
369 | 1.2.2.2.4.1.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Admin | 100 | 49 | 26 | 41 | 31
370 | 1.2.2.2.4.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 368FS-1d,369FS-1d | 371 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Formworker | 100 | 82 | 14 | 37 | 43
371 | 1.2.2.2.4.1.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 370 | 372 | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Site Manager | 100 | 83 | 26 | 63 | 13
372 | 1.2.2.2.4.1.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 371 | 375 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Post Tension | 100 | 88 | 25 | 45 | 5
373 | 1.2.2.2.4.2 | Strip Formwork - Lvl 2 | 5 | 21 November 2024 8:00 AM | 26 November 2024 5:00 PM | 384FS+8d | 485,506 | 21 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Tiler | 100 | 100 | 17 | 91 | 44
374 | 1.2.2.2.4.3 | Lvl 3 - FRP - Suspended Slab | 19 | 21 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-16 17:00 | 5 | Timber Floorer | 100 | 38 | 15 | 46 | 60
375 | 1.2.2.2.4.3.1 | Scaffold Stair Removal/Adjustment | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 372 | 376SS | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Foreman | 100 | 88 | 14 | 31 | 6
376 | 1.2.2.2.4.3.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 375SS | 377 | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Project Manager | 100 | 22 | 14 | 84 | 29
377 | 1.2.2.2.4.3.3 | Formworker setout, drop material and 80% Deck | 6 | 22 October 2024 8:00 AM | 28 October 2024 5:00 PM | 376 | 378FS-1d,379 | 22 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Fire | 100 | 18 | 29 | 29 | 52
378 | 1.2.2.2.4.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 377FS-1d | 380,381 | 28 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Contract Administrator | 100 | 24 | 35 | 11 | 26
379 | 1.2.2.2.4.3.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 29 October 2024 8:00 AM | 31 October 2024 5:00 PM | 377 |  | 29 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Formworker | 100 | 54 | 33 | 68 | 59
380 | 1.2.2.2.4.3.6 | Services | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Project Manager | 100 | 25 | 32 | 83 | 57
381 | 1.2.2.2.4.3.7 | Post Tension | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Development Manager | 100 | 13 | 10 | 64 | 18
382 | 1.2.2.2.4.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 5 November 2024 8:00 AM | 7 November 2024 5:00 PM | 380FS-1d,381FS-1d | 383 | 5 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Electrician | 100 | 20 | 28 | 19 | 23
383 | 1.2.2.2.4.3.9 | Formworker setdowns and edge boards | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 382 | 384 | 8 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Electrician | 100 | 63 | 25 | 29 | 19
384 | 1.2.2.2.4.3.10 | Pour | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 383 | 385FS+12d,373FS+8d,387 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Contract Administrator | 100 | 62 | 22 | 84 | 16
385 | 1.2.2.2.4.4 | Strip Formwork - Lvl 3 | 5 | 26 November 2024 8:00 AM | 30 November 2024 5:00 PM | 384FS+12d | 511 | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Plasterboarder | 100 | 62 | 21 | 100 | 9
386 | 1.2.2.2.4.5 | L4 Strucutral Steel Roof | 38 | 12 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 12 November 2024 8:00 AM | 2025-01-08 17:00 | 5 | Electrician | 100 | 77 | 15 | 39 | 7
387 | 1.2.2.2.4.5.1 | Scaffold Perimeter Protection | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 384 | 388SS | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Window | 100 | 52 | 23 | 73 | 38
388 | 1.2.2.2.4.5.2 | Setout | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 387SS | 389 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Metal Work | 100 | 48 | 13 | 47 | 47
389 | 1.2.2.2.4.5.3 | Formworker setout, drop material and 80% Walls | 5 | 14 November 2024 8:00 AM | 19 November 2024 5:00 PM | 388 | 390FS-1d | 14 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Line Market | 100 | 21 | 16 | 11 | 22
390 | 1.2.2.2.4.5.4 | Steel Fixer - Walls | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 389FS-1d | 391 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Cleaner | 100 | 63 | 13 | 28 | 24
391 | 1.2.2.2.4.5.5 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 390 | 392 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Floor Sealer | 100 | 18 | 16 | 48 | 13
392 | 1.2.2.2.4.5.6 | Pour | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 391 | 393 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Renderer | 100 | 13 | 14 | 42 | 34
393 | 1.2.2.2.4.5.7 | Strip Formwork | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 392 | 394 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Carpenter | 100 | 17 | 22 | 28 | 56
394 | 1.2.2.2.4.5.8 | Structural Steel Setout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 393 | 395 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Timber Floorer | 100 | 19 | 10 | 30 | 43
395 | 1.2.2.2.4.5.9 | Install Structural Steel | 8 | 29 November 2024 8:00 AM | 7 December 2024 5:00 PM | 394 | 396 | 29 November 2024 8:00 AM | 2024-12-09 17:00 | 2 | Subcontractor | 100 | 57 | 15 | 78 | 52
396 | 1.2.2.2.4.5.10 | Install Metal Deck Roofing | 15 | 9 December 2024 8:00 AM | 3 January 2025 5:00 PM | 395 | 516,8 | 9 December 2024 8:00 AM | 2025-01-08 17:00 | 5 | Joiner | 100 | 13 | 15 | 19 | 29
397 | 1.2.2.3 | Structural Works Complete | 0 | 3 January 2025 5:00 PM | 3 January 2025 5:00 PM | 120,307,361,91,138,229 |  | 3 January 2025 5:00 PM | 2025-01-03 17:00 | 0 | Subcontractor | 100 | 80 | 10 | 40 | 9
398 | 1.2.3 | FAÇADE WORKS | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | 13 July 2024 8:00 AM | 2025-03-23 17:00 | 1 | Landscaper | 100 | 91 | 30 | 47 | 7
399 | 1.2.3.1 | Building A | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | 13 July 2024 8:00 AM | 2025-03-24 17:00 | 2 | Contract Administrator | 100 | 79 | 31 | 16 | 54
400 | 1.2.3.1.1 | Lvl 1 | 44 | 13 July 2024 8:00 AM | 2 September 2024 5:00 PM |  |  | 13 July 2024 8:00 AM | 2024-09-04 17:00 | 2 | Joiner | 100 | 76 | 30 | 37 | 33
401 | 1.2.3.1.1.1 | Survey & Setout | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 116FS+5d | 402 | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Surveyor | 100 | 27 | 20 | 0 | 53
402 | 1.2.3.1.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 15 July 2024 8:00 AM | 19 July 2024 5:00 PM | 401 | 403 | 15 July 2024 8:00 AM | 2024-07-19 17:00 | 0 | Concretor | 100 | 69 | 29 | 46 | 39
403 | 1.2.3.1.1.3 | Façade & External Walls | 20 | 20 July 2024 8:00 AM | 12 August 2024 5:00 PM | 402 | 404 | 20 July 2024 8:00 AM | 2024-08-17 17:00 | 5 | Cleaner | 100 | 33 | 10 | 87 | 8
404 | 1.2.3.1.1.4 | Windows Install | 18 | 13 August 2024 8:00 AM | 2 September 2024 5:00 PM | 403 | 405,411 | 13 August 2024 8:00 AM | 2024-09-04 17:00 | 2 | Subcontractor | 100 | 96 | 15 | 65 | 15
405 | 1.2.3.1.1.5 | Level 1 Weathertight | 0 | 2 September 2024 5:00 PM | 2 September 2024 5:00 PM | 404 | 558 | 2 September 2024 5:00 PM | 2024-09-02 17:00 | 0 | Electrician | 100 | 91 | 19 | 14 | 34
406 | 1.2.3.1.2 | Lvl 2 | 83 | 17 August 2024 8:00 AM | 23 November 2024 5:00 PM |  |  | 17 August 2024 8:00 AM | 2024-11-24 17:00 | 1 | Concretor | 100 | 23 | 10 | 64 | 51
407 | 1.2.3.1.2.1 | Survey & Setout | 1 | 17 August 2024 8:00 AM | 17 August 2024 5:00 PM | 149FS+5d | 408 | 17 August 2024 8:00 AM | 2024-08-17 17:00 | 0 | Concretor | 100 | 57 | 15 | 97 | 38
408 | 1.2.3.1.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 19 August 2024 8:00 AM | 23 August 2024 5:00 PM | 407 | 577 | 19 August 2024 8:00 AM | 2024-08-23 17:00 | 0 | Reinforcement Fixer | 100 | 67 | 16 | 10 | 3
409 | 1.2.3.1.2.3 | Façade & External Walls | 22 | 9 October 2024 8:00 AM | 2 November 2024 5:00 PM | 150FS-10d | 410 | 9 October 2024 8:00 AM | 2024-11-04 17:00 | 2 | Metal Work | 100 | 98 | 22 | 20 | 50
410 | 1.2.3.1.2.4 | Windows Install | 18 | 4 November 2024 8:00 AM | 23 November 2024 5:00 PM | 409 | 411 | 4 November 2024 8:00 AM | 2024-11-25 17:00 | 2 | Painter | 100 | 77 | 31 | 94 | 37
411 | 1.2.3.1.2.5 | Level 2 Weathertight | 0 | 23 November 2024 5:00 PM | 23 November 2024 5:00 PM | 404,410 | 585 | 23 November 2024 5:00 PM | 2024-11-23 17:00 | 0 | Electrician | 100 | 96 | 27 | 20 | 55
412 | 1.2.3.1.3 | Lvl 3 | 40 | 13 November 2024 8:00 AM | 7 January 2025 5:00 PM |  |  | 13 November 2024 8:00 AM | 2025-01-08 17:00 | 1 | Metal Work | 100 | 59 | 24 | 27 | 46
413 | 1.2.3.1.3.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 174FS+5d | 414FS-1d | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Renderer | 100 | 12 | 10 | 90 | 39
414 | 1.2.3.1.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 413FS-1d |  | 30 November 2024 8:00 AM | 2024-12-04 17:00 | 0 | Tiler | 100 | 91 | 14 | 53 | 19
415 | 1.2.3.1.3.3 | Façade & External Walls | 22 | 13 November 2024 8:00 AM | 7 December 2024 5:00 PM | 174FS-10d | 416 | 13 November 2024 8:00 AM | 2024-12-12 17:00 | 5 | Stone Mason | 100 | 37 | 18 | 39 | 29
416 | 1.2.3.1.3.4 | Windows Install | 18 | 9 December 2024 8:00 AM | 7 January 2025 5:00 PM | 415 | 610FS-6d,417 | 9 December 2024 8:00 AM | 2025-01-07 17:00 | 0 | Excavation | 100 | 34 | 14 | 73 | 27
417 | 1.2.3.1.3.5 | Level 3 Weathertight | 0 | 7 January 2025 5:00 PM | 7 January 2025 5:00 PM | 416 | 612,444 | 7 January 2025 5:00 PM | 2025-01-07 17:00 | 0 | Waterproofer | 100 | 96 | 19 | 62 | 46
418 | 1.2.3.1.4 | Lvl 4 | 44 | 17 December 2024 8:00 AM | 15 February 2025 5:00 PM |  |  | 17 December 2024 8:00 AM | 2025-02-17 17:00 | 2 | Site Manager | 100 | 74 | 12 | 20 | 55
419 | 1.2.3.1.4.1 | Survey & Setout | 1 | 17 December 2024 8:00 AM | 17 December 2024 5:00 PM | 186FS+5d | 420FS-1d | 17 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Waterproofer | 100 | 67 | 22 | 67 | 7
420 | 1.2.3.1.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 17 December 2024 8:00 AM | 20 December 2024 5:00 PM | 419FS-1d | 421 | 17 December 2024 8:00 AM | 2024-12-20 17:00 | 0 | Project Manager | 100 | 29 | 14 | 43 | 31
421 | 1.2.3.1.4.3 | Façade & External Walls | 22 | 21 December 2024 8:00 AM | 24 January 2025 5:00 PM | 186FS-10d,420 | 422 | 21 December 2024 8:00 AM | 2025-01-24 17:00 | 0 | Mechanical | 100 | 14 | 33 | 78 | 2
422 | 1.2.3.1.4.4 | Windows Install | 18 | 27 January 2025 8:00 AM | 15 February 2025 5:00 PM | 421 | 637FS-6d,423 | 27 January 2025 8:00 AM | 2025-02-19 17:00 | 4 | Plasterboarder | 100 | 66 | 11 | 41 | 13
423 | 1.2.3.1.4.5 | Level 4 Weathertight | 0 | 15 February 2025 5:00 PM | 15 February 2025 5:00 PM | 422 | 639,444 | 15 February 2025 5:00 PM | 2025-02-15 17:00 | 0 | Landscaper | 100 | 83 | 33 | 19 | 8
424 | 1.2.3.1.5 | Lvl 5 | 40 | 30 November 2024 8:00 AM | 24 January 2025 5:00 PM |  |  | 30 November 2024 8:00 AM | 2025-01-24 17:00 | 0 | Electrician | 100 | 98 | 28 | 100 | 16
425 | 1.2.3.1.5.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 198FS+5d | 426FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Contract Administrator | 100 | 40 | 14 | 30 | 12
426 | 1.2.3.1.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 425FS-1d | 663 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Stone Mason | 100 | 19 | 21 | 28 | 56
427 | 1.2.3.1.5.3 | Façade & External Walls | 22 | 30 November 2024 8:00 AM | 3 January 2025 5:00 PM | 198FS-10d | 428 | 30 November 2024 8:00 AM | 2025-01-04 17:00 | 1 | Site Manager | 100 | 67 | 31 | 12 | 56
428 | 1.2.3.1.5.4 | Windows Install | 18 | 4 January 2025 8:00 AM | 24 January 2025 5:00 PM | 427 | 669FS-6d,429,444 | 4 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Surveyor | 100 | 61 | 19 | 96 | 54
429 | 1.2.3.1.5.5 | Level 5 Weathertight | 0 | 24 January 2025 5:00 PM | 24 January 2025 5:00 PM | 428 | 671 | 24 January 2025 5:00 PM | 2025-01-24 17:00 | 0 | Timber Floorer | 100 | 21 | 14 | 65 | 18
430 | 1.2.3.1.6 | Lvl 6 | 59 | 19 November 2024 8:00 AM | 5 February 2025 5:00 PM |  |  | 19 November 2024 8:00 AM | 2025-02-10 17:00 | 5 | Timber Floorer | 100 | 75 | 31 | 91 | 33
431 | 1.2.3.1.6.1 | Survey & Setout | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 209FS+5d | 432 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Admin | 100 | 80 | 18 | 56 | 36
432 | 1.2.3.1.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 6 December 2024 8:00 AM | 10 December 2024 5:00 PM | 210FS-10d,431 | 433,690 | 6 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Tiler | 100 | 17 | 15 | 95 | 46
433 | 1.2.3.1.6.3 | Façade & External Walls | 22 | 11 December 2024 8:00 AM | 14 January 2025 5:00 PM | 432 | 434 | 11 December 2024 8:00 AM | 2025-01-15 17:00 | 1 | Scaffolder | 100 | 96 | 35 | 91 | 32
434 | 1.2.3.1.6.4 | Windows Install | 18 | 15 January 2025 8:00 AM | 5 February 2025 5:00 PM | 433 | 696FS-6d,435 | 15 January 2025 8:00 AM | 2025-02-06 17:00 | 1 | Contract Administrator | 100 | 87 | 15 | 50 | 22
435 | 1.2.3.1.6.5 | Level 6 Weathertight | 0 | 5 February 2025 5:00 PM | 5 February 2025 5:00 PM | 434 | 698,444 | 5 February 2025 5:00 PM | 2025-02-05 17:00 | 0 | Floor Sealer | 100 | 79 | 32 | 11 | 36
436 | 1.2.3.1.7 | Lvl 7 | 59 | 5 December 2024 8:00 AM | 21 February 2025 5:00 PM |  |  | 5 December 2024 8:00 AM | 2025-02-26 17:00 | 5 | Post Tension | 100 | 27 | 26 | 42 | 43
437 | 1.2.3.1.7.1 | Survey & Setout | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 221FS+5d | 438FS-1d | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Metal Work | 100 | 26 | 27 | 61 | 28
438 | 1.2.3.1.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 5 December 2024 8:00 AM | 9 December 2024 5:00 PM | 437FS-1d | 722 | 5 December 2024 8:00 AM | 2024-12-09 17:00 | 0 | Metal Work | 100 | 94 | 31 | 77 | 46
439 | 1.2.3.1.7.3 | Façade & External Walls | 22 | 8 January 2025 8:00 AM | 3 February 2025 5:00 PM | 223FS+10d | 440 | 8 January 2025 8:00 AM | 2025-02-06 17:00 | 3 | Plasterboarder | 100 | 74 | 29 | 65 | 40
440 | 1.2.3.1.7.4 | Windows Install | 16 | 4 February 2025 8:00 AM | 21 February 2025 5:00 PM | 439 | 728FS-6d,441,3446FS-5d | 4 February 2025 8:00 AM | 2025-02-21 17:00 | 0 | Tiler | 100 | 51 | 20 | 13 | 53
441 | 1.2.3.1.7.5 | Level 7 Weathertight | 0 | 21 February 2025 5:00 PM | 21 February 2025 5:00 PM | 440 | 730,442 | 21 February 2025 5:00 PM | 2025-02-21 17:00 | 0 | Floor Sealer | 100 | 82 | 28 | 52 | 10
442 | 1.2.3.1.8 | Defect Rectification | 15 | 22 February 2025 8:00 AM | 11 March 2025 5:00 PM | 441 | 443 | 22 February 2025 8:00 AM | 2025-03-14 17:00 | 3 | Subcontractor | 100 | 53 | 17 | 30 | 56
443 | 1.2.3.1.9 | Strip Scaffold | 10 | 12 March 2025 8:00 AM | 22 March 2025 5:00 PM | 442 | 444,3456 | 12 March 2025 8:00 AM | 2025-03-25 17:00 | 3 | Reinforcement Fixer | 100 | 74 | 19 | 1 | 11
444 | 1.2.3.1.10 | Building A Façade Complete | 0 | 22 March 2025 5:00 PM | 22 March 2025 5:00 PM | 443,435,428,423,417 | 5 | 22 March 2025 5:00 PM | 2025-03-22 17:00 | 0 | Electrician | 100 | 38 | 11 | 61 | 40
445 | 1.2.3.2 | Building B | 89 | 4 October 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | 4 October 2024 8:00 AM | 2025-02-01 17:00 | 4 | Admin | 100 | 45 | 27 | 52 | 17
446 | 1.2.3.2.1 | Lvl 1 | 44 | 4 October 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 4 October 2024 8:00 AM | 2024-11-30 17:00 | 4 | Window | 100 | 62 | 25 | 58 | 11
447 | 1.2.3.2.1.1 | Survey & Setout | 1 | 4 October 2024 8:00 AM | 4 October 2024 5:00 PM | 241 | 448 | 4 October 2024 8:00 AM | 2024-10-04 17:00 | 0 | Window | 100 | 48 | 20 | 10 | 2
448 | 1.2.3.2.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 8 October 2024 8:00 AM | 12 October 2024 5:00 PM | 447 | 449,758,852,1322FS+6d,1510FS+6d,1416FS+6d,946FS+2d,1040FS+2d,1134FS+4d,1228FS+4d | 8 October 2024 8:00 AM | 2024-10-12 17:00 | 0 | Reinforcement Fixer | 100 | 39 | 11 | 83 | 58
449 | 1.2.3.2.1.3 | Façade & External Walls | 20 | 14 October 2024 8:00 AM | 5 November 2024 5:00 PM | 448 | 450 | 14 October 2024 8:00 AM | 2024-11-10 17:00 | 5 | Project Manager | 100 | 87 | 23 | 59 | 30
450 | 1.2.3.2.1.4 | Windows Install | 18 | 6 November 2024 8:00 AM | 26 November 2024 5:00 PM | 449 | 451 | 6 November 2024 8:00 AM | 2024-11-29 17:00 | 3 | Plumber | 100 | 89 | 22 | 82 | 38
451 | 1.2.3.2.1.5 | Level 1 Weathertight | 0 | 26 November 2024 5:00 PM | 26 November 2024 5:00 PM | 450 | 1640 | 26 November 2024 5:00 PM | 2024-11-26 17:00 | 0 | Electrician | 100 | 75 | 13 | 15 | 59
452 | 1.2.3.2.2 | Lvl 2 | 42 | 26 October 2024 8:00 AM | 13 December 2024 5:00 PM |  |  | 26 October 2024 8:00 AM | 2024-12-14 17:00 | 1 | Concretor | 100 | 31 | 28 | 24 | 10
453 | 1.2.3.2.2.1 | Survey & Setout | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 253 | 454 | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Window | 100 | 33 | 31 | 79 | 40
454 | 1.2.3.2.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 453 | 455 | 28 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Head Contractor | 100 | 16 | 10 | 12 | 59
455 | 1.2.3.2.2.3 | Façade & External Walls | 20 | 2 November 2024 8:00 AM | 25 November 2024 5:00 PM | 454 | 456 | 2 November 2024 8:00 AM | 2024-11-29 17:00 | 4 | Painter | 100 | 10 | 29 | 31 | 8
456 | 1.2.3.2.2.4 | Windows Install | 16 | 26 November 2024 8:00 AM | 13 December 2024 5:00 PM | 455 | 457 | 26 November 2024 8:00 AM | 2024-12-17 17:00 | 4 | Mechanical | 100 | 98 | 30 | 18 | 36
457 | 1.2.3.2.2.5 | Level 2 Weathertight | 0 | 13 December 2024 5:00 PM | 13 December 2024 5:00 PM | 456 |  | 13 December 2024 5:00 PM | 2024-12-13 17:00 | 0 | Excavation | 100 | 64 | 29 | 0 | 22
458 | 1.2.3.2.3 | Lvl 3 | 43 | 16 November 2024 8:00 AM | 14 January 2025 5:00 PM |  |  | 16 November 2024 8:00 AM | 2025-01-15 17:00 | 1 | Renderer | 100 | 61 | 35 | 2 | 14
459 | 1.2.3.2.3.1 | Survey & Setout | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 265 | 460 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Joiner | 100 | 82 | 35 | 42 | 13
460 | 1.2.3.2.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 459 | 461 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 100 | 73 | 11 | 23 | 51
461 | 1.2.3.2.3.3 | Façade & External Walls | 20 | 22 November 2024 8:00 AM | 14 December 2024 5:00 PM | 460 | 462 | 22 November 2024 8:00 AM | 2024-12-15 17:00 | 1 | Contract Administrator | 100 | 10 | 27 | 47 | 3
462 | 1.2.3.2.3.4 | Windows Install | 18 | 16 December 2024 8:00 AM | 14 January 2025 5:00 PM | 461 | 1638FS-6d,463 | 16 December 2024 8:00 AM | 2025-01-19 17:00 | 5 | Reinforcement Fixer | 100 | 56 | 20 | 94 | 39
463 | 1.2.3.2.3.5 | Level 3 Weathertight | 0 | 14 January 2025 5:00 PM | 14 January 2025 5:00 PM | 462 | 1640 | 14 January 2025 5:00 PM | 2025-01-14 17:00 | 0 | Admin | 100 | 88 | 34 | 32 | 37
464 | 1.2.3.2.4 | Lvl 4 | 42 | 23 November 2024 8:00 AM | 20 January 2025 5:00 PM |  |  | 23 November 2024 8:00 AM | 2025-01-23 17:00 | 3 | Formworker | 100 | 10 | 28 | 85 | 56
465 | 1.2.3.2.4.1 | Survey & Setout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 277 | 466FS-1d | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Metal Work | 100 | 67 | 10 | 83 | 24
466 | 1.2.3.2.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 23 November 2024 8:00 AM | 27 November 2024 5:00 PM | 465FS-1d | 467 | 23 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Landscaper | 100 | 16 | 28 | 32 | 10
467 | 1.2.3.2.4.3 | Façade & External Walls | 20 | 28 November 2024 8:00 AM | 20 December 2024 5:00 PM | 466 | 468 | 28 November 2024 8:00 AM | 2024-12-24 17:00 | 4 | Line Market | 100 | 82 | 15 | 4 | 34
468 | 1.2.3.2.4.4 | Windows Install | 18 | 21 December 2024 8:00 AM | 20 January 2025 5:00 PM | 467 | 1665FS-6d,469 | 21 December 2024 8:00 AM | 2025-01-24 17:00 | 4 | Landscaper | 100 | 84 | 31 | 84 | 37
469 | 1.2.3.2.4.5 | Level 4 Weathertight | 0 | 20 January 2025 5:00 PM | 20 January 2025 5:00 PM | 468 | 1665FS-6d | 20 January 2025 5:00 PM | 2025-01-20 17:00 | 0 | Carpet | 100 | 64 | 17 | 59 | 54
470 | 1.2.3.2.5 | Lvl 5 | 42 | 26 November 2024 8:00 AM | 22 January 2025 5:00 PM |  |  | 26 November 2024 8:00 AM | 2025-01-26 17:00 | 4 | Head Contractor | 100 | 18 | 13 | 15 | 57
471 | 1.2.3.2.5.1 | Survey & Setout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 289 | 472FS-1d | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Subcontractor | 100 | 73 | 18 | 44 | 21
472 | 1.2.3.2.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 26 November 2024 8:00 AM | 29 November 2024 5:00 PM | 471FS-1d | 473 | 26 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Window | 100 | 33 | 16 | 0 | 18
473 | 1.2.3.2.5.3 | Façade & External Walls | 20 | 30 November 2024 8:00 AM | 23 December 2024 5:00 PM | 472 | 474 | 30 November 2024 8:00 AM | 2024-12-28 17:00 | 5 | Timber Floorer | 100 | 100 | 35 | 16 | 11
474 | 1.2.3.2.5.4 | Windows Install | 18 | 24 December 2024 8:00 AM | 22 January 2025 5:00 PM | 473 | 475 | 24 December 2024 8:00 AM | 2025-01-27 17:00 | 5 | Surveyor | 100 | 94 | 16 | 53 | 13
475 | 1.2.3.2.5.5 | Level 5 Weathertight | 0 | 22 January 2025 5:00 PM | 22 January 2025 5:00 PM | 474 | 1692FS-4d | 22 January 2025 5:00 PM | 2025-01-22 17:00 | 0 | Foreman | 100 | 67 | 33 | 38 | 8
476 | 1.2.3.2.6 | Lvl 6 | 42 | 30 November 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | 30 November 2024 8:00 AM | 2025-01-28 17:00 | 0 | Renderer | 100 | 37 | 25 | 13 | 3
477 | 1.2.3.2.6.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 301 | 478FS-1d | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Concretor | 100 | 77 | 27 | 46 | 8
478 | 1.2.3.2.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 477FS-1d | 479 | 30 November 2024 8:00 AM | 2024-12-04 17:00 | 0 | Fire | 100 | 57 | 14 | 10 | 17
479 | 1.2.3.2.6.3 | Façade & External Walls | 20 | 5 December 2024 8:00 AM | 6 January 2025 5:00 PM | 478 | 480 | 5 December 2024 8:00 AM | 2025-01-10 17:00 | 4 | Window | 100 | 26 | 30 | 99 | 52
480 | 1.2.3.2.6.4 | Windows Install | 18 | 7 January 2025 8:00 AM | 28 January 2025 5:00 PM | 479 | 481 | 7 January 2025 8:00 AM | 2025-01-29 17:00 | 1 | Painter | 100 | 46 | 22 | 90 | 44
481 | 1.2.3.2.6.5 | Level 6 Weathertight | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 480 | 1719FS-6d,482 | 28 January 2025 5:00 PM | 2025-01-28 17:00 | 0 | Excavation | 100 | 63 | 14 | 80 | 9
482 | 1.2.3.2.6.6 | Building B Façade Complete | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 481 | 6 | 28 January 2025 5:00 PM | 2025-01-28 17:00 | 0 | Landscaper | 100 | 59 | 23 | 12 | 56
483 | 1.2.3.3 | Building C | 63 | 27 November 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-02-21 17:00 | 3 | Formworker | 100 | 52 | 24 | 76 | 2
484 | 1.2.3.3.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-01-28 17:00 | 1 | Site Manager | 100 | 51 | 22 | 13 | 7
485 | 1.2.3.3.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 486 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Timber Floorer | 100 | 30 | 24 | 84 | 51
486 | 1.2.3.3.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 485 | 487 | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Timber Floorer | 100 | 68 | 32 | 57 | 34
487 | 1.2.3.3.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 486 | 488 | 4 December 2024 8:00 AM | 2025-01-06 17:00 | 2 | Joiner | 100 | 75 | 21 | 52 | 7
488 | 1.2.3.3.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 487 |  | 6 January 2025 8:00 AM | 2025-02-01 17:00 | 5 | Floor Sealer | 100 | 27 | 21 | 33 | 29
489 | 1.2.3.3.2 | Lvl 2 | 44 | 16 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | 16 December 2024 8:00 AM | 2025-02-14 17:00 | 0 | Project Manager | 100 | 40 | 22 | 72 | 57
490 | 1.2.3.3.2.1 | Survey & Setout | 1 | 16 December 2024 8:00 AM | 16 December 2024 5:00 PM | 331 | 491 | 16 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Hoarding | 100 | 46 | 20 | 49 | 11
491 | 1.2.3.3.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 17 December 2024 8:00 AM | 21 December 2024 5:00 PM | 490 | 492 | 17 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Electrician | 100 | 55 | 31 | 23 | 14
492 | 1.2.3.3.2.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 491 | 493 | 23 December 2024 8:00 AM | 2025-01-26 17:00 | 3 | Tiler | 100 | 49 | 27 | 33 | 47
493 | 1.2.3.3.2.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 492 |  | 24 January 2025 8:00 AM | 2025-02-15 17:00 | 1 | Window | 100 | 35 | 35 | 100 | 52
494 | 1.2.3.3.3 | Lvl 3 | 42 | 21 December 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | 21 December 2024 8:00 AM | 2025-02-22 17:00 | 4 | Waterproofer | 100 | 66 | 14 | 80 | 32
495 | 1.2.3.3.3.1 | Survey & Setout | 1 | 21 December 2024 8:00 AM | 21 December 2024 5:00 PM | 343 | 496FS-1d | 21 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Excavation | 100 | 50 | 14 | 72 | 14
496 | 1.2.3.3.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 21 December 2024 8:00 AM | 3 January 2025 5:00 PM | 495FS-1d | 497 | 21 December 2024 8:00 AM | 2025-01-03 17:00 | 0 | Stone Mason | 100 | 90 | 22 | 53 | 3
497 | 1.2.3.3.3.3 | Façade & External Walls | 20 | 4 January 2025 8:00 AM | 28 January 2025 5:00 PM | 496 | 498 | 4 January 2025 8:00 AM | 2025-01-30 17:00 | 2 | Waterproofer | 100 | 12 | 29 | 40 | 4
498 | 1.2.3.3.3.4 | Windows Install | 18 | 29 January 2025 8:00 AM | 18 February 2025 5:00 PM | 497 | 2654FS-6d | 29 January 2025 8:00 AM | 2025-02-20 17:00 | 2 | Tiler | 100 | 82 | 24 | 98 | 38
499 | 1.2.3.3.4 | Lvl 4 | 42 | 18 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-02-18 17:00 | 4 | Admin | 100 | 56 | 13 | 19 | 58
500 | 1.2.3.3.4.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 355 | 501FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Carpenter | 100 | 80 | 33 | 92 | 50
501 | 1.2.3.3.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 500FS-1d | 502 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Timber Floorer | 100 | 17 | 33 | 94 | 51
502 | 1.2.3.3.4.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 501 | 503 | 23 December 2024 8:00 AM | 2025-01-26 17:00 | 3 | Development Manager | 100 | 56 | 35 | 78 | 59
503 | 1.2.3.3.4.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 502 | 3151FS-6d,7 | 24 January 2025 8:00 AM | 2025-02-15 17:00 | 1 | Cleaner | 100 | 10 | 26 | 50 | 22
504 | 1.2.3.4 | Building D | 62 | 27 November 2024 8:00 AM | 17 February 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-02-17 17:00 | 0 | Landscaper | 100 | 67 | 12 | 11 | 54
505 | 1.2.3.4.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-01-29 17:00 | 2 | Electrician | 100 | 74 | 21 | 86 | 30
506 | 1.2.3.4.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 507 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Mechanical | 100 | 66 | 24 | 83 | 49
507 | 1.2.3.4.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 506 | 508,3361 | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Stone Mason | 100 | 76 | 13 | 96 | 10
508 | 1.2.3.4.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 507 | 509 | 4 December 2024 8:00 AM | 2025-01-05 17:00 | 1 | Electrician | 100 | 66 | 16 | 70 | 26
509 | 1.2.3.4.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 508 |  | 6 January 2025 8:00 AM | 2025-01-30 17:00 | 3 | Tiler | 100 | 14 | 19 | 78 | 58
510 | 1.2.3.4.2 | Lvl 2 | 44 | 2 December 2024 8:00 AM | 31 January 2025 5:00 PM |  |  | 2 December 2024 8:00 AM | 2025-02-05 17:00 | 5 | Admin | 100 | 20 | 30 | 80 | 28
511 | 1.2.3.4.2.1 | Survey & Setout | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 385 | 512 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Cleaner | 100 | 18 | 11 | 72 | 41
512 | 1.2.3.4.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 3 December 2024 8:00 AM | 7 December 2024 5:00 PM | 511 | 513,3388 | 3 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Tiler | 100 | 21 | 11 | 94 | 35
513 | 1.2.3.4.2.3 | Façade & External Walls | 20 | 9 December 2024 8:00 AM | 9 January 2025 5:00 PM | 512 | 514 | 9 December 2024 8:00 AM | 2025-01-13 17:00 | 4 | Subcontractor | 100 | 67 | 16 | 12 | 3
514 | 1.2.3.4.2.4 | Windows Install | 18 | 10 January 2025 8:00 AM | 31 January 2025 5:00 PM | 513 |  | 10 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Mechanical | 100 | 91 | 20 | 6 | 26
515 | 1.2.3.4.3 | Lvl 3 | 37 | 4 January 2025 8:00 AM | 17 February 2025 5:00 PM |  |  | 4 January 2025 8:00 AM | 2025-02-20 17:00 | 3 | Fire | 100 | 49 | 16 | 38 | 19
516 | 1.2.3.4.3.1 | Survey & Setout | 1 | 4 January 2025 8:00 AM | 4 January 2025 5:00 PM | 396 | 517FS-1d | 4 January 2025 8:00 AM | 2025-01-04 17:00 | 0 | Development Manager | 100 | 44 | 15 | 71 | 31
517 | 1.2.3.4.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 3 | 4 January 2025 8:00 AM | 7 January 2025 5:00 PM | 516FS-1d | 518,3415 | 4 January 2025 8:00 AM | 2025-01-07 17:00 | 0 | Hoarding | 100 | 47 | 28 | 91 | 6
518 | 1.2.3.4.3.3 | Façade & External Walls | 18 | 8 January 2025 8:00 AM | 29 January 2025 5:00 PM | 517 | 519 | 8 January 2025 8:00 AM | 2025-01-31 17:00 | 2 | Excavation | 100 | 71 | 16 | 93 | 52
519 | 1.2.3.4.3.4 | Windows Install | 16 | 30 January 2025 8:00 AM | 17 February 2025 5:00 PM | 518 | 3421FS-6d,8 | 30 January 2025 8:00 AM | 2025-02-17 17:00 | 0 | Carpenter | 100 | 85 | 28 | 29 | 43
520 | 1.2.4 | FIT-OUT WORKS | 185 | 13 September 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 13 September 2024 8:00 AM | 2025-05-06 17:00 | 1 | Hoarding | 50 | 11 | 17 | 61 | 51
521 | 1.2.4.1 | Basement 2 - Services & Fitoff | 140 | 13 September 2024 8:00 AM | 7 March 2025 5:00 PM |  |  | 13 September 2024 8:00 AM | 2025-03-12 17:00 | 5 | Landscaper | 100 | 43 | 27 | 67 | 13
522 | 1.2.4.1.1 | Services rough in | 60 | 13 September 2024 8:00 AM | 23 November 2024 5:00 PM | 107 | 523 | 13 September 2024 8:00 AM | 2024-11-23 17:00 | 0 | Plumber | 100 | 58 | 33 | 81 | 31
523 | 1.2.4.1.2 | Block walls (Metal Door Frames) | 6 | 25 November 2024 8:00 AM | 30 November 2024 5:00 PM | 522 | 524,525 | 25 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Window | 100 | 57 | 31 | 65 | 10
524 | 1.2.4.1.3 | Render works as specified | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 527 | 2 December 2024 8:00 AM | 2024-12-19 17:00 | 5 | Reinforcement Fixer | 100 | 39 | 27 | 92 | 16
525 | 1.2.4.1.4 | Carpentry fitoff | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 526 | 2 December 2024 8:00 AM | 2024-12-18 17:00 | 4 | Painter | 100 | 79 | 13 | 2 | 50
526 | 1.2.4.1.5 | Services Plant & Equipment Install | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 525 |  | 16 December 2024 8:00 AM | 2025-01-11 17:00 | 4 | Post Tension | 100 | 54 | 24 | 59 | 3
527 | 1.2.4.1.6 | Doors & Hardware | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 524 | 528 | 16 December 2024 8:00 AM | 2025-01-11 17:00 | 4 | Carpet | 100 | 34 | 34 | 93 | 12
528 | 1.2.4.1.7 | Services Fitoff | 12 | 8 January 2025 8:00 AM | 21 January 2025 5:00 PM | 527 | 529 | 8 January 2025 8:00 AM | 2025-01-25 17:00 | 4 | Carpet | 100 | 11 | 35 | 69 | 33
529 | 1.2.4.1.8 | Finishes & Painting | 12 | 22 January 2025 8:00 AM | 5 February 2025 5:00 PM | 528 | 530 | 22 January 2025 8:00 AM | 2025-02-07 17:00 | 2 | Carpet | 100 | 81 | 23 | 76 | 58
530 | 1.2.4.1.9 | Metalwork Items | 8 | 6 February 2025 8:00 AM | 14 February 2025 5:00 PM | 529 | 531 | 6 February 2025 8:00 AM | 2025-02-19 17:00 | 5 | Carpet | 100 | 27 | 26 | 22 | 18
531 | 1.2.4.1.10 | Builders Clean | 6 | 15 February 2025 8:00 AM | 21 February 2025 5:00 PM | 530 | 532 | 15 February 2025 8:00 AM | 2025-02-22 17:00 | 1 | Painter | 100 | 61 | 20 | 60 | 9
532 | 1.2.4.1.11 | Car Park Clean, Patch and Floor Sealer | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 531 | 533 | 22 February 2025 8:00 AM | 2025-03-04 17:00 | 1 | Waterproofer | 100 | 72 | 31 | 23 | 38
533 | 1.2.4.1.12 | Line Marking | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 532 |  | 4 March 2025 8:00 AM | 2025-03-07 17:00 | 0 | Excavation | 100 | 93 | 31 | 3 | 27
534 | 1.2.4.2 | Basement 1 - Services & Fitoff | 140 | 1 October 2024 8:00 AM | 25 March 2025 5:00 PM |  |  | 1 October 2024 8:00 AM | 2025-03-29 17:00 | 4 | Painter | 100 | 47 | 22 | 79 | 3
535 | 1.2.4.2.1 | Services rough in | 60 | 1 October 2024 8:00 AM | 11 December 2024 5:00 PM | 119 | 536 | 1 October 2024 8:00 AM | 2024-12-11 17:00 | 0 | Electrician | 100 | 89 | 18 | 24 | 34
536 | 1.2.4.2.2 | Block walls (Metal Door Frames) | 6 | 12 December 2024 8:00 AM | 18 December 2024 5:00 PM | 535 | 537,538 | 12 December 2024 8:00 AM | 2024-12-20 17:00 | 2 | Plasterboarder | 100 | 81 | 24 | 44 | 31
537 | 1.2.4.2.3 | Render works as specified | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 540 | 19 December 2024 8:00 AM | 2025-01-13 17:00 | 3 | Carpet | 100 | 40 | 20 | 22 | 15
538 | 1.2.4.2.4 | Carpentry fitoff | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 539 | 19 December 2024 8:00 AM | 2025-01-14 17:00 | 4 | Timber Floorer | 100 | 46 | 22 | 0 | 41
539 | 1.2.4.2.5 | Services Plant & Equipment Install | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 538 |  | 11 January 2025 8:00 AM | 2025-01-27 17:00 | 3 | Subcontractor | 100 | 67 | 16 | 77 | 36
540 | 1.2.4.2.6 | Doors & Hardware | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 537 | 541 | 11 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Joiner | 100 | 83 | 32 | 11 | 27
541 | 1.2.4.2.7 | Services Fitoff | 12 | 27 January 2025 8:00 AM | 8 February 2025 5:00 PM | 540 | 542 | 27 January 2025 8:00 AM | 2025-02-11 17:00 | 3 | Hoarding | 100 | 92 | 14 | 63 | 43
542 | 1.2.4.2.8 | Finishes & Painting | 12 | 10 February 2025 8:00 AM | 22 February 2025 5:00 PM | 541 | 543 | 10 February 2025 8:00 AM | 2025-02-27 17:00 | 5 | Head Contractor | 100 | 59 | 22 | 30 | 11
543 | 1.2.4.2.9 | Metalwork Items | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 542 | 544 | 24 February 2025 8:00 AM | 2025-03-05 17:00 | 1 | Concretor | 100 | 100 | 19 | 7 | 53
544 | 1.2.4.2.10 | Builders Clean | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 543 | 545 | 5 March 2025 8:00 AM | 2025-03-13 17:00 | 2 | Reinforcement Fixer | 100 | 99 | 33 | 94 | 29
545 | 1.2.4.2.11 | Car Park Clean, Patch and Floor Sealer | 8 | 12 March 2025 8:00 AM | 20 March 2025 5:00 PM | 544 | 546 | 12 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Concretor | 100 | 93 | 33 | 72 | 28
546 | 1.2.4.2.12 | Line Marking | 4 | 21 March 2025 8:00 AM | 25 March 2025 5:00 PM | 545 |  | 21 March 2025 8:00 AM | 2025-03-25 17:00 | 0 | Electrician | 100 | 67 | 20 | 100 | 35
547 | 1.2.4.3 | Building A | 155 | 21 October 2024 8:00 AM | 5 May 2025 5:00 PM |  | 3440 | 21 October 2024 8:00 AM | 2025-05-10 17:00 | 5 | Tiler | 50 | 83 | 19 | 61 | 32
548 | 1.2.4.3.1 | Lvl 1 - Services & Finishes | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-14 17:00 | 1 | Metal Work | 100 | 73 | 13 | 48 | 17
549 | 1.2.4.3.1.1 | Internal Works | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-15 17:00 | 2 | Scaffolder | 100 | 83 | 34 | 44 | 35
550 | 1.2.4.3.1.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 150 | 551FS-2d | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Site Manager | 100 | 59 | 35 | 31 | 51
551 | 1.2.4.3.1.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 550FS-2d | 552 | 21 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Landscaper | 100 | 75 | 12 | 67 | 49
552 | 1.2.4.3.1.1.3 | Internal Wall Framing | 10 | 1 November 2024 8:00 AM | 12 November 2024 5:00 PM | 551 | 554,553 | 1 November 2024 8:00 AM | 2024-11-16 17:00 | 4 | Floor Sealer | 100 | 22 | 22 | 76 | 45
553 | 1.2.4.3.1.1.4 | Sheet one side of walls | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 556,555 | 13 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Excavation | 100 | 53 | 28 | 29 | 24
554 | 1.2.4.3.1.1.5 | Service Rough-In | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 555 | 13 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Cleaner | 100 | 47 | 28 | 97 | 26
555 | 1.2.4.3.1.1.6 | ITP for services in the walls | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 553,554 | 556,562 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Reinforcement Fixer | 100 | 73 | 29 | 73 | 42
556 | 1.2.4.3.1.1.7 | Sheet other side of walls | 8 | 25 November 2024 8:00 AM | 3 December 2024 5:00 PM | 553,555 | 557 | 25 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Stone Mason | 100 | 70 | 15 | 12 | 40
557 | 1.2.4.3.1.1.8 | Frame & Sheet Ceilings | 8 | 4 December 2024 8:00 AM | 12 December 2024 5:00 PM | 556 | 558 | 4 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Excavation | 100 | 76 | 34 | 73 | 3
558 | 1.2.4.3.1.1.9 | Sheet, Set & Sand Ceilings | 8 | 13 December 2024 8:00 AM | 21 December 2024 5:00 PM | 557,405 | 559 | 13 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Formworker | 100 | 51 | 27 | 13 | 4
559 | 1.2.4.3.1.1.10 | Paint undercoat | 4 | 23 December 2024 8:00 AM | 4 January 2025 5:00 PM | 558 | 560 | 23 December 2024 8:00 AM | 2025-01-04 17:00 | 0 | Window | 100 | 84 | 27 | 82 | 10
560 | 1.2.4.3.1.1.11 | Floor Levelling and Floor Finish | 6 | 6 January 2025 8:00 AM | 11 January 2025 5:00 PM | 559 | 561 | 6 January 2025 8:00 AM | 2025-01-14 17:00 | 3 | Hoarding | 100 | 51 | 20 | 38 | 39
561 | 1.2.4.3.1.1.12 | Timber Flooring | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 560 | 567,568,563 | 13 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Line Market | 100 | 81 | 24 | 88 | 18
562 | 1.2.4.3.1.1.13 | Measure & Manufacture Joinery | 40 | 25 November 2024 8:00 AM | 18 January 2025 5:00 PM | 555 | 563 | 25 November 2024 8:00 AM | 2025-01-21 17:00 | 3 | Mechanical | 100 | 57 | 17 | 8 | 20
563 | 1.2.4.3.1.1.14 | Install Joinery | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 561,562 | 565 | 22 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Cleaner | 100 | 91 | 27 | 64 | 6
564 | 1.2.4.3.1.1.15 | Measure & Manufacture Stone Benchtops | 12 | 17 January 2025 8:00 AM | 1 February 2025 8:00 AM | 565SF |  | 17 January 2025 8:00 AM | 2025-02-04 08:00 | 3 | Project Manager | 100 | 59 | 16 | 15 | 52
565 | 1.2.4.3.1.1.16 | Install Stone Benchtops | 5 | 1 February 2025 8:00 AM | 6 February 2025 5:00 PM | 563 | 564SF,566 | 1 February 2025 8:00 AM | 2025-02-06 17:00 | 0 | Contract Administrator | 100 | 43 | 30 | 30 | 29
566 | 1.2.4.3.1.1.17 | Fixtures & Fittings Fit-off | 3 | 7 February 2025 8:00 AM | 10 February 2025 5:00 PM | 565 | 574 | 7 February 2025 8:00 AM | 2025-02-10 17:00 | 0 | Surveyor | 100 | 44 | 30 | 46 | 13
567 | 1.2.4.3.1.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 561 | 569 | 22 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Cleaner | 100 | 83 | 15 | 32 | 27
568 | 1.2.4.3.1.1.19 | Lighting Fit-off | 3 | 22 January 2025 8:00 AM | 24 January 2025 5:00 PM | 561 | 569 | 22 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Site Manager | 100 | 35 | 23 | 18 | 57
569 | 1.2.4.3.1.1.20 | Setting Defects | 4 | 28 January 2025 8:00 AM | 31 January 2025 5:00 PM | 567,568 | 570 | 28 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Landscaper | 100 | 90 | 31 | 80 | 7
570 | 1.2.4.3.1.1.21 | Paint Finish Coat | 4 | 1 February 2025 8:00 AM | 5 February 2025 5:00 PM | 569 | 573,571 | 1 February 2025 8:00 AM | 2025-02-05 17:00 | 0 | Development Manager | 100 | 16 | 34 | 94 | 22
571 | 1.2.4.3.1.1.22 | Carpet | 3 | 6 February 2025 8:00 AM | 8 February 2025 5:00 PM | 570 | 572 | 6 February 2025 8:00 AM | 2025-02-08 17:00 | 0 | Head Contractor | 100 | 26 | 29 | 74 | 55
572 | 1.2.4.3.1.1.23 | Final Clean & Commissioning | 4 | 10 February 2025 8:00 AM | 13 February 2025 5:00 PM | 571 |  | 10 February 2025 8:00 AM | 2025-02-13 17:00 | 0 | Cleaner | 100 | 23 | 31 | 0 | 10
573 | 1.2.4.3.1.1.24 | Defects Inspections & Rectifications | 6 | 6 February 2025 8:00 AM | 12 February 2025 5:00 PM | 570 | 574 | 6 February 2025 8:00 AM | 2025-02-13 17:00 | 1 | Carpenter | 100 | 48 | 15 | 56 | 10
574 | 1.2.4.3.1.2 | LVL 1 - FITOUT COMPLETE | 0 | 12 February 2025 5:00 PM | 12 February 2025 5:00 PM | 566,573 |  | 12 February 2025 5:00 PM | 2025-02-12 17:00 | 0 | Project Manager | 100 | 40 | 22 | 65 | 37
575 | 1.2.4.3.2 | Lvl 2 - Services & Finishes | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-11 17:00 | 5 | Window | 100 | 18 | 28 | 79 | 12
576 | 1.2.4.3.2.1 | Internal Works | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-10 17:00 | 4 | Plumber | 100 | 27 | 19 | 42 | 60
577 | 1.2.4.3.2.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 408,150 | 578FS-2d | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Fire | 100 | 67 | 20 | 94 | 20
578 | 1.2.4.3.2.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 577FS-2d | 579 | 21 October 2024 8:00 AM | 2024-11-02 17:00 | 2 | Hoarding | 100 | 31 | 14 | 67 | 34
579 | 1.2.4.3.2.1.3 | Internal Wall Framing | 8 | 1 November 2024 8:00 AM | 9 November 2024 5:00 PM | 578 | 581,580 | 1 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Carpet | 100 | 79 | 19 | 63 | 33
580 | 1.2.4.3.2.1.4 | Sheet one side of walls | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 583,582 | 11 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Contract Administrator | 100 | 91 | 30 | 89 | 25
581 | 1.2.4.3.2.1.5 | Service Rough-In | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 582 | 11 November 2024 8:00 AM | 2024-11-21 17:00 | 2 | Carpenter | 100 | 73 | 12 | 13 | 40
582 | 1.2.4.3.2.1.6 | ITP for services in the walls | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 580,581 | 583,589 | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Mechanical | 100 | 66 | 22 | 30 | 39
583 | 1.2.4.3.2.1.7 | Sheet other side of walls | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 580,582 | 584 | 22 November 2024 8:00 AM | 2024-12-03 17:00 | 3 | Contract Administrator | 100 | 66 | 34 | 18 | 45
584 | 1.2.4.3.2.1.8 | Frame & Sheet Ceilings | 8 | 2 December 2024 8:00 AM | 10 December 2024 5:00 PM | 583 | 585 | 2 December 2024 8:00 AM | 2024-12-12 17:00 | 2 | Head Contractor | 100 | 80 | 23 | 70 | 7
585 | 1.2.4.3.2.1.9 | Sheet, Set & Sand Ceilings | 8 | 11 December 2024 8:00 AM | 19 December 2024 5:00 PM | 584,411 | 586 | 11 December 2024 8:00 AM | 2024-12-21 17:00 | 2 | Line Market | 100 | 61 | 18 | 62 | 31
586 | 1.2.4.3.2.1.10 | Paint undercoat | 4 | 20 December 2024 8:00 AM | 24 December 2024 5:00 PM | 585 | 587 | 20 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Foreman | 100 | 80 | 12 | 26 | 8
587 | 1.2.4.3.2.1.11 | Floor Levelling and Floor Finish | 6 | 3 January 2025 8:00 AM | 9 January 2025 5:00 PM | 586 | 588 | 3 January 2025 8:00 AM | 2025-01-12 17:00 | 3 | Concretor | 100 | 72 | 30 | 38 | 38
588 | 1.2.4.3.2.1.12 | Timber Flooring | 6 | 10 January 2025 8:00 AM | 16 January 2025 5:00 PM | 587 | 594,595,590 | 10 January 2025 8:00 AM | 2025-01-16 17:00 | 0 | Head Contractor | 100 | 44 | 32 | 67 | 10
589 | 1.2.4.3.2.1.13 | Measure & Manufacture Joinery | 40 | 22 November 2024 8:00 AM | 16 January 2025 5:00 PM | 582 | 590 | 22 November 2024 8:00 AM | 2025-01-18 17:00 | 2 | Hoarding | 100 | 44 | 10 | 45 | 49
590 | 1.2.4.3.2.1.14 | Install Joinery | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 588,589 | 592 | 17 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Plumber | 100 | 25 | 29 | 85 | 19
591 | 1.2.4.3.2.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 January 2025 8:00 AM | 28 January 2025 8:00 AM | 592SF |  | 13 January 2025 8:00 AM | 2025-01-28 08:00 | 0 | Metal Work | 100 | 66 | 24 | 95 | 25
592 | 1.2.4.3.2.1.16 | Install Stone Benchtops | 5 | 28 January 2025 8:00 AM | 1 February 2025 5:00 PM | 590 | 591SF,593 | 28 January 2025 8:00 AM | 2025-02-01 17:00 | 0 | Concretor | 100 | 36 | 11 | 73 | 44
593 | 1.2.4.3.2.1.17 | Fixtures & Fittings Fit-off | 3 | 3 February 2025 8:00 AM | 5 February 2025 5:00 PM | 592 | 601 | 3 February 2025 8:00 AM | 2025-02-05 17:00 | 0 | Plumber | 100 | 59 | 22 | 44 | 18
594 | 1.2.4.3.2.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 17 January 2025 8:00 AM | 21 January 2025 5:00 PM | 588 | 596 | 17 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Formworker | 100 | 36 | 13 | 27 | 48
595 | 1.2.4.3.2.1.19 | Lighting Fit-off | 3 | 17 January 2025 8:00 AM | 20 January 2025 5:00 PM | 588 | 596 | 17 January 2025 8:00 AM | 2025-01-20 17:00 | 0 | Painter | 100 | 96 | 15 | 29 | 31
596 | 1.2.4.3.2.1.20 | Setting Defects | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 594,595 | 597 | 22 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Formworker | 100 | 33 | 33 | 86 | 9
597 | 1.2.4.3.2.1.21 | Paint Finish Coat | 3 | 28 January 2025 8:00 AM | 30 January 2025 5:00 PM | 596 | 600,598 | 28 January 2025 8:00 AM | 2025-01-30 17:00 | 0 | Electrician | 100 | 40 | 19 | 61 | 5
598 | 1.2.4.3.2.1.22 | Carpet | 2 | 31 January 2025 8:00 AM | 1 February 2025 5:00 PM | 597 | 599 | 31 January 2025 8:00 AM | 2025-02-01 17:00 | 0 | Post Tension | 100 | 58 | 20 | 17 | 47
599 | 1.2.4.3.2.1.23 | Final Clean & Commissioning | 4 | 3 February 2025 8:00 AM | 6 February 2025 5:00 PM | 598 |  | 3 February 2025 8:00 AM | 2025-02-06 17:00 | 0 | Waterproofer | 100 | 27 | 32 | 89 | 27
600 | 1.2.4.3.2.1.24 | Defects Inspections & Rectifications | 6 | 31 January 2025 8:00 AM | 6 February 2025 5:00 PM | 597 | 601 | 31 January 2025 8:00 AM | 2025-02-08 17:00 | 2 | Plasterboarder | 100 | 75 | 21 | 82 | 32
601 | 1.2.4.3.2.2 | LVL 2 - FITOUT COMPLETE | 0 | 6 February 2025 5:00 PM | 6 February 2025 5:00 PM | 593,600 |  | 6 February 2025 5:00 PM | 2025-02-06 17:00 | 0 | Carpenter | 100 | 92 | 34 | 14 | 53
602 | 1.2.4.3.3 | Lvl 3 - Services & Finishes | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | 25 November 2024 8:00 AM | 2025-03-21 17:00 | 4 | Scaffolder | 100 | 92 | 27 | 92 | 7
603 | 1.2.4.3.3.1 | Internal Works | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | 25 November 2024 8:00 AM | 2025-03-22 17:00 | 5 | Foreman | 100 | 24 | 27 | 76 | 22
604 | 1.2.4.3.3.1.1 | Pre-load Levels | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 174 | 605FS-2d | 25 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Carpenter | 100 | 70 | 21 | 11 | 60
605 | 1.2.4.3.3.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 25 November 2024 8:00 AM | 5 December 2024 5:00 PM | 604FS-2d | 606 | 25 November 2024 8:00 AM | 2024-12-08 17:00 | 3 | Stone Mason | 100 | 36 | 27 | 51 | 47
606 | 1.2.4.3.3.1.3 | Internal Wall Framing | 8 | 6 December 2024 8:00 AM | 14 December 2024 5:00 PM | 605 | 608,607 | 6 December 2024 8:00 AM | 2024-12-14 17:00 | 0 | Surveyor | 100 | 28 | 30 | 2 | 15
607 | 1.2.4.3.3.1.4 | Sheet one side of walls | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 610,609 | 16 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Renderer | 100 | 59 | 19 | 60 | 60
608 | 1.2.4.3.3.1.5 | Service Rough-In | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 609 | 16 December 2024 8:00 AM | 2024-12-25 17:00 | 1 | Carpet | 100 | 82 | 14 | 10 | 17
609 | 1.2.4.3.3.1.6 | ITP for services in the walls | 2 | 3 January 2025 8:00 AM | 4 January 2025 5:00 PM | 607,608 | 610,616 | 3 January 2025 8:00 AM | 2025-01-04 17:00 | 0 | Subcontractor | 100 | 85 | 15 | 41 | 46
610 | 1.2.4.3.3.1.7 | Sheet other side of walls | 8 | 6 January 2025 8:00 AM | 14 January 2025 5:00 PM | 607,609,416FS-6d | 611 | 6 January 2025 8:00 AM | 2025-01-15 17:00 | 1 | Fire | 100 | 97 | 19 | 28 | 22
611 | 1.2.4.3.3.1.8 | Frame & Sheet Ceilings | 8 | 15 January 2025 8:00 AM | 23 January 2025 5:00 PM | 610 | 612 | 15 January 2025 8:00 AM | 2025-01-24 17:00 | 1 | Reinforcement Fixer | 100 | 91 | 29 | 19 | 19
612 | 1.2.4.3.3.1.9 | Sheet, Set & Sand Ceilings | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 611,417 | 613 | 24 January 2025 8:00 AM | 2025-02-05 17:00 | 2 | Fire | 100 | 38 | 26 | 2 | 39
613 | 1.2.4.3.3.1.10 | Paint undercoat | 4 | 4 February 2025 8:00 AM | 7 February 2025 5:00 PM | 612 | 614 | 4 February 2025 8:00 AM | 2025-02-07 17:00 | 0 | Mechanical | 100 | 94 | 13 | 3 | 59
614 | 1.2.4.3.3.1.11 | Floor Levelling and Floor Finish | 7 | 8 February 2025 8:00 AM | 15 February 2025 5:00 PM | 613 | 615 | 8 February 2025 8:00 AM | 2025-02-16 17:00 | 1 | Surveyor | 100 | 80 | 34 | 75 | 48
615 | 1.2.4.3.3.1.12 | Timber Flooring | 6 | 17 February 2025 8:00 AM | 22 February 2025 5:00 PM | 614 | 621,622,617 | 17 February 2025 8:00 AM | 2025-02-22 17:00 | 0 | Plasterboarder | 100 | 63 | 24 | 42 | 51
616 | 1.2.4.3.3.1.13 | Measure & Manufacture Joinery | 40 | 6 January 2025 8:00 AM | 21 February 2025 5:00 PM | 609 | 617 | 6 January 2025 8:00 AM | 2025-02-21 17:00 | 0 | Metal Work | 100 | 91 | 11 | 40 | 36
617 | 1.2.4.3.3.1.14 | Install Joinery | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 615,616 | 619 | 24 February 2025 8:00 AM | 2025-03-04 17:00 | 0 | Renderer | 100 | 15 | 32 | 55 | 14
618 | 1.2.4.3.3.1.15 | Measure & Manufacture Stone Benchtops | 12 | 19 February 2025 8:00 AM | 5 March 2025 8:00 AM | 619SF |  | 19 February 2025 8:00 AM | 2025-03-07 08:00 | 2 | Carpet | 100 | 77 | 34 | 38 | 29
619 | 1.2.4.3.3.1.16 | Install Stone Benchtops | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 617 | 618SF,620 | 5 March 2025 8:00 AM | 2025-03-11 17:00 | 0 | Tiler | 100 | 99 | 31 | 51 | 44
620 | 1.2.4.3.3.1.17 | Fixtures & Fittings Fit-off | 3 | 12 March 2025 8:00 AM | 14 March 2025 5:00 PM | 619 | 628 | 12 March 2025 8:00 AM | 2025-03-14 17:00 | 0 | Foreman | 100 | 10 | 28 | 2 | 14
621 | 1.2.4.3.3.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 24 February 2025 8:00 AM | 27 February 2025 5:00 PM | 615 | 623 | 24 February 2025 8:00 AM | 2025-02-27 17:00 | 0 | Head Contractor | 100 | 15 | 16 | 80 | 23
622 | 1.2.4.3.3.1.19 | Lighting Fit-off | 3 | 24 February 2025 8:00 AM | 26 February 2025 5:00 PM | 615 | 623 | 24 February 2025 8:00 AM | 2025-02-26 17:00 | 0 | Formworker | 100 | 43 | 34 | 89 | 35
623 | 1.2.4.3.3.1.20 | Setting Defects | 4 | 28 February 2025 8:00 AM | 4 March 2025 5:00 PM | 621,622 | 624 | 28 February 2025 8:00 AM | 2025-03-04 17:00 | 0 | Concretor | 100 | 43 | 16 | 75 | 19
624 | 1.2.4.3.3.1.21 | Paint Finish Coat | 3 | 5 March 2025 8:00 AM | 7 March 2025 5:00 PM | 623 | 627,625 | 5 March 2025 8:00 AM | 2025-03-07 17:00 | 0 | Plasterboarder | 100 | 68 | 30 | 22 | 46
625 | 1.2.4.3.3.1.22 | Carpet | 2 | 8 March 2025 8:00 AM | 10 March 2025 5:00 PM | 624 | 626 | 8 March 2025 8:00 AM | 2025-03-10 17:00 | 0 | Plumber | 100 | 29 | 21 | 10 | 52
626 | 1.2.4.3.3.1.23 | Final Clean & Commissioning | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 625 |  | 11 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Hoarding | 100 | 50 | 11 | 93 | 48
627 | 1.2.4.3.3.1.24 | Defects Inspections & Rectifications | 8 | 8 March 2025 8:00 AM | 17 March 2025 5:00 PM | 624 | 628 | 8 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Head Contractor | 100 | 40 | 10 | 75 | 23
628 | 1.2.4.3.3.2 | LVL 3 - FITOUT COMPLETE | 0 | 17 March 2025 5:00 PM | 17 March 2025 5:00 PM | 620,627 | 753 | 17 March 2025 5:00 PM | 2025-03-17 17:00 | 0 | Project Manager | 100 | 24 | 13 | 28 | 40
629 | 1.2.4.3.4 | Lvl 4 - Services & Finishes | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | 11 December 2024 8:00 AM | 2025-04-25 17:00 | 3 | Renderer | 100 | 14 | 34 | 100 | 22
630 | 1.2.4.3.4.1 | Internal Works | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | 11 December 2024 8:00 AM | 2025-04-22 17:00 | 0 | Renderer | 100 | 82 | 18 | 41 | 26
631 | 1.2.4.3.4.1.1 | Pre-load Levels | 2 | 11 December 2024 8:00 AM | 12 December 2024 5:00 PM | 186 | 632FS-2d | 11 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Tiler | 100 | 13 | 31 | 12 | 31
632 | 1.2.4.3.4.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 11 December 2024 8:00 AM | 21 December 2024 5:00 PM | 631FS-2d | 633 | 11 December 2024 8:00 AM | 2024-12-24 17:00 | 3 | Renderer | 100 | 31 | 21 | 15 | 12
633 | 1.2.4.3.4.1.3 | Internal Wall Framing | 8 | 23 December 2024 8:00 AM | 9 January 2025 5:00 PM | 632 | 635,634 | 23 December 2024 8:00 AM | 2025-01-11 17:00 | 2 | Waterproofer | 100 | 64 | 33 | 14 | 24
634 | 1.2.4.3.4.1.4 | Sheet one side of walls | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 637,636 | 10 January 2025 8:00 AM | 2025-01-18 17:00 | 0 | Reinforcement Fixer | 100 | 98 | 18 | 56 | 44
635 | 1.2.4.3.4.1.5 | Service Rough-In | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 636 | 10 January 2025 8:00 AM | 2025-01-18 17:00 | 0 | Development Manager | 100 | 20 | 10 | 7 | 17
636 | 1.2.4.3.4.1.6 | ITP for services in the walls | 2 | 20 January 2025 8:00 AM | 21 January 2025 5:00 PM | 634,635 | 637,643 | 20 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Renderer | 100 | 23 | 28 | 56 | 25
637 | 1.2.4.3.4.1.7 | Sheet other side of walls | 8 | 10 February 2025 8:00 AM | 18 February 2025 5:00 PM | 634,636,422FS-6d | 638 | 10 February 2025 8:00 AM | 2025-02-18 17:00 | 0 | Concretor | 100 | 100 | 22 | 22 | 51
638 | 1.2.4.3.4.1.8 | Frame & Sheet Ceilings | 8 | 19 February 2025 8:00 AM | 27 February 2025 5:00 PM | 637 | 639 | 19 February 2025 8:00 AM | 2025-02-27 17:00 | 0 | Carpenter | 100 | 79 | 12 | 63 | 20
639 | 1.2.4.3.4.1.9 | Sheet, Set & Sand Ceilings | 8 | 28 February 2025 8:00 AM | 8 March 2025 5:00 PM | 638,423 | 640 | 28 February 2025 8:00 AM | 2025-03-11 17:00 | 3 | Timber Floorer | 100 | 25 | 16 | 9 | 38
640 | 1.2.4.3.4.1.10 | Paint undercoat | 4 | 10 March 2025 8:00 AM | 13 March 2025 5:00 PM | 639 | 641 | 10 March 2025 8:00 AM | 2025-03-13 17:00 | 0 | Tiler | 100 | 34 | 26 | 56 | 52
641 | 1.2.4.3.4.1.11 | Floor Levelling and Floor Finish | 6 | 14 March 2025 8:00 AM | 20 March 2025 5:00 PM | 640 | 642 | 14 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Post Tension | 100 | 70 | 28 | 21 | 49
642 | 1.2.4.3.4.1.12 | Timber Flooring | 6 | 21 March 2025 8:00 AM | 27 March 2025 5:00 PM | 641 | 648,649,644 | 21 March 2025 8:00 AM | 2025-03-27 17:00 | 0 | Electrician | 100 | 27 | 20 | 3 | 14
643 | 1.2.4.3.4.1.13 | Measure & Manufacture Joinery | 40 | 22 January 2025 8:00 AM | 10 March 2025 5:00 PM | 636 | 644 | 22 January 2025 8:00 AM | 2025-03-15 17:00 | 5 | Carpet | 100 | 26 | 30 | 28 | 29
644 | 1.2.4.3.4.1.14 | Install Joinery | 8 | 28 March 2025 8:00 AM | 5 April 2025 5:00 PM | 642,643 | 646 | 28 March 2025 8:00 AM | 2025-04-05 17:00 | 0 | Mechanical | 100 | 49 | 31 | 60 | 48
645 | 1.2.4.3.4.1.15 | Measure & Manufacture Stone Benchtops | 12 | 24 March 2025 8:00 AM | 7 April 2025 8:00 AM | 646SF |  | 24 March 2025 8:00 AM | 2025-04-10 08:00 | 3 | Development Manager | 100 | 17 | 34 | 30 | 47
646 | 1.2.4.3.4.1.16 | Install Stone Benchtops | 6 | 7 April 2025 8:00 AM | 12 April 2025 5:00 PM | 644 | 645SF,647 | 7 April 2025 8:00 AM | 2025-04-14 17:00 | 2 | Fire | 100 | 26 | 31 | 58 | 39
647 | 1.2.4.3.4.1.17 | Fixtures & Fittings Fit-off | 3 | 14 April 2025 8:00 AM | 16 April 2025 5:00 PM | 646 | 655 | 14 April 2025 8:00 AM | 2025-04-16 17:00 | 0 | Plumber | 100 | 55 | 19 | 34 | 25
648 | 1.2.4.3.4.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 28 March 2025 8:00 AM | 1 April 2025 5:00 PM | 642 | 650 | 28 March 2025 8:00 AM | 2025-04-01 17:00 | 0 | Metal Work | 100 | 59 | 17 | 67 | 54
649 | 1.2.4.3.4.1.19 | Lighting Fit-off | 3 | 28 March 2025 8:00 AM | 31 March 2025 5:00 PM | 642 | 650 | 28 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Electrician | 100 | 42 | 11 | 43 | 46
650 | 1.2.4.3.4.1.20 | Setting Defects | 4 | 2 April 2025 8:00 AM | 5 April 2025 5:00 PM | 648,649 | 651 | 2 April 2025 8:00 AM | 2025-04-05 17:00 | 0 | Plasterboarder | 100 | 19 | 28 | 75 | 54
651 | 1.2.4.3.4.1.21 | Paint Finish Coat | 3 | 7 April 2025 8:00 AM | 9 April 2025 5:00 PM | 650 | 654,652 | 7 April 2025 8:00 AM | 2025-04-09 17:00 | 0 | Subcontractor | 100 | 65 | 26 | 87 | 54
652 | 1.2.4.3.4.1.22 | Carpet | 2 | 10 April 2025 8:00 AM | 11 April 2025 5:00 PM | 651 | 653 | 10 April 2025 8:00 AM | 2025-04-11 17:00 | 0 | Cleaner | 100 | 77 | 11 | 66 | 5
653 | 1.2.4.3.4.1.23 | Final Clean & Commissioning | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 652 |  | 12 April 2025 8:00 AM | 2025-04-23 17:00 | 1 | Metal Work | 100 | 92 | 31 | 33 | 43
654 | 1.2.4.3.4.1.24 | Defects Inspections & Rectifications | 8 | 10 April 2025 8:00 AM | 22 April 2025 5:00 PM | 651 | 655 | 10 April 2025 8:00 AM | 2025-04-22 17:00 | 0 | Concretor | 100 | 68 | 19 | 96 | 23
655 | 1.2.4.3.4.2 | LVL 4 - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 647,654 | 753 | 22 April 2025 5:00 PM | 2025-04-22 17:00 | 0 | Timber Floorer | 100 | 13 | 30 | 94 | 45
656 | 1.2.4.3.5 | Lvl 5 - Services & Finishes | 100 | 12 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | 12 December 2024 8:00 AM | 2025-04-19 17:00 | 2 | Development Manager | 100 | 70 | 19 | 59 | 10
657 | 1.2.4.3.5.1 | Survey & Setout | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 289,198 | 658FS-1d | 12 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Landscaper | 100 | 95 | 16 | 42 | 25
658 | 1.2.4.3.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 657FS-1d | 660,663 | 12 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Scaffolder | 100 | 57 | 13 | 46 | 39
659 | 1.2.4.3.5.3 | External Works | 34 | 17 December 2024 8:00 AM | 4 February 2025 5:00 PM |  |  | 17 December 2024 8:00 AM | 2025-02-08 17:00 | 4 | Project Manager | 100 | 45 | 13 | 9 | 23
660 | 1.2.4.3.5.3.1 | Façade & External Walls | 18 | 17 December 2024 8:00 AM | 15 January 2025 5:00 PM | 658 | 661 | 17 December 2024 8:00 AM | 2025-01-16 17:00 | 1 | Electrician | 100 | 89 | 18 | 89 | 35
661 | 1.2.4.3.5.3.2 | Windows Install | 16 | 16 January 2025 8:00 AM | 4 February 2025 5:00 PM | 660 | 669FS-6d | 16 January 2025 8:00 AM | 2025-02-07 17:00 | 3 | Surveyor | 100 | 91 | 24 | 92 | 50
662 | 1.2.4.3.5.4 | Internal Works | 91 | 23 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-04-18 17:00 | 1 | Painter | 100 | 10 | 26 | 28 | 39
663 | 1.2.4.3.5.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 658,426 | 664FS-2d | 23 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Project Manager | 100 | 25 | 25 | 33 | 17
664 | 1.2.4.3.5.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 663FS-2d | 665 | 23 December 2024 8:00 AM | 2025-01-14 17:00 | 3 | Joiner | 100 | 95 | 23 | 52 | 17
665 | 1.2.4.3.5.4.3 | Internal Wall Framing | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 664 | 667,666 | 13 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Mechanical | 100 | 25 | 17 | 54 | 3
666 | 1.2.4.3.5.4.4 | Sheet one side of walls | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 669,668 | 22 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Window | 100 | 48 | 33 | 18 | 58
667 | 1.2.4.3.5.4.5 | Service Rough-In | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 668 | 22 January 2025 8:00 AM | 2025-02-03 17:00 | 3 | Landscaper | 100 | 26 | 20 | 86 | 54
668 | 1.2.4.3.5.4.6 | ITP for services in the walls | 2 | 1 February 2025 8:00 AM | 3 February 2025 5:00 PM | 666,667 | 669,675 | 1 February 2025 8:00 AM | 2025-02-03 17:00 | 0 | Cleaner | 100 | 32 | 24 | 85 | 55
669 | 1.2.4.3.5.4.7 | Sheet other side of walls | 8 | 4 February 2025 8:00 AM | 12 February 2025 5:00 PM | 661FS-6d,666,668,428FS-6d | 670 | 4 February 2025 8:00 AM | 2025-02-12 17:00 | 0 | Stone Mason | 100 | 98 | 28 | 22 | 31
670 | 1.2.4.3.5.4.8 | Frame & Sheet Ceilings | 8 | 13 February 2025 8:00 AM | 21 February 2025 5:00 PM | 669 | 671 | 13 February 2025 8:00 AM | 2025-02-23 17:00 | 2 | Hoarding | 100 | 72 | 33 | 21 | 18
671 | 1.2.4.3.5.4.9 | Sheet, Set & Sand Ceilings | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 670,429 | 672 | 22 February 2025 8:00 AM | 2025-03-03 17:00 | 0 | Waterproofer | 100 | 94 | 28 | 34 | 18
672 | 1.2.4.3.5.4.10 | Paint undercoat | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 671 | 673 | 4 March 2025 8:00 AM | 2025-03-07 17:00 | 0 | Renderer | 100 | 56 | 12 | 56 | 51
673 | 1.2.4.3.5.4.11 | Floor Levelling and Floor Finish | 6 | 8 March 2025 8:00 AM | 14 March 2025 5:00 PM | 672 | 674 | 8 March 2025 8:00 AM | 2025-03-17 17:00 | 3 | Excavation | 100 | 36 | 22 | 100 | 60
674 | 1.2.4.3.5.4.12 | Timber Flooring | 6 | 15 March 2025 8:00 AM | 21 March 2025 5:00 PM | 673 | 680,681,676 | 15 March 2025 8:00 AM | 2025-03-21 17:00 | 0 | Plumber | 100 | 72 | 35 | 60 | 40
675 | 1.2.4.3.5.4.13 | Measure & Manufacture Joinery | 40 | 4 February 2025 8:00 AM | 21 March 2025 5:00 PM | 668 | 676 | 4 February 2025 8:00 AM | 2025-03-24 17:00 | 3 | Window | 100 | 27 | 15 | 20 | 5
676 | 1.2.4.3.5.4.14 | Install Joinery | 8 | 22 March 2025 8:00 AM | 31 March 2025 5:00 PM | 674,675 | 678 | 22 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Site Manager | 100 | 93 | 10 | 6 | 26
677 | 1.2.4.3.5.4.15 | Measure & Manufacture Stone Benchtops | 15 | 14 March 2025 8:00 AM | 1 April 2025 8:00 AM | 678SF | 687 | 14 March 2025 8:00 AM | 2025-04-06 08:00 | 5 | Foreman | 100 | 22 | 28 | 88 | 43
678 | 1.2.4.3.5.4.16 | Install Stone Benchtops | 6 | 1 April 2025 8:00 AM | 7 April 2025 5:00 PM | 676 | 677SF,679 | 1 April 2025 8:00 AM | 2025-04-08 17:00 | 1 | Scaffolder | 100 | 77 | 11 | 97 | 41
679 | 1.2.4.3.5.4.17 | Fixtures & Fittings Fit-off | 8 | 8 April 2025 8:00 AM | 16 April 2025 5:00 PM | 678 | 687 | 8 April 2025 8:00 AM | 2025-04-16 17:00 | 0 | Head Contractor | 100 | 20 | 32 | 99 | 3
680 | 1.2.4.3.5.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 674 | 682 | 22 March 2025 8:00 AM | 2025-03-26 17:00 | 0 | Waterproofer | 100 | 93 | 21 | 9 | 37
681 | 1.2.4.3.5.4.19 | Lighting Fit-off | 3 | 22 March 2025 8:00 AM | 25 March 2025 5:00 PM | 674 | 682 | 22 March 2025 8:00 AM | 2025-03-25 17:00 | 0 | Contract Administrator | 100 | 26 | 19 | 42 | 28
682 | 1.2.4.3.5.4.20 | Setting Defects | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 680,681 | 683 | 27 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Tiler | 100 | 60 | 32 | 59 | 17
683 | 1.2.4.3.5.4.21 | Paint Finish Coat | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 682 | 686,684 | 1 April 2025 8:00 AM | 2025-04-03 17:00 | 0 | Painter | 100 | 58 | 24 | 14 | 36
684 | 1.2.4.3.5.4.22 | Carpet | 2 | 4 April 2025 8:00 AM | 5 April 2025 5:00 PM | 683 | 685 | 4 April 2025 8:00 AM | 2025-04-05 17:00 | 0 | Head Contractor | 100 | 51 | 13 | 28 | 38
685 | 1.2.4.3.5.4.23 | Final Clean & Commissioning | 10 | 7 April 2025 8:00 AM | 17 April 2025 5:00 PM | 684 | 687 | 7 April 2025 8:00 AM | 2025-04-20 17:00 | 3 | Plasterboarder | 100 | 76 | 32 | 42 | 13
686 | 1.2.4.3.5.4.24 | Defects Inspections & Rectifications | 8 | 4 April 2025 8:00 AM | 12 April 2025 5:00 PM | 683 | 687 | 4 April 2025 8:00 AM | 2025-04-15 17:00 | 3 | Waterproofer | 100 | 12 | 34 | 47 | 13
687 | 1.2.4.3.5.5 | LVL 5 - FITOUT COMPLETE | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 679,686,685,677 |  | 17 April 2025 5:00 PM | 2025-04-17 17:00 | 0 | Site Manager | 100 | 58 | 34 | 96 | 20
688 | 1.2.4.3.6 | Lvl 6 - Services & Finishes | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-04-18 17:00 | 3 | Head Contractor | 100 | 75 | 26 | 38 | 12
689 | 1.2.4.3.6.1 | Internal Works | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-04-17 17:00 | 2 | Excavation | 100 | 50 | 11 | 43 | 24
690 | 1.2.4.3.6.1.1 | Pre-load Levels | 2 | 18 December 2024 8:00 AM | 19 December 2024 5:00 PM | 432,210 | 691FS-2d | 18 December 2024 8:00 AM | 2024-12-19 17:00 | 0 | Project Manager | 100 | 11 | 11 | 31 | 44
691 | 1.2.4.3.6.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 18 December 2024 8:00 AM | 7 January 2025 5:00 PM | 690FS-2d | 692 | 18 December 2024 8:00 AM | 2025-01-07 17:00 | 0 | Carpet | 100 | 59 | 20 | 63 | 37
692 | 1.2.4.3.6.1.3 | Internal Wall Framing | 8 | 8 January 2025 8:00 AM | 16 January 2025 5:00 PM | 691 | 694,693 | 8 January 2025 8:00 AM | 2025-01-16 17:00 | 0 | Plumber | 100 | 67 | 29 | 3 | 59
693 | 1.2.4.3.6.1.4 | Sheet one side of walls | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 696,695 | 17 January 2025 8:00 AM | 2025-01-29 17:00 | 2 | Subcontractor | 100 | 17 | 16 | 36 | 24
694 | 1.2.4.3.6.1.5 | Service Rough-In | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 695 | 17 January 2025 8:00 AM | 2025-01-30 17:00 | 3 | Waterproofer | 100 | 56 | 33 | 28 | 49
695 | 1.2.4.3.6.1.6 | ITP for services in the walls | 2 | 28 January 2025 8:00 AM | 29 January 2025 5:00 PM | 693,694 | 696,702 | 28 January 2025 8:00 AM | 2025-01-29 17:00 | 0 | Foreman | 100 | 82 | 22 | 59 | 46
696 | 1.2.4.3.6.1.7 | Sheet other side of walls | 8 | 30 January 2025 8:00 AM | 7 February 2025 5:00 PM | 693,695,434FS-6d | 697 | 30 January 2025 8:00 AM | 2025-02-07 17:00 | 0 | Subcontractor | 100 | 39 | 13 | 97 | 6
697 | 1.2.4.3.6.1.8 | Frame & Sheet Ceilings | 8 | 8 February 2025 8:00 AM | 17 February 2025 5:00 PM | 696 | 698 | 8 February 2025 8:00 AM | 2025-02-20 17:00 | 3 | Scaffolder | 100 | 33 | 20 | 78 | 15
698 | 1.2.4.3.6.1.9 | Sheet, Set & Sand Ceilings | 8 | 18 February 2025 8:00 AM | 26 February 2025 5:00 PM | 697,435 | 699 | 18 February 2025 8:00 AM | 2025-02-27 17:00 | 1 | Stone Mason | 100 | 59 | 16 | 74 | 48
699 | 1.2.4.3.6.1.10 | Paint undercoat | 4 | 27 February 2025 8:00 AM | 3 March 2025 5:00 PM | 698 | 700 | 27 February 2025 8:00 AM | 2025-03-03 17:00 | 0 | Floor Sealer | 100 | 86 | 17 | 47 | 59
700 | 1.2.4.3.6.1.11 | Floor Levelling and Floor Finish | 6 | 4 March 2025 8:00 AM | 10 March 2025 5:00 PM | 699 | 701 | 4 March 2025 8:00 AM | 2025-03-12 17:00 | 2 | Renderer | 100 | 86 | 20 | 62 | 39
701 | 1.2.4.3.6.1.12 | Timber Flooring | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 700 | 707,708,703 | 11 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Carpet | 100 | 18 | 30 | 38 | 34
702 | 1.2.4.3.6.1.13 | Measure & Manufacture Joinery | 40 | 30 January 2025 8:00 AM | 17 March 2025 5:00 PM | 695 | 703 | 30 January 2025 8:00 AM | 2025-03-21 17:00 | 4 | Project Manager | 100 | 17 | 30 | 51 | 11
703 | 1.2.4.3.6.1.14 | Install Joinery | 8 | 18 March 2025 8:00 AM | 26 March 2025 5:00 PM | 701,702 | 705 | 18 March 2025 8:00 AM | 2025-03-28 17:00 | 2 | Metal Work | 100 | 22 | 25 | 29 | 58
704 | 1.2.4.3.6.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 March 2025 8:00 AM | 27 March 2025 8:00 AM | 705SF |  | 13 March 2025 8:00 AM | 2025-03-28 08:00 | 1 | Reinforcement Fixer | 100 | 49 | 18 | 92 | 14
705 | 1.2.4.3.6.1.16 | Install Stone Benchtops | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 703 | 704SF,706 | 27 March 2025 8:00 AM | 2025-04-02 17:00 | 0 | Metal Work | 100 | 35 | 13 | 97 | 55
706 | 1.2.4.3.6.1.17 | Fixtures & Fittings Fit-off | 7 | 3 April 2025 8:00 AM | 10 April 2025 5:00 PM | 705 | 714 | 3 April 2025 8:00 AM | 2025-04-12 17:00 | 2 | Formworker | 100 | 18 | 26 | 72 | 56
707 | 1.2.4.3.6.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 18 March 2025 8:00 AM | 21 March 2025 5:00 PM | 701 | 709 | 18 March 2025 8:00 AM | 2025-03-21 17:00 | 0 | Post Tension | 100 | 49 | 24 | 9 | 8
708 | 1.2.4.3.6.1.19 | Lighting Fit-off | 3 | 18 March 2025 8:00 AM | 20 March 2025 5:00 PM | 701 | 709 | 18 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Development Manager | 100 | 63 | 24 | 48 | 24
709 | 1.2.4.3.6.1.20 | Setting Defects | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 707,708 | 710 | 22 March 2025 8:00 AM | 2025-03-26 17:00 | 0 | Waterproofer | 100 | 42 | 10 | 85 | 34
710 | 1.2.4.3.6.1.21 | Paint Finish Coat | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 709 | 713,711 | 27 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Subcontractor | 100 | 50 | 14 | 7 | 10
711 | 1.2.4.3.6.1.22 | Carpet | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 710 | 712 | 1 April 2025 8:00 AM | 2025-04-03 17:00 | 0 | Admin | 100 | 30 | 13 | 22 | 28
712 | 1.2.4.3.6.1.23 | Final Clean & Commissioning | 10 | 4 April 2025 8:00 AM | 15 April 2025 5:00 PM | 711 |  | 4 April 2025 8:00 AM | 2025-04-15 17:00 | 0 | Development Manager | 100 | 94 | 12 | 39 | 9
713 | 1.2.4.3.6.1.24 | Defects Inspections & Rectifications | 8 | 1 April 2025 8:00 AM | 9 April 2025 5:00 PM | 710 | 714 | 1 April 2025 8:00 AM | 2025-04-10 17:00 | 1 | Waterproofer | 100 | 76 | 24 | 75 | 35
714 | 1.2.4.3.6.2 | LVL 6 - FITOUT COMPLETE | 0 | 10 April 2025 5:00 PM | 10 April 2025 5:00 PM | 706,713 | 5 | 10 April 2025 5:00 PM | 2025-04-10 17:00 | 0 | Surveyor | 100 | 95 | 34 | 44 | 9
715 | 1.2.4.3.7 | Lvl 7 - Services & Finishes | 105 | 18 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | - | 0 | Development Manager | 50 | 69 | 33 | 76 | 3
716 | 1.2.4.3.7.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 301,223 | 717FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Window | 100 | 34 | 23 | 7 | 12
717 | 1.2.4.3.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 716FS-1d | 719,722 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Plumber | 100 | 48 | 26 | 48 | 29
718 | 1.2.4.3.7.3 | External Works | 34 | 23 December 2024 8:00 AM | 10 February 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-02-11 17:00 | 1 | Site Manager | 100 | 96 | 31 | 23 | 51
719 | 1.2.4.3.7.3.1 | Façade & External Walls | 18 | 23 December 2024 8:00 AM | 21 January 2025 5:00 PM | 717 | 720 | 23 December 2024 8:00 AM | 2025-01-22 17:00 | 1 | Metal Work | 100 | 96 | 27 | 72 | 51
720 | 1.2.4.3.7.3.2 | Windows Install | 16 | 22 January 2025 8:00 AM | 10 February 2025 5:00 PM | 719 | 728FS-6d | 22 January 2025 8:00 AM | 2025-02-15 17:00 | 5 | Window | 100 | 70 | 30 | 88 | 53
721 | 1.2.4.3.7.4 | Internal Works | 101 | 23 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | - | 0 | Hoarding | 50 | 32 | 14 | 26 | 58
722 | 1.2.4.3.7.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 717,438 | 723FS-2d | 23 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Reinforcement Fixer | 100 | 77 | 20 | 86 | 58
723 | 1.2.4.3.7.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 722FS-2d | 724 | 23 December 2024 8:00 AM | 2025-01-13 17:00 | 2 | Carpet | 100 | 81 | 18 | 41 | 60
724 | 1.2.4.3.7.4.3 | Internal Wall Framing | 10 | 13 January 2025 8:00 AM | 23 January 2025 5:00 PM | 723 | 726,725 | 13 January 2025 8:00 AM | 2025-01-28 17:00 | 5 | Foreman | 100 | 30 | 12 | 89 | 43
725 | 1.2.4.3.7.4.4 | Sheet one side of walls | 9 | 24 January 2025 8:00 AM | 4 February 2025 5:00 PM | 724 | 728,727 | 24 January 2025 8:00 AM | 2025-02-05 17:00 | 1 | Head Contractor | 100 | 37 | 18 | 82 | 13
726 | 1.2.4.3.7.4.5 | Service Rough-In | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 724 | 727 | 24 January 2025 8:00 AM | 2025-02-03 17:00 | 0 | Stone Mason | 100 | 50 | 24 | 18 | 56
727 | 1.2.4.3.7.4.6 | ITP for services in the walls | 2 | 5 February 2025 8:00 AM | 6 February 2025 5:00 PM | 725,726 | 728,734 | 5 February 2025 8:00 AM | 2025-02-06 17:00 | 0 | Painter | 100 | 77 | 17 | 86 | 47
728 | 1.2.4.3.7.4.7 | Sheet other side of walls | 8 | 15 February 2025 8:00 AM | 24 February 2025 5:00 PM | 720FS-6d,725,727,440FS-6d | 729 | 15 February 2025 8:00 AM | 2025-02-24 17:00 | 0 | Metal Work | 100 | 57 | 17 | 25 | 58
729 | 1.2.4.3.7.4.8 | Frame & Sheet Ceilings | 8 | 25 February 2025 8:00 AM | 5 March 2025 5:00 PM | 728 | 730 | 25 February 2025 8:00 AM | 2025-03-06 17:00 | 1 | Tiler | 100 | 50 | 19 | 25 | 51
730 | 1.2.4.3.7.4.9 | Sheet, Set & Sand Ceilings | 8 | 6 March 2025 8:00 AM | 14 March 2025 5:00 PM | 729,441 | 731 | 6 March 2025 8:00 AM | 2025-03-15 17:00 | 1 | Concretor | 100 | 91 | 33 | 1 | 57
731 | 1.2.4.3.7.4.10 | Paint undercoat | 4 | 15 March 2025 8:00 AM | 19 March 2025 5:00 PM | 730 | 732 | 15 March 2025 8:00 AM | 2025-03-19 17:00 | 0 | Tiler | 100 | 31 | 27 | 87 | 30
732 | 1.2.4.3.7.4.11 | Floor Levelling and Floor Finish | 6 | 20 March 2025 8:00 AM | 26 March 2025 5:00 PM | 731 | 733 | 20 March 2025 8:00 AM | 2025-03-28 17:00 | 2 | Stone Mason | 100 | 11 | 17 | 42 | 35
733 | 1.2.4.3.7.4.12 | Timber Flooring | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 732 | 739,740,735 | 27 March 2025 8:00 AM | 2025-04-05 17:00 | 3 | Subcontractor | 100 | 38 | 17 | 63 | 56
734 | 1.2.4.3.7.4.13 | Measure & Manufacture Joinery | 40 | 7 February 2025 8:00 AM | 25 March 2025 5:00 PM | 727 | 735 | 7 February 2025 8:00 AM | 2025-03-27 17:00 | 2 | Surveyor | 100 | 47 | 18 | 68 | 3
735 | 1.2.4.3.7.4.14 | Install Joinery | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733,734 | 737 | 3 April 2025 8:00 AM | 2025-04-13 17:00 | 2 | Metal Work | 100 | 64 | 34 | 18 | 26
736 | 1.2.4.3.7.4.15 | Measure & Manufacture Stone Benchtops | 12 | 29 March 2025 8:00 AM | 12 April 2025 8:00 AM | 737SF | 746 | 29 March 2025 8:00 AM | 2025-04-17 08:00 | 5 | Contract Administrator | 100 | 29 | 17 | 24 | 36
737 | 1.2.4.3.7.4.16 | Install Stone Benchtops | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 735 | 736SF,738 | 12 April 2025 8:00 AM | 2025-04-22 17:00 | 0 | Renderer | 100 | 98 | 34 | 94 | 13
738 | 1.2.4.3.7.4.17 | Fixtures & Fittings Fit-off | 7 | 23 April 2025 8:00 AM | 2 May 2025 5:00 PM | 737 | 746 | 23 April 2025 8:00 AM | 2025-05-05 17:00 | 3 | Foreman | 100 | 18 | 26 | 40 | 24
739 | 1.2.4.3.7.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733 | 741 | 3 April 2025 8:00 AM | 2025-04-13 17:00 | 2 | Mechanical | 100 | 32 | 34 | 96 | 55
740 | 1.2.4.3.7.4.19 | Lighting Fit-off | 5 | 3 April 2025 8:00 AM | 8 April 2025 5:00 PM | 733 | 741 | 3 April 2025 8:00 AM | 2025-04-08 17:00 | 0 | Hoarding | 100 | 41 | 27 | 65 | 20
741 | 1.2.4.3.7.4.20 | Setting Defects | 4 | 12 April 2025 8:00 AM | 16 April 2025 5:00 PM | 739,740 | 742 | 12 April 2025 8:00 AM | 2025-04-16 17:00 | 0 | Cleaner | 100 | 46 | 27 | 81 | 59
742 | 1.2.4.3.7.4.21 | Paint Finish Coat | 4 | 17 April 2025 8:00 AM | 24 April 2025 5:00 PM | 741 | 745,743 | 17 April 2025 8:00 AM | 2025-04-24 17:00 | 0 | Cleaner | 100 | 40 | 31 | 56 | 23
743 | 1.2.4.3.7.4.22 | Carpet | 3 | 28 April 2025 8:00 AM | 30 April 2025 5:00 PM | 742 | 744 | 28 April 2025 8:00 AM | - | 0 | Contract Administrator | 95 | 60 | 24 | 92 | 22
744 | 1.2.4.3.7.4.23 | Final Clean & Commissioning | 4 | 1 May 2025 8:00 AM | 5 May 2025 5:00 PM | 743 | 746 | - | - | 0 | Painter | 0 | 21 | 14 | 10 | 5
745 | 1.2.4.3.7.4.24 | Defects Inspections & Rectifications | 6 | 28 April 2025 8:00 AM | 3 May 2025 5:00 PM | 742 | 746 | 28 April 2025 8:00 AM | - | 0 | Window | 50 | 75 | 11 | 92 | 36
746 | 1.2.4.3.7.5 | LVL 7 - FITOUT COMPLETE | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 738,745,744,736 | 5,754 | - | - | 0 | Tiler | 0 | 91 | 16 | 37 | 46
747 | 1.2.4.3.8 | Lvl 8 (Roof) - Services | 96 | 7 January 2025 8:00 AM | 5 May 2025 5:00 PM |  |  | 7 January 2025 8:00 AM | - | 0 | Concretor | 95 | 62 | 35 | 34 | 55
748 | 1.2.4.3.8.1 | Survey & Setout | 1 | 7 January 2025 8:00 AM | 7 January 2025 5:00 PM | 301FS+24d | 749FS-1d | 7 January 2025 8:00 AM | 2025-01-07 17:00 | 0 | Tiler | 100 | 41 | 11 | 98 | 58
749 | 1.2.4.3.8.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 7 January 2025 8:00 AM | 10 January 2025 5:00 PM | 748FS-1d | 751 | 7 January 2025 8:00 AM | 2025-01-10 17:00 | 0 | Plasterboarder | 100 | 65 | 17 | 27 | 3
750 | 1.2.4.3.8.3 | External Services (Plant) | 56 | 11 January 2025 8:00 AM | 18 March 2025 5:00 PM |  |  | 11 January 2025 8:00 AM | 2025-03-25 17:00 | 7 | Excavation | 100 | 60 | 26 | 27 | 19
751 | 1.2.4.3.8.3.1 | Heat Pumps & Associated Services | 32 | 11 January 2025 8:00 AM | 18 February 2025 5:00 PM | 749 | 752 | 11 January 2025 8:00 AM | 2025-02-23 17:00 | 5 | Reinforcement Fixer | 100 | 95 | 29 | 53 | 54
752 | 1.2.4.3.8.3.2 | Louvres, Balustrades & Roof Safety System | 24 | 19 February 2025 8:00 AM | 18 March 2025 5:00 PM | 751 | 753 | 19 February 2025 8:00 AM | 2025-03-19 17:00 | 1 | Subcontractor | 100 | 31 | 25 | 38 | 47
753 | 1.2.4.3.8.4 | LVL 8 (ROOF) - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 752,655,628 | 5,754 | 22 April 2025 5:00 PM | 2025-04-22 17:00 | 0 | Fire | 100 | 33 | 19 | 1 | 35
754 | 1.2.4.3.8.5 | Building A Fitout Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 753,746 |  | - | - | 0 | Head Contractor | 0 | 97 | 13 | 52 | 6
755 | 1.2.4.4 | Building B | 135 | 14 October 2024 8:00 AM | 29 March 2025 5:00 PM |  | 3440 | - | - | 0 | Stone Mason | 0 | 13 | 24 | 92 | 10
756 | 1.2.4.4.1 | Level 1 | 52 | 14 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 66 | 33 | 49 | 52
757 | 1.2.4.4.1.1 | Apartment B010 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 32 | 12 | 22 | 36
758 | 1.2.4.4.1.1.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 759,762,763,830 | - | - | 0 | Electrician | 0 | 85 | 16 | 54 | 39
759 | 1.2.4.4.1.1.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 758 | 761,760 | - | - | 0 | Painter | 0 | 87 | 11 | 1 | 41
760 | 1.2.4.4.1.1.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 759 |  | - | - | 0 | Metal Work | 0 | 92 | 18 | 75 | 46
761 | 1.2.4.4.1.1.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 759 | 764 | - | - | 0 | Project Manager | 0 | 99 | 19 | 12 | 8
762 | 1.2.4.4.1.1.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 771 | - | - | 0 | Carpenter | 0 | 22 | 27 | 2 | 16
763 | 1.2.4.4.1.1.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 834 | - | - | 0 | Development Manager | 0 | 30 | 21 | 82 | 25
764 | 1.2.4.4.1.1.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 761 | 765,766,767,768,769 | - | - | 0 | Contract Administrator | 0 | 38 | 31 | 91 | 7
765 | 1.2.4.4.1.1.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769 | - | - | 0 | Development Manager | 0 | 68 | 30 | 71 | 34
766 | 1.2.4.4.1.1.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769,833 | - | - | 0 | Timber Floorer | 0 | 18 | 29 | 92 | 18
767 | 1.2.4.4.1.1.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 832 | - | - | 0 | Foreman | 0 | 14 | 23 | 47 | 25
768 | 1.2.4.4.1.1.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 |  | - | - | 0 | Waterproofer | 0 | 27 | 21 | 49 | 51
769 | 1.2.4.4.1.1.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 764,765,766 | 770 | - | - | 0 | Timber Floorer | 0 | 78 | 23 | 87 | 16
770 | 1.2.4.4.1.1.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 769 | 771 | - | - | 0 | Tiler | 0 | 44 | 10 | 63 | 44
771 | 1.2.4.4.1.1.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 762,770 | 772,773,774,775,777,779 | - | - | 0 | Contract Administrator | 0 | 29 | 13 | 81 | 33
772 | 1.2.4.4.1.1.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 776,779 | - | - | 0 | Stone Mason | 0 | 92 | 20 | 44 | 19
773 | 1.2.4.4.1.1.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 779 | - | - | 0 | Scaffolder | 0 | 99 | 32 | 73 | 32
774 | 1.2.4.4.1.1.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 778,779 | - | - | 0 | Foreman | 0 | 65 | 11 | 81 | 18
775 | 1.2.4.4.1.1.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | - | - | 0 | Surveyor | 0 | 21 | 26 | 49 | 39
776 | 1.2.4.4.1.1.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 772 | 779 | - | - | 0 | Cleaner | 0 | 14 | 29 | 62 | 24
777 | 1.2.4.4.1.1.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | - | - | 0 | Fire | 0 | 31 | 28 | 89 | 18
778 | 1.2.4.4.1.1.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 774 | 779 | - | - | 0 | Foreman | 0 | 81 | 12 | 96 | 15
779 | 1.2.4.4.1.1.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 771,772,773,774,775,776,777,778 | 780 | - | - | 0 | Post Tension | 0 | 90 | 14 | 88 | 32
780 | 1.2.4.4.1.1.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 779 | 781 | - | - | 0 | Joiner | 0 | 38 | 24 | 55 | 48
781 | 1.2.4.4.1.1.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 780 | 782,799,816 | - | - | 0 | Floor Sealer | 0 | 22 | 30 | 15 | 33
782 | 1.2.4.4.1.1.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 783 | - | - | 0 | Waterproofer | 0 | 77 | 25 | 2 | 58
783 | 1.2.4.4.1.1.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 782 | 784 | - | - | 0 | Head Contractor | 0 | 62 | 35 | 25 | 13
784 | 1.2.4.4.1.1.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 783 | 785 | - | - | 0 | Carpet | 0 | 68 | 22 | 63 | 56
785 | 1.2.4.4.1.1.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 784 | 786 | - | - | 0 | Hoarding | 0 | 23 | 11 | 97 | 19
786 | 1.2.4.4.1.1.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 785 | 787,788 | - | - | 0 | Landscaper | 0 | 54 | 31 | 76 | 3
787 | 1.2.4.4.1.1.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 786 | 791 | - | - | 0 | Window | 0 | 81 | 20 | 66 | 18
788 | 1.2.4.4.1.1.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 786 | 789 | - | - | 0 | Metal Work | 0 | 41 | 24 | 2 | 57
789 | 1.2.4.4.1.1.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 788 | 790 | - | - | 0 | Painter | 0 | 10 | 26 | 55 | 60
790 | 1.2.4.4.1.1.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 789 |  | - | - | 0 | Development Manager | 0 | 92 | 26 | 36 | 21
791 | 1.2.4.4.1.1.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 787 | 792,793,794,795,796 | - | - | 0 | Site Manager | 0 | 46 | 15 | 77 | 46
792 | 1.2.4.4.1.1.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 791 |  | - | - | 0 | Renderer | 0 | 93 | 30 | 80 | 45
793 | 1.2.4.4.1.1.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Plumber | 0 | 71 | 24 | 58 | 5
794 | 1.2.4.4.1.1.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Floor Sealer | 0 | 100 | 23 | 41 | 4
795 | 1.2.4.4.1.1.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Waterproofer | 0 | 80 | 13 | 16 | 58
796 | 1.2.4.4.1.1.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | - | - | 0 | Stone Mason | 0 | 36 | 14 | 99 | 23
797 | 1.2.4.4.1.1.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 847 | - | - | 0 | Electrician | 0 | 25 | 35 | 34 | 36
798 | 1.2.4.4.1.1.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Hoarding | 0 | 90 | 28 | 90 | 32
799 | 1.2.4.4.1.1.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 800 | - | - | 0 | Window | 0 | 97 | 27 | 14 | 10
800 | 1.2.4.4.1.1.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 799 | 801 | - | - | 0 | Concretor | 0 | 15 | 24 | 52 | 9
801 | 1.2.4.4.1.1.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 800 | 802 | - | - | 0 | Mechanical | 0 | 67 | 19 | 84 | 29
802 | 1.2.4.4.1.1.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 801 | 803 | - | - | 0 | Scaffolder | 0 | 13 | 27 | 48 | 47
803 | 1.2.4.4.1.1.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 802 | 804 | - | - | 0 | Excavation | 0 | 10 | 19 | 19 | 26
804 | 1.2.4.4.1.1.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 803 | 805 | - | - | 0 | Plumber | 0 | 26 | 15 | 76 | 17
805 | 1.2.4.4.1.1.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 804 | 806 | - | - | 0 | Waterproofer | 0 | 58 | 24 | 36 | 46
806 | 1.2.4.4.1.1.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 805 | 807 | - | - | 0 | Window | 0 | 35 | 20 | 92 | 7
807 | 1.2.4.4.1.1.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 806 | 808 | - | - | 0 | Tiler | 0 | 70 | 19 | 69 | 51
808 | 1.2.4.4.1.1.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 807 | 809 | - | - | 0 | Timber Floorer | 0 | 72 | 30 | 56 | 15
809 | 1.2.4.4.1.1.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 808 | 810 | - | - | 0 | Project Manager | 0 | 50 | 27 | 44 | 11
810 | 1.2.4.4.1.1.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 809 | 814,811,812,813 | - | - | 0 | Landscaper | 0 | 83 | 22 | 90 | 7
811 | 1.2.4.4.1.1.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | - | - | 0 | Plumber | 0 | 97 | 29 | 7 | 5
812 | 1.2.4.4.1.1.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | - | - | 0 | Admin | 0 | 72 | 29 | 94 | 42
813 | 1.2.4.4.1.1.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | - | - | 0 | Excavation | 0 | 40 | 15 | 83 | 22
814 | 1.2.4.4.1.1.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 810,811,812,813 |  | - | - | 0 | Hoarding | 0 | 12 | 14 | 17 | 51
815 | 1.2.4.4.1.1.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 13 | 25 | 64 | 40
816 | 1.2.4.4.1.1.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 817 | - | - | 0 | Hoarding | 0 | 31 | 19 | 79 | 54
817 | 1.2.4.4.1.1.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 816 | 818 | - | - | 0 | Development Manager | 0 | 15 | 25 | 4 | 49
818 | 1.2.4.4.1.1.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 817 | 819 | - | - | 0 | Waterproofer | 0 | 64 | 34 | 24 | 34
819 | 1.2.4.4.1.1.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 818 | 820 | - | - | 0 | Reinforcement Fixer | 0 | 55 | 22 | 68 | 14
820 | 1.2.4.4.1.1.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 819 | 821 | - | - | 0 | Window | 0 | 84 | 18 | 61 | 58
821 | 1.2.4.4.1.1.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 820 | 822 | - | - | 0 | Site Manager | 0 | 16 | 25 | 74 | 46
822 | 1.2.4.4.1.1.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 821 | 823 | - | - | 0 | Floor Sealer | 0 | 18 | 26 | 65 | 32
823 | 1.2.4.4.1.1.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 822 | 824,825,826,827 | - | - | 0 | Mechanical | 0 | 56 | 22 | 1 | 25
824 | 1.2.4.4.1.1.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Tiler | 0 | 43 | 24 | 42 | 50
825 | 1.2.4.4.1.1.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Concretor | 0 | 100 | 10 | 96 | 49
826 | 1.2.4.4.1.1.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Head Contractor | 0 | 54 | 34 | 25 | 17
827 | 1.2.4.4.1.1.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | - | - | 0 | Carpenter | 0 | 92 | 27 | 75 | 43
828 | 1.2.4.4.1.1.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 824,825,826,827 |  | - | - | 0 | Cleaner | 0 | 70 | 14 | 96 | 27
829 | 1.2.4.4.1.1.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 59 | 11 | 42 | 28
830 | 1.2.4.4.1.1.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 758 | 831 | - | - | 0 | Contract Administrator | 0 | 41 | 27 | 76 | 31
831 | 1.2.4.4.1.1.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 830 |  | - | - | 0 | Site Manager | 0 | 78 | 29 | 100 | 6
832 | 1.2.4.4.1.1.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 767 | 835 | - | - | 0 | Stone Mason | 0 | 12 | 24 | 2 | 60
833 | 1.2.4.4.1.1.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 766 | 835 | - | - | 0 | Contract Administrator | 0 | 21 | 28 | 24 | 57
834 | 1.2.4.4.1.1.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 763 | 835 | - | - | 0 | Renderer | 0 | 83 | 35 | 56 | 23
835 | 1.2.4.4.1.1.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 832,833,834 | 836 | - | - | 0 | Fire | 0 | 82 | 18 | 43 | 25
836 | 1.2.4.4.1.1.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 835 | 837 | - | - | 0 | Admin | 0 | 84 | 14 | 34 | 28
837 | 1.2.4.4.1.1.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 836 | 838 | - | - | 0 | Line Market | 0 | 84 | 23 | 79 | 51
838 | 1.2.4.4.1.1.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 837 | 839 | - | - | 0 | Contract Administrator | 0 | 52 | 32 | 36 | 27
839 | 1.2.4.4.1.1.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 838 | 840 | - | - | 0 | Scaffolder | 0 | 78 | 26 | 17 | 18
840 | 1.2.4.4.1.1.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 839 | 841 | - | - | 0 | Window | 0 | 26 | 35 | 87 | 41
841 | 1.2.4.4.1.1.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 840 | 842 | - | - | 0 | Formworker | 0 | 32 | 32 | 93 | 41
842 | 1.2.4.4.1.1.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 841 | 843,844,845,846 | - | - | 0 | Renderer | 0 | 23 | 17 | 93 | 13
843 | 1.2.4.4.1.1.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Stone Mason | 0 | 83 | 18 | 41 | 35
844 | 1.2.4.4.1.1.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Carpet | 0 | 12 | 24 | 34 | 7
845 | 1.2.4.4.1.1.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Stone Mason | 0 | 81 | 29 | 7 | 24
846 | 1.2.4.4.1.1.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | - | - | 0 | Timber Floorer | 0 | 89 | 10 | 58 | 49
847 | 1.2.4.4.1.1.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 793,794,795,796,797 | 848 | - | - | 0 | Plumber | 0 | 26 | 20 | 23 | 22
848 | 1.2.4.4.1.1.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 847 | 849 | - | - | 0 | Foreman | 0 | 67 | 20 | 68 | 55
849 | 1.2.4.4.1.1.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 848 | 850 | - | - | 0 | Fire | 0 | 18 | 30 | 34 | 29
850 | 1.2.4.4.1.1.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 849 |  | - | - | 0 | Plasterboarder | 0 | 22 | 11 | 71 | 18
851 | 1.2.4.4.1.2 | Apartment B011 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 42 | 30 | 68 | 27
852 | 1.2.4.4.1.2.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 853,856,857,924 | - | - | 0 | Subcontractor | 0 | 73 | 33 | 49 | 59
853 | 1.2.4.4.1.2.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 852 | 855,854 | - | - | 0 | Line Market | 0 | 34 | 16 | 57 | 25
854 | 1.2.4.4.1.2.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 853 |  | - | - | 0 | Formworker | 0 | 72 | 14 | 22 | 9
855 | 1.2.4.4.1.2.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 853 | 858 | - | - | 0 | Development Manager | 0 | 50 | 24 | 19 | 48
856 | 1.2.4.4.1.2.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 865 | - | - | 0 | Post Tension | 0 | 26 | 26 | 19 | 44
857 | 1.2.4.4.1.2.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 928 | - | - | 0 | Subcontractor | 0 | 71 | 10 | 26 | 20
858 | 1.2.4.4.1.2.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 855 | 859,860,861,862,863 | - | - | 0 | Landscaper | 0 | 10 | 35 | 1 | 45
859 | 1.2.4.4.1.2.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863 | - | - | 0 | Carpet | 0 | 86 | 13 | 34 | 25
860 | 1.2.4.4.1.2.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863,927 | - | - | 0 | Line Market | 0 | 34 | 35 | 73 | 22
861 | 1.2.4.4.1.2.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 926 | - | - | 0 | Site Manager | 0 | 34 | 17 | 74 | 28
862 | 1.2.4.4.1.2.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 |  | - | - | 0 | Surveyor | 0 | 42 | 28 | 68 | 39
863 | 1.2.4.4.1.2.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 858,859,860 | 864 | - | - | 0 | Project Manager | 0 | 47 | 15 | 21 | 2
864 | 1.2.4.4.1.2.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 863 | 865 | - | - | 0 | Site Manager | 0 | 53 | 11 | 99 | 41
865 | 1.2.4.4.1.2.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 856,864 | 866,867,868,869,871,873 | - | - | 0 | Hoarding | 0 | 87 | 12 | 46 | 36
866 | 1.2.4.4.1.2.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 870,873 | - | - | 0 | Admin | 0 | 68 | 35 | 73 | 4
867 | 1.2.4.4.1.2.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 873 | - | - | 0 | Plasterboarder | 0 | 28 | 20 | 20 | 3
868 | 1.2.4.4.1.2.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 872,873 | - | - | 0 | Stone Mason | 0 | 18 | 21 | 37 | 39
869 | 1.2.4.4.1.2.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | - | - | 0 | Waterproofer | 0 | 91 | 17 | 7 | 45
870 | 1.2.4.4.1.2.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 866 | 873 | - | - | 0 | Scaffolder | 0 | 13 | 24 | 8 | 3
871 | 1.2.4.4.1.2.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | - | - | 0 | Waterproofer | 0 | 83 | 16 | 76 | 25
872 | 1.2.4.4.1.2.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 868 | 873 | - | - | 0 | Surveyor | 0 | 84 | 11 | 12 | 24
873 | 1.2.4.4.1.2.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 865,866,867,868,869,870,871,872 | 874 | - | - | 0 | Hoarding | 0 | 100 | 33 | 18 | 27
874 | 1.2.4.4.1.2.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 873 | 875 | - | - | 0 | Contract Administrator | 0 | 95 | 28 | 85 | 32
875 | 1.2.4.4.1.2.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 874 | 876,893,910 | - | - | 0 | Fire | 0 | 92 | 14 | 100 | 23
876 | 1.2.4.4.1.2.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 877 | - | - | 0 | Excavation | 0 | 35 | 14 | 60 | 38
877 | 1.2.4.4.1.2.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 876 | 878 | - | - | 0 | Development Manager | 0 | 40 | 24 | 95 | 24
878 | 1.2.4.4.1.2.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 877 | 879 | - | - | 0 | Fire | 0 | 60 | 24 | 8 | 8
879 | 1.2.4.4.1.2.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 878 | 880 | - | - | 0 | Head Contractor | 0 | 44 | 15 | 34 | 24
880 | 1.2.4.4.1.2.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 879 | 881,882 | - | - | 0 | Stone Mason | 0 | 78 | 22 | 87 | 58
881 | 1.2.4.4.1.2.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 880 | 885 | - | - | 0 | Post Tension | 0 | 24 | 14 | 81 | 17
882 | 1.2.4.4.1.2.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 880 | 883 | - | - | 0 | Plumber | 0 | 96 | 14 | 63 | 58
883 | 1.2.4.4.1.2.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 882 | 884 | - | - | 0 | Waterproofer | 0 | 91 | 27 | 11 | 3
884 | 1.2.4.4.1.2.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 883 |  | - | - | 0 | Reinforcement Fixer | 0 | 57 | 16 | 97 | 17
885 | 1.2.4.4.1.2.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 881 | 886,887,888,889,890 | - | - | 0 | Head Contractor | 0 | 34 | 13 | 67 | 52
886 | 1.2.4.4.1.2.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 885 |  | - | - | 0 | Hoarding | 0 | 36 | 11 | 70 | 6
887 | 1.2.4.4.1.2.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Tiler | 0 | 68 | 22 | 70 | 37
888 | 1.2.4.4.1.2.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Surveyor | 0 | 28 | 31 | 30 | 40
889 | 1.2.4.4.1.2.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Site Manager | 0 | 48 | 24 | 66 | 6
890 | 1.2.4.4.1.2.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | - | - | 0 | Renderer | 0 | 67 | 33 | 28 | 22
891 | 1.2.4.4.1.2.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 941 | - | - | 0 | Carpenter | 0 | 81 | 23 | 75 | 50
892 | 1.2.4.4.1.2.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Floor Sealer | 0 | 27 | 26 | 71 | 7
893 | 1.2.4.4.1.2.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 894 | - | - | 0 | Contract Administrator | 0 | 29 | 11 | 93 | 22
894 | 1.2.4.4.1.2.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 893 | 895 | - | - | 0 | Site Manager | 0 | 45 | 26 | 28 | 12
895 | 1.2.4.4.1.2.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 894 | 896 | - | - | 0 | Foreman | 0 | 55 | 20 | 92 | 58
896 | 1.2.4.4.1.2.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 895 | 897 | - | - | 0 | Scaffolder | 0 | 88 | 25 | 20 | 19
897 | 1.2.4.4.1.2.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 896 | 898 | - | - | 0 | Development Manager | 0 | 52 | 18 | 18 | 6
898 | 1.2.4.4.1.2.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 897 | 899 | - | - | 0 | Project Manager | 0 | 27 | 21 | 24 | 41
899 | 1.2.4.4.1.2.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 898 | 900 | - | - | 0 | Plumber | 0 | 41 | 14 | 79 | 10
900 | 1.2.4.4.1.2.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 899 | 901 | - | - | 0 | Head Contractor | 0 | 46 | 11 | 89 | 52
901 | 1.2.4.4.1.2.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 900 | 902 | - | - | 0 | Hoarding | 0 | 30 | 25 | 35 | 3
902 | 1.2.4.4.1.2.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 901 | 903 | - | - | 0 | Electrician | 0 | 53 | 18 | 44 | 36
903 | 1.2.4.4.1.2.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 902 | 904 | - | - | 0 | Carpet | 0 | 66 | 13 | 94 | 40
904 | 1.2.4.4.1.2.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 903 | 908,905,906,907 | - | - | 0 | Landscaper | 0 | 46 | 17 | 65 | 50
905 | 1.2.4.4.1.2.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | - | - | 0 | Scaffolder | 0 | 78 | 24 | 14 | 14
906 | 1.2.4.4.1.2.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | - | - | 0 | Stone Mason | 0 | 38 | 24 | 8 | 37
907 | 1.2.4.4.1.2.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | - | - | 0 | Painter | 0 | 57 | 16 | 10 | 41
908 | 1.2.4.4.1.2.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 904,905,906,907 |  | - | - | 0 | Line Market | 0 | 94 | 26 | 8 | 53
909 | 1.2.4.4.1.2.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | - | - | 0 | Mechanical | 0 | 96 | 15 | 31 | 42
910 | 1.2.4.4.1.2.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 911 | - | - | 0 | Scaffolder | 0 | 70 | 34 | 81 | 27
911 | 1.2.4.4.1.2.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 910 | 912 | - | - | 0 | Line Market | 0 | 10 | 31 | 53 | 46
912 | 1.2.4.4.1.2.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 911 | 913 | - | - | 0 | Joiner | 0 | 19 | 34 | 27 | 60
913 | 1.2.4.4.1.2.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 912 | 914 | - | - | 0 | Line Market | 0 | 14 | 28 | 65 | 48
914 | 1.2.4.4.1.2.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 913 | 915 | - | - | 0 | Surveyor | 0 | 33 | 24 | 0 | 14
915 | 1.2.4.4.1.2.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 914 | 916 | - | - | 0 | Renderer | 0 | 54 | 12 | 75 | 30
916 | 1.2.4.4.1.2.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 915 | 917 | - | - | 0 | Carpet | 0 | 17 | 19 | 39 | 56
917 | 1.2.4.4.1.2.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 916 | 918,919,920,921 | - | - | 0 | Cleaner | 0 | 48 | 12 | 41 | 33
918 | 1.2.4.4.1.2.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Tiler | 0 | 81 | 16 | 67 | 53
919 | 1.2.4.4.1.2.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Surveyor | 0 | 51 | 16 | 8 | 28
920 | 1.2.4.4.1.2.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Tiler | 0 | 11 | 10 | 62 | 10
921 | 1.2.4.4.1.2.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | - | - | 0 | Reinforcement Fixer | 0 | 48 | 17 | 82 | 26
922 | 1.2.4.4.1.2.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 918,919,920,921 |  | - | - | 0 | Stone Mason | 0 | 33 | 10 | 88 | 60
923 | 1.2.4.4.1.2.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | - | - | 0 | Project Manager | 0 | 48 | 32 | 94 | 30
924 | 1.2.4.4.1.2.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 852 | 925 | - | - | 0 | Plasterboarder | 0 | 23 | 20 | 13 | 57
925 | 1.2.4.4.1.2.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 924 |  | - | - | 0 | Formworker | 0 | 98 | 30 | 88 | 14
926 | 1.2.4.4.1.2.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 861 | 929 | - | - | 0 | Renderer | 0 | 75 | 27 | 60 | 44
927 | 1.2.4.4.1.2.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 860 | 929 | - | - | 0 | Carpenter | 0 | 71 | 35 | 79 | 42
928 | 1.2.4.4.1.2.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 857 | 929 | - | - | 0 | Timber Floorer | 0 | 92 | 19 | 28 | 36
929 | 1.2.4.4.1.2.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 926,927,928 | 930 | - | - | 0 | Line Market | 0 | 38 | 11 | 62 | 50
930 | 1.2.4.4.1.2.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 929 | 931 | - | - | 0 | Joiner | 0 | 15 | 24 | 65 | 6
931 | 1.2.4.4.1.2.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 930 | 932 | - | - | 0 | Concretor | 0 | 26 | 29 | 74 | 12
932 | 1.2.4.4.1.2.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 931 | 933 | - | - | 0 | Timber Floorer | 0 | 45 | 21 | 28 | 38
933 | 1.2.4.4.1.2.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 932 | 934 | - | - | 0 | Stone Mason | 0 | 38 | 18 | 1 | 55
934 | 1.2.4.4.1.2.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 933 | 935 | - | - | 0 | Development Manager | 0 | 16 | 10 | 47 | 29
935 | 1.2.4.4.1.2.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 934 | 936 | - | - | 0 | Floor Sealer | 0 | 27 | 33 | 98 | 6
936 | 1.2.4.4.1.2.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 935 | 937,938,939,940 | - | - | 0 | Hoarding | 0 | 50 | 29 | 24 | 15
937 | 1.2.4.4.1.2.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Formworker | 0 | 67 | 16 | 6 | 31
938 | 1.2.4.4.1.2.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Hoarding | 0 | 37 | 14 | 59 | 10
939 | 1.2.4.4.1.2.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Concretor | 0 | 37 | 20 | 91 | 6
940 | 1.2.4.4.1.2.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | - | - | 0 | Joiner | 0 | 20 | 33 | 64 | 19
941 | 1.2.4.4.1.2.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 887,888,889,890,891 | 942 | - | - | 0 | Timber Floorer | 0 | 87 | 16 | 30 | 44
942 | 1.2.4.4.1.2.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 941 | 943 | - | - | 0 | Tiler | 0 | 48 | 26 | 45 | 7
943 | 1.2.4.4.1.2.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 942 | 944 | - | - | 0 | Renderer | 0 | 89 | 14 | 34 | 15
944 | 1.2.4.4.1.2.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 943 |  | - | - | 0 | Contract Administrator | 0 | 42 | 11 | 66 | 37
945 | 1.2.4.4.1.3 | Apartment B012 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Waterproofer | 0 | 77 | 14 | 33 | 17
946 | 1.2.4.4.1.3.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 947,950,951,1018 | - | - | 0 | Carpet | 0 | 26 | 25 | 71 | 49
947 | 1.2.4.4.1.3.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 946 | 949,948 | - | - | 0 | Waterproofer | 0 | 83 | 20 | 77 | 38
948 | 1.2.4.4.1.3.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 947 |  | - | - | 0 | Surveyor | 0 | 26 | 24 | 88 | 40
949 | 1.2.4.4.1.3.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 947 | 952 | - | - | 0 | Subcontractor | 0 | 42 | 31 | 97 | 4
950 | 1.2.4.4.1.3.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 959 | - | - | 0 | Scaffolder | 0 | 74 | 20 | 73 | 13
951 | 1.2.4.4.1.3.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 1022 | - | - | 0 | Electrician | 0 | 41 | 28 | 74 | 57
952 | 1.2.4.4.1.3.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 949 | 953,954,955,956,957 | - | - | 0 | Fire | 0 | 21 | 34 | 13 | 33
953 | 1.2.4.4.1.3.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957 | - | - | 0 | Landscaper | 0 | 86 | 24 | 38 | 21
954 | 1.2.4.4.1.3.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957,1021 | - | - | 0 | Electrician | 0 | 62 | 22 | 90 | 19
955 | 1.2.4.4.1.3.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 1020 | - | - | 0 | Landscaper | 0 | 37 | 19 | 2 | 56
956 | 1.2.4.4.1.3.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 |  | - | - | 0 | Line Market | 0 | 19 | 31 | 22 | 10
957 | 1.2.4.4.1.3.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 952,953,954 | 958 | - | - | 0 | Fire | 0 | 65 | 25 | 97 | 41
958 | 1.2.4.4.1.3.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 957 | 959 | - | - | 0 | Floor Sealer | 0 | 56 | 16 | 33 | 39
959 | 1.2.4.4.1.3.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 950,958 | 960,961,962,963,965,967 | - | - | 0 | Electrician | 0 | 72 | 31 | 25 | 45
960 | 1.2.4.4.1.3.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 964,967 | - | - | 0 | Line Market | 0 | 86 | 29 | 14 | 30
961 | 1.2.4.4.1.3.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 967 | - | - | 0 | Admin | 0 | 34 | 29 | 43 | 10
962 | 1.2.4.4.1.3.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 966,967 | - | - | 0 | Electrician | 0 | 99 | 13 | 39 | 9
963 | 1.2.4.4.1.3.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | - | - | 0 | Plasterboarder | 0 | 46 | 13 | 61 | 13
964 | 1.2.4.4.1.3.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 960 | 967 | - | - | 0 | Reinforcement Fixer | 0 | 84 | 13 | 66 | 56
965 | 1.2.4.4.1.3.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | - | - | 0 | Scaffolder | 0 | 32 | 12 | 34 | 23
966 | 1.2.4.4.1.3.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 962 | 967 | - | - | 0 | Concretor | 0 | 42 | 35 | 81 | 34
967 | 1.2.4.4.1.3.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 959,960,961,962,963,964,965,966 | 968 | - | - | 0 | Hoarding | 0 | 64 | 33 | 76 | 17
968 | 1.2.4.4.1.3.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 967 | 969 | - | - | 0 | Site Manager | 0 | 94 | 33 | 88 | 22
969 | 1.2.4.4.1.3.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 968 | 970,987,1004 | - | - | 0 | Cleaner | 0 | 75 | 29 | 17 | 18
970 | 1.2.4.4.1.3.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 971 | - | - | 0 | Tiler | 0 | 66 | 14 | 42 | 42
971 | 1.2.4.4.1.3.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 970 | 972 | - | - | 0 | Subcontractor | 0 | 49 | 14 | 46 | 58
972 | 1.2.4.4.1.3.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 971 | 973 | - | - | 0 | Plasterboarder | 0 | 56 | 10 | 68 | 6
973 | 1.2.4.4.1.3.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 972 | 974 | - | - | 0 | Excavation | 0 | 34 | 20 | 30 | 46
974 | 1.2.4.4.1.3.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 973 | 975,976 | - | - | 0 | Mechanical | 0 | 16 | 32 | 93 | 55
975 | 1.2.4.4.1.3.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 974 | 979 | - | - | 0 | Fire | 0 | 42 | 34 | 39 | 55
976 | 1.2.4.4.1.3.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 974 | 977 | - | - | 0 | Timber Floorer | 0 | 52 | 10 | 86 | 20
977 | 1.2.4.4.1.3.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 976 | 978 | - | - | 0 | Subcontractor | 0 | 59 | 29 | 16 | 25
978 | 1.2.4.4.1.3.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 977 |  | - | - | 0 | Excavation | 0 | 91 | 27 | 49 | 5
979 | 1.2.4.4.1.3.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 975 | 980,981,982,983,984 | - | - | 0 | Metal Work | 0 | 86 | 33 | 75 | 41
980 | 1.2.4.4.1.3.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 979 |  | - | - | 0 | Carpenter | 0 | 37 | 26 | 4 | 8
981 | 1.2.4.4.1.3.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Contract Administrator | 0 | 44 | 28 | 75 | 7
982 | 1.2.4.4.1.3.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Carpet | 0 | 43 | 17 | 41 | 50
983 | 1.2.4.4.1.3.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Concretor | 0 | 74 | 35 | 45 | 59
984 | 1.2.4.4.1.3.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | - | - | 0 | Carpet | 0 | 91 | 15 | 98 | 28
985 | 1.2.4.4.1.3.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1035 | - | - | 0 | Waterproofer | 0 | 29 | 29 | 71 | 27
986 | 1.2.4.4.1.3.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 40 | 27 | 69 | 55
987 | 1.2.4.4.1.3.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 988 | - | - | 0 | Site Manager | 0 | 16 | 11 | 14 | 21
988 | 1.2.4.4.1.3.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 987 | 989 | - | - | 0 | Admin | 0 | 81 | 25 | 75 | 27
989 | 1.2.4.4.1.3.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 988 | 990 | - | - | 0 | Foreman | 0 | 75 | 12 | 26 | 60
990 | 1.2.4.4.1.3.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 989 | 991 | - | - | 0 | Formworker | 0 | 12 | 31 | 40 | 41
991 | 1.2.4.4.1.3.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 990 | 992 | - | - | 0 | Formworker | 0 | 53 | 17 | 68 | 19
992 | 1.2.4.4.1.3.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 991 | 993 | - | - | 0 | Subcontractor | 0 | 77 | 31 | 35 | 56
993 | 1.2.4.4.1.3.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 992 | 994 | - | - | 0 | Timber Floorer | 0 | 38 | 35 | 61 | 43
994 | 1.2.4.4.1.3.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 993 | 995 | - | - | 0 | Concretor | 0 | 41 | 24 | 10 | 28
995 | 1.2.4.4.1.3.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 994 | 996 | - | - | 0 | Metal Work | 0 | 22 | 18 | 14 | 50
996 | 1.2.4.4.1.3.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 995 | 997 | - | - | 0 | Joiner | 0 | 61 | 27 | 31 | 30
997 | 1.2.4.4.1.3.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 996 | 998 | - | - | 0 | Post Tension | 0 | 33 | 25 | 7 | 5
998 | 1.2.4.4.1.3.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 997 | 1002,999,1000,1001 | - | - | 0 | Subcontractor | 0 | 78 | 27 | 97 | 52
999 | 1.2.4.4.1.3.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | - | - | 0 | Timber Floorer | 0 | 57 | 35 | 11 | 42
1000 | 1.2.4.4.1.3.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | - | - | 0 | Mechanical | 0 | 24 | 10 | 62 | 56
1001 | 1.2.4.4.1.3.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | - | - | 0 | Reinforcement Fixer | 0 | 77 | 18 | 100 | 6
1002 | 1.2.4.4.1.3.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 998,999,1000,1001 |  | - | - | 0 | Cleaner | 0 | 86 | 35 | 71 | 50
1003 | 1.2.4.4.1.3.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | - | - | 0 | Fire | 0 | 56 | 12 | 79 | 18
1004 | 1.2.4.4.1.3.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 1005 | - | - | 0 | Admin | 0 | 39 | 25 | 66 | 31
1005 | 1.2.4.4.1.3.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1004 | 1006 | - | - | 0 | Admin | 0 | 96 | 28 | 85 | 29
1006 | 1.2.4.4.1.3.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1005 | 1007 | - | - | 0 | Mechanical | 0 | 56 | 29 | 32 | 39
1007 | 1.2.4.4.1.3.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1006 | 1008 | - | - | 0 | Excavation | 0 | 30 | 27 | 31 | 43
1008 | 1.2.4.4.1.3.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1007 | 1009 | - | - | 0 | Contract Administrator | 0 | 24 | 13 | 84 | 38
1009 | 1.2.4.4.1.3.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1008 | 1010 | - | - | 0 | Floor Sealer | 0 | 77 | 21 | 92 | 11
1010 | 1.2.4.4.1.3.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1009 | 1011 | - | - | 0 | Electrician | 0 | 88 | 28 | 70 | 30
1011 | 1.2.4.4.1.3.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1010 | 1012,1013,1014,1015 | - | - | 0 | Development Manager | 0 | 27 | 32 | 28 | 26
1012 | 1.2.4.4.1.3.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Subcontractor | 0 | 93 | 13 | 29 | 6
1013 | 1.2.4.4.1.3.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Reinforcement Fixer | 0 | 40 | 15 | 48 | 52
1014 | 1.2.4.4.1.3.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Head Contractor | 0 | 27 | 21 | 14 | 9
1015 | 1.2.4.4.1.3.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | - | - | 0 | Painter | 0 | 28 | 34 | 94 | 24
1016 | 1.2.4.4.1.3.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1012,1013,1014,1015 |  | - | - | 0 | Renderer | 0 | 67 | 32 | 97 | 32
1017 | 1.2.4.4.1.3.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 80 | 10 | 26 | 46
1018 | 1.2.4.4.1.3.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 946 | 1019 | - | - | 0 | Carpenter | 0 | 44 | 17 | 93 | 31
1019 | 1.2.4.4.1.3.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1018 |  | - | - | 0 | Reinforcement Fixer | 0 | 53 | 28 | 21 | 13
1020 | 1.2.4.4.1.3.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 955 | 1023 | - | - | 0 | Site Manager | 0 | 72 | 13 | 58 | 3
1021 | 1.2.4.4.1.3.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 954 | 1023 | - | - | 0 | Site Manager | 0 | 20 | 23 | 35 | 8
1022 | 1.2.4.4.1.3.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 951 | 1023 | - | - | 0 | Floor Sealer | 0 | 60 | 32 | 27 | 46
1023 | 1.2.4.4.1.3.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1020,1021,1022 | 1024 | - | - | 0 | Post Tension | 0 | 91 | 16 | 21 | 22
1024 | 1.2.4.4.1.3.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1023 | 1025 | - | - | 0 | Joiner | 0 | 16 | 12 | 99 | 23
1025 | 1.2.4.4.1.3.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1024 | 1026 | - | - | 0 | Scaffolder | 0 | 38 | 10 | 96 | 18
1026 | 1.2.4.4.1.3.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1025 | 1027 | - | - | 0 | Contract Administrator | 0 | 100 | 27 | 17 | 21
1027 | 1.2.4.4.1.3.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1026 | 1028 | - | - | 0 | Stone Mason | 0 | 14 | 30 | 79 | 22
1028 | 1.2.4.4.1.3.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1027 | 1029 | - | - | 0 | Excavation | 0 | 69 | 17 | 77 | 11
1029 | 1.2.4.4.1.3.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1028 | 1030 | - | - | 0 | Line Market | 0 | 28 | 17 | 58 | 38
1030 | 1.2.4.4.1.3.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1029 | 1031,1032,1033,1034 | - | - | 0 | Concretor | 0 | 95 | 31 | 89 | 56
1031 | 1.2.4.4.1.3.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Concretor | 0 | 60 | 17 | 5 | 27
1032 | 1.2.4.4.1.3.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Landscaper | 0 | 83 | 18 | 86 | 60
1033 | 1.2.4.4.1.3.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Project Manager | 0 | 46 | 26 | 32 | 47
1034 | 1.2.4.4.1.3.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | - | - | 0 | Stone Mason | 0 | 17 | 11 | 0 | 56
1035 | 1.2.4.4.1.3.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 981,982,983,984,985 | 1036 | - | - | 0 | Post Tension | 0 | 69 | 21 | 48 | 51
1036 | 1.2.4.4.1.3.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1035 | 1037 | - | - | 0 | Landscaper | 0 | 73 | 16 | 92 | 42
1037 | 1.2.4.4.1.3.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1036 | 1038 | - | - | 0 | Tiler | 0 | 19 | 20 | 54 | 45
1038 | 1.2.4.4.1.3.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1037 |  | - | - | 0 | Renderer | 0 | 55 | 18 | 47 | 13
1039 | 1.2.4.4.1.4 | Apartment B013 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 25 | 35 | 22 | 42
1040 | 1.2.4.4.1.4.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 1041,1044,1045,1112 | - | - | 0 | Fire | 0 | 85 | 34 | 10 | 12
1041 | 1.2.4.4.1.4.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 1040 | 1043,1042 | - | - | 0 | Contract Administrator | 0 | 95 | 16 | 54 | 23
1042 | 1.2.4.4.1.4.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1041 |  | - | - | 0 | Carpet | 0 | 79 | 11 | 96 | 54
1043 | 1.2.4.4.1.4.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1041 | 1046 | - | - | 0 | Joiner | 0 | 94 | 15 | 5 | 47
1044 | 1.2.4.4.1.4.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1053 | - | - | 0 | Reinforcement Fixer | 0 | 59 | 25 | 82 | 55
1045 | 1.2.4.4.1.4.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1116 | - | - | 0 | Surveyor | 0 | 57 | 18 | 84 | 19
1046 | 1.2.4.4.1.4.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1043 | 1047,1048,1049,1050,1051 | - | - | 0 | Carpenter | 0 | 49 | 13 | 8 | 41
1047 | 1.2.4.4.1.4.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051 | - | - | 0 | Development Manager | 0 | 47 | 20 | 61 | 45
1048 | 1.2.4.4.1.4.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051,1115 | - | - | 0 | Tiler | 0 | 20 | 23 | 75 | 33
1049 | 1.2.4.4.1.4.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1114 | - | - | 0 | Plumber | 0 | 78 | 15 | 66 | 28
1050 | 1.2.4.4.1.4.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 |  | - | - | 0 | Scaffolder | 0 | 38 | 32 | 6 | 45
1051 | 1.2.4.4.1.4.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1046,1047,1048 | 1052 | - | - | 0 | Carpet | 0 | 89 | 31 | 44 | 4
1052 | 1.2.4.4.1.4.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1051 | 1053 | - | - | 0 | Head Contractor | 0 | 96 | 12 | 16 | 38
1053 | 1.2.4.4.1.4.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1044,1052 | 1054,1055,1056,1057,1059,1061 | - | - | 0 | Carpet | 0 | 71 | 24 | 14 | 6
1054 | 1.2.4.4.1.4.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1058,1061 | - | - | 0 | Landscaper | 0 | 34 | 24 | 2 | 20
1055 | 1.2.4.4.1.4.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Contract Administrator | 0 | 67 | 18 | 58 | 27
1056 | 1.2.4.4.1.4.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1060,1061 | - | - | 0 | Metal Work | 0 | 93 | 13 | 70 | 36
1057 | 1.2.4.4.1.4.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Surveyor | 0 | 40 | 13 | 24 | 55
1058 | 1.2.4.4.1.4.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1054 | 1061 | - | - | 0 | Window | 0 | 52 | 24 | 89 | 46
1059 | 1.2.4.4.1.4.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Contract Administrator | 0 | 81 | 23 | 2 | 3
1060 | 1.2.4.4.1.4.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1056 | 1061 | - | - | 0 | Cleaner | 0 | 20 | 24 | 94 | 39
1061 | 1.2.4.4.1.4.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1053,1054,1055,1056,1057,1058,1059,1060 | 1062 | - | - | 0 | Reinforcement Fixer | 0 | 23 | 19 | 87 | 52
1062 | 1.2.4.4.1.4.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1061 | 1063 | - | - | 0 | Development Manager | 0 | 54 | 35 | 66 | 36
1063 | 1.2.4.4.1.4.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1062 | 1064,1081,1098 | - | - | 0 | Development Manager | 0 | 77 | 15 | 54 | 55
1064 | 1.2.4.4.1.4.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1065 | - | - | 0 | Renderer | 0 | 61 | 31 | 70 | 2
1065 | 1.2.4.4.1.4.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1064 | 1066 | - | - | 0 | Plasterboarder | 0 | 12 | 27 | 83 | 40
1066 | 1.2.4.4.1.4.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1065 | 1067 | - | - | 0 | Post Tension | 0 | 40 | 25 | 69 | 26
1067 | 1.2.4.4.1.4.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1066 | 1068 | - | - | 0 | Carpet | 0 | 16 | 20 | 20 | 45
1068 | 1.2.4.4.1.4.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1067 | 1069,1070 | - | - | 0 | Electrician | 0 | 68 | 17 | 82 | 60
1069 | 1.2.4.4.1.4.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1068 | 1073 | - | - | 0 | Joiner | 0 | 80 | 35 | 22 | 23
1070 | 1.2.4.4.1.4.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1068 | 1071 | - | - | 0 | Reinforcement Fixer | 0 | 40 | 17 | 31 | 24
1071 | 1.2.4.4.1.4.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1070 | 1072 | - | - | 0 | Waterproofer | 0 | 48 | 17 | 53 | 3
1072 | 1.2.4.4.1.4.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1071 |  | - | - | 0 | Window | 0 | 26 | 21 | 5 | 43
1073 | 1.2.4.4.1.4.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1069 | 1074,1075,1076,1077,1078 | - | - | 0 | Line Market | 0 | 54 | 33 | 90 | 35
1074 | 1.2.4.4.1.4.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1073 |  | - | - | 0 | Line Market | 0 | 79 | 11 | 13 | 37
1075 | 1.2.4.4.1.4.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Reinforcement Fixer | 0 | 49 | 24 | 92 | 33
1076 | 1.2.4.4.1.4.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Electrician | 0 | 44 | 27 | 41 | 53
1077 | 1.2.4.4.1.4.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Post Tension | 0 | 45 | 16 | 26 | 42
1078 | 1.2.4.4.1.4.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Plumber | 0 | 99 | 21 | 51 | 54
1079 | 1.2.4.4.1.4.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1129 | - | - | 0 | Floor Sealer | 0 | 89 | 35 | 46 | 12
1080 | 1.2.4.4.1.4.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Timber Floorer | 0 | 98 | 22 | 80 | 36
1081 | 1.2.4.4.1.4.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1082 | - | - | 0 | Admin | 0 | 92 | 14 | 0 | 53
1082 | 1.2.4.4.1.4.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1081 | 1083 | - | - | 0 | Line Market | 0 | 82 | 22 | 75 | 34
1083 | 1.2.4.4.1.4.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1082 | 1084 | - | - | 0 | Joiner | 0 | 17 | 13 | 98 | 24
1084 | 1.2.4.4.1.4.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1083 | 1085 | - | - | 0 | Waterproofer | 0 | 77 | 13 | 16 | 26
1085 | 1.2.4.4.1.4.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1084 | 1086 | - | - | 0 | Plasterboarder | 0 | 60 | 26 | 29 | 7
1086 | 1.2.4.4.1.4.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1085 | 1087 | - | - | 0 | Subcontractor | 0 | 48 | 33 | 62 | 17
1087 | 1.2.4.4.1.4.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1086 | 1088 | - | - | 0 | Metal Work | 0 | 13 | 32 | 71 | 13
1088 | 1.2.4.4.1.4.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1087 | 1089 | - | - | 0 | Renderer | 0 | 19 | 31 | 84 | 54
1089 | 1.2.4.4.1.4.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1088 | 1090 | - | - | 0 | Carpenter | 0 | 17 | 27 | 46 | 8
1090 | 1.2.4.4.1.4.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1089 | 1091 | - | - | 0 | Timber Floorer | 0 | 68 | 21 | 78 | 22
1091 | 1.2.4.4.1.4.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1090 | 1092 | - | - | 0 | Site Manager | 0 | 43 | 12 | 5 | 43
1092 | 1.2.4.4.1.4.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1091 | 1096,1093,1094,1095 | - | - | 0 | Head Contractor | 0 | 31 | 22 | 53 | 13
1093 | 1.2.4.4.1.4.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Admin | 0 | 27 | 27 | 54 | 10
1094 | 1.2.4.4.1.4.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Hoarding | 0 | 81 | 12 | 17 | 60
1095 | 1.2.4.4.1.4.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Window | 0 | 80 | 31 | 3 | 16
1096 | 1.2.4.4.1.4.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1092,1093,1094,1095 |  | - | - | 0 | Post Tension | 0 | 64 | 30 | 51 | 25
1097 | 1.2.4.4.1.4.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | - | - | 0 | Development Manager | 0 | 35 | 30 | 38 | 6
1098 | 1.2.4.4.1.4.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1099 | - | - | 0 | Tiler | 0 | 58 | 34 | 16 | 9
1099 | 1.2.4.4.1.4.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1098 | 1100 | - | - | 0 | Project Manager | 0 | 60 | 19 | 77 | 33
1100 | 1.2.4.4.1.4.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1099 | 1101 | - | - | 0 | Painter | 0 | 29 | 18 | 71 | 17
1101 | 1.2.4.4.1.4.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1100 | 1102 | - | - | 0 | Contract Administrator | 0 | 16 | 22 | 9 | 30
1102 | 1.2.4.4.1.4.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1101 | 1103 | - | - | 0 | Plumber | 0 | 12 | 33 | 61 | 17
1103 | 1.2.4.4.1.4.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1102 | 1104 | - | - | 0 | Stone Mason | 0 | 91 | 15 | 73 | 28
1104 | 1.2.4.4.1.4.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1103 | 1105 | - | - | 0 | Landscaper | 0 | 81 | 11 | 20 | 17
1105 | 1.2.4.4.1.4.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1104 | 1106,1107,1108,1109 | - | - | 0 | Foreman | 0 | 12 | 26 | 83 | 7
1106 | 1.2.4.4.1.4.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Post Tension | 0 | 62 | 20 | 33 | 29
1107 | 1.2.4.4.1.4.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Hoarding | 0 | 36 | 24 | 59 | 37
1108 | 1.2.4.4.1.4.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Excavation | 0 | 93 | 25 | 10 | 26
1109 | 1.2.4.4.1.4.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Painter | 0 | 19 | 30 | 94 | 7
1110 | 1.2.4.4.1.4.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1106,1107,1108,1109 |  | - | - | 0 | Development Manager | 0 | 81 | 14 | 45 | 10
1111 | 1.2.4.4.1.4.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | - | - | 0 | Landscaper | 0 | 92 | 35 | 4 | 10
1112 | 1.2.4.4.1.4.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 1040 | 1113 | - | - | 0 | Electrician | 0 | 51 | 30 | 80 | 10
1113 | 1.2.4.4.1.4.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1112 |  | - | - | 0 | Development Manager | 0 | 63 | 34 | 74 | 36
1114 | 1.2.4.4.1.4.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1049 | 1117 | - | - | 0 | Post Tension | 0 | 49 | 34 | 71 | 9
1115 | 1.2.4.4.1.4.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1048 | 1117 | - | - | 0 | Post Tension | 0 | 11 | 27 | 60 | 36
1116 | 1.2.4.4.1.4.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1045 | 1117 | - | - | 0 | Electrician | 0 | 45 | 18 | 38 | 12
1117 | 1.2.4.4.1.4.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1114,1115,1116 | 1118 | - | - | 0 | Surveyor | 0 | 59 | 22 | 65 | 24
1118 | 1.2.4.4.1.4.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1117 | 1119 | - | - | 0 | Renderer | 0 | 91 | 29 | 20 | 13
1119 | 1.2.4.4.1.4.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1118 | 1120 | - | - | 0 | Subcontractor | 0 | 60 | 26 | 97 | 60
1120 | 1.2.4.4.1.4.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1119 | 1121 | - | - | 0 | Post Tension | 0 | 57 | 29 | 2 | 32
1121 | 1.2.4.4.1.4.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1120 | 1122 | - | - | 0 | Plumber | 0 | 67 | 26 | 12 | 20
1122 | 1.2.4.4.1.4.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1121 | 1123 | - | - | 0 | Hoarding | 0 | 27 | 31 | 61 | 36
1123 | 1.2.4.4.1.4.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1122 | 1124 | - | - | 0 | Contract Administrator | 0 | 12 | 28 | 41 | 37
1124 | 1.2.4.4.1.4.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1123 | 1125,1126,1127,1128 | - | - | 0 | Floor Sealer | 0 | 33 | 34 | 34 | 18
1125 | 1.2.4.4.1.4.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Mechanical | 0 | 11 | 33 | 7 | 31
1126 | 1.2.4.4.1.4.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Window | 0 | 80 | 30 | 52 | 24
1127 | 1.2.4.4.1.4.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Painter | 0 | 22 | 23 | 79 | 3
1128 | 1.2.4.4.1.4.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Subcontractor | 0 | 70 | 31 | 6 | 60
1129 | 1.2.4.4.1.4.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1075,1076,1077,1078,1079 | 1130 | - | - | 0 | Plasterboarder | 0 | 72 | 23 | 81 | 39
1130 | 1.2.4.4.1.4.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1129 | 1131 | - | - | 0 | Renderer | 0 | 13 | 23 | 59 | 45
1131 | 1.2.4.4.1.4.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1130 | 1132 | - | - | 0 | Foreman | 0 | 17 | 20 | 100 | 21
1132 | 1.2.4.4.1.4.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1131 |  | - | - | 0 | Renderer | 0 | 75 | 14 | 23 | 50
1133 | 1.2.4.4.1.5 | Apartment B014 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | - | - | 0 | Joiner | 0 | 96 | 22 | 18 | 47
1134 | 1.2.4.4.1.5.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1135,1138,1139,1206 | - | - | 0 | Contract Administrator | 0 | 73 | 12 | 76 | 37
1135 | 1.2.4.4.1.5.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1134 | 1137,1136 | - | - | 0 | Formworker | 0 | 97 | 12 | 53 | 47
1136 | 1.2.4.4.1.5.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1135 |  | - | - | 0 | Project Manager | 0 | 17 | 10 | 54 | 29
1137 | 1.2.4.4.1.5.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1135 | 1140 | - | - | 0 | Line Market | 0 | 50 | 26 | 13 | 50
1138 | 1.2.4.4.1.5.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1147 | - | - | 0 | Reinforcement Fixer | 0 | 38 | 17 | 19 | 30
1139 | 1.2.4.4.1.5.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1210 | - | - | 0 | Site Manager | 0 | 45 | 18 | 63 | 37
1140 | 1.2.4.4.1.5.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1137 | 1141,1142,1143,1144,1145 | - | - | 0 | Renderer | 0 | 36 | 13 | 62 | 32
1141 | 1.2.4.4.1.5.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145 | - | - | 0 | Hoarding | 0 | 80 | 33 | 33 | 25
1142 | 1.2.4.4.1.5.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145,1209 | - | - | 0 | Project Manager | 0 | 47 | 20 | 87 | 48
1143 | 1.2.4.4.1.5.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1208 | - | - | 0 | Hoarding | 0 | 74 | 16 | 94 | 33
1144 | 1.2.4.4.1.5.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 |  | - | - | 0 | Scaffolder | 0 | 77 | 20 | 41 | 40
1145 | 1.2.4.4.1.5.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1140,1141,1142 | 1146 | - | - | 0 | Timber Floorer | 0 | 100 | 25 | 96 | 37
1146 | 1.2.4.4.1.5.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1145 | 1147 | - | - | 0 | Electrician | 0 | 54 | 29 | 33 | 48
1147 | 1.2.4.4.1.5.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1138,1146 | 1148,1149,1150,1151,1153,1155 | - | - | 0 | Cleaner | 0 | 56 | 17 | 58 | 41
1148 | 1.2.4.4.1.5.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1152,1155 | - | - | 0 | Site Manager | 0 | 59 | 13 | 30 | 18
1149 | 1.2.4.4.1.5.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Electrician | 0 | 44 | 25 | 20 | 20
1150 | 1.2.4.4.1.5.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1154,1155 | - | - | 0 | Project Manager | 0 | 84 | 17 | 5 | 56
1151 | 1.2.4.4.1.5.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Waterproofer | 0 | 24 | 32 | 34 | 29
1152 | 1.2.4.4.1.5.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1148 | 1155 | - | - | 0 | Plumber | 0 | 79 | 25 | 93 | 43
1153 | 1.2.4.4.1.5.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Stone Mason | 0 | 73 | 35 | 56 | 46
1154 | 1.2.4.4.1.5.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1150 | 1155 | - | - | 0 | Hoarding | 0 | 68 | 29 | 38 | 21
1155 | 1.2.4.4.1.5.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1147,1148,1149,1150,1151,1152,1153,1154 | 1156 | - | - | 0 | Waterproofer | 0 | 77 | 31 | 20 | 46
1156 | 1.2.4.4.1.5.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1155 | 1157 | - | - | 0 | Admin | 0 | 33 | 13 | 58 | 36
1157 | 1.2.4.4.1.5.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1156 | 1158,1175,1192 | - | - | 0 | Electrician | 0 | 97 | 21 | 26 | 45
1158 | 1.2.4.4.1.5.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1159 | - | - | 0 | Contract Administrator | 0 | 24 | 14 | 66 | 55
1159 | 1.2.4.4.1.5.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1158 | 1160 | - | - | 0 | Admin | 0 | 52 | 34 | 24 | 39
1160 | 1.2.4.4.1.5.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1159 | 1161 | - | - | 0 | Fire | 0 | 38 | 21 | 75 | 15
1161 | 1.2.4.4.1.5.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1160 | 1162 | - | - | 0 | Plasterboarder | 0 | 88 | 29 | 27 | 47
1162 | 1.2.4.4.1.5.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1161 | 1163,1164 | - | - | 0 | Formworker | 0 | 29 | 21 | 100 | 32
1163 | 1.2.4.4.1.5.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1162 | 1167 | - | - | 0 | Scaffolder | 0 | 49 | 14 | 83 | 19
1164 | 1.2.4.4.1.5.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1162 | 1165 | - | - | 0 | Contract Administrator | 0 | 98 | 30 | 15 | 39
1165 | 1.2.4.4.1.5.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1164 | 1166 | - | - | 0 | Development Manager | 0 | 71 | 30 | 37 | 23
1166 | 1.2.4.4.1.5.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1165 |  | - | - | 0 | Project Manager | 0 | 35 | 10 | 60 | 9
1167 | 1.2.4.4.1.5.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1163 | 1168,1169,1170,1171,1172 | - | - | 0 | Admin | 0 | 88 | 28 | 74 | 12
1168 | 1.2.4.4.1.5.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1167 |  | - | - | 0 | Admin | 0 | 55 | 29 | 3 | 37
1169 | 1.2.4.4.1.5.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Admin | 0 | 66 | 13 | 81 | 53
1170 | 1.2.4.4.1.5.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Joiner | 0 | 43 | 24 | 30 | 33
1171 | 1.2.4.4.1.5.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Cleaner | 0 | 35 | 14 | 73 | 8
1172 | 1.2.4.4.1.5.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Foreman | 0 | 99 | 14 | 72 | 55
1173 | 1.2.4.4.1.5.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1223 | - | - | 0 | Fire | 0 | 46 | 19 | 94 | 48
1174 | 1.2.4.4.1.5.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Plumber | 0 | 89 | 28 | 26 | 33
1175 | 1.2.4.4.1.5.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1176 | - | - | 0 | Renderer | 0 | 14 | 26 | 7 | 37
1176 | 1.2.4.4.1.5.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1175 | 1177 | - | - | 0 | Formworker | 0 | 88 | 11 | 22 | 3
1177 | 1.2.4.4.1.5.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1176 | 1178 | - | - | 0 | Plumber | 0 | 34 | 24 | 16 | 34
1178 | 1.2.4.4.1.5.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1177 | 1179 | - | - | 0 | Subcontractor | 0 | 77 | 26 | 71 | 3
1179 | 1.2.4.4.1.5.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1178 | 1180 | - | - | 0 | Carpenter | 0 | 87 | 30 | 35 | 51
1180 | 1.2.4.4.1.5.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1179 | 1181 | - | - | 0 | Timber Floorer | 0 | 68 | 30 | 93 | 48
1181 | 1.2.4.4.1.5.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1180 | 1182 | - | - | 0 | Carpenter | 0 | 56 | 29 | 80 | 42
1182 | 1.2.4.4.1.5.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1181 | 1183 | - | - | 0 | Renderer | 0 | 59 | 35 | 81 | 49
1183 | 1.2.4.4.1.5.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1182 | 1184 | - | - | 0 | Floor Sealer | 0 | 47 | 23 | 48 | 15
1184 | 1.2.4.4.1.5.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1183 | 1185 | - | - | 0 | Head Contractor | 0 | 29 | 23 | 45 | 8
1185 | 1.2.4.4.1.5.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1184 | 1186 | - | - | 0 | Development Manager | 0 | 86 | 27 | 28 | 9
1186 | 1.2.4.4.1.5.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1185 | 1190,1187,1188,1189 | - | - | 0 | Painter | 0 | 90 | 33 | 60 | 20
1187 | 1.2.4.4.1.5.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Development Manager | 0 | 87 | 13 | 81 | 34
1188 | 1.2.4.4.1.5.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Concretor | 0 | 39 | 14 | 73 | 15
1189 | 1.2.4.4.1.5.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Reinforcement Fixer | 0 | 28 | 32 | 96 | 3
1190 | 1.2.4.4.1.5.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1186,1187,1188,1189 |  | - | - | 0 | Admin | 0 | 88 | 20 | 83 | 51
1191 | 1.2.4.4.1.5.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Timber Floorer | 0 | 93 | 11 | 57 | 9
1192 | 1.2.4.4.1.5.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1193 | - | - | 0 | Painter | 0 | 59 | 27 | 36 | 33
1193 | 1.2.4.4.1.5.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1192 | 1194 | - | - | 0 | Subcontractor | 0 | 79 | 35 | 49 | 48
1194 | 1.2.4.4.1.5.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1193 | 1195 | - | - | 0 | Surveyor | 0 | 35 | 15 | 95 | 45
1195 | 1.2.4.4.1.5.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1194 | 1196 | - | - | 0 | Landscaper | 0 | 94 | 11 | 74 | 29
1196 | 1.2.4.4.1.5.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1195 | 1197 | - | - | 0 | Concretor | 0 | 86 | 19 | 3 | 2
1197 | 1.2.4.4.1.5.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1196 | 1198 | - | - | 0 | Foreman | 0 | 72 | 25 | 19 | 34
1198 | 1.2.4.4.1.5.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1197 | 1199 | - | - | 0 | Stone Mason | 0 | 97 | 33 | 48 | 22
1199 | 1.2.4.4.1.5.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1198 | 1200,1201,1202,1203 | - | - | 0 | Head Contractor | 0 | 11 | 31 | 22 | 45
1200 | 1.2.4.4.1.5.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Surveyor | 0 | 44 | 31 | 56 | 4
1201 | 1.2.4.4.1.5.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Project Manager | 0 | 42 | 34 | 54 | 11
1202 | 1.2.4.4.1.5.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Waterproofer | 0 | 59 | 13 | 94 | 23
1203 | 1.2.4.4.1.5.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Concretor | 0 | 78 | 26 | 49 | 3
1204 | 1.2.4.4.1.5.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1200,1201,1202,1203 |  | - | - | 0 | Post Tension | 0 | 59 | 24 | 84 | 27
1205 | 1.2.4.4.1.5.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | - | - | 0 | Mechanical | 0 | 25 | 33 | 53 | 4
1206 | 1.2.4.4.1.5.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1134 | 1207 | - | - | 0 | Excavation | 0 | 69 | 30 | 67 | 45
1207 | 1.2.4.4.1.5.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1206 |  | - | - | 0 | Reinforcement Fixer | 0 | 27 | 31 | 42 | 23
1208 | 1.2.4.4.1.5.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1143 | 1211 | - | - | 0 | Renderer | 0 | 19 | 10 | 2 | 32
1209 | 1.2.4.4.1.5.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1142 | 1211 | - | - | 0 | Joiner | 0 | 98 | 34 | 97 | 5
1210 | 1.2.4.4.1.5.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1139 | 1211 | - | - | 0 | Contract Administrator | 0 | 20 | 25 | 61 | 2
1211 | 1.2.4.4.1.5.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1208,1209,1210 | 1212 | - | - | 0 | Tiler | 0 | 38 | 26 | 4 | 34
1212 | 1.2.4.4.1.5.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1211 | 1213 | - | - | 0 | Mechanical | 0 | 46 | 14 | 30 | 3
1213 | 1.2.4.4.1.5.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1212 | 1214 | - | - | 0 | Site Manager | 0 | 42 | 32 | 33 | 13
1214 | 1.2.4.4.1.5.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1213 | 1215 | - | - | 0 | Site Manager | 0 | 35 | 13 | 22 | 53
1215 | 1.2.4.4.1.5.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1214 | 1216 | - | - | 0 | Carpenter | 0 | 58 | 14 | 41 | 59
1216 | 1.2.4.4.1.5.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1215 | 1217 | - | - | 0 | Surveyor | 0 | 70 | 29 | 4 | 20
1217 | 1.2.4.4.1.5.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1216 | 1218 | - | - | 0 | Formworker | 0 | 59 | 30 | 32 | 38
1218 | 1.2.4.4.1.5.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1217 | 1219,1220,1221,1222 | - | - | 0 | Line Market | 0 | 30 | 18 | 6 | 6
1219 | 1.2.4.4.1.5.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Site Manager | 0 | 99 | 34 | 30 | 13
1220 | 1.2.4.4.1.5.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Landscaper | 0 | 40 | 15 | 9 | 51
1221 | 1.2.4.4.1.5.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Post Tension | 0 | 66 | 29 | 91 | 33
1222 | 1.2.4.4.1.5.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Metal Work | 0 | 34 | 27 | 83 | 15
1223 | 1.2.4.4.1.5.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1169,1170,1171,1172,1173 | 1224 | - | - | 0 | Window | 0 | 59 | 30 | 49 | 49
1224 | 1.2.4.4.1.5.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1223 | 1225 | - | - | 0 | Electrician | 0 | 85 | 29 | 44 | 19
1225 | 1.2.4.4.1.5.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1224 | 1226 | - | - | 0 | Excavation | 0 | 60 | 10 | 49 | 33
1226 | 1.2.4.4.1.5.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1225 |  | - | - | 0 | Surveyor | 0 | 36 | 19 | 33 | 24
1227 | 1.2.4.4.1.6 | Apartment B015 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | - | - | 0 | Window | 0 | 46 | 29 | 35 | 41
1228 | 1.2.4.4.1.6.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1229,1232,1233,1300 | - | - | 0 | Subcontractor | 0 | 23 | 25 | 76 | 23
1229 | 1.2.4.4.1.6.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1228 | 1231,1230 | - | - | 0 | Landscaper | 0 | 34 | 27 | 97 | 33
1230 | 1.2.4.4.1.6.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1229 |  | - | - | 0 | Painter | 0 | 25 | 22 | 12 | 59
1231 | 1.2.4.4.1.6.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1229 | 1234 | - | - | 0 | Site Manager | 0 | 29 | 10 | 59 | 28
1232 | 1.2.4.4.1.6.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1241 | - | - | 0 | Metal Work | 0 | 92 | 22 | 94 | 48
1233 | 1.2.4.4.1.6.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1304 | - | - | 0 | Head Contractor | 0 | 56 | 29 | 33 | 26
1234 | 1.2.4.4.1.6.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1231 | 1235,1236,1237,1238,1239 | - | - | 0 | Scaffolder | 0 | 12 | 19 | 38 | 57
1235 | 1.2.4.4.1.6.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239 | - | - | 0 | Window | 0 | 51 | 18 | 59 | 50
1236 | 1.2.4.4.1.6.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239,1303 | - | - | 0 | Development Manager | 0 | 10 | 16 | 52 | 36
1237 | 1.2.4.4.1.6.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1302 | - | - | 0 | Concretor | 0 | 31 | 32 | 69 | 17
1238 | 1.2.4.4.1.6.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 |  | - | - | 0 | Admin | 0 | 32 | 32 | 45 | 28
1239 | 1.2.4.4.1.6.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1234,1235,1236 | 1240 | - | - | 0 | Joiner | 0 | 64 | 29 | 44 | 20
1240 | 1.2.4.4.1.6.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1239 | 1241 | - | - | 0 | Stone Mason | 0 | 80 | 30 | 97 | 41
1241 | 1.2.4.4.1.6.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1232,1240 | 1242,1243,1244,1245,1247,1249 | - | - | 0 | Plumber | 0 | 13 | 26 | 17 | 12
1242 | 1.2.4.4.1.6.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1246,1249 | - | - | 0 | Stone Mason | 0 | 61 | 13 | 19 | 21
1243 | 1.2.4.4.1.6.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Carpet | 0 | 61 | 27 | 11 | 9
1244 | 1.2.4.4.1.6.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1248,1249 | - | - | 0 | Waterproofer | 0 | 99 | 10 | 98 | 19
1245 | 1.2.4.4.1.6.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Plumber | 0 | 92 | 33 | 40 | 39
1246 | 1.2.4.4.1.6.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1242 | 1249 | - | - | 0 | Project Manager | 0 | 96 | 14 | 51 | 3
1247 | 1.2.4.4.1.6.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Concretor | 0 | 99 | 18 | 83 | 2
1248 | 1.2.4.4.1.6.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1244 | 1249 | - | - | 0 | Cleaner | 0 | 17 | 28 | 20 | 42
1249 | 1.2.4.4.1.6.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1241,1242,1243,1244,1245,1246,1247,1248 | 1250 | - | - | 0 | Tiler | 0 | 41 | 35 | 90 | 19
1250 | 1.2.4.4.1.6.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1249 | 1251 | - | - | 0 | Hoarding | 0 | 86 | 27 | 25 | 50
1251 | 1.2.4.4.1.6.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1250 | 1252,1269,1286 | - | - | 0 | Surveyor | 0 | 84 | 20 | 84 | 8
1252 | 1.2.4.4.1.6.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1253 | - | - | 0 | Post Tension | 0 | 71 | 24 | 55 | 50
1253 | 1.2.4.4.1.6.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1252 | 1254 | - | - | 0 | Site Manager | 0 | 72 | 25 | 45 | 43
1254 | 1.2.4.4.1.6.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1253 | 1255 | - | - | 0 | Foreman | 0 | 72 | 28 | 94 | 59
1255 | 1.2.4.4.1.6.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1254 | 1256 | - | - | 0 | Joiner | 0 | 67 | 34 | 51 | 34
1256 | 1.2.4.4.1.6.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1255 | 1257,1258 | - | - | 0 | Contract Administrator | 0 | 42 | 34 | 97 | 6
1257 | 1.2.4.4.1.6.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1256 | 1261 | - | - | 0 | Joiner | 0 | 10 | 35 | 91 | 5
1258 | 1.2.4.4.1.6.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1256 | 1259 | - | - | 0 | Post Tension | 0 | 100 | 23 | 87 | 51
1259 | 1.2.4.4.1.6.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1258 | 1260 | - | - | 0 | Renderer | 0 | 16 | 16 | 70 | 21
1260 | 1.2.4.4.1.6.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1259 |  | - | - | 0 | Scaffolder | 0 | 42 | 23 | 62 | 57
1261 | 1.2.4.4.1.6.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1257 | 1262,1263,1264,1265,1266 | - | - | 0 | Joiner | 0 | 40 | 24 | 37 | 32
1262 | 1.2.4.4.1.6.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1261 |  | - | - | 0 | Line Market | 0 | 11 | 28 | 5 | 36
1263 | 1.2.4.4.1.6.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Tiler | 0 | 27 | 30 | 68 | 39
1264 | 1.2.4.4.1.6.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Post Tension | 0 | 74 | 11 | 22 | 48
1265 | 1.2.4.4.1.6.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Admin | 0 | 93 | 14 | 85 | 33
1266 | 1.2.4.4.1.6.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Metal Work | 0 | 21 | 15 | 57 | 24
1267 | 1.2.4.4.1.6.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1317 | - | - | 0 | Post Tension | 0 | 68 | 32 | 77 | 19
1268 | 1.2.4.4.1.6.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 45 | 19 | 8 | 20
1269 | 1.2.4.4.1.6.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1270 | - | - | 0 | Excavation | 0 | 38 | 12 | 2 | 50
1270 | 1.2.4.4.1.6.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1269 | 1271 | - | - | 0 | Project Manager | 0 | 34 | 21 | 76 | 16
1271 | 1.2.4.4.1.6.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1270 | 1272 | - | - | 0 | Development Manager | 0 | 85 | 31 | 87 | 36
1272 | 1.2.4.4.1.6.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1271 | 1273 | - | - | 0 | Renderer | 0 | 14 | 19 | 70 | 30
1273 | 1.2.4.4.1.6.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1272 | 1274 | - | - | 0 | Foreman | 0 | 69 | 34 | 0 | 20
1274 | 1.2.4.4.1.6.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1273 | 1275 | - | - | 0 | Floor Sealer | 0 | 93 | 25 | 73 | 20
1275 | 1.2.4.4.1.6.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1274 | 1276 | - | - | 0 | Surveyor | 0 | 30 | 22 | 15 | 2
1276 | 1.2.4.4.1.6.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1275 | 1277 | - | - | 0 | Subcontractor | 0 | 39 | 32 | 46 | 4
1277 | 1.2.4.4.1.6.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1276 | 1278 | - | - | 0 | Line Market | 0 | 66 | 11 | 68 | 32
1278 | 1.2.4.4.1.6.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1277 | 1279 | - | - | 0 | Stone Mason | 0 | 12 | 20 | 100 | 15
1279 | 1.2.4.4.1.6.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1278 | 1280 | - | - | 0 | Carpet | 0 | 55 | 13 | 81 | 32
1280 | 1.2.4.4.1.6.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1279 | 1284,1281,1282,1283 | - | - | 0 | Admin | 0 | 63 | 29 | 91 | 5
1281 | 1.2.4.4.1.6.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Scaffolder | 0 | 80 | 35 | 40 | 44
1282 | 1.2.4.4.1.6.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Landscaper | 0 | 97 | 12 | 99 | 57
1283 | 1.2.4.4.1.6.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Landscaper | 0 | 49 | 17 | 95 | 3
1284 | 1.2.4.4.1.6.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1280,1281,1282,1283 |  | - | - | 0 | Subcontractor | 0 | 42 | 33 | 15 | 7
1285 | 1.2.4.4.1.6.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 80 | 18 | 2 | 60
1286 | 1.2.4.4.1.6.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1287 | - | - | 0 | Concretor | 0 | 59 | 15 | 35 | 50
1287 | 1.2.4.4.1.6.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1286 | 1288 | - | - | 0 | Timber Floorer | 0 | 37 | 28 | 2 | 20
1288 | 1.2.4.4.1.6.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1287 | 1289 | - | - | 0 | Waterproofer | 0 | 67 | 32 | 72 | 29
1289 | 1.2.4.4.1.6.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1288 | 1290 | - | - | 0 | Head Contractor | 0 | 44 | 12 | 20 | 28
1290 | 1.2.4.4.1.6.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1289 | 1291 | - | - | 0 | Landscaper | 0 | 64 | 20 | 6 | 14
1291 | 1.2.4.4.1.6.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1290 | 1292 | - | - | 0 | Development Manager | 0 | 87 | 32 | 87 | 33
1292 | 1.2.4.4.1.6.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1291 | 1293 | - | - | 0 | Metal Work | 0 | 49 | 18 | 98 | 43
1293 | 1.2.4.4.1.6.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1292 | 1294,1295,1296,1297 | - | - | 0 | Stone Mason | 0 | 64 | 12 | 32 | 49
1294 | 1.2.4.4.1.6.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Plasterboarder | 0 | 81 | 14 | 50 | 18
1295 | 1.2.4.4.1.6.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Post Tension | 0 | 89 | 30 | 46 | 11
1296 | 1.2.4.4.1.6.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Scaffolder | 0 | 34 | 33 | 89 | 12
1297 | 1.2.4.4.1.6.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Contract Administrator | 0 | 84 | 35 | 28 | 46
1298 | 1.2.4.4.1.6.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1294,1295,1296,1297 |  | - | - | 0 | Renderer | 0 | 14 | 35 | 10 | 22
1299 | 1.2.4.4.1.6.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 50 | 24 | 38 | 54
1300 | 1.2.4.4.1.6.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1228 | 1301 | - | - | 0 | Landscaper | 0 | 47 | 27 | 31 | 29
1301 | 1.2.4.4.1.6.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1300 |  | - | - | 0 | Concretor | 0 | 61 | 33 | 36 | 31
1302 | 1.2.4.4.1.6.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1237 | 1305 | - | - | 0 | Formworker | 0 | 64 | 17 | 71 | 13
1303 | 1.2.4.4.1.6.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1236 | 1305 | - | - | 0 | Waterproofer | 0 | 78 | 17 | 90 | 44
1304 | 1.2.4.4.1.6.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1233 | 1305 | - | - | 0 | Painter | 0 | 75 | 20 | 10 | 6
1305 | 1.2.4.4.1.6.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1302,1303,1304 | 1306 | - | - | 0 | Carpenter | 0 | 50 | 27 | 95 | 27
1306 | 1.2.4.4.1.6.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1305 | 1307 | - | - | 0 | Post Tension | 0 | 19 | 22 | 85 | 3
1307 | 1.2.4.4.1.6.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1306 | 1308 | - | - | 0 | Concretor | 0 | 94 | 28 | 17 | 46
1308 | 1.2.4.4.1.6.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1307 | 1309 | - | - | 0 | Mechanical | 0 | 26 | 34 | 54 | 28
1309 | 1.2.4.4.1.6.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1308 | 1310 | - | - | 0 | Development Manager | 0 | 45 | 21 | 46 | 60
1310 | 1.2.4.4.1.6.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1309 | 1311 | - | - | 0 | Hoarding | 0 | 56 | 25 | 19 | 7
1311 | 1.2.4.4.1.6.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1310 | 1312 | - | - | 0 | Subcontractor | 0 | 88 | 23 | 3 | 50
1312 | 1.2.4.4.1.6.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1311 | 1313,1314,1315,1316 | - | - | 0 | Plasterboarder | 0 | 37 | 32 | 12 | 57
1313 | 1.2.4.4.1.6.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Plumber | 0 | 38 | 11 | 76 | 44
1314 | 1.2.4.4.1.6.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Mechanical | 0 | 28 | 13 | 26 | 23
1315 | 1.2.4.4.1.6.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Electrician | 0 | 21 | 22 | 15 | 42
1316 | 1.2.4.4.1.6.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Plumber | 0 | 34 | 14 | 12 | 38
1317 | 1.2.4.4.1.6.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1263,1264,1265,1266,1267 | 1318 | - | - | 0 | Timber Floorer | 0 | 89 | 27 | 100 | 53
1318 | 1.2.4.4.1.6.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1317 | 1319 | - | - | 0 | Excavation | 0 | 53 | 11 | 26 | 51
1319 | 1.2.4.4.1.6.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1318 | 1320 | - | - | 0 | Project Manager | 0 | 46 | 29 | 2 | 59
1320 | 1.2.4.4.1.6.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1319 |  | - | - | 0 | Reinforcement Fixer | 0 | 99 | 35 | 4 | 22
1321 | 1.2.4.4.1.7 | Apartment B016 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Floor Sealer | 0 | 37 | 17 | 59 | 20
1322 | 1.2.4.4.1.7.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1323,1326,1327,1394 | - | - | 0 | Window | 0 | 98 | 14 | 12 | 35
1323 | 1.2.4.4.1.7.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1322 | 1325,1324 | - | - | 0 | Electrician | 0 | 74 | 11 | 78 | 22
1324 | 1.2.4.4.1.7.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1323 |  | - | - | 0 | Subcontractor | 0 | 73 | 35 | 87 | 22
1325 | 1.2.4.4.1.7.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1323 | 1328 | - | - | 0 | Mechanical | 0 | 10 | 12 | 56 | 31
1326 | 1.2.4.4.1.7.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1335 | - | - | 0 | Scaffolder | 0 | 82 | 17 | 39 | 56
1327 | 1.2.4.4.1.7.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1398 | - | - | 0 | Tiler | 0 | 54 | 11 | 91 | 19
1328 | 1.2.4.4.1.7.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1325 | 1329,1330,1331,1332,1333 | - | - | 0 | Post Tension | 0 | 95 | 31 | 11 | 28
1329 | 1.2.4.4.1.7.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333 | - | - | 0 | Timber Floorer | 0 | 40 | 11 | 11 | 48
1330 | 1.2.4.4.1.7.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333,1397 | - | - | 0 | Joiner | 0 | 28 | 21 | 28 | 30
1331 | 1.2.4.4.1.7.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1396 | - | - | 0 | Excavation | 0 | 55 | 16 | 45 | 21
1332 | 1.2.4.4.1.7.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 |  | - | - | 0 | Line Market | 0 | 51 | 20 | 49 | 12
1333 | 1.2.4.4.1.7.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1328,1329,1330 | 1334 | - | - | 0 | Metal Work | 0 | 20 | 10 | 100 | 14
1334 | 1.2.4.4.1.7.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1333 | 1335 | - | - | 0 | Hoarding | 0 | 81 | 16 | 18 | 30
1335 | 1.2.4.4.1.7.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1326,1334 | 1336,1337,1338,1339,1341,1343 | - | - | 0 | Carpet | 0 | 75 | 23 | 69 | 7
1336 | 1.2.4.4.1.7.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1340,1343 | - | - | 0 | Subcontractor | 0 | 32 | 27 | 3 | 10
1337 | 1.2.4.4.1.7.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Subcontractor | 0 | 100 | 27 | 47 | 2
1338 | 1.2.4.4.1.7.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1342,1343 | - | - | 0 | Hoarding | 0 | 59 | 13 | 97 | 4
1339 | 1.2.4.4.1.7.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Excavation | 0 | 43 | 24 | 53 | 24
1340 | 1.2.4.4.1.7.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1336 | 1343 | - | - | 0 | Tiler | 0 | 77 | 33 | 22 | 51
1341 | 1.2.4.4.1.7.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Post Tension | 0 | 97 | 35 | 87 | 6
1342 | 1.2.4.4.1.7.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1338 | 1343 | - | - | 0 | Formworker | 0 | 90 | 10 | 46 | 36
1343 | 1.2.4.4.1.7.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1335,1336,1337,1338,1339,1340,1341,1342 | 1344 | - | - | 0 | Site Manager | 0 | 32 | 16 | 21 | 6
1344 | 1.2.4.4.1.7.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1343 | 1345 | - | - | 0 | Site Manager | 0 | 84 | 20 | 3 | 15
1345 | 1.2.4.4.1.7.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1344 | 1346,1363,1380 | - | - | 0 | Mechanical | 0 | 36 | 32 | 54 | 19
1346 | 1.2.4.4.1.7.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1347 | - | - | 0 | Reinforcement Fixer | 0 | 50 | 35 | 77 | 54
1347 | 1.2.4.4.1.7.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1346 | 1348 | - | - | 0 | Window | 0 | 18 | 13 | 52 | 27
1348 | 1.2.4.4.1.7.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1347 | 1349 | - | - | 0 | Hoarding | 0 | 51 | 28 | 12 | 15
1349 | 1.2.4.4.1.7.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1348 | 1350 | - | - | 0 | Joiner | 0 | 40 | 19 | 90 | 32
1350 | 1.2.4.4.1.7.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1349 | 1351,1352 | - | - | 0 | Excavation | 0 | 38 | 23 | 47 | 31
1351 | 1.2.4.4.1.7.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1350 | 1355 | - | - | 0 | Contract Administrator | 0 | 74 | 15 | 49 | 13
1352 | 1.2.4.4.1.7.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1350 | 1353 | - | - | 0 | Foreman | 0 | 67 | 28 | 19 | 23
1353 | 1.2.4.4.1.7.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1352 | 1354 | - | - | 0 | Site Manager | 0 | 45 | 18 | 0 | 5
1354 | 1.2.4.4.1.7.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1353 |  | - | - | 0 | Plasterboarder | 0 | 29 | 19 | 40 | 51
1355 | 1.2.4.4.1.7.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1351 | 1356,1357,1358,1359,1360 | - | - | 0 | Painter | 0 | 91 | 22 | 70 | 41
1356 | 1.2.4.4.1.7.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1355 |  | - | - | 0 | Landscaper | 0 | 79 | 27 | 25 | 9
1357 | 1.2.4.4.1.7.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Tiler | 0 | 76 | 17 | 78 | 5
1358 | 1.2.4.4.1.7.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Electrician | 0 | 18 | 31 | 99 | 27
1359 | 1.2.4.4.1.7.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Contract Administrator | 0 | 20 | 11 | 66 | 27
1360 | 1.2.4.4.1.7.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Joiner | 0 | 88 | 15 | 36 | 26
1361 | 1.2.4.4.1.7.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1411 | - | - | 0 | Foreman | 0 | 54 | 20 | 41 | 25
1362 | 1.2.4.4.1.7.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 55 | 27 | 89 | 36
1363 | 1.2.4.4.1.7.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1364 | - | - | 0 | Joiner | 0 | 64 | 28 | 59 | 43
1364 | 1.2.4.4.1.7.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1363 | 1365 | - | - | 0 | Project Manager | 0 | 82 | 34 | 43 | 36
1365 | 1.2.4.4.1.7.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1364 | 1366 | - | - | 0 | Landscaper | 0 | 70 | 24 | 29 | 19
1366 | 1.2.4.4.1.7.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1365 | 1367 | - | - | 0 | Hoarding | 0 | 67 | 23 | 43 | 58
1367 | 1.2.4.4.1.7.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1366 | 1368 | - | - | 0 | Contract Administrator | 0 | 31 | 16 | 14 | 43
1368 | 1.2.4.4.1.7.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1367 | 1369 | - | - | 0 | Line Market | 0 | 44 | 12 | 69 | 33
1369 | 1.2.4.4.1.7.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1368 | 1370 | - | - | 0 | Hoarding | 0 | 59 | 21 | 10 | 53
1370 | 1.2.4.4.1.7.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1369 | 1371 | - | - | 0 | Hoarding | 0 | 90 | 29 | 79 | 35
1371 | 1.2.4.4.1.7.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1370 | 1372 | - | - | 0 | Tiler | 0 | 59 | 14 | 62 | 16
1372 | 1.2.4.4.1.7.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1371 | 1373 | - | - | 0 | Line Market | 0 | 86 | 27 | 86 | 13
1373 | 1.2.4.4.1.7.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1372 | 1374 | - | - | 0 | Electrician | 0 | 66 | 35 | 1 | 23
1374 | 1.2.4.4.1.7.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1373 | 1378,1375,1376,1377 | - | - | 0 | Development Manager | 0 | 96 | 30 | 78 | 52
1375 | 1.2.4.4.1.7.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Project Manager | 0 | 90 | 34 | 51 | 14
1376 | 1.2.4.4.1.7.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Site Manager | 0 | 46 | 21 | 6 | 46
1377 | 1.2.4.4.1.7.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Joiner | 0 | 31 | 22 | 59 | 40
1378 | 1.2.4.4.1.7.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1374,1375,1376,1377 |  | - | - | 0 | Admin | 0 | 27 | 33 | 39 | 37
1379 | 1.2.4.4.1.7.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Electrician | 0 | 20 | 13 | 51 | 37
1380 | 1.2.4.4.1.7.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1381 | - | - | 0 | Subcontractor | 0 | 78 | 34 | 19 | 3
1381 | 1.2.4.4.1.7.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1380 | 1382 | - | - | 0 | Painter | 0 | 52 | 34 | 97 | 2
1382 | 1.2.4.4.1.7.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1381 | 1383 | - | - | 0 | Metal Work | 0 | 24 | 28 | 62 | 59
1383 | 1.2.4.4.1.7.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1382 | 1384 | - | - | 0 | Post Tension | 0 | 26 | 29 | 14 | 11
1384 | 1.2.4.4.1.7.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1383 | 1385 | - | - | 0 | Landscaper | 0 | 98 | 35 | 58 | 39
1385 | 1.2.4.4.1.7.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1384 | 1386 | - | - | 0 | Electrician | 0 | 78 | 14 | 55 | 39
1386 | 1.2.4.4.1.7.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1385 | 1387 | - | - | 0 | Scaffolder | 0 | 69 | 34 | 66 | 27
1387 | 1.2.4.4.1.7.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1386 | 1388,1389,1390,1391 | - | - | 0 | Floor Sealer | 0 | 89 | 34 | 62 | 42
1388 | 1.2.4.4.1.7.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Head Contractor | 0 | 56 | 21 | 28 | 35
1389 | 1.2.4.4.1.7.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Carpet | 0 | 60 | 28 | 4 | 21
1390 | 1.2.4.4.1.7.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Scaffolder | 0 | 25 | 30 | 45 | 30
1391 | 1.2.4.4.1.7.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Carpet | 0 | 22 | 18 | 22 | 39
1392 | 1.2.4.4.1.7.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1388,1389,1390,1391 |  | - | - | 0 | Tiler | 0 | 68 | 18 | 100 | 57
1393 | 1.2.4.4.1.7.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | - | - | 0 | Excavation | 0 | 53 | 22 | 49 | 2
1394 | 1.2.4.4.1.7.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1322 | 1395 | - | - | 0 | Scaffolder | 0 | 62 | 30 | 48 | 8
1395 | 1.2.4.4.1.7.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1394 |  | - | - | 0 | Tiler | 0 | 29 | 15 | 35 | 4
1396 | 1.2.4.4.1.7.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1331 | 1399 | - | - | 0 | Surveyor | 0 | 74 | 35 | 19 | 48
1397 | 1.2.4.4.1.7.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1330 | 1399 | - | - | 0 | Plasterboarder | 0 | 17 | 15 | 40 | 57
1398 | 1.2.4.4.1.7.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1327 | 1399 | - | - | 0 | Line Market | 0 | 81 | 21 | 84 | 42
1399 | 1.2.4.4.1.7.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1396,1397,1398 | 1400 | - | - | 0 | Hoarding | 0 | 37 | 21 | 90 | 53
1400 | 1.2.4.4.1.7.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1399 | 1401 | - | - | 0 | Contract Administrator | 0 | 66 | 35 | 53 | 39
1401 | 1.2.4.4.1.7.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1400 | 1402 | - | - | 0 | Project Manager | 0 | 23 | 13 | 43 | 50
1402 | 1.2.4.4.1.7.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1401 | 1403 | - | - | 0 | Waterproofer | 0 | 76 | 19 | 57 | 26
1403 | 1.2.4.4.1.7.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1402 | 1404 | - | - | 0 | Line Market | 0 | 83 | 19 | 41 | 22
1404 | 1.2.4.4.1.7.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1403 | 1405 | - | - | 0 | Tiler | 0 | 47 | 29 | 37 | 7
1405 | 1.2.4.4.1.7.41.12 | Grout | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1404 | 1406 | - | - | 0 | Cleaner | 0 | 11 | 21 | 26 | 44
1406 | 1.2.4.4.1.7.41.13 | Paint/Cladding | 3 | 14 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1405 | 1407,1408,1409,1410 | - | - | 0 | Landscaper | 0 | 44 | 35 | 49 | 58
1407 | 1.2.4.4.1.7.41.14 | Silicone | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Reinforcement Fixer | 0 | 51 | 26 | 75 | 24
1408 | 1.2.4.4.1.7.41.15 | Hydraulic Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Subcontractor | 0 | 17 | 30 | 14 | 22
1409 | 1.2.4.4.1.7.41.16 | Electrical Fit Off | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Development Manager | 0 | 83 | 30 | 51 | 15
1410 | 1.2.4.4.1.7.41.17 | Fit Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Waterproofer | 0 | 83 | 16 | 100 | 22
1411 | 1.2.4.4.1.7.42 | Carpet Install | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1357,1358,1359,1360,1361 | 1412 | - | - | 0 | Admin | 0 | 100 | 26 | 97 | 41
1412 | 1.2.4.4.1.7.43 | Paint (FINAL Coat) | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1411 | 1413 | - | - | 0 | Carpenter | 0 | 75 | 26 | 74 | 7
1413 | 1.2.4.4.1.7.44 | FINAL CLEAN | 1 | 11 December 2024 8:00 AM | 11 December 2024 5:00 PM | 1412 | 1414 | - | - | 0 | Site Manager | 0 | 51 | 18 | 17 | 46
1414 | 1.2.4.4.1.7.45 | UNIT LOCKED | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 1413 |  | - | - | 0 | Subcontractor | 0 | 64 | 14 | 63 | 54
1415 | 1.2.4.4.1.8 | Apartment B017 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Post Tension | 0 | 12 | 30 | 70 | 37
1416 | 1.2.4.4.1.8.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1417,1420,1421,1488 | - | - | 0 | Surveyor | 0 | 46 | 20 | 32 | 26
1417 | 1.2.4.4.1.8.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1416 | 1419,1418 | - | - | 0 | Waterproofer | 0 | 95 | 18 | 10 | 50
1418 | 1.2.4.4.1.8.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1417 |  | - | - | 0 | Tiler | 0 | 49 | 19 | 91 | 39
1419 | 1.2.4.4.1.8.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1417 | 1422 | - | - | 0 | Cleaner | 0 | 24 | 34 | 87 | 38
1420 | 1.2.4.4.1.8.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1429 | - | - | 0 | Site Manager | 0 | 76 | 29 | 83 | 39
1421 | 1.2.4.4.1.8.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1492 | - | - | 0 | Formworker | 0 | 44 | 27 | 13 | 32
1422 | 1.2.4.4.1.8.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1419 | 1423,1424,1425,1426,1427 | - | - | 0 | Formworker | 0 | 62 | 11 | 56 | 34
1423 | 1.2.4.4.1.8.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427 | - | - | 0 | Formworker | 0 | 27 | 26 | 33 | 18
1424 | 1.2.4.4.1.8.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427,1491 | - | - | 0 | Post Tension | 0 | 21 | 15 | 52 | 22
1425 | 1.2.4.4.1.8.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1490 | - | - | 0 | Fire | 0 | 21 | 35 | 89 | 30
1426 | 1.2.4.4.1.8.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 |  | - | - | 0 | Carpet | 0 | 36 | 35 | 11 | 54
1427 | 1.2.4.4.1.8.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1422,1423,1424 | 1428 | - | - | 0 | Formworker | 0 | 64 | 24 | 29 | 8
1428 | 1.2.4.4.1.8.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1427 | 1429 | - | - | 0 | Plasterboarder | 0 | 76 | 14 | 55 | 15
1429 | 1.2.4.4.1.8.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1420,1428 | 1430,1431,1432,1433,1435,1437 | - | - | 0 | Metal Work | 0 | 11 | 27 | 91 | 45
1430 | 1.2.4.4.1.8.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1434,1437 | - | - | 0 | Hoarding | 0 | 50 | 33 | 56 | 40
1431 | 1.2.4.4.1.8.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Carpet | 0 | 33 | 34 | 29 | 31
1432 | 1.2.4.4.1.8.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1436,1437 | - | - | 0 | Stone Mason | 0 | 73 | 31 | 54 | 19
1433 | 1.2.4.4.1.8.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Renderer | 0 | 95 | 19 | 48 | 8
1434 | 1.2.4.4.1.8.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1430 | 1437 | - | - | 0 | Foreman | 0 | 28 | 24 | 43 | 50
1435 | 1.2.4.4.1.8.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Tiler | 0 | 39 | 30 | 8 | 8
1436 | 1.2.4.4.1.8.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1432 | 1437 | - | - | 0 | Timber Floorer | 0 | 80 | 25 | 83 | 58
1437 | 1.2.4.4.1.8.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1429,1430,1431,1432,1433,1434,1435,1436 | 1438 | - | - | 0 | Mechanical | 0 | 64 | 21 | 98 | 23
1438 | 1.2.4.4.1.8.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1437 | 1439 | - | - | 0 | Stone Mason | 0 | 83 | 28 | 42 | 4
1439 | 1.2.4.4.1.8.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1438 | 1440,1457,1474 | - | - | 0 | Foreman | 0 | 42 | 32 | 97 | 37
1440 | 1.2.4.4.1.8.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1441 | - | - | 0 | Contract Administrator | 0 | 56 | 25 | 62 | 31
1441 | 1.2.4.4.1.8.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1440 | 1442 | - | - | 0 | Carpet | 0 | 43 | 30 | 66 | 57
1442 | 1.2.4.4.1.8.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1441 | 1443 | - | - | 0 | Floor Sealer | 0 | 11 | 17 | 80 | 17
1443 | 1.2.4.4.1.8.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1442 | 1444 | - | - | 0 | Reinforcement Fixer | 0 | 39 | 25 | 10 | 58
1444 | 1.2.4.4.1.8.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1443 | 1445,1446 | - | - | 0 | Line Market | 0 | 47 | 26 | 15 | 35
1445 | 1.2.4.4.1.8.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1444 | 1449 | - | - | 0 | Hoarding | 0 | 95 | 31 | 28 | 17
1446 | 1.2.4.4.1.8.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1444 | 1447 | - | - | 0 | Development Manager | 0 | 80 | 16 | 18 | 5
1447 | 1.2.4.4.1.8.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1446 | 1448 | - | - | 0 | Head Contractor | 0 | 45 | 30 | 41 | 56
1448 | 1.2.4.4.1.8.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1447 |  | - | - | 0 | Renderer | 0 | 15 | 18 | 80 | 50
1449 | 1.2.4.4.1.8.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1445 | 1450,1451,1452,1453,1454 | - | - | 0 | Surveyor | 0 | 91 | 28 | 80 | 51
1450 | 1.2.4.4.1.8.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1449 |  | - | - | 0 | Cleaner | 0 | 24 | 27 | 94 | 15
1451 | 1.2.4.4.1.8.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Floor Sealer | 0 | 15 | 18 | 98 | 11
1452 | 1.2.4.4.1.8.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Subcontractor | 0 | 62 | 20 | 89 | 45
1453 | 1.2.4.4.1.8.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Renderer | 0 | 54 | 33 | 34 | 36
1454 | 1.2.4.4.1.8.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Cleaner | 0 | 92 | 22 | 79 | 19
1455 | 1.2.4.4.1.8.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1505 | - | - | 0 | Mechanical | 0 | 97 | 15 | 23 | 48
1456 | 1.2.4.4.1.8.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 70 | 26 | 87 | 54
1457 | 1.2.4.4.1.8.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1458 | - | - | 0 | Mechanical | 0 | 36 | 27 | 5 | 34
1458 | 1.2.4.4.1.8.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1457 | 1459 | - | - | 0 | Foreman | 0 | 15 | 33 | 9 | 8
1459 | 1.2.4.4.1.8.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1458 | 1460 | - | - | 0 | Waterproofer | 0 | 34 | 17 | 34 | 32
1460 | 1.2.4.4.1.8.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1459 | 1461 | - | - | 0 | Project Manager | 0 | 86 | 31 | 34 | 21
1461 | 1.2.4.4.1.8.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1460 | 1462 | - | - | 0 | Carpet | 0 | 11 | 18 | 71 | 39
1462 | 1.2.4.4.1.8.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1461 | 1463 | - | - | 0 | Admin | 0 | 87 | 10 | 72 | 34
1463 | 1.2.4.4.1.8.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1462 | 1464 | - | - | 0 | Scaffolder | 0 | 36 | 23 | 54 | 24
1464 | 1.2.4.4.1.8.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1463 | 1465 | - | - | 0 | Joiner | 0 | 11 | 32 | 15 | 49
1465 | 1.2.4.4.1.8.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1464 | 1466 | - | - | 0 | Painter | 0 | 98 | 24 | 73 | 27
1466 | 1.2.4.4.1.8.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1465 | 1467 | - | - | 0 | Foreman | 0 | 13 | 18 | 12 | 35
1467 | 1.2.4.4.1.8.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1466 | 1468 | - | - | 0 | Plasterboarder | 0 | 54 | 13 | 69 | 17
1468 | 1.2.4.4.1.8.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1467 | 1472,1469,1470,1471 | - | - | 0 | Plasterboarder | 0 | 71 | 19 | 11 | 33
1469 | 1.2.4.4.1.8.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Window | 0 | 15 | 30 | 98 | 49
1470 | 1.2.4.4.1.8.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Electrician | 0 | 10 | 15 | 69 | 48
1471 | 1.2.4.4.1.8.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Reinforcement Fixer | 0 | 41 | 11 | 54 | 54
1472 | 1.2.4.4.1.8.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1468,1469,1470,1471 |  | - | - | 0 | Carpenter | 0 | 72 | 17 | 87 | 41
1473 | 1.2.4.4.1.8.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Project Manager | 0 | 92 | 24 | 69 | 59
1474 | 1.2.4.4.1.8.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1475 | - | - | 0 | Metal Work | 0 | 61 | 23 | 53 | 9
1475 | 1.2.4.4.1.8.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1474 | 1476 | - | - | 0 | Formworker | 0 | 12 | 25 | 65 | 34
1476 | 1.2.4.4.1.8.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1475 | 1477 | - | - | 0 | Landscaper | 0 | 59 | 33 | 26 | 23
1477 | 1.2.4.4.1.8.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1476 | 1478 | - | - | 0 | Fire | 0 | 64 | 31 | 27 | 12
1478 | 1.2.4.4.1.8.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1477 | 1479 | - | - | 0 | Head Contractor | 0 | 42 | 33 | 82 | 56
1479 | 1.2.4.4.1.8.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1478 | 1480 | - | - | 0 | Contract Administrator | 0 | 66 | 28 | 67 | 51
1480 | 1.2.4.4.1.8.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1479 | 1481 | - | - | 0 | Project Manager | 0 | 52 | 12 | 49 | 16
1481 | 1.2.4.4.1.8.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1480 | 1482,1483,1484,1485 | - | - | 0 | Window | 0 | 41 | 33 | 15 | 7
1482 | 1.2.4.4.1.8.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Timber Floorer | 0 | 20 | 27 | 10 | 8
1483 | 1.2.4.4.1.8.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Renderer | 0 | 81 | 14 | 37 | 6
1484 | 1.2.4.4.1.8.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Painter | 0 | 16 | 30 | 64 | 37
1485 | 1.2.4.4.1.8.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Plasterboarder | 0 | 59 | 29 | 91 | 10
1486 | 1.2.4.4.1.8.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1482,1483,1484,1485 |  | - | - | 0 | Project Manager | 0 | 62 | 33 | 86 | 23
1487 | 1.2.4.4.1.8.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 48 | 26 | 37 | 20
1488 | 1.2.4.4.1.8.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1416 | 1489 | - | - | 0 | Floor Sealer | 0 | 51 | 16 | 32 | 56
1489 | 1.2.4.4.1.8.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1488 |  | - | - | 0 | Joiner | 0 | 50 | 21 | 65 | 53
1490 | 1.2.4.4.1.8.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1425 | 1493 | - | - | 0 | Admin | 0 | 24 | 26 | 85 | 48
1491 | 1.2.4.4.1.8.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1424 | 1493 | - | - | 0 | Line Market | 0 | 79 | 11 | 90 | 30
1492 | 1.2.4.4.1.8.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1421 | 1493 | - | - | 0 | Scaffolder | 0 | 31 | 12 | 80 | 59
1493 | 1.2.4.4.1.8.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1490,1491,1492 | 1494 | - | - | 0 | Surveyor | 0 | 63 | 24 | 38 | 55
1494 | 1.2.4.4.1.8.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1493 | 1495 | - | - | 0 | Concretor | 0 | 73 | 22 | 82 | 44
1495 | 1.2.4.4.1.8.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1494 | 1496 | - | - | 0 | Waterproofer | 0 | 99 | 25 | 9 | 24
1496 | 1.2.4.4.1.8.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1495 | 1497 | - | - | 0 | Development Manager | 0 | 13 | 35 | 65 | 56
1497 | 1.2.4.4.1.8.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1496 | 1498 | - | - | 0 | Scaffolder | 0 | 28 | 19 | 44 | 15
1498 | 1.2.4.4.1.8.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1497 | 1499 | - | - | 0 | Surveyor | 0 | 86 | 31 | 94 | 60

## Progress 75%
ID | Outline_Number | Name | Duration | Start_Date | Finish_Date | Predecessors | Successors | Actual_Start | Actual_End | Delay | Trade | Progress | Worker_Score | Temp | Rain_Probability | Wind_Speed
2 | 1.1 | MILESTONES / KEY DATES | 633 | 17 April 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 17 April 2023 7:00 AM | - | 0 |  | 70.4545 | - | - | - | -
3 | 1.1.1 | Site Establishment | 0 | 5 June 2023 7:00 AM | 5 June 2023 7:00 AM |  | 25SS | 5 June 2023 7:00 AM | 2023-06-05 07:00 | 0 | Plasterboarder | 100 | 33 | 30 | 69 | 19
4 | 1.1.2 | Basement Completed (B2) | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 88 |  | 2 May 2024 5:00 PM | 2024-05-02 17:00 | 0 | Timber Floorer | 100 | 93 | 24 | 2 | 16
5 | 1.1.3 | Building A Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 444,753,746,714 | 3466,9 | 5 May 2025 5:00 PM | 2025-05-05 17:00 | 0 | Floor Sealer | 100 | 72 | 30 | 36 | 57
6 | 1.1.4 | Building B Complete | 0 | 29 March 2025 5:00 PM | 29 March 2025 5:00 PM | 228,482,306,1737 | 3466,9 | 29 March 2025 5:00 PM | 2025-03-29 17:00 | 0 | Scaffolder | 100 | 89 | 22 | 78 | 33
7 | 1.1.5 | Building C Complete | 0 | 16 April 2025 5:00 PM | 16 April 2025 5:00 PM | 306,360,503,3169 | 3466,9 | 16 April 2025 5:00 PM | 2025-04-16 17:00 | 0 | Painter | 100 | 19 | 14 | 44 | 60
8 | 1.1.6 | Building D Complete | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 360,396,519,3439 | 3466,9 | 17 April 2025 5:00 PM | 2025-04-17 17:00 | 0 | Post Tension | 100 | 72 | 18 | 31 | 43
9 | 1.1.7 | Practical Completion (Net) | 0 | 28 May 2025 5:00 PM | 28 May 2025 5:00 PM | 3465,3440,5,3460,6,7,8 |  | 28 May 2025 5:00 PM | 2025-05-28 17:00 | 0 | Admin | 100 | 56 | 30 | 35 | 39
10 | 1.1.8 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | 28 July 2023 8:00 AM | 2023-08-15 17:00 | 0 | Plasterboarder | 100 | 34 | 14 | 40 | 35
11 | 1.1.9 | Inclement Weatherallowed (Spent) | 19 | 29 May 2025 8:00 AM | 21 June 2025 5:00 PM | 3466 | 12 | 29 May 2025 8:00 AM | 2025-06-23 17:00 | 2 | Subcontractor | 100 | 15 | 12 | 75 | 32
12 | 1.1.10 | Inclement Weatherallowed (Remaining) | 1 | 23 June 2025 8:00 AM | 23 June 2025 5:00 PM | 11 | 3469 | 23 June 2025 8:00 AM | 2025-06-23 17:00 | 0 | Painter | 100 | 50 | 33 | 73 | 35
13 | 1.1.11 | Practical Completion (Gross) - Building Handover | 0 | 23 June 2025 5:00 PM | 23 June 2025 5:00 PM | 3469 |  | 23 June 2025 5:00 PM | 2025-06-23 17:00 | 0 | Contract Administrator | 100 | 88 | 22 | 67 | 45
14 | 1.1.12 | PRE CONSTRUCTION WORKS | 210.13 | 17 April 2023 7:00 AM | 16 January 2024 5:00 PM |  |  | 17 April 2023 7:00 AM | 2024-01-16 17:00 | 0 | Stone Mason | 100 | 70 | 22 | 98 | 35
15 | 1.1.12.1 | Authority Approvals, (Access Deeds by Client etc (Ultra to assist in coordination) These are qualifying causes of delay resulting in EOT time & costs) | 372 | 17 April 2023 7:00 AM | 1 August 2024 5:00 PM |  |  | 17 April 2023 7:00 AM | 2024-08-04 17:00 | 3 | Scaffolder | 100 | 19 | 24 | 60 | 26
16 | 1.1.12.1.1 | Section 73 - BPA Design & Stormwater Works | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Mechanical | 100 | 85 | 35 | 39 | 22
17 | 1.1.12.1.2 | Rail Approval | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Scaffolder | 100 | 63 | 17 | 5 | 5
18 | 1.1.12.1.3 | CC1 - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  | 25,19 | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Electrician | 100 | 93 | 19 | 7 | 35
19 | 1.1.12.1.4 | CC1a - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM | 18 | 25,20 | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Post Tension | 100 | 60 | 35 | 80 | 46
20 | 1.1.12.1.5 | CC2 - Structure (SoG - Podium) | 120 | 17 April 2023 8:00 AM | 12 September 2023 5:00 PM | 19 | 21 | 17 April 2023 8:00 AM | 2023-09-13 17:00 | 1 | Floor Sealer | 100 | 75 | 15 | 51 | 10
21 | 1.1.12.1.6 | CC3 - Structure (Podium - Roof) + Facade | 156 | 13 September 2023 8:00 AM | 8 April 2024 5:00 PM | 20 | 22 | 13 September 2023 8:00 AM | 2024-04-13 17:00 | 5 | Window | 100 | 13 | 24 | 47 | 16
22 | 1.1.12.1.7 | CC4 - Services & Fit Out | 60 | 9 April 2024 8:00 AM | 20 June 2024 5:00 PM | 21 | 23 | 9 April 2024 8:00 AM | 2024-06-21 17:00 | 1 | Plumber | 100 | 71 | 25 | 85 | 39
23 | 1.1.12.1.8 | CC5 - External Works and Public Domain | 36 | 21 June 2024 8:00 AM | 1 August 2024 5:00 PM | 22 |  | 21 June 2024 8:00 AM | 2024-08-04 17:00 | 3 | Development Manager | 100 | 46 | 24 | 87 | 24
24 | 1.1.12.2 | SITE ESTABLISHMENT | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM |  |  | 26 June 2023 8:00 AM | 2023-06-30 17:00 | 0 | Head Contractor | 100 | 85 | 10 | 99 | 53
25 | 1.1.12.2.1 | Site Establishment, Enviro Protection, Survey Set out & Hoardings | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM | 18,3SS,19 | 28 | 26 June 2023 8:00 AM | 2023-06-30 17:00 | 0 | Painter | 100 | 22 | 30 | 48 | 39
26 | 1.2 | CONSTRUCTION WORKS | 571 | 3 July 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 3 July 2023 7:00 AM | 2025-06-24 17:00 | 1 | Mechanical | 100 | 65 | 11 | 2 | 33
27 | 1.2.1 | EARTHWORKS, PILING - BASEMENT | 234 | 3 July 2023 7:00 AM | 2 May 2024 5:00 PM |  |  | 3 July 2023 7:00 AM | 2024-05-06 17:00 | 4 | Contract Administrator | 100 | 25 | 23 | 51 | 8
28 | 1.2.1.1 | Demolition, Clear & Cut/Level Site | 6 | 3 July 2023 7:00 AM | 8 July 2023 5:00 PM | 25 | 10SS,29SS | 3 July 2023 7:00 AM | 2023-07-08 17:00 | 0 | Plasterboarder | 100 | 22 | 25 | 82 | 58
29 | 1.2.1.2 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | 28 July 2023 8:00 AM | 2023-08-15 17:00 | 0 | Head Contractor | 100 | 26 | 29 | 29 | 19
30 | 1.2.1.3 | Install Piling Matt | 12 | 16 August 2023 8:00 AM | 30 August 2023 5:00 PM | 10,29 | 34FS-6d | 16 August 2023 8:00 AM | 2023-09-03 17:00 | 4 | Tiler | 100 | 11 | 21 | 74 | 41
31 | 1.2.1.4 | Crane Base Ex, Piles & FRP | 8 | 18 December 2023 8:00 AM | 5 January 2024 5:00 PM | 53 | 3442FS+8d | 18 December 2023 8:00 AM | 2024-01-08 17:00 | 3 | Cleaner | 100 | 44 | 29 | 28 | 18
32 | 1.2.1.5 | Piling and Capping Beam | 58 | 28 August 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | 28 August 2023 8:00 AM | 2023-11-13 17:00 | 4 | Concretor | 100 | 14 | 26 | 34 | 47
33 | 1.2.1.5.1 | Buildings A | 28 | 28 August 2023 8:00 AM | 3 October 2023 5:00 PM |  |  | 28 August 2023 8:00 AM | 2023-10-03 17:00 | 0 | Formworker | 100 | 45 | 22 | 36 | 9
34 | 1.2.1.5.1.1 | Perimeter Piling (75 Piles) | 16 | 28 August 2023 8:00 AM | 15 September 2023 5:00 PM | 30FS-6d | 35FS-6d,37,46 | 28 August 2023 8:00 AM | 2023-09-20 17:00 | 5 | Electrician | 100 | 54 | 20 | 97 | 34
35 | 1.2.1.5.1.2 | Capping Beam - Detailed Excavation & FRP | 18 | 9 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34FS-6d |  | 9 September 2023 8:00 AM | 2023-10-06 17:00 | 3 | Metal Work | 100 | 74 | 14 | 48 | 11
36 | 1.2.1.5.2 | Buildings B | 24 | 16 September 2023 8:00 AM | 17 October 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-10-21 17:00 | 4 | Renderer | 100 | 40 | 32 | 55 | 50
37 | 1.2.1.5.2.1 | Perimeter Piling (56 Piles) | 12 | 16 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34 | 38FS-6d,40 | 16 September 2023 8:00 AM | 2023-10-08 17:00 | 5 | Carpenter | 100 | 71 | 11 | 93 | 37
38 | 1.2.1.5.2.2 | Capping Beam - Detailed Excavation & FRP | 18 | 25 September 2023 8:00 AM | 17 October 2023 5:00 PM | 37FS-6d | 56 | 25 September 2023 8:00 AM | 2023-10-22 17:00 | 5 | Development Manager | 100 | 88 | 10 | 11 | 60
39 | 1.2.1.5.3 | Buildings C & D | 30 | 4 October 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | 4 October 2023 8:00 AM | 2023-11-09 17:00 | 0 | Foreman | 100 | 16 | 11 | 37 | 11
40 | 1.2.1.5.3.1 | Foundation Piling (Gnd Lvl) - (17 Piles) | 6 | 4 October 2023 8:00 AM | 10 October 2023 5:00 PM | 37 | 41 | 4 October 2023 8:00 AM | 2023-10-10 17:00 | 0 | Cleaner | 100 | 70 | 34 | 70 | 4
41 | 1.2.1.5.3.2 | Perimeter Piling (82 Piles) | 18 | 11 October 2023 8:00 AM | 1 November 2023 5:00 PM | 40 | 42FS-6d | 11 October 2023 8:00 AM | 2023-11-03 17:00 | 2 | Reinforcement Fixer | 100 | 79 | 19 | 79 | 48
42 | 1.2.1.5.3.3 | Capping Beam - Detailed Excavation & FRP | 12 | 26 October 2023 8:00 AM | 9 November 2023 5:00 PM | 41FS-6d | 66 | 26 October 2023 8:00 AM | 2023-11-10 17:00 | 1 | Excavation | 100 | 30 | 35 | 30 | 58
43 | 1.2.1.6 | Bulk Excavation & Shotcrete | 142 | 16 September 2023 8:00 AM | 22 March 2024 5:00 PM |  |  | 16 September 2023 8:00 AM | 2024-03-22 17:00 | 0 | Reinforcement Fixer | 100 | 32 | 10 | 20 | 3
44 | 1.2.1.6.1 | Building A | 70 | 16 September 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-12-16 17:00 | 0 | Carpet | 100 | 47 | 27 | 11 | 3
45 | 1.2.1.6.1.1 | Excavate - Gnd - B1 | 57 | 16 September 2023 8:00 AM | 28 November 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-11-28 17:00 | 0 | Hoarding | 100 | 31 | 18 | 47 | 57
46 | 1.2.1.6.1.1.1 | Excavation | 21 | 16 September 2023 8:00 AM | 13 October 2023 5:00 PM | 34 | 47,56,51,71 | 16 September 2023 8:00 AM | 2023-10-18 17:00 | 5 | Carpet | 100 | 94 | 28 | 49 | 30
47 | 1.2.1.6.1.1.2 | Installation of Anchors | 8 | 20 October 2023 8:00 AM | 30 October 2023 5:00 PM | 46 | 48,49SS+11d | 20 October 2023 8:00 AM | 2023-11-01 17:00 | 2 | Plumber | 100 | 37 | 26 | 54 | 53
48 | 1.2.1.6.1.1.3 | Install Bracing | 4 | 31 October 2023 8:00 AM | 3 November 2023 5:00 PM | 47 |  | 31 October 2023 8:00 AM | 2023-11-03 17:00 | 0 | Project Manager | 100 | 95 | 14 | 28 | 46
49 | 1.2.1.6.1.1.4 | Shotcrete | 20 | 3 November 2023 8:00 AM | 28 November 2023 5:00 PM | 47SS+11d |  | 3 November 2023 8:00 AM | 2023-11-28 17:00 | 0 | Painter | 100 | 29 | 12 | 72 | 3
50 | 1.2.1.6.1.2 | Excavate - B1-B2 | 44 | 20 October 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | 20 October 2023 8:00 AM | 2023-12-16 17:00 | 0 | Carpet | 100 | 28 | 16 | 21 | 7
51 | 1.2.1.6.1.2.1 | Excavation | 14 | 20 October 2023 8:00 AM | 7 November 2023 5:00 PM | 46 | 52,53,56,71 | 20 October 2023 8:00 AM | 2023-11-10 17:00 | 3 | Electrician | 100 | 77 | 15 | 71 | 59
52 | 1.2.1.6.1.2.2 | Shotcrete | 16 | 15 November 2023 8:00 AM | 7 December 2023 5:00 PM | 51 | 53 | 15 November 2023 8:00 AM | 2023-12-12 17:00 | 5 | Fire | 100 | 45 | 28 | 74 | 4
53 | 1.2.1.6.1.2.3 | Foundation Piling (Basement 2 Lvl) - (35 Piles) | 8 | 8 December 2023 8:00 AM | 16 December 2023 5:00 PM | 51,52 | 63,31 | 8 December 2023 8:00 AM | 2023-12-16 17:00 | 0 | Formworker | 100 | 71 | 27 | 59 | 40
54 | 1.2.1.6.2 | Building B | 66 | 15 November 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | 15 November 2023 8:00 AM | 2024-02-16 17:00 | 0 | Site Manager | 100 | 77 | 28 | 81 | 47
55 | 1.2.1.6.2.1 | Excavate - Gnd - B1 | 46 | 15 November 2023 8:00 AM | 22 January 2024 5:00 PM |  |  | 15 November 2023 8:00 AM | 2024-01-26 17:00 | 4 | Plumber | 100 | 34 | 23 | 60 | 57
56 | 1.2.1.6.2.1.1 | Excavation | 22 | 15 November 2023 8:00 AM | 14 December 2023 5:00 PM | 38,46,51 | 57,59,61,71 | 15 November 2023 8:00 AM | 2023-12-16 17:00 | 2 | Excavation | 100 | 69 | 18 | 68 | 16
57 | 1.2.1.6.2.1.2 | Installation of Anchors | 8 | 20 December 2023 8:00 AM | 8 January 2024 5:00 PM | 56 | 58 | 20 December 2023 8:00 AM | 2024-01-09 17:00 | 1 | Cleaner | 100 | 62 | 31 | 70 | 45
58 | 1.2.1.6.2.1.3 | Install Bracing | 4 | 9 January 2024 8:00 AM | 12 January 2024 5:00 PM | 57 | 59 | 9 January 2024 8:00 AM | 2024-01-12 17:00 | 0 | Head Contractor | 100 | 21 | 14 | 72 | 38
59 | 1.2.1.6.2.1.4 | Shotcrete | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,58 | 61 | 20 December 2023 8:00 AM | 2024-01-23 17:00 | 1 | Floor Sealer | 100 | 52 | 13 | 62 | 23
60 | 1.2.1.6.2.2 | Excavate - B1-B2 | 40 | 20 December 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | 20 December 2023 8:00 AM | 2024-02-20 17:00 | 4 | Fire | 100 | 61 | 24 | 64 | 15
61 | 1.2.1.6.2.2.1 | Excavation | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,59 | 66,63,71,62 | 20 December 2023 8:00 AM | 2024-01-27 17:00 | 5 | Metal Work | 100 | 66 | 19 | 85 | 18
62 | 1.2.1.6.2.2.2 | Shotcrete | 10 | 1 February 2024 8:00 AM | 12 February 2024 5:00 PM | 61 | 63 | 1 February 2024 8:00 AM | 2024-02-12 17:00 | 0 | Contract Administrator | 100 | 56 | 26 | 17 | 44
63 | 1.2.1.6.2.2.3 | Foundation Piling (Basement 2 Lvl) - (23 Piles) | 4 | 13 February 2024 8:00 AM | 16 February 2024 5:00 PM | 61,53,62 | 74 | 13 February 2024 8:00 AM | 2024-02-16 17:00 | 0 | Stone Mason | 100 | 88 | 13 | 37 | 14
64 | 1.2.1.6.3 | Buildings C & D | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | 23 January 2024 8:00 AM | 2024-03-22 17:00 | 0 | Mechanical | 100 | 61 | 21 | 14 | 43
65 | 1.2.1.6.3.1 | Excavate - Gnd - B2 | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | 23 January 2024 8:00 AM | 2024-03-27 17:00 | 5 | Foreman | 100 | 20 | 13 | 44 | 37
66 | 1.2.1.6.3.1.1 | Excavation | 30 | 23 January 2024 8:00 AM | 28 February 2024 5:00 PM | 42,61 | 67,71 | 23 January 2024 8:00 AM | 2024-03-01 17:00 | 2 | Plumber | 100 | 61 | 32 | 20 | 2
67 | 1.2.1.6.3.1.2 | Installation of Anchors | 8 | 29 February 2024 8:00 AM | 8 March 2024 5:00 PM | 66 | 68 | 29 February 2024 8:00 AM | 2024-03-08 17:00 | 0 | Site Manager | 100 | 84 | 28 | 71 | 35
68 | 1.2.1.6.3.1.3 | Install Bracing | 4 | 9 March 2024 8:00 AM | 13 March 2024 5:00 PM | 67 | 69 | 9 March 2024 8:00 AM | 2024-03-13 17:00 | 0 | Fire | 100 | 64 | 12 | 34 | 26
69 | 1.2.1.6.3.1.4 | Shotcrete | 6 | 14 March 2024 8:00 AM | 20 March 2024 5:00 PM | 68 | 70,84 | 14 March 2024 8:00 AM | 2024-03-20 17:00 | 0 | Contract Administrator | 100 | 83 | 31 | 66 | 32
70 | 1.2.1.6.3.1.5 | Foundation Piling (Basement 2 Lvl) - (5 Piles) | 2 | 21 March 2024 8:00 AM | 22 March 2024 5:00 PM | 69 | 86 | 21 March 2024 8:00 AM | 2024-03-22 17:00 | 0 | Mechanical | 100 | 46 | 14 | 21 | 20
71 | 1.2.1.6.4 | Complete Bulk Exacavation | 0 | 28 February 2024 5:00 PM | 28 February 2024 5:00 PM | 46,51,56,61,66 |  | 28 February 2024 5:00 PM | 2024-02-28 17:00 | 0 | Admin | 100 | 78 | 19 | 72 | 21
72 | 1.2.1.7 | Detail Excavation, Services & Base course | 61 | 17 February 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | 17 February 2024 8:00 AM | 2024-05-07 17:00 | 5 | Window | 100 | 97 | 11 | 6 | 28
73 | 1.2.1.7.1 | Stage 1 (Building A) | 32 | 17 February 2024 8:00 AM | 25 March 2024 5:00 PM |  |  | 17 February 2024 8:00 AM | 2024-03-29 17:00 | 4 | Concretor | 100 | 46 | 20 | 55 | 55
74 | 1.2.1.7.1.1 | Detailed Excavation | 11 | 17 February 2024 8:00 AM | 29 February 2024 5:00 PM | 63 | 75,79 | 17 February 2024 8:00 AM | 2024-03-02 17:00 | 2 | Formworker | 100 | 63 | 10 | 29 | 2
75 | 1.2.1.7.1.2 | In-Ground Services | 8 | 1 March 2024 8:00 AM | 9 March 2024 5:00 PM | 74 | 76 | 1 March 2024 8:00 AM | 2024-03-12 17:00 | 3 | Plumber | 100 | 63 | 27 | 4 | 44
76 | 1.2.1.7.1.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 11 March 2024 8:00 AM | 15 March 2024 5:00 PM | 75 | 77 | 11 March 2024 8:00 AM | 2024-03-15 17:00 | 0 | Foreman | 100 | 66 | 35 | 9 | 4
77 | 1.2.1.7.1.4 | Base Course to Basement | 8 | 16 March 2024 8:00 AM | 25 March 2024 5:00 PM | 76 | 88 | 16 March 2024 8:00 AM | 2024-03-25 17:00 | 0 | Metal Work | 100 | 99 | 31 | 70 | 35
78 | 1.2.1.7.2 | Stage 2 (Building B) | 32 | 1 March 2024 8:00 AM | 10 April 2024 5:00 PM |  |  | 1 March 2024 8:00 AM | 2024-04-15 17:00 | 5 | Reinforcement Fixer | 100 | 81 | 25 | 57 | 46
79 | 1.2.1.7.2.1 | Detailed Excavation | 12 | 1 March 2024 8:00 AM | 14 March 2024 5:00 PM | 74 | 80 | 1 March 2024 8:00 AM | 2024-03-17 17:00 | 3 | Surveyor | 100 | 75 | 13 | 36 | 59
80 | 1.2.1.7.2.2 | In-Ground Services | 9 | 15 March 2024 8:00 AM | 25 March 2024 5:00 PM | 79 | 81 | 15 March 2024 8:00 AM | 2024-03-27 17:00 | 2 | Surveyor | 100 | 57 | 16 | 68 | 31
81 | 1.2.1.7.2.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 6 | 26 March 2024 8:00 AM | 4 April 2024 5:00 PM | 80 | 82 | 26 March 2024 8:00 AM | 2024-04-05 17:00 | 1 | Metal Work | 100 | 84 | 33 | 87 | 55
82 | 1.2.1.7.2.4 | Base Course to Basement | 5 | 5 April 2024 8:00 AM | 10 April 2024 5:00 PM | 81 | 93 | 5 April 2024 8:00 AM | 2024-04-10 17:00 | 0 | Window | 100 | 74 | 23 | 47 | 26
83 | 1.2.1.7.3 | Stage 3 (Buildings C&D) | 33 | 21 March 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | 21 March 2024 8:00 AM | 2024-05-03 17:00 | 1 | Development Manager | 100 | 58 | 16 | 40 | 18
84 | 1.2.1.7.3.1 | Detailed Excavation | 12 | 21 March 2024 8:00 AM | 6 April 2024 5:00 PM | 69 | 85 | 21 March 2024 8:00 AM | 2024-04-09 17:00 | 3 | Floor Sealer | 100 | 83 | 24 | 55 | 42
85 | 1.2.1.7.3.2 | In-Ground Services | 8 | 8 April 2024 8:00 AM | 16 April 2024 5:00 PM | 84 | 86 | 8 April 2024 8:00 AM | 2024-04-16 17:00 | 0 | Carpenter | 100 | 49 | 29 | 96 | 44
86 | 1.2.1.7.3.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 17 April 2024 8:00 AM | 22 April 2024 5:00 PM | 85,70 | 87 | 17 April 2024 8:00 AM | 2024-04-22 17:00 | 0 | Line Market | 100 | 56 | 21 | 86 | 21
87 | 1.2.1.7.3.4 | Base Course to Basement | 8 | 23 April 2024 8:00 AM | 2 May 2024 5:00 PM | 86 | 88 | 23 April 2024 8:00 AM | 2024-05-04 17:00 | 2 | Painter | 100 | 69 | 24 | 95 | 20
88 | 1.2.1.7.4 | Basement Earthworks and Piling Complete | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 87,77 | 122,4 | 2 May 2024 5:00 PM | 2024-05-02 17:00 | 0 | Concretor | 100 | 33 | 29 | 65 | 33
89 | 1.2.2 | STRUCTURE WORKS | 217 | 11 April 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 11 April 2024 8:00 AM | 2025-01-04 17:00 | 1 | Metal Work | 100 | 93 | 29 | 22 | 38
90 | 1.2.2.1 | CC2 - Basement to Podium L1 - A, B, C, D | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  |  | 11 April 2024 8:00 AM | 2024-10-04 17:00 | 4 | Line Market | 100 | 70 | 28 | 43 | 3
91 | 1.2.2.1.1 | Basement to Podium (Level 1 - A & B ) | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | 11 April 2024 8:00 AM | 2024-10-01 17:00 | 1 | Development Manager | 100 | 91 | 25 | 80 | 35
92 | 1.2.2.1.1.1 | Basement 2 - FRP - SoG | 23 | 11 April 2024 8:00 AM | 8 May 2024 5:00 PM |  |  | 11 April 2024 8:00 AM | 2024-05-11 17:00 | 3 | Cleaner | 100 | 34 | 10 | 40 | 32
93 | 1.2.2.1.1.1.1 | Reinforcement Fix | 13 | 11 April 2024 8:00 AM | 26 April 2024 5:00 PM | 82 | 94 | 11 April 2024 8:00 AM | 2024-04-27 17:00 | 1 | Plumber | 100 | 37 | 26 | 87 | 37
94 | 1.2.2.1.1.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 9 | 27 April 2024 8:00 AM | 7 May 2024 5:00 PM | 93 | 95 | 27 April 2024 8:00 AM | 2024-05-07 17:00 | 0 | Stone Mason | 100 | 60 | 20 | 3 | 24
95 | 1.2.2.1.1.1.3 | Pour | 1 | 8 May 2024 8:00 AM | 8 May 2024 5:00 PM | 94 | 97 | 8 May 2024 8:00 AM | 2024-05-08 17:00 | 0 | Landscaper | 100 | 98 | 22 | 82 | 45
96 | 1.2.2.1.1.2 | Basement 1 - FRP - Suspended Slab | 25 | 9 May 2024 8:00 AM | 6 June 2024 5:00 PM |  |  | 9 May 2024 8:00 AM | 2024-06-07 17:00 | 1 | Hoarding | 100 | 75 | 17 | 82 | 59
97 | 1.2.2.1.1.2.1 | Scaffold Stair Removal/Adjustment | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 95 | 98SS | 9 May 2024 8:00 AM | 2024-05-10 17:00 | 0 | Subcontractor | 100 | 51 | 34 | 11 | 7
98 | 1.2.2.1.1.2.2 | Setout and Install Lift/Stair Formwork | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 97SS | 99 | 9 May 2024 8:00 AM | 2024-05-10 17:00 | 0 | Plasterboarder | 100 | 96 | 21 | 14 | 41
99 | 1.2.2.1.1.2.3 | Formworker setout, drop material and 80% Deck | 9 | 11 May 2024 8:00 AM | 21 May 2024 5:00 PM | 98 | 100FS-1d,101 | 11 May 2024 8:00 AM | 2024-05-21 17:00 | 0 | Formworker | 100 | 12 | 19 | 62 | 33
100 | 1.2.2.1.1.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 21 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99FS-1d | 102,103 | 21 May 2024 8:00 AM | 2024-05-24 17:00 | 0 | Plumber | 100 | 10 | 19 | 40 | 37
101 | 1.2.2.1.1.2.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 22 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99 |  | 22 May 2024 8:00 AM | 2024-05-24 17:00 | 0 | Painter | 100 | 61 | 13 | 13 | 59
102 | 1.2.2.1.1.2.6 | Services | 4 | 25 May 2024 8:00 AM | 29 May 2024 5:00 PM | 100 | 104FS-1d | 25 May 2024 8:00 AM | 2024-05-29 17:00 | 0 | Reinforcement Fixer | 100 | 88 | 28 | 69 | 29
103 | 1.2.2.1.1.2.7 | Post Tension | 3 | 25 May 2024 8:00 AM | 28 May 2024 5:00 PM | 100 | 104FS-1d | 25 May 2024 8:00 AM | 2024-05-28 17:00 | 0 | Plasterboarder | 100 | 79 | 33 | 69 | 19
104 | 1.2.2.1.1.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 29 May 2024 8:00 AM | 31 May 2024 5:00 PM | 102FS-1d,103FS-1d | 105 | 29 May 2024 8:00 AM | 2024-05-31 17:00 | 0 | Admin | 100 | 45 | 32 | 46 | 47
105 | 1.2.2.1.1.2.9 | Formworker setdowns and edge boards | 4 | 1 June 2024 8:00 AM | 5 June 2024 5:00 PM | 104 | 106 | 1 June 2024 8:00 AM | 2024-06-05 17:00 | 0 | Window | 100 | 27 | 12 | 89 | 21
106 | 1.2.2.1.1.2.10 | Pour | 1 | 6 June 2024 8:00 AM | 6 June 2024 5:00 PM | 105 | 109 | 6 June 2024 8:00 AM | 2024-06-06 17:00 | 0 | Mechanical | 100 | 99 | 23 | 73 | 48
107 | 1.2.2.1.1.3 | Strip Formwork - Basement 1 | 5 | 7 September 2024 8:00 AM | 12 September 2024 5:00 PM | 161FS+5d | 522 | 7 September 2024 8:00 AM | 2024-09-12 17:00 | 0 | Contract Administrator | 100 | 99 | 26 | 5 | 2
108 | 1.2.2.1.1.4 | Lvl 1 - FRP - Suspended Slab | 28 | 7 June 2024 8:00 AM | 11 July 2024 5:00 PM |  |  | 7 June 2024 8:00 AM | 2024-07-14 17:00 | 3 | Plasterboarder | 100 | 26 | 32 | 4 | 10
109 | 1.2.2.1.1.4.1 | Scaffold Stair Removal/Adjustment | 1 | 7 June 2024 8:00 AM | 7 June 2024 5:00 PM | 106 | 110SS | 7 June 2024 8:00 AM | 2024-06-07 17:00 | 0 | Surveyor | 100 | 68 | 27 | 6 | 52
110 | 1.2.2.1.1.4.2 | Setout and Install Lift/Stair Formwork | 3 | 7 June 2024 8:00 AM | 12 June 2024 5:00 PM | 109SS | 111 | 7 June 2024 8:00 AM | 2024-06-12 17:00 | 0 | Metal Work | 100 | 36 | 18 | 80 | 49
111 | 1.2.2.1.1.4.3 | Formworker setout, drop material and 80% Deck | 10 | 13 June 2024 8:00 AM | 24 June 2024 5:00 PM | 110 | 112FS-1d,113,128 | 13 June 2024 8:00 AM | 2024-06-24 17:00 | 0 | Project Manager | 100 | 24 | 10 | 65 | 53
112 | 1.2.2.1.1.4.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 6 | 24 June 2024 8:00 AM | 29 June 2024 5:00 PM | 111FS-1d | 114,115 | 24 June 2024 8:00 AM | 2024-06-29 17:00 | 0 | Renderer | 100 | 24 | 12 | 4 | 18
113 | 1.2.2.1.1.4.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 25 June 2024 8:00 AM | 28 June 2024 5:00 PM | 111 | 118 | 25 June 2024 8:00 AM | 2024-06-28 17:00 | 0 | Tiler | 100 | 77 | 13 | 3 | 4
114 | 1.2.2.1.1.4.6 | Services | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 112 | 116FS-1d | 1 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Carpet | 100 | 45 | 11 | 23 | 33
115 | 1.2.2.1.1.4.7 | Post Tension | 4 | 1 July 2024 8:00 AM | 4 July 2024 5:00 PM | 112 | 116FS-1d | 1 July 2024 8:00 AM | 2024-07-04 17:00 | 0 | Reinforcement Fixer | 100 | 69 | 14 | 14 | 45
116 | 1.2.2.1.1.4.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 114FS-1d,115FS-1d | 117,401FS+5d | 4 July 2024 8:00 AM | 2024-07-06 17:00 | 0 | Carpet | 100 | 54 | 32 | 56 | 47
117 | 1.2.2.1.1.4.9 | Formworker setdowns and edge boards | 3 | 8 July 2024 8:00 AM | 10 July 2024 5:00 PM | 116 | 118 | 8 July 2024 8:00 AM | 2024-07-10 17:00 | 0 | Carpenter | 100 | 47 | 27 | 60 | 5
118 | 1.2.2.1.1.4.10 | Pour | 1 | 11 July 2024 8:00 AM | 11 July 2024 5:00 PM | 117,113 | 140 | 11 July 2024 8:00 AM | 2024-07-11 17:00 | 0 | Carpet | 100 | 52 | 13 | 56 | 16
119 | 1.2.2.1.1.5 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d | 535 | 25 September 2024 8:00 AM | 2024-09-30 17:00 | 0 | Painter | 100 | 99 | 22 | 40 | 25
120 | 1.2.2.1.2 | Basement to Podium (Level 1 - C & D) | 127 | 3 May 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | 3 May 2024 8:00 AM | 2024-10-03 17:00 | 3 | Concretor | 100 | 80 | 34 | 63 | 14
121 | 1.2.2.1.2.1 | Basement 2 - FRP - SoG | 12 | 3 May 2024 8:00 AM | 16 May 2024 5:00 PM |  |  | 3 May 2024 8:00 AM | 2024-05-19 17:00 | 3 | Subcontractor | 100 | 28 | 23 | 64 | 48
122 | 1.2.2.1.2.1.1 | Reinforcement Fix | 6 | 3 May 2024 8:00 AM | 9 May 2024 5:00 PM | 88 | 123 | 3 May 2024 8:00 AM | 2024-05-09 17:00 | 0 | Cleaner | 100 | 44 | 26 | 11 | 5
123 | 1.2.2.1.2.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 5 | 10 May 2024 8:00 AM | 15 May 2024 5:00 PM | 122 | 124 | 10 May 2024 8:00 AM | 2024-05-15 17:00 | 0 | Line Market | 100 | 53 | 21 | 24 | 48
124 | 1.2.2.1.2.1.3 | Pour | 1 | 16 May 2024 8:00 AM | 16 May 2024 5:00 PM | 123 | 126 | 16 May 2024 8:00 AM | 2024-05-16 17:00 | 0 | Stone Mason | 100 | 39 | 27 | 43 | 48
125 | 1.2.2.1.2.2 | Lvl 1 - FRP - Suspended Slab | 48 | 17 May 2024 8:00 AM | 13 July 2024 5:00 PM |  |  | 17 May 2024 8:00 AM | 2024-07-13 17:00 | 0 | Plasterboarder | 100 | 18 | 25 | 20 | 29
126 | 1.2.2.1.2.2.1 | Scaffold Stair Removal/Adjustment | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 124 | 127SS | 17 May 2024 8:00 AM | 2024-05-17 17:00 | 0 | Foreman | 100 | 82 | 25 | 6 | 25
127 | 1.2.2.1.2.2.2 | Setout and Install Lift/Stair Formwork | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 126SS | 128 | 17 May 2024 8:00 AM | 2024-05-17 17:00 | 0 | Plasterboarder | 100 | 82 | 10 | 14 | 31
128 | 1.2.2.1.2.2.3 | Formworker setout, drop material and 80% Deck | 6 | 25 June 2024 8:00 AM | 1 July 2024 5:00 PM | 127,111 | 129FS-1d,130 | 25 June 2024 8:00 AM | 2024-07-01 17:00 | 0 | Electrician | 100 | 13 | 32 | 94 | 17
129 | 1.2.2.1.2.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128FS-1d | 131,132 | 1 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Project Manager | 100 | 63 | 18 | 49 | 36
130 | 1.2.2.1.2.2.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128 |  | 2 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Waterproofer | 100 | 37 | 23 | 9 | 37
131 | 1.2.2.1.2.2.6 | Services | 2 | 4 July 2024 8:00 AM | 5 July 2024 5:00 PM | 129 | 133FS-1d | 4 July 2024 8:00 AM | 2024-07-05 17:00 | 0 | Window | 100 | 26 | 32 | 43 | 18
132 | 1.2.2.1.2.2.7 | Post Tension | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 129 | 133FS-1d | 4 July 2024 8:00 AM | 2024-07-06 17:00 | 0 | Line Market | 100 | 31 | 29 | 60 | 39
133 | 1.2.2.1.2.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 6 July 2024 8:00 AM | 9 July 2024 5:00 PM | 131FS-1d,132FS-1d | 134 | 6 July 2024 8:00 AM | 2024-07-09 17:00 | 0 | Line Market | 100 | 24 | 13 | 97 | 51
134 | 1.2.2.1.2.2.9 | Formworker setdowns and edge boards | 3 | 10 July 2024 8:00 AM | 12 July 2024 5:00 PM | 133 | 135 | 10 July 2024 8:00 AM | 2024-07-12 17:00 | 0 | Concretor | 100 | 76 | 31 | 78 | 40
135 | 1.2.2.1.2.2.10 | Pour | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 134 | 309,233 | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Cleaner | 100 | 60 | 25 | 97 | 51
136 | 1.2.2.1.2.3 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d |  | 25 September 2024 8:00 AM | 2024-09-30 17:00 | 0 | Mechanical | 100 | 87 | 20 | 70 | 35
137 | 1.2.2.2 | CC3 - Remainder of Structure | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 12 July 2024 8:00 AM | 2025-01-06 17:00 | 3 | Head Contractor | 100 | 11 | 12 | 74 | 43
138 | 1.2.2.2.1 | Building A | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | 12 July 2024 8:00 AM | 2025-01-07 17:00 | 4 | Landscaper | 100 | 73 | 35 | 83 | 56
139 | 1.2.2.2.1.1 | Lvl 2 - FRP - Suspended Slab | 26 | 12 July 2024 8:00 AM | 10 August 2024 5:00 PM |  |  | 12 July 2024 8:00 AM | 2024-08-14 17:00 | 4 | Reinforcement Fixer | 100 | 12 | 14 | 16 | 47
140 | 1.2.2.2.1.1.1 | Scaffold Perimeter Protection | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 118 | 141SS | 12 July 2024 8:00 AM | 2024-07-16 17:00 | 0 | Tiler | 100 | 71 | 20 | 3 | 30
141 | 1.2.2.2.1.1.2 | Setout and Install Lift/Stair Formwork | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 140SS | 142 | 12 July 2024 8:00 AM | 2024-07-16 17:00 | 0 | Reinforcement Fixer | 100 | 14 | 28 | 59 | 28
142 | 1.2.2.2.1.1.3 | Formworker setout, drop material and 80% Deck | 6 | 17 July 2024 8:00 AM | 23 July 2024 5:00 PM | 141 | 143FS-1d,144 | 17 July 2024 8:00 AM | 2024-07-23 17:00 | 0 | Painter | 100 | 95 | 28 | 48 | 32
143 | 1.2.2.2.1.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 23 July 2024 8:00 AM | 26 July 2024 5:00 PM | 142FS-1d | 145,146 | 23 July 2024 8:00 AM | 2024-07-26 17:00 | 0 | Window | 100 | 44 | 17 | 30 | 18
144 | 1.2.2.2.1.1.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 24 July 2024 8:00 AM | 27 July 2024 5:00 PM | 142 | 146 | 24 July 2024 8:00 AM | 2024-07-27 17:00 | 0 | Post Tension | 100 | 33 | 15 | 46 | 15
145 | 1.2.2.2.1.1.6 | Services | 3 | 27 July 2024 8:00 AM | 30 July 2024 5:00 PM | 143 | 147FS-1d | 27 July 2024 8:00 AM | 2024-07-30 17:00 | 0 | Painter | 100 | 53 | 18 | 21 | 10
146 | 1.2.2.2.1.1.7 | Post Tension | 3 | 29 July 2024 8:00 AM | 31 July 2024 5:00 PM | 143,144 | 147FS-1d | 29 July 2024 8:00 AM | 2024-07-31 17:00 | 0 | Window | 100 | 84 | 29 | 22 | 37
147 | 1.2.2.2.1.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 5 | 31 July 2024 8:00 AM | 5 August 2024 5:00 PM | 145FS-1d,146FS-1d | 148 | 31 July 2024 8:00 AM | 2024-08-05 17:00 | 0 | Foreman | 100 | 72 | 23 | 63 | 47
148 | 1.2.2.2.1.1.9 | Formworker setdowns and edge boards | 4 | 6 August 2024 8:00 AM | 9 August 2024 5:00 PM | 147 | 149 | 6 August 2024 8:00 AM | 2024-08-09 17:00 | 0 | Excavation | 100 | 16 | 12 | 86 | 43
149 | 1.2.2.2.1.1.10 | Pour | 1 | 10 August 2024 8:00 AM | 10 August 2024 5:00 PM | 148 | 152,407FS+5d | 10 August 2024 8:00 AM | 2024-08-10 17:00 | 0 | Fire | 100 | 26 | 31 | 7 | 44
150 | 1.2.2.2.1.2 | Strip Formwork - Lvl 2 | 5 | 15 October 2024 8:00 AM | 19 October 2024 5:00 PM | 185FS+5d | 577,550,409FS-10d | 15 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Window | 100 | 21 | 32 | 33 | 50
151 | 1.2.2.2.1.3 | Lvl 3 - FRP - Suspended Slab | 18 | 12 August 2024 8:00 AM | 31 August 2024 5:00 PM |  |  | 12 August 2024 8:00 AM | 2024-09-03 17:00 | 3 | Hoarding | 100 | 54 | 21 | 84 | 43
152 | 1.2.2.2.1.3.1 | Scaffold Perimeter Protection | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 149 | 153SS | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 0 | Project Manager | 100 | 73 | 26 | 14 | 53
153 | 1.2.2.2.1.3.2 | Setout and Install Lift/Stair Formwork | 1 | 12 August 2024 8:00 AM | 12 August 2024 5:00 PM | 152SS | 154 | 12 August 2024 8:00 AM | 2024-08-12 17:00 | 0 | Waterproofer | 100 | 58 | 15 | 65 | 49
154 | 1.2.2.2.1.3.3 | Formworker setout, drop material and 80% Deck | 6 | 13 August 2024 8:00 AM | 19 August 2024 5:00 PM | 153 | 155FS-1d,156 | 13 August 2024 8:00 AM | 2024-08-19 17:00 | 0 | Formworker | 100 | 67 | 27 | 20 | 11
155 | 1.2.2.2.1.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 19 August 2024 8:00 AM | 22 August 2024 5:00 PM | 154FS-1d | 157,158 | 19 August 2024 8:00 AM | 2024-08-22 17:00 | 0 | Tiler | 100 | 53 | 28 | 80 | 13
156 | 1.2.2.2.1.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 August 2024 8:00 AM | 21 August 2024 5:00 PM | 154 |  | 20 August 2024 8:00 AM | 2024-08-21 17:00 | 0 | Hoarding | 100 | 21 | 13 | 70 | 55
157 | 1.2.2.2.1.3.6 | Services | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | 23 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Mechanical | 100 | 92 | 26 | 26 | 24
158 | 1.2.2.2.1.3.7 | Post Tension | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | 23 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Development Manager | 100 | 15 | 22 | 3 | 14
159 | 1.2.2.2.1.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 24 August 2024 8:00 AM | 27 August 2024 5:00 PM | 157FS-1d,158FS-1d | 160 | 24 August 2024 8:00 AM | 2024-08-27 17:00 | 0 | Cleaner | 100 | 66 | 20 | 3 | 40
160 | 1.2.2.2.1.3.9 | Formworker setdowns and edge boards | 3 | 28 August 2024 8:00 AM | 30 August 2024 5:00 PM | 159 | 161 | 28 August 2024 8:00 AM | 2024-08-30 17:00 | 0 | Electrician | 100 | 93 | 10 | 18 | 18
161 | 1.2.2.2.1.3.10 | Pour | 1 | 31 August 2024 8:00 AM | 31 August 2024 5:00 PM | 160 | 164,3445,107FS+5d | 31 August 2024 8:00 AM | 2024-08-31 17:00 | 0 | Floor Sealer | 100 | 31 | 34 | 93 | 35
162 | 1.2.2.2.1.4 | Strip Formwork - Lvl 3 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d |  | 19 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Timber Floorer | 100 | 39 | 21 | 97 | 12
163 | 1.2.2.2.1.5 | Lvl 4 - FRP - Suspended Slab | 15 | 2 September 2024 8:00 AM | 18 September 2024 5:00 PM |  |  | 2 September 2024 8:00 AM | 2024-09-19 17:00 | 1 | Window | 100 | 68 | 18 | 31 | 45
164 | 1.2.2.2.1.5.1 | Scaffold Perimeter Protection | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 161 | 165SS | 2 September 2024 8:00 AM | 2024-09-02 17:00 | 0 | Joiner | 100 | 10 | 20 | 38 | 32
165 | 1.2.2.2.1.5.2 | Setout and Install Lift/Stair Formwork | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 164SS | 166FS-1d | 2 September 2024 8:00 AM | 2024-09-02 17:00 | 0 | Foreman | 100 | 66 | 15 | 38 | 18
166 | 1.2.2.2.1.5.3 | Formworker setout, drop material and 80% Deck | 6 | 2 September 2024 8:00 AM | 7 September 2024 5:00 PM | 165FS-1d | 167FS-1d,168 | 2 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Head Contractor | 100 | 58 | 28 | 78 | 49
167 | 1.2.2.2.1.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 7 September 2024 8:00 AM | 11 September 2024 5:00 PM | 166FS-1d | 169,170 | 7 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Landscaper | 100 | 76 | 13 | 63 | 35
168 | 1.2.2.2.1.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 9 September 2024 8:00 AM | 10 September 2024 5:00 PM | 166 |  | 9 September 2024 8:00 AM | 2024-09-10 17:00 | 0 | Timber Floorer | 100 | 98 | 12 | 53 | 38
169 | 1.2.2.2.1.5.6 | Services | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | 12 September 2024 8:00 AM | 2024-09-13 17:00 | 0 | Surveyor | 100 | 17 | 11 | 21 | 54
170 | 1.2.2.2.1.5.7 | Post Tension | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | 12 September 2024 8:00 AM | 2024-09-13 17:00 | 0 | Reinforcement Fixer | 100 | 25 | 20 | 49 | 38
171 | 1.2.2.2.1.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 13 September 2024 8:00 AM | 14 September 2024 5:00 PM | 169FS-1d,170FS-1d | 172 | 13 September 2024 8:00 AM | 2024-09-14 17:00 | 0 | Fire | 100 | 35 | 30 | 29 | 49
172 | 1.2.2.2.1.5.9 | Formworker setdowns and edge boards | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 171 | 173 | 16 September 2024 8:00 AM | 2024-09-17 17:00 | 0 | Floor Sealer | 100 | 27 | 30 | 28 | 15
173 | 1.2.2.2.1.5.10 | Pour | 1 | 18 September 2024 8:00 AM | 18 September 2024 5:00 PM | 172 | 176,119FS+5d,136FS+5d | 18 September 2024 8:00 AM | 2024-09-18 17:00 | 0 | Surveyor | 100 | 57 | 28 | 17 | 22
174 | 1.2.2.2.1.6 | Strip Formwork - Lvl 4 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d | 413FS+5d,604,415FS-10d | 19 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Window | 100 | 35 | 12 | 75 | 30
175 | 1.2.2.2.1.7 | Lvl 5 - FRP - Suspended Slab | 15 | 19 September 2024 8:00 AM | 8 October 2024 5:00 PM |  |  | 19 September 2024 8:00 AM | 2024-10-11 17:00 | 3 | Site Manager | 100 | 26 | 15 | 40 | 9
176 | 1.2.2.2.1.7.1 | Scaffold Perimeter Protection | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 173 | 177SS | 19 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Joiner | 100 | 73 | 35 | 64 | 7
177 | 1.2.2.2.1.7.2 | Setout and Install Lift/Stair Formwork | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 176SS | 178FS-1d | 19 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Tiler | 100 | 57 | 35 | 77 | 60
178 | 1.2.2.2.1.7.3 | Formworker setout, drop material and 80% Deck | 6 | 19 September 2024 8:00 AM | 25 September 2024 5:00 PM | 177FS-1d | 179FS-1d,180 | 19 September 2024 8:00 AM | 2024-09-25 17:00 | 0 | Post Tension | 100 | 69 | 28 | 4 | 37
179 | 1.2.2.2.1.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 25 September 2024 8:00 AM | 28 September 2024 5:00 PM | 178FS-1d | 181,182 | 25 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Tiler | 100 | 82 | 23 | 80 | 49
180 | 1.2.2.2.1.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 26 September 2024 8:00 AM | 27 September 2024 5:00 PM | 178 |  | 26 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Floor Sealer | 100 | 20 | 20 | 13 | 34
181 | 1.2.2.2.1.7.6 | Services | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | 30 September 2024 8:00 AM | 2024-10-01 17:00 | 0 | Landscaper | 100 | 68 | 32 | 14 | 18
182 | 1.2.2.2.1.7.7 | Post Tension | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | 30 September 2024 8:00 AM | 2024-10-01 17:00 | 0 | Electrician | 100 | 47 | 25 | 79 | 6
183 | 1.2.2.2.1.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 1 October 2024 8:00 AM | 2 October 2024 5:00 PM | 181FS-1d,182FS-1d | 184 | 1 October 2024 8:00 AM | 2024-10-02 17:00 | 0 | Painter | 100 | 57 | 35 | 71 | 3
184 | 1.2.2.2.1.7.9 | Formworker setdowns and edge boards | 2 | 3 October 2024 8:00 AM | 4 October 2024 5:00 PM | 183 | 185 | 3 October 2024 8:00 AM | 2024-10-04 17:00 | 0 | Concretor | 100 | 44 | 21 | 46 | 43
185 | 1.2.2.2.1.7.10 | Pour | 1 | 8 October 2024 8:00 AM | 8 October 2024 5:00 PM | 184 | 188,150FS+5d | 8 October 2024 8:00 AM | 2024-10-08 17:00 | 0 | Subcontractor | 100 | 40 | 28 | 7 | 21
186 | 1.2.2.2.1.8 | Strip Formwork - Lvl 5 | 5 | 5 December 2024 8:00 AM | 10 December 2024 5:00 PM | 221FS+5d | 631,421FS-10d,419FS+5d | 5 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Carpet | 100 | 89 | 33 | 25 | 12
187 | 1.2.2.2.1.9 | Lvl 6 - FRP - Suspended Slab | 15 | 9 October 2024 8:00 AM | 25 October 2024 5:00 PM |  |  | 9 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Carpet | 100 | 76 | 24 | 22 | 41
188 | 1.2.2.2.1.9.1 | Scaffold Perimeter Protection | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 185 | 189SS | 9 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Contract Administrator | 100 | 80 | 11 | 28 | 60
189 | 1.2.2.2.1.9.2 | Setout and Install Lift/Stair Formwork | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 188SS | 190FS-1d | 9 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Mechanical | 100 | 34 | 19 | 68 | 34
190 | 1.2.2.2.1.9.3 | Formworker setout, drop material and 80% Deck | 6 | 9 October 2024 8:00 AM | 15 October 2024 5:00 PM | 189FS-1d | 191FS-1d,192 | 9 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Concretor | 100 | 84 | 24 | 74 | 20
191 | 1.2.2.2.1.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 October 2024 8:00 AM | 18 October 2024 5:00 PM | 190FS-1d | 193,194 | 15 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Carpenter | 100 | 24 | 23 | 15 | 58
192 | 1.2.2.2.1.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 190 |  | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Waterproofer | 100 | 80 | 33 | 92 | 10
193 | 1.2.2.2.1.9.6 | Services | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Floor Sealer | 100 | 62 | 13 | 93 | 12
194 | 1.2.2.2.1.9.7 | Post Tension | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Landscaper | 100 | 10 | 13 | 44 | 45
195 | 1.2.2.2.1.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 193FS-1d,194FS-1d | 196 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Contract Administrator | 100 | 62 | 20 | 76 | 15
196 | 1.2.2.2.1.9.9 | Formworker setdowns and edge boards | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 195 | 197 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Reinforcement Fixer | 100 | 79 | 25 | 61 | 55
197 | 1.2.2.2.1.9.10 | Pour | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 196 | 200 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Electrician | 100 | 11 | 23 | 50 | 58
198 | 1.2.2.2.1.10 | Strip Formwork - Lvl 6 | 5 | 6 December 2024 8:00 AM | 11 December 2024 5:00 PM | 225 | 657,425FS+5d,427FS-10d | 6 December 2024 8:00 AM | 2024-12-11 17:00 | 0 | Hoarding | 100 | 71 | 25 | 70 | 38
199 | 1.2.2.2.1.11 | Lvl 7 - FRP - Suspended Slab | 15 | 26 October 2024 8:00 AM | 12 November 2024 5:00 PM |  |  | 26 October 2024 8:00 AM | 2024-11-16 17:00 | 4 | Subcontractor | 100 | 19 | 30 | 10 | 19
200 | 1.2.2.2.1.11.1 | Scaffold Perimeter Protection | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 197 | 201SS | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Metal Work | 100 | 36 | 21 | 71 | 55
201 | 1.2.2.2.1.11.2 | Setout and Install Lift/Stair Formwork | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 200SS | 202FS-1d | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Concretor | 100 | 62 | 30 | 36 | 14
202 | 1.2.2.2.1.11.3 | Formworker setout, drop material and 80% Deck | 6 | 26 October 2024 8:00 AM | 1 November 2024 5:00 PM | 201FS-1d | 203FS-1d,204 | 26 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Concretor | 100 | 93 | 27 | 83 | 45
203 | 1.2.2.2.1.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 1 November 2024 8:00 AM | 5 November 2024 5:00 PM | 202FS-1d | 205,206 | 1 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Project Manager | 100 | 20 | 35 | 85 | 35
204 | 1.2.2.2.1.11.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 202 |  | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Painter | 100 | 59 | 20 | 40 | 17
205 | 1.2.2.2.1.11.6 | Services | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Plasterboarder | 100 | 67 | 31 | 58 | 14
206 | 1.2.2.2.1.11.7 | Post Tension | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Admin | 100 | 58 | 31 | 82 | 23
207 | 1.2.2.2.1.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 205FS-1d,206FS-1d | 208 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Excavation | 100 | 100 | 17 | 22 | 16
208 | 1.2.2.2.1.11.9 | Formworker setdowns and edge boards | 2 | 9 November 2024 8:00 AM | 11 November 2024 5:00 PM | 207 | 209 | 9 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Subcontractor | 100 | 11 | 14 | 24 | 9
209 | 1.2.2.2.1.11.10 | Pour | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 208 | 212,162FS+5d,174FS+5d,431FS+5d | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Carpenter | 100 | 31 | 22 | 62 | 46
210 | 1.2.2.2.1.12 | Strip Formwork - Lvl 7 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 225FS+5d | 690,432FS-10d | 12 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Concretor | 100 | 70 | 20 | 35 | 15
211 | 1.2.2.2.1.13 | Lvl 8 (Roof) - FRP - Suspended Slab | 14 | 13 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | 13 November 2024 8:00 AM | 2024-12-01 17:00 | 3 | Formworker | 100 | 56 | 10 | 95 | 37
212 | 1.2.2.2.1.13.1 | Scaffold Perimeter Protection | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 209 | 213SS | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Electrician | 100 | 10 | 17 | 73 | 54
213 | 1.2.2.2.1.13.2 | Setout and Install Lift/Stair Formwork | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 212SS | 214FS-1d | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Joiner | 100 | 50 | 21 | 64 | 35
214 | 1.2.2.2.1.13.3 | Formworker setout, drop material and 80% Deck | 6 | 13 November 2024 8:00 AM | 19 November 2024 5:00 PM | 213FS-1d | 215FS-1d,216 | 13 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Cleaner | 100 | 85 | 11 | 3 | 54
215 | 1.2.2.2.1.13.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214FS-1d | 217,218 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Timber Floorer | 100 | 10 | 22 | 18 | 31
216 | 1.2.2.2.1.13.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214 |  | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Mechanical | 100 | 47 | 25 | 6 | 48
217 | 1.2.2.2.1.13.6 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Contract Administrator | 100 | 90 | 13 | 59 | 43
218 | 1.2.2.2.1.13.7 | Post Tension | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Stone Mason | 100 | 87 | 12 | 15 | 58
219 | 1.2.2.2.1.13.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 217FS-1d,218FS-1d | 220 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Surveyor | 100 | 68 | 28 | 31 | 3
220 | 1.2.2.2.1.13.9 | Formworker setdowns and edge boards | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 219 | 221 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Renderer | 100 | 36 | 10 | 44 | 53
221 | 1.2.2.2.1.13.10 | Pour - Structure Top Out | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 220 | 223FS+12d,222,225,186FS+5d,437FS+5d | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Admin | 100 | 50 | 23 | 37 | 5
222 | 1.2.2.2.1.13.11 | Structure Top Out | 0 | 28 November 2024 5:00 PM | 28 November 2024 5:00 PM | 221 |  | 28 November 2024 5:00 PM | 2024-11-28 17:00 | 0 | Head Contractor | 100 | 92 | 22 | 2 | 16
223 | 1.2.2.2.1.14 | Strip Formwork - Lvl 8 | 4 | 13 December 2024 8:00 AM | 17 December 2024 5:00 PM | 221FS+12d | 716,439FS+10d | 13 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Development Manager | 100 | 46 | 11 | 45 | 57
224 | 1.2.2.2.1.15 | Lift Shaft | 23 | 29 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 29 November 2024 8:00 AM | 2025-01-08 17:00 | 5 | Plasterboarder | 100 | 69 | 14 | 89 | 28
225 | 1.2.2.2.1.15.1 | FRP Lift Over-run | 6 | 29 November 2024 8:00 AM | 5 December 2024 5:00 PM | 221 | 226FS+5d,228,198,210FS+5d | 29 November 2024 8:00 AM | 2024-12-08 17:00 | 3 | Cleaner | 100 | 88 | 16 | 77 | 14
226 | 1.2.2.2.1.15.2 | Strip Lift Shaft Formwork | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 225FS+5d | 227 | 12 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Contract Administrator | 100 | 31 | 32 | 89 | 37
227 | 1.2.2.2.1.15.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 17 December 2024 8:00 AM | 3 January 2025 5:00 PM | 226 | 3451 | 17 December 2024 8:00 AM | 2025-01-05 17:00 | 2 | Timber Floorer | 100 | 84 | 21 | 61 | 25
228 | 1.2.2.2.1.15.4 | Building A Structure Complete | 0 | 5 December 2024 5:00 PM | 5 December 2024 5:00 PM | 225 | 6 | 5 December 2024 5:00 PM | 2024-12-05 17:00 | 0 | Reinforcement Fixer | 100 | 25 | 33 | 88 | 26
229 | 1.2.2.2.2 | Building B | 119 | 13 July 2024 8:00 AM | 30 November 2024 5:00 PM |  | 397 | 13 July 2024 8:00 AM | 2024-11-30 17:00 | 0 | Head Contractor | 100 | 77 | 13 | 22 | 10
230 | 1.2.2.2.2.1 | Lvl 2 - FRP - Suspended Slab | 18 | 13 July 2024 8:00 AM | 2 August 2024 5:00 PM |  |  | 13 July 2024 8:00 AM | 2024-08-02 17:00 | 0 | Plumber | 100 | 87 | 16 | 16 | 19
231 | 1.2.2.2.2.1.1 | Scaffold Perimeter Protection | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 232SS |  | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Window | 100 | 85 | 14 | 22 | 16
232 | 1.2.2.2.2.1.2 | Setout and Install Lift/Stair Formwork | 1 | 13 July 2024 8:00 AM | 15 July 2024 8:00 AM | 233SF | 231SS | 13 July 2024 8:00 AM | 2024-07-15 08:00 | 0 | Plumber | 100 | 42 | 23 | 34 | 45
233 | 1.2.2.2.2.1.3 | Formworker setout, drop material and 80% Deck | 6 | 15 July 2024 8:00 AM | 20 July 2024 5:00 PM | 135 | 234FS-1d,235,232SF | 15 July 2024 8:00 AM | 2024-07-20 17:00 | 0 | Joiner | 100 | 74 | 21 | 8 | 18
234 | 1.2.2.2.2.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 20 July 2024 8:00 AM | 24 July 2024 5:00 PM | 233FS-1d | 236,237 | 20 July 2024 8:00 AM | 2024-07-24 17:00 | 0 | Subcontractor | 100 | 14 | 23 | 99 | 27
235 | 1.2.2.2.2.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 22 July 2024 8:00 AM | 23 July 2024 5:00 PM | 233 |  | 22 July 2024 8:00 AM | 2024-07-23 17:00 | 0 | Floor Sealer | 100 | 86 | 32 | 8 | 43
236 | 1.2.2.2.2.1.6 | Services | 2 | 25 July 2024 8:00 AM | 26 July 2024 5:00 PM | 234 | 238FS-1d | 25 July 2024 8:00 AM | 2024-07-26 17:00 | 0 | Excavation | 100 | 81 | 28 | 46 | 3
237 | 1.2.2.2.2.1.7 | Post Tension | 3 | 25 July 2024 8:00 AM | 27 July 2024 5:00 PM | 234 | 238FS-1d | 25 July 2024 8:00 AM | 2024-07-27 17:00 | 0 | Floor Sealer | 100 | 16 | 12 | 9 | 57
238 | 1.2.2.2.2.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 27 July 2024 8:00 AM | 29 July 2024 5:00 PM | 236FS-1d,237FS-1d | 239 | 27 July 2024 8:00 AM | 2024-07-29 17:00 | 0 | Plumber | 100 | 18 | 35 | 80 | 35
239 | 1.2.2.2.2.1.9 | Formworker setdowns and edge boards | 3 | 30 July 2024 8:00 AM | 1 August 2024 5:00 PM | 238 | 240 | 30 July 2024 8:00 AM | 2024-08-01 17:00 | 0 | Hoarding | 100 | 71 | 33 | 37 | 2
240 | 1.2.2.2.2.1.10 | Pour | 1 | 2 August 2024 8:00 AM | 2 August 2024 5:00 PM | 239 | 243,309FS+30d | 2 August 2024 8:00 AM | 2024-08-02 17:00 | 0 | Hoarding | 100 | 51 | 13 | 53 | 60
241 | 1.2.2.2.2.2 | Strip Formwork - Lvl 2 | 5 | 28 September 2024 8:00 AM | 3 October 2024 5:00 PM | 276 | 447 | 28 September 2024 8:00 AM | 2024-10-03 17:00 | 0 | Excavation | 100 | 46 | 22 | 79 | 17
242 | 1.2.2.2.2.3 | Lvl 3 - FRP - Suspended Slab | 18 | 3 August 2024 8:00 AM | 23 August 2024 5:00 PM |  |  | 3 August 2024 8:00 AM | 2024-08-24 17:00 | 1 | Head Contractor | 100 | 29 | 17 | 51 | 21
243 | 1.2.2.2.2.3.1 | Scaffold Perimeter Protection | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 240 | 244SS | 3 August 2024 8:00 AM | 2024-08-03 17:00 | 0 | Concretor | 100 | 80 | 10 | 4 | 48
244 | 1.2.2.2.2.3.2 | Setout and Install Lift/Stair Formwork | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 243SS | 245 | 3 August 2024 8:00 AM | 2024-08-03 17:00 | 0 | Surveyor | 100 | 66 | 32 | 67 | 54
245 | 1.2.2.2.2.3.3 | Formworker setout, drop material and 80% Deck | 6 | 5 August 2024 8:00 AM | 10 August 2024 5:00 PM | 244 | 246FS-1d,247 | 5 August 2024 8:00 AM | 2024-08-12 17:00 | 2 | Admin | 100 | 79 | 17 | 61 | 51
246 | 1.2.2.2.2.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 10 August 2024 8:00 AM | 14 August 2024 5:00 PM | 245FS-1d | 248,249 | 10 August 2024 8:00 AM | 2024-08-14 17:00 | 0 | Carpenter | 100 | 11 | 32 | 17 | 27
247 | 1.2.2.2.2.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 245 |  | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 0 | Floor Sealer | 100 | 96 | 23 | 80 | 13
248 | 1.2.2.2.2.3.6 | Services | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | 15 August 2024 8:00 AM | 2024-08-16 17:00 | 0 | Carpet | 100 | 11 | 12 | 82 | 25
249 | 1.2.2.2.2.3.7 | Post Tension | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | 15 August 2024 8:00 AM | 2024-08-16 17:00 | 0 | Concretor | 100 | 11 | 13 | 70 | 46
250 | 1.2.2.2.2.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 16 August 2024 8:00 AM | 19 August 2024 5:00 PM | 248FS-1d,249FS-1d | 251 | 16 August 2024 8:00 AM | 2024-08-19 17:00 | 0 | Admin | 100 | 89 | 25 | 72 | 5
251 | 1.2.2.2.2.3.9 | Formworker setdowns and edge boards | 3 | 20 August 2024 8:00 AM | 22 August 2024 5:00 PM | 250 | 252 | 20 August 2024 8:00 AM | 2024-08-22 17:00 | 0 | Plumber | 100 | 62 | 24 | 40 | 50
252 | 1.2.2.2.2.3.10 | Pour | 1 | 23 August 2024 8:00 AM | 23 August 2024 5:00 PM | 251 | 255,3447 | 23 August 2024 8:00 AM | 2024-08-23 17:00 | 0 | Fire | 100 | 61 | 12 | 16 | 54
253 | 1.2.2.2.2.4 | Strip Formwork - Lvl 3 | 5 | 21 October 2024 8:00 AM | 25 October 2024 5:00 PM | 288 | 453,1605 | 21 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Scaffolder | 100 | 77 | 24 | 57 | 27
254 | 1.2.2.2.2.5 | Lvl 4 - FRP - Suspended Slab | 15 | 24 August 2024 8:00 AM | 10 September 2024 5:00 PM |  |  | 24 August 2024 8:00 AM | 2024-09-15 17:00 | 5 | Metal Work | 100 | 12 | 14 | 47 | 13
255 | 1.2.2.2.2.5.1 | Scaffold Perimeter Protection | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 252 | 256SS | 24 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Foreman | 100 | 89 | 31 | 19 | 29
256 | 1.2.2.2.2.5.2 | Setout and Install Lift/Stair Formwork | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 255SS | 257FS-1d | 24 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Project Manager | 100 | 10 | 25 | 31 | 6
257 | 1.2.2.2.2.5.3 | Formworker setout, drop material and 80% Deck | 6 | 24 August 2024 8:00 AM | 30 August 2024 5:00 PM | 256FS-1d | 258FS-1d,259 | 24 August 2024 8:00 AM | 2024-09-01 17:00 | 2 | Excavation | 100 | 85 | 19 | 29 | 5
258 | 1.2.2.2.2.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 30 August 2024 8:00 AM | 3 September 2024 5:00 PM | 257FS-1d | 260,261 | 30 August 2024 8:00 AM | 2024-09-03 17:00 | 0 | Fire | 100 | 29 | 11 | 0 | 12
259 | 1.2.2.2.2.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 31 August 2024 8:00 AM | 2 September 2024 5:00 PM | 257 |  | 31 August 2024 8:00 AM | 2024-09-02 17:00 | 0 | Plumber | 100 | 50 | 33 | 57 | 59
260 | 1.2.2.2.2.5.6 | Services | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | 4 September 2024 8:00 AM | 2024-09-05 17:00 | 0 | Foreman | 100 | 27 | 10 | 80 | 55
261 | 1.2.2.2.2.5.7 | Post Tension | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | 4 September 2024 8:00 AM | 2024-09-05 17:00 | 0 | Waterproofer | 100 | 44 | 23 | 67 | 32
262 | 1.2.2.2.2.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 5 September 2024 8:00 AM | 6 September 2024 5:00 PM | 260FS-1d,261FS-1d | 263 | 5 September 2024 8:00 AM | 2024-09-06 17:00 | 0 | Admin | 100 | 23 | 10 | 1 | 20
263 | 1.2.2.2.2.5.9 | Formworker setdowns and edge boards | 2 | 7 September 2024 8:00 AM | 9 September 2024 5:00 PM | 262 | 264 | 7 September 2024 8:00 AM | 2024-09-09 17:00 | 0 | Window | 100 | 27 | 14 | 19 | 15
264 | 1.2.2.2.2.5.10 | Pour | 1 | 10 September 2024 8:00 AM | 10 September 2024 5:00 PM | 263 | 267 | 10 September 2024 8:00 AM | 2024-09-10 17:00 | 0 | Plasterboarder | 100 | 30 | 26 | 100 | 18
265 | 1.2.2.2.2.6 | Strip Formwork - Lvl 4 | 5 | 11 November 2024 8:00 AM | 15 November 2024 5:00 PM | 300 | 459,1632 | 11 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Carpet | 100 | 55 | 27 | 95 | 24
266 | 1.2.2.2.2.7 | Lvl 5 - FRP - Suspended Slab | 15 | 11 September 2024 8:00 AM | 27 September 2024 5:00 PM |  |  | 11 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Plasterboarder | 100 | 41 | 16 | 55 | 29
267 | 1.2.2.2.2.7.1 | Scaffold Perimeter Protection | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 264 | 268SS | 11 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Carpet | 100 | 81 | 28 | 82 | 12
268 | 1.2.2.2.2.7.2 | Setout and Install Lift/Stair Formwork | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 267SS | 269FS-1d | 11 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Floor Sealer | 100 | 80 | 28 | 59 | 25
269 | 1.2.2.2.2.7.3 | Formworker setout, drop material and 80% Deck | 6 | 11 September 2024 8:00 AM | 17 September 2024 5:00 PM | 268FS-1d | 270FS-1d,271 | 11 September 2024 8:00 AM | 2024-09-18 17:00 | 1 | Excavation | 100 | 78 | 21 | 94 | 36
270 | 1.2.2.2.2.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 17 September 2024 8:00 AM | 20 September 2024 5:00 PM | 269FS-1d | 272,273 | 17 September 2024 8:00 AM | 2024-09-20 17:00 | 0 | Floor Sealer | 100 | 97 | 13 | 12 | 11
271 | 1.2.2.2.2.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 18 September 2024 8:00 AM | 19 September 2024 5:00 PM | 269 |  | 18 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Line Market | 100 | 16 | 21 | 10 | 43
272 | 1.2.2.2.2.7.6 | Services | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Carpenter | 100 | 30 | 17 | 80 | 15
273 | 1.2.2.2.2.7.7 | Post Tension | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Admin | 100 | 41 | 29 | 5 | 11
274 | 1.2.2.2.2.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 September 2024 8:00 AM | 24 September 2024 5:00 PM | 272FS-1d,273FS-1d | 275 | 23 September 2024 8:00 AM | 2024-09-24 17:00 | 0 | Plumber | 100 | 92 | 22 | 98 | 18
275 | 1.2.2.2.2.7.9 | Formworker setdowns and edge boards | 2 | 25 September 2024 8:00 AM | 26 September 2024 5:00 PM | 274 | 276 | 25 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Timber Floorer | 100 | 78 | 16 | 63 | 34
276 | 1.2.2.2.2.7.10 | Pour | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 275 | 279,241 | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Site Manager | 100 | 89 | 22 | 17 | 56
277 | 1.2.2.2.2.8 | Strip Formwork - Lvl 5 | 5 | 18 November 2024 8:00 AM | 22 November 2024 5:00 PM | 303 | 465,1659 | 18 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Hoarding | 100 | 38 | 13 | 66 | 5
278 | 1.2.2.2.2.9 | Lvl 6 - FRP - Suspended Slab | 17 | 28 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | 28 September 2024 8:00 AM | 2024-10-22 17:00 | 3 | Joiner | 100 | 28 | 29 | 86 | 2
279 | 1.2.2.2.2.9.1 | Scaffold Perimeter Protection | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 276 | 280SS | 28 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Post Tension | 100 | 70 | 24 | 6 | 18
280 | 1.2.2.2.2.9.2 | Setout and Install Lift/Stair Formwork | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 279SS | 281FS-1d | 28 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Electrician | 100 | 19 | 31 | 15 | 47
281 | 1.2.2.2.2.9.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 280FS-1d | 282FS-1d,283 | 28 September 2024 8:00 AM | 2024-10-05 17:00 | 1 | Site Manager | 100 | 31 | 12 | 42 | 51
282 | 1.2.2.2.2.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 281FS-1d | 284,285 | 4 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Cleaner | 100 | 42 | 28 | 32 | 26
283 | 1.2.2.2.2.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 281 |  | 8 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Admin | 100 | 47 | 10 | 55 | 40
284 | 1.2.2.2.2.9.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Concretor | 100 | 63 | 32 | 3 | 58
285 | 1.2.2.2.2.9.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Mechanical | 100 | 80 | 33 | 84 | 46
286 | 1.2.2.2.2.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 284FS-1d,285FS-1d | 287 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Development Manager | 100 | 99 | 27 | 100 | 60
287 | 1.2.2.2.2.9.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 286 | 288 | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Concretor | 100 | 37 | 21 | 13 | 42
288 | 1.2.2.2.2.9.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 287 | 291,253 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Head Contractor | 100 | 87 | 13 | 86 | 53
289 | 1.2.2.2.2.10 | Strip Formwork - Lvl 6 | 5 | 20 November 2024 8:00 AM | 25 November 2024 5:00 PM | 300FS+8d | 657,471,1686 | 20 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Window | 100 | 26 | 23 | 2 | 29
290 | 1.2.2.2.2.11 | Lvl 7 (Roof) - FRP - Suspended Slab | 18 | 21 October 2024 8:00 AM | 9 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-13 17:00 | 4 | Stone Mason | 100 | 35 | 25 | 64 | 32
291 | 1.2.2.2.2.11.1 | Scaffold Perimeter Protection | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 288 | 292SS | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Surveyor | 100 | 44 | 26 | 32 | 29
292 | 1.2.2.2.2.11.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 291SS | 293FS-1d | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Carpenter | 100 | 23 | 12 | 54 | 58
293 | 1.2.2.2.2.11.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 292FS-1d | 294FS-1d,295 | 21 October 2024 8:00 AM | 2024-10-27 17:00 | 1 | Fire | 100 | 37 | 13 | 35 | 6
294 | 1.2.2.2.2.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293FS-1d | 296,297 | 26 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Foreman | 100 | 78 | 32 | 87 | 51
295 | 1.2.2.2.2.11.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 28 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293 |  | 28 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Plasterboarder | 100 | 96 | 29 | 13 | 42
296 | 1.2.2.2.2.11.6 | Services | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Formworker | 100 | 17 | 19 | 46 | 16
297 | 1.2.2.2.2.11.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Line Market | 100 | 25 | 30 | 95 | 16
298 | 1.2.2.2.2.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 296FS-1d,297FS-1d | 299 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Plasterboarder | 100 | 91 | 18 | 39 | 11
299 | 1.2.2.2.2.11.9 | Formworker setdowns and edge boards | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 298 | 300 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Electrician | 100 | 60 | 22 | 61 | 28
300 | 1.2.2.2.2.11.10 | Pour | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 299 | 303,289FS+8d,301FS+12d,1739FS+24d,265 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Carpenter | 100 | 47 | 13 | 42 | 57
301 | 1.2.2.2.2.12 | Strip Formwork - Lvl 7 | 5 | 25 November 2024 8:00 AM | 29 November 2024 5:00 PM | 300FS+12d | 716,748FS+24d,477,1713 | 25 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Head Contractor | 100 | 73 | 12 | 92 | 46
302 | 1.2.2.2.2.13 | Lift Shaft | 18 | 11 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 11 November 2024 8:00 AM | 2024-12-04 17:00 | 4 | Electrician | 100 | 28 | 12 | 83 | 39
303 | 1.2.2.2.2.13.1 | FRP Lift Over-run | 6 | 11 November 2024 8:00 AM | 16 November 2024 5:00 PM | 300 | 304,277 | 11 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Carpet | 100 | 25 | 12 | 12 | 19
304 | 1.2.2.2.2.13.2 | Strip Lift Shaft Formwork | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 303 | 305 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Waterproofer | 100 | 100 | 10 | 61 | 48
305 | 1.2.2.2.2.13.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 304 | 3452,306 | 22 November 2024 8:00 AM | 2024-12-02 17:00 | 2 | Post Tension | 100 | 30 | 12 | 4 | 34
306 | 1.2.2.2.2.13.4 | Building B Structure Complete | 0 | 30 November 2024 5:00 PM | 30 November 2024 5:00 PM | 305 | 7,6 | 30 November 2024 5:00 PM | 2024-11-30 17:00 | 0 | Electrician | 100 | 15 | 19 | 24 | 31
307 | 1.2.2.2.3 | Building C | 90 | 7 September 2024 8:00 AM | 23 December 2024 5:00 PM |  | 397 | 7 September 2024 8:00 AM | 2024-12-27 17:00 | 4 | Metal Work | 100 | 12 | 25 | 39 | 11
308 | 1.2.2.2.3.1 | Lvl 2 - FRP - Suspended Slab | 17 | 7 September 2024 8:00 AM | 26 September 2024 5:00 PM |  |  | 7 September 2024 8:00 AM | 2024-09-29 17:00 | 3 | Joiner | 100 | 25 | 33 | 86 | 59
309 | 1.2.2.2.3.1.1 | Scaffold Stair Removal/Adjustment | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 135,240FS+30d | 310SS | 7 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Line Market | 100 | 67 | 31 | 25 | 59
310 | 1.2.2.2.3.1.2 | Setout and Install Lift/Stair Formwork | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 309SS | 311 | 7 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Plasterboarder | 100 | 56 | 13 | 4 | 45
311 | 1.2.2.2.3.1.3 | Formworker setout, drop material and 80% Deck | 6 | 9 September 2024 8:00 AM | 14 September 2024 5:00 PM | 310 | 312FS-1d,313,365FS+10d | 9 September 2024 8:00 AM | 2024-09-14 17:00 | 0 | Plasterboarder | 100 | 78 | 29 | 77 | 3
312 | 1.2.2.2.3.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 14 September 2024 8:00 AM | 18 September 2024 5:00 PM | 311FS-1d | 314,315 | 14 September 2024 8:00 AM | 2024-09-18 17:00 | 0 | Excavation | 100 | 12 | 13 | 66 | 25
313 | 1.2.2.2.3.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 311 |  | 16 September 2024 8:00 AM | 2024-09-17 17:00 | 0 | Development Manager | 100 | 31 | 33 | 72 | 21
314 | 1.2.2.2.3.1.6 | Services | 2 | 19 September 2024 8:00 AM | 20 September 2024 5:00 PM | 312 | 316FS-1d | 19 September 2024 8:00 AM | 2024-09-20 17:00 | 0 | Carpet | 100 | 48 | 22 | 4 | 24
315 | 1.2.2.2.3.1.7 | Post Tension | 3 | 19 September 2024 8:00 AM | 21 September 2024 5:00 PM | 312 | 316FS-1d | 19 September 2024 8:00 AM | 2024-09-21 17:00 | 0 | Project Manager | 100 | 13 | 11 | 9 | 49
316 | 1.2.2.2.3.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 314FS-1d,315FS-1d | 317 | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Project Manager | 100 | 18 | 24 | 94 | 28
317 | 1.2.2.2.3.1.9 | Formworker setdowns and edge boards | 2 | 24 September 2024 8:00 AM | 25 September 2024 5:00 PM | 316 | 318 | 24 September 2024 8:00 AM | 2024-09-25 17:00 | 0 | Stone Mason | 100 | 11 | 16 | 64 | 18
318 | 1.2.2.2.3.1.10 | Pour | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 317 | 321 | 26 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Head Contractor | 100 | 75 | 29 | 52 | 48
319 | 1.2.2.2.3.2 | Strip Formwork - Lvl 2 | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 354 | 331FS+5d | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Carpet | 100 | 57 | 31 | 81 | 35
320 | 1.2.2.2.3.3 | Lvl 3 - FRP - Suspended Slab | 17 | 27 September 2024 8:00 AM | 18 October 2024 5:00 PM |  |  | 27 September 2024 8:00 AM | 2024-10-21 17:00 | 3 | Surveyor | 100 | 28 | 17 | 25 | 10
321 | 1.2.2.2.3.3.1 | Scaffold Stair Removal/Adjustment | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 318 | 322SS | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Post Tension | 100 | 42 | 35 | 66 | 28
322 | 1.2.2.2.3.3.2 | Setout and Install Lift/Stair Formwork | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 321SS | 323 | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Timber Floorer | 100 | 10 | 33 | 88 | 5
323 | 1.2.2.2.3.3.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 322 | 324FS-1d,325 | 28 September 2024 8:00 AM | 2024-10-08 17:00 | 4 | Post Tension | 100 | 56 | 31 | 18 | 40
324 | 1.2.2.2.3.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 323FS-1d | 326,327 | 4 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Plasterboarder | 100 | 27 | 33 | 100 | 40
325 | 1.2.2.2.3.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 323 |  | 8 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Formworker | 100 | 89 | 12 | 11 | 50
326 | 1.2.2.2.3.3.6 | Services | 2 | 11 October 2024 8:00 AM | 12 October 2024 5:00 PM | 324 | 328FS-1d | 11 October 2024 8:00 AM | 2024-10-12 17:00 | 0 | Line Market | 100 | 100 | 35 | 91 | 46
327 | 1.2.2.2.3.3.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 324 | 328FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Reinforcement Fixer | 100 | 80 | 23 | 63 | 58
328 | 1.2.2.2.3.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 326FS-1d,327FS-1d | 329 | 14 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Metal Work | 100 | 48 | 31 | 80 | 56
329 | 1.2.2.2.3.3.9 | Formworker setdowns and edge boards | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 328 | 330 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Waterproofer | 100 | 24 | 22 | 11 | 24
330 | 1.2.2.2.3.3.10 | Pour | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 329 | 333 | 18 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Excavation | 100 | 99 | 16 | 69 | 16
331 | 1.2.2.2.3.4 | Strip Formwork - Lvl 3 | 5 | 10 December 2024 8:00 AM | 14 December 2024 5:00 PM | 319FS+5d | 490,1748,2151,1774,2177FS+5d | 10 December 2024 8:00 AM | 2024-12-14 17:00 | 0 | Line Market | 100 | 53 | 10 | 24 | 52
332 | 1.2.2.2.3.5 | Lvl 4 - FRP - Suspended Slab | 17 | 19 October 2024 8:00 AM | 7 November 2024 5:00 PM |  |  | 19 October 2024 8:00 AM | 2024-11-08 17:00 | 1 | Hoarding | 100 | 20 | 20 | 8 | 48
333 | 1.2.2.2.3.5.1 | Scaffold Stair Removal/Adjustment | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 330 | 334SS | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Contract Administrator | 100 | 86 | 10 | 45 | 39
334 | 1.2.2.2.3.5.2 | Setout and Install Lift/Stair Formwork | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 333SS | 335 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Site Manager | 100 | 55 | 27 | 13 | 30
335 | 1.2.2.2.3.5.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 334 | 336FS-1d,337 | 21 October 2024 8:00 AM | 2024-10-29 17:00 | 3 | Cleaner | 100 | 78 | 27 | 31 | 53
336 | 1.2.2.2.3.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 335FS-1d | 338,339 | 26 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Plumber | 100 | 66 | 24 | 13 | 2
337 | 1.2.2.2.3.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 335 |  | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Project Manager | 100 | 37 | 16 | 2 | 25
338 | 1.2.2.2.3.5.6 | Services | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 336 | 340FS-1d | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Concretor | 100 | 54 | 11 | 23 | 48
339 | 1.2.2.2.3.5.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 336 | 340FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Carpenter | 100 | 34 | 30 | 11 | 31
340 | 1.2.2.2.3.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 338FS-1d,339FS-1d | 341 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Head Contractor | 100 | 24 | 22 | 94 | 59
341 | 1.2.2.2.3.5.9 | Formworker setdowns and edge boards | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 340 | 342 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Mechanical | 100 | 20 | 28 | 46 | 30
342 | 1.2.2.2.3.5.10 | Pour | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 341 | 345 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Surveyor | 100 | 13 | 27 | 50 | 2
343 | 1.2.2.2.3.6 | Strip Formwork - Lvl 4 | 5 | 16 December 2024 8:00 AM | 20 December 2024 5:00 PM | 354FS+15d | 495,2648,2674FS+5d | 16 December 2024 8:00 AM | 2024-12-20 17:00 | 0 | Plasterboarder | 100 | 44 | 25 | 20 | 49
344 | 1.2.2.2.3.7 | Lvl 5 (Roof) - FRP - Suspended Slab | 17 | 8 November 2024 8:00 AM | 27 November 2024 5:00 PM |  |  | 8 November 2024 8:00 AM | 2024-11-29 17:00 | 2 | Hoarding | 100 | 41 | 16 | 65 | 59
345 | 1.2.2.2.3.7.1 | Scaffold Stair Removal/Adjustment | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 342 | 346SS | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Waterproofer | 100 | 94 | 20 | 29 | 45
346 | 1.2.2.2.3.7.2 | Setout and Install Lift/Stair Formwork | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 345SS | 347 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Renderer | 100 | 45 | 13 | 45 | 15
347 | 1.2.2.2.3.7.3 | Formworker setout, drop material and 80% Deck | 6 | 9 November 2024 8:00 AM | 15 November 2024 5:00 PM | 346 | 348FS-1d,349 | 9 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Excavation | 100 | 86 | 23 | 90 | 17
348 | 1.2.2.2.3.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 November 2024 8:00 AM | 19 November 2024 5:00 PM | 347FS-1d | 350,351 | 15 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Carpet | 100 | 62 | 31 | 0 | 48
349 | 1.2.2.2.3.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 347 |  | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Timber Floorer | 100 | 50 | 33 | 21 | 58
350 | 1.2.2.2.3.7.6 | Services | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 348 | 352FS-1d | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 100 | 48 | 23 | 91 | 43
351 | 1.2.2.2.3.7.7 | Post Tension | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 348 | 352FS-1d | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Carpet | 100 | 15 | 16 | 45 | 5
352 | 1.2.2.2.3.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 350FS-1d,351FS-1d | 353 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Fire | 100 | 81 | 25 | 7 | 10
353 | 1.2.2.2.3.7.9 | Formworker setdowns and edge boards | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 352 | 354 | 25 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Contract Administrator | 100 | 62 | 14 | 26 | 39
354 | 1.2.2.2.3.7.10 | Pour | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 353 | 357,355FS+12d,343FS+15d,360,319 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Admin | 100 | 90 | 32 | 90 | 5
355 | 1.2.2.2.3.8 | Strip Formwork - Lvl 5 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 354FS+12d | 500,3145,3171FS+5d | 12 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Renderer | 100 | 77 | 28 | 95 | 22
356 | 1.2.2.2.3.9 | Lift Shaft | 22 | 28 November 2024 8:00 AM | 23 December 2024 5:00 PM |  |  | 28 November 2024 8:00 AM | 2024-12-24 17:00 | 1 | Plasterboarder | 100 | 76 | 18 | 87 | 33
357 | 1.2.2.2.3.9.1 | FRP Lift Over-run | 10 | 28 November 2024 8:00 AM | 9 December 2024 5:00 PM | 354 | 358 | 28 November 2024 8:00 AM | 2024-12-13 17:00 | 4 | Plumber | 100 | 87 | 34 | 41 | 50
358 | 1.2.2.2.3.9.2 | Strip Lift Shaft Formwork | 4 | 10 December 2024 8:00 AM | 13 December 2024 5:00 PM | 357 | 359 | 10 December 2024 8:00 AM | 2024-12-13 17:00 | 0 | Project Manager | 100 | 64 | 22 | 33 | 50
359 | 1.2.2.2.3.9.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 14 December 2024 8:00 AM | 23 December 2024 5:00 PM | 358 | 3453,360 | 14 December 2024 8:00 AM | 2024-12-25 17:00 | 2 | Head Contractor | 100 | 79 | 31 | 19 | 15
360 | 1.2.2.2.3.10 | Building C Structure Complete | 0 | 23 December 2024 5:00 PM | 23 December 2024 5:00 PM | 354,359 | 8,7 | 23 December 2024 5:00 PM | 2024-12-23 17:00 | 0 | Excavation | 100 | 42 | 15 | 38 | 18
361 | 1.2.2.2.4 | Building D | 76 | 26 September 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | 26 September 2024 8:00 AM | 2025-01-06 17:00 | 3 | Landscaper | 100 | 21 | 24 | 58 | 35
362 | 1.2.2.2.4.1 | Lvl 2 - FRP - Suspended Slab | 19 | 26 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | 26 September 2024 8:00 AM | 2024-10-23 17:00 | 4 | Joiner | 100 | 75 | 22 | 86 | 50
363 | 1.2.2.2.4.1.1 | Scaffold Stair Removal/Adjustment | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 364SS |  | 26 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Tiler | 100 | 57 | 12 | 77 | 24
364 | 1.2.2.2.4.1.2 | Setout and Install Lift/Stair Formwork | 1 | 26 September 2024 8:00 AM | 27 September 2024 8:00 AM | 365SF | 363SS | 26 September 2024 8:00 AM | 2024-09-27 08:00 | 0 | Fire | 100 | 28 | 15 | 96 | 13
365 | 1.2.2.2.4.1.3 | Formworker setout, drop material and 80% Deck | 6 | 27 September 2024 8:00 AM | 3 October 2024 5:00 PM | 311FS+10d | 366FS-1d,367,364SF | 27 September 2024 8:00 AM | 2024-10-04 17:00 | 1 | Cleaner | 100 | 68 | 23 | 31 | 35
366 | 1.2.2.2.4.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 3 October 2024 8:00 AM | 10 October 2024 5:00 PM | 365FS-1d | 368,369 | 3 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Joiner | 100 | 54 | 19 | 41 | 54
367 | 1.2.2.2.4.1.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 4 October 2024 8:00 AM | 9 October 2024 5:00 PM | 365 |  | 4 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Head Contractor | 100 | 59 | 15 | 80 | 12
368 | 1.2.2.2.4.1.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Line Market | 100 | 49 | 32 | 36 | 58
369 | 1.2.2.2.4.1.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Admin | 100 | 49 | 26 | 41 | 31
370 | 1.2.2.2.4.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 368FS-1d,369FS-1d | 371 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Formworker | 100 | 82 | 14 | 37 | 43
371 | 1.2.2.2.4.1.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 370 | 372 | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Site Manager | 100 | 83 | 26 | 63 | 13
372 | 1.2.2.2.4.1.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 371 | 375 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Post Tension | 100 | 88 | 25 | 45 | 5
373 | 1.2.2.2.4.2 | Strip Formwork - Lvl 2 | 5 | 21 November 2024 8:00 AM | 26 November 2024 5:00 PM | 384FS+8d | 485,506 | 21 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Tiler | 100 | 100 | 17 | 91 | 44
374 | 1.2.2.2.4.3 | Lvl 3 - FRP - Suspended Slab | 19 | 21 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-16 17:00 | 5 | Timber Floorer | 100 | 38 | 15 | 46 | 60
375 | 1.2.2.2.4.3.1 | Scaffold Stair Removal/Adjustment | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 372 | 376SS | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Foreman | 100 | 88 | 14 | 31 | 6
376 | 1.2.2.2.4.3.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 375SS | 377 | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Project Manager | 100 | 22 | 14 | 84 | 29
377 | 1.2.2.2.4.3.3 | Formworker setout, drop material and 80% Deck | 6 | 22 October 2024 8:00 AM | 28 October 2024 5:00 PM | 376 | 378FS-1d,379 | 22 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Fire | 100 | 18 | 29 | 29 | 52
378 | 1.2.2.2.4.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 377FS-1d | 380,381 | 28 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Contract Administrator | 100 | 24 | 35 | 11 | 26
379 | 1.2.2.2.4.3.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 29 October 2024 8:00 AM | 31 October 2024 5:00 PM | 377 |  | 29 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Formworker | 100 | 54 | 33 | 68 | 59
380 | 1.2.2.2.4.3.6 | Services | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Project Manager | 100 | 25 | 32 | 83 | 57
381 | 1.2.2.2.4.3.7 | Post Tension | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Development Manager | 100 | 13 | 10 | 64 | 18
382 | 1.2.2.2.4.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 5 November 2024 8:00 AM | 7 November 2024 5:00 PM | 380FS-1d,381FS-1d | 383 | 5 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Electrician | 100 | 20 | 28 | 19 | 23
383 | 1.2.2.2.4.3.9 | Formworker setdowns and edge boards | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 382 | 384 | 8 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Electrician | 100 | 63 | 25 | 29 | 19
384 | 1.2.2.2.4.3.10 | Pour | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 383 | 385FS+12d,373FS+8d,387 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Contract Administrator | 100 | 62 | 22 | 84 | 16
385 | 1.2.2.2.4.4 | Strip Formwork - Lvl 3 | 5 | 26 November 2024 8:00 AM | 30 November 2024 5:00 PM | 384FS+12d | 511 | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Plasterboarder | 100 | 62 | 21 | 100 | 9
386 | 1.2.2.2.4.5 | L4 Strucutral Steel Roof | 38 | 12 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 12 November 2024 8:00 AM | 2025-01-08 17:00 | 5 | Electrician | 100 | 77 | 15 | 39 | 7
387 | 1.2.2.2.4.5.1 | Scaffold Perimeter Protection | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 384 | 388SS | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Window | 100 | 52 | 23 | 73 | 38
388 | 1.2.2.2.4.5.2 | Setout | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 387SS | 389 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Metal Work | 100 | 48 | 13 | 47 | 47
389 | 1.2.2.2.4.5.3 | Formworker setout, drop material and 80% Walls | 5 | 14 November 2024 8:00 AM | 19 November 2024 5:00 PM | 388 | 390FS-1d | 14 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Line Market | 100 | 21 | 16 | 11 | 22
390 | 1.2.2.2.4.5.4 | Steel Fixer - Walls | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 389FS-1d | 391 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Cleaner | 100 | 63 | 13 | 28 | 24
391 | 1.2.2.2.4.5.5 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 390 | 392 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Floor Sealer | 100 | 18 | 16 | 48 | 13
392 | 1.2.2.2.4.5.6 | Pour | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 391 | 393 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Renderer | 100 | 13 | 14 | 42 | 34
393 | 1.2.2.2.4.5.7 | Strip Formwork | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 392 | 394 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Carpenter | 100 | 17 | 22 | 28 | 56
394 | 1.2.2.2.4.5.8 | Structural Steel Setout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 393 | 395 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Timber Floorer | 100 | 19 | 10 | 30 | 43
395 | 1.2.2.2.4.5.9 | Install Structural Steel | 8 | 29 November 2024 8:00 AM | 7 December 2024 5:00 PM | 394 | 396 | 29 November 2024 8:00 AM | 2024-12-09 17:00 | 2 | Subcontractor | 100 | 57 | 15 | 78 | 52
396 | 1.2.2.2.4.5.10 | Install Metal Deck Roofing | 15 | 9 December 2024 8:00 AM | 3 January 2025 5:00 PM | 395 | 516,8 | 9 December 2024 8:00 AM | 2025-01-08 17:00 | 5 | Joiner | 100 | 13 | 15 | 19 | 29
397 | 1.2.2.3 | Structural Works Complete | 0 | 3 January 2025 5:00 PM | 3 January 2025 5:00 PM | 120,307,361,91,138,229 |  | 3 January 2025 5:00 PM | 2025-01-03 17:00 | 0 | Subcontractor | 100 | 80 | 10 | 40 | 9
398 | 1.2.3 | FAÇADE WORKS | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | 13 July 2024 8:00 AM | 2025-03-23 17:00 | 1 | Landscaper | 100 | 91 | 30 | 47 | 7
399 | 1.2.3.1 | Building A | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | 13 July 2024 8:00 AM | 2025-03-24 17:00 | 2 | Contract Administrator | 100 | 79 | 31 | 16 | 54
400 | 1.2.3.1.1 | Lvl 1 | 44 | 13 July 2024 8:00 AM | 2 September 2024 5:00 PM |  |  | 13 July 2024 8:00 AM | 2024-09-04 17:00 | 2 | Joiner | 100 | 76 | 30 | 37 | 33
401 | 1.2.3.1.1.1 | Survey & Setout | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 116FS+5d | 402 | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Surveyor | 100 | 27 | 20 | 0 | 53
402 | 1.2.3.1.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 15 July 2024 8:00 AM | 19 July 2024 5:00 PM | 401 | 403 | 15 July 2024 8:00 AM | 2024-07-19 17:00 | 0 | Concretor | 100 | 69 | 29 | 46 | 39
403 | 1.2.3.1.1.3 | Façade & External Walls | 20 | 20 July 2024 8:00 AM | 12 August 2024 5:00 PM | 402 | 404 | 20 July 2024 8:00 AM | 2024-08-17 17:00 | 5 | Cleaner | 100 | 33 | 10 | 87 | 8
404 | 1.2.3.1.1.4 | Windows Install | 18 | 13 August 2024 8:00 AM | 2 September 2024 5:00 PM | 403 | 405,411 | 13 August 2024 8:00 AM | 2024-09-04 17:00 | 2 | Subcontractor | 100 | 96 | 15 | 65 | 15
405 | 1.2.3.1.1.5 | Level 1 Weathertight | 0 | 2 September 2024 5:00 PM | 2 September 2024 5:00 PM | 404 | 558 | 2 September 2024 5:00 PM | 2024-09-02 17:00 | 0 | Electrician | 100 | 91 | 19 | 14 | 34
406 | 1.2.3.1.2 | Lvl 2 | 83 | 17 August 2024 8:00 AM | 23 November 2024 5:00 PM |  |  | 17 August 2024 8:00 AM | 2024-11-24 17:00 | 1 | Concretor | 100 | 23 | 10 | 64 | 51
407 | 1.2.3.1.2.1 | Survey & Setout | 1 | 17 August 2024 8:00 AM | 17 August 2024 5:00 PM | 149FS+5d | 408 | 17 August 2024 8:00 AM | 2024-08-17 17:00 | 0 | Concretor | 100 | 57 | 15 | 97 | 38
408 | 1.2.3.1.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 19 August 2024 8:00 AM | 23 August 2024 5:00 PM | 407 | 577 | 19 August 2024 8:00 AM | 2024-08-23 17:00 | 0 | Reinforcement Fixer | 100 | 67 | 16 | 10 | 3
409 | 1.2.3.1.2.3 | Façade & External Walls | 22 | 9 October 2024 8:00 AM | 2 November 2024 5:00 PM | 150FS-10d | 410 | 9 October 2024 8:00 AM | 2024-11-04 17:00 | 2 | Metal Work | 100 | 98 | 22 | 20 | 50
410 | 1.2.3.1.2.4 | Windows Install | 18 | 4 November 2024 8:00 AM | 23 November 2024 5:00 PM | 409 | 411 | 4 November 2024 8:00 AM | 2024-11-25 17:00 | 2 | Painter | 100 | 77 | 31 | 94 | 37
411 | 1.2.3.1.2.5 | Level 2 Weathertight | 0 | 23 November 2024 5:00 PM | 23 November 2024 5:00 PM | 404,410 | 585 | 23 November 2024 5:00 PM | 2024-11-23 17:00 | 0 | Electrician | 100 | 96 | 27 | 20 | 55
412 | 1.2.3.1.3 | Lvl 3 | 40 | 13 November 2024 8:00 AM | 7 January 2025 5:00 PM |  |  | 13 November 2024 8:00 AM | 2025-01-08 17:00 | 1 | Metal Work | 100 | 59 | 24 | 27 | 46
413 | 1.2.3.1.3.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 174FS+5d | 414FS-1d | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Renderer | 100 | 12 | 10 | 90 | 39
414 | 1.2.3.1.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 413FS-1d |  | 30 November 2024 8:00 AM | 2024-12-04 17:00 | 0 | Tiler | 100 | 91 | 14 | 53 | 19
415 | 1.2.3.1.3.3 | Façade & External Walls | 22 | 13 November 2024 8:00 AM | 7 December 2024 5:00 PM | 174FS-10d | 416 | 13 November 2024 8:00 AM | 2024-12-12 17:00 | 5 | Stone Mason | 100 | 37 | 18 | 39 | 29
416 | 1.2.3.1.3.4 | Windows Install | 18 | 9 December 2024 8:00 AM | 7 January 2025 5:00 PM | 415 | 610FS-6d,417 | 9 December 2024 8:00 AM | 2025-01-07 17:00 | 0 | Excavation | 100 | 34 | 14 | 73 | 27
417 | 1.2.3.1.3.5 | Level 3 Weathertight | 0 | 7 January 2025 5:00 PM | 7 January 2025 5:00 PM | 416 | 612,444 | 7 January 2025 5:00 PM | 2025-01-07 17:00 | 0 | Waterproofer | 100 | 96 | 19 | 62 | 46
418 | 1.2.3.1.4 | Lvl 4 | 44 | 17 December 2024 8:00 AM | 15 February 2025 5:00 PM |  |  | 17 December 2024 8:00 AM | 2025-02-17 17:00 | 2 | Site Manager | 100 | 74 | 12 | 20 | 55
419 | 1.2.3.1.4.1 | Survey & Setout | 1 | 17 December 2024 8:00 AM | 17 December 2024 5:00 PM | 186FS+5d | 420FS-1d | 17 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Waterproofer | 100 | 67 | 22 | 67 | 7
420 | 1.2.3.1.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 17 December 2024 8:00 AM | 20 December 2024 5:00 PM | 419FS-1d | 421 | 17 December 2024 8:00 AM | 2024-12-20 17:00 | 0 | Project Manager | 100 | 29 | 14 | 43 | 31
421 | 1.2.3.1.4.3 | Façade & External Walls | 22 | 21 December 2024 8:00 AM | 24 January 2025 5:00 PM | 186FS-10d,420 | 422 | 21 December 2024 8:00 AM | 2025-01-24 17:00 | 0 | Mechanical | 100 | 14 | 33 | 78 | 2
422 | 1.2.3.1.4.4 | Windows Install | 18 | 27 January 2025 8:00 AM | 15 February 2025 5:00 PM | 421 | 637FS-6d,423 | 27 January 2025 8:00 AM | 2025-02-19 17:00 | 4 | Plasterboarder | 100 | 66 | 11 | 41 | 13
423 | 1.2.3.1.4.5 | Level 4 Weathertight | 0 | 15 February 2025 5:00 PM | 15 February 2025 5:00 PM | 422 | 639,444 | 15 February 2025 5:00 PM | 2025-02-15 17:00 | 0 | Landscaper | 100 | 83 | 33 | 19 | 8
424 | 1.2.3.1.5 | Lvl 5 | 40 | 30 November 2024 8:00 AM | 24 January 2025 5:00 PM |  |  | 30 November 2024 8:00 AM | 2025-01-24 17:00 | 0 | Electrician | 100 | 98 | 28 | 100 | 16
425 | 1.2.3.1.5.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 198FS+5d | 426FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Contract Administrator | 100 | 40 | 14 | 30 | 12
426 | 1.2.3.1.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 425FS-1d | 663 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Stone Mason | 100 | 19 | 21 | 28 | 56
427 | 1.2.3.1.5.3 | Façade & External Walls | 22 | 30 November 2024 8:00 AM | 3 January 2025 5:00 PM | 198FS-10d | 428 | 30 November 2024 8:00 AM | 2025-01-04 17:00 | 1 | Site Manager | 100 | 67 | 31 | 12 | 56
428 | 1.2.3.1.5.4 | Windows Install | 18 | 4 January 2025 8:00 AM | 24 January 2025 5:00 PM | 427 | 669FS-6d,429,444 | 4 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Surveyor | 100 | 61 | 19 | 96 | 54
429 | 1.2.3.1.5.5 | Level 5 Weathertight | 0 | 24 January 2025 5:00 PM | 24 January 2025 5:00 PM | 428 | 671 | 24 January 2025 5:00 PM | 2025-01-24 17:00 | 0 | Timber Floorer | 100 | 21 | 14 | 65 | 18
430 | 1.2.3.1.6 | Lvl 6 | 59 | 19 November 2024 8:00 AM | 5 February 2025 5:00 PM |  |  | 19 November 2024 8:00 AM | 2025-02-10 17:00 | 5 | Timber Floorer | 100 | 75 | 31 | 91 | 33
431 | 1.2.3.1.6.1 | Survey & Setout | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 209FS+5d | 432 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Admin | 100 | 80 | 18 | 56 | 36
432 | 1.2.3.1.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 6 December 2024 8:00 AM | 10 December 2024 5:00 PM | 210FS-10d,431 | 433,690 | 6 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Tiler | 100 | 17 | 15 | 95 | 46
433 | 1.2.3.1.6.3 | Façade & External Walls | 22 | 11 December 2024 8:00 AM | 14 January 2025 5:00 PM | 432 | 434 | 11 December 2024 8:00 AM | 2025-01-15 17:00 | 1 | Scaffolder | 100 | 96 | 35 | 91 | 32
434 | 1.2.3.1.6.4 | Windows Install | 18 | 15 January 2025 8:00 AM | 5 February 2025 5:00 PM | 433 | 696FS-6d,435 | 15 January 2025 8:00 AM | 2025-02-06 17:00 | 1 | Contract Administrator | 100 | 87 | 15 | 50 | 22
435 | 1.2.3.1.6.5 | Level 6 Weathertight | 0 | 5 February 2025 5:00 PM | 5 February 2025 5:00 PM | 434 | 698,444 | 5 February 2025 5:00 PM | 2025-02-05 17:00 | 0 | Floor Sealer | 100 | 79 | 32 | 11 | 36
436 | 1.2.3.1.7 | Lvl 7 | 59 | 5 December 2024 8:00 AM | 21 February 2025 5:00 PM |  |  | 5 December 2024 8:00 AM | 2025-02-26 17:00 | 5 | Post Tension | 100 | 27 | 26 | 42 | 43
437 | 1.2.3.1.7.1 | Survey & Setout | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 221FS+5d | 438FS-1d | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Metal Work | 100 | 26 | 27 | 61 | 28
438 | 1.2.3.1.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 5 December 2024 8:00 AM | 9 December 2024 5:00 PM | 437FS-1d | 722 | 5 December 2024 8:00 AM | 2024-12-09 17:00 | 0 | Metal Work | 100 | 94 | 31 | 77 | 46
439 | 1.2.3.1.7.3 | Façade & External Walls | 22 | 8 January 2025 8:00 AM | 3 February 2025 5:00 PM | 223FS+10d | 440 | 8 January 2025 8:00 AM | 2025-02-06 17:00 | 3 | Plasterboarder | 100 | 74 | 29 | 65 | 40
440 | 1.2.3.1.7.4 | Windows Install | 16 | 4 February 2025 8:00 AM | 21 February 2025 5:00 PM | 439 | 728FS-6d,441,3446FS-5d | 4 February 2025 8:00 AM | 2025-02-21 17:00 | 0 | Tiler | 100 | 51 | 20 | 13 | 53
441 | 1.2.3.1.7.5 | Level 7 Weathertight | 0 | 21 February 2025 5:00 PM | 21 February 2025 5:00 PM | 440 | 730,442 | 21 February 2025 5:00 PM | 2025-02-21 17:00 | 0 | Floor Sealer | 100 | 82 | 28 | 52 | 10
442 | 1.2.3.1.8 | Defect Rectification | 15 | 22 February 2025 8:00 AM | 11 March 2025 5:00 PM | 441 | 443 | 22 February 2025 8:00 AM | 2025-03-14 17:00 | 3 | Subcontractor | 100 | 53 | 17 | 30 | 56
443 | 1.2.3.1.9 | Strip Scaffold | 10 | 12 March 2025 8:00 AM | 22 March 2025 5:00 PM | 442 | 444,3456 | 12 March 2025 8:00 AM | 2025-03-25 17:00 | 3 | Reinforcement Fixer | 100 | 74 | 19 | 1 | 11
444 | 1.2.3.1.10 | Building A Façade Complete | 0 | 22 March 2025 5:00 PM | 22 March 2025 5:00 PM | 443,435,428,423,417 | 5 | 22 March 2025 5:00 PM | 2025-03-22 17:00 | 0 | Electrician | 100 | 38 | 11 | 61 | 40
445 | 1.2.3.2 | Building B | 89 | 4 October 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | 4 October 2024 8:00 AM | 2025-02-01 17:00 | 4 | Admin | 100 | 45 | 27 | 52 | 17
446 | 1.2.3.2.1 | Lvl 1 | 44 | 4 October 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 4 October 2024 8:00 AM | 2024-11-30 17:00 | 4 | Window | 100 | 62 | 25 | 58 | 11
447 | 1.2.3.2.1.1 | Survey & Setout | 1 | 4 October 2024 8:00 AM | 4 October 2024 5:00 PM | 241 | 448 | 4 October 2024 8:00 AM | 2024-10-04 17:00 | 0 | Window | 100 | 48 | 20 | 10 | 2
448 | 1.2.3.2.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 8 October 2024 8:00 AM | 12 October 2024 5:00 PM | 447 | 449,758,852,1322FS+6d,1510FS+6d,1416FS+6d,946FS+2d,1040FS+2d,1134FS+4d,1228FS+4d | 8 October 2024 8:00 AM | 2024-10-12 17:00 | 0 | Reinforcement Fixer | 100 | 39 | 11 | 83 | 58
449 | 1.2.3.2.1.3 | Façade & External Walls | 20 | 14 October 2024 8:00 AM | 5 November 2024 5:00 PM | 448 | 450 | 14 October 2024 8:00 AM | 2024-11-10 17:00 | 5 | Project Manager | 100 | 87 | 23 | 59 | 30
450 | 1.2.3.2.1.4 | Windows Install | 18 | 6 November 2024 8:00 AM | 26 November 2024 5:00 PM | 449 | 451 | 6 November 2024 8:00 AM | 2024-11-29 17:00 | 3 | Plumber | 100 | 89 | 22 | 82 | 38
451 | 1.2.3.2.1.5 | Level 1 Weathertight | 0 | 26 November 2024 5:00 PM | 26 November 2024 5:00 PM | 450 | 1640 | 26 November 2024 5:00 PM | 2024-11-26 17:00 | 0 | Electrician | 100 | 75 | 13 | 15 | 59
452 | 1.2.3.2.2 | Lvl 2 | 42 | 26 October 2024 8:00 AM | 13 December 2024 5:00 PM |  |  | 26 October 2024 8:00 AM | 2024-12-14 17:00 | 1 | Concretor | 100 | 31 | 28 | 24 | 10
453 | 1.2.3.2.2.1 | Survey & Setout | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 253 | 454 | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Window | 100 | 33 | 31 | 79 | 40
454 | 1.2.3.2.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 453 | 455 | 28 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Head Contractor | 100 | 16 | 10 | 12 | 59
455 | 1.2.3.2.2.3 | Façade & External Walls | 20 | 2 November 2024 8:00 AM | 25 November 2024 5:00 PM | 454 | 456 | 2 November 2024 8:00 AM | 2024-11-29 17:00 | 4 | Painter | 100 | 10 | 29 | 31 | 8
456 | 1.2.3.2.2.4 | Windows Install | 16 | 26 November 2024 8:00 AM | 13 December 2024 5:00 PM | 455 | 457 | 26 November 2024 8:00 AM | 2024-12-17 17:00 | 4 | Mechanical | 100 | 98 | 30 | 18 | 36
457 | 1.2.3.2.2.5 | Level 2 Weathertight | 0 | 13 December 2024 5:00 PM | 13 December 2024 5:00 PM | 456 |  | 13 December 2024 5:00 PM | 2024-12-13 17:00 | 0 | Excavation | 100 | 64 | 29 | 0 | 22
458 | 1.2.3.2.3 | Lvl 3 | 43 | 16 November 2024 8:00 AM | 14 January 2025 5:00 PM |  |  | 16 November 2024 8:00 AM | 2025-01-15 17:00 | 1 | Renderer | 100 | 61 | 35 | 2 | 14
459 | 1.2.3.2.3.1 | Survey & Setout | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 265 | 460 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Joiner | 100 | 82 | 35 | 42 | 13
460 | 1.2.3.2.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 459 | 461 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 100 | 73 | 11 | 23 | 51
461 | 1.2.3.2.3.3 | Façade & External Walls | 20 | 22 November 2024 8:00 AM | 14 December 2024 5:00 PM | 460 | 462 | 22 November 2024 8:00 AM | 2024-12-15 17:00 | 1 | Contract Administrator | 100 | 10 | 27 | 47 | 3
462 | 1.2.3.2.3.4 | Windows Install | 18 | 16 December 2024 8:00 AM | 14 January 2025 5:00 PM | 461 | 1638FS-6d,463 | 16 December 2024 8:00 AM | 2025-01-19 17:00 | 5 | Reinforcement Fixer | 100 | 56 | 20 | 94 | 39
463 | 1.2.3.2.3.5 | Level 3 Weathertight | 0 | 14 January 2025 5:00 PM | 14 January 2025 5:00 PM | 462 | 1640 | 14 January 2025 5:00 PM | 2025-01-14 17:00 | 0 | Admin | 100 | 88 | 34 | 32 | 37
464 | 1.2.3.2.4 | Lvl 4 | 42 | 23 November 2024 8:00 AM | 20 January 2025 5:00 PM |  |  | 23 November 2024 8:00 AM | 2025-01-23 17:00 | 3 | Formworker | 100 | 10 | 28 | 85 | 56
465 | 1.2.3.2.4.1 | Survey & Setout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 277 | 466FS-1d | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Metal Work | 100 | 67 | 10 | 83 | 24
466 | 1.2.3.2.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 23 November 2024 8:00 AM | 27 November 2024 5:00 PM | 465FS-1d | 467 | 23 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Landscaper | 100 | 16 | 28 | 32 | 10
467 | 1.2.3.2.4.3 | Façade & External Walls | 20 | 28 November 2024 8:00 AM | 20 December 2024 5:00 PM | 466 | 468 | 28 November 2024 8:00 AM | 2024-12-24 17:00 | 4 | Line Market | 100 | 82 | 15 | 4 | 34
468 | 1.2.3.2.4.4 | Windows Install | 18 | 21 December 2024 8:00 AM | 20 January 2025 5:00 PM | 467 | 1665FS-6d,469 | 21 December 2024 8:00 AM | 2025-01-24 17:00 | 4 | Landscaper | 100 | 84 | 31 | 84 | 37
469 | 1.2.3.2.4.5 | Level 4 Weathertight | 0 | 20 January 2025 5:00 PM | 20 January 2025 5:00 PM | 468 | 1665FS-6d | 20 January 2025 5:00 PM | 2025-01-20 17:00 | 0 | Carpet | 100 | 64 | 17 | 59 | 54
470 | 1.2.3.2.5 | Lvl 5 | 42 | 26 November 2024 8:00 AM | 22 January 2025 5:00 PM |  |  | 26 November 2024 8:00 AM | 2025-01-26 17:00 | 4 | Head Contractor | 100 | 18 | 13 | 15 | 57
471 | 1.2.3.2.5.1 | Survey & Setout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 289 | 472FS-1d | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Subcontractor | 100 | 73 | 18 | 44 | 21
472 | 1.2.3.2.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 26 November 2024 8:00 AM | 29 November 2024 5:00 PM | 471FS-1d | 473 | 26 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Window | 100 | 33 | 16 | 0 | 18
473 | 1.2.3.2.5.3 | Façade & External Walls | 20 | 30 November 2024 8:00 AM | 23 December 2024 5:00 PM | 472 | 474 | 30 November 2024 8:00 AM | 2024-12-28 17:00 | 5 | Timber Floorer | 100 | 100 | 35 | 16 | 11
474 | 1.2.3.2.5.4 | Windows Install | 18 | 24 December 2024 8:00 AM | 22 January 2025 5:00 PM | 473 | 475 | 24 December 2024 8:00 AM | 2025-01-27 17:00 | 5 | Surveyor | 100 | 94 | 16 | 53 | 13
475 | 1.2.3.2.5.5 | Level 5 Weathertight | 0 | 22 January 2025 5:00 PM | 22 January 2025 5:00 PM | 474 | 1692FS-4d | 22 January 2025 5:00 PM | 2025-01-22 17:00 | 0 | Foreman | 100 | 67 | 33 | 38 | 8
476 | 1.2.3.2.6 | Lvl 6 | 42 | 30 November 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | 30 November 2024 8:00 AM | 2025-01-28 17:00 | 0 | Renderer | 100 | 37 | 25 | 13 | 3
477 | 1.2.3.2.6.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 301 | 478FS-1d | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Concretor | 100 | 77 | 27 | 46 | 8
478 | 1.2.3.2.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 477FS-1d | 479 | 30 November 2024 8:00 AM | 2024-12-04 17:00 | 0 | Fire | 100 | 57 | 14 | 10 | 17
479 | 1.2.3.2.6.3 | Façade & External Walls | 20 | 5 December 2024 8:00 AM | 6 January 2025 5:00 PM | 478 | 480 | 5 December 2024 8:00 AM | 2025-01-10 17:00 | 4 | Window | 100 | 26 | 30 | 99 | 52
480 | 1.2.3.2.6.4 | Windows Install | 18 | 7 January 2025 8:00 AM | 28 January 2025 5:00 PM | 479 | 481 | 7 January 2025 8:00 AM | 2025-01-29 17:00 | 1 | Painter | 100 | 46 | 22 | 90 | 44
481 | 1.2.3.2.6.5 | Level 6 Weathertight | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 480 | 1719FS-6d,482 | 28 January 2025 5:00 PM | 2025-01-28 17:00 | 0 | Excavation | 100 | 63 | 14 | 80 | 9
482 | 1.2.3.2.6.6 | Building B Façade Complete | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 481 | 6 | 28 January 2025 5:00 PM | 2025-01-28 17:00 | 0 | Landscaper | 100 | 59 | 23 | 12 | 56
483 | 1.2.3.3 | Building C | 63 | 27 November 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-02-21 17:00 | 3 | Formworker | 100 | 52 | 24 | 76 | 2
484 | 1.2.3.3.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-01-28 17:00 | 1 | Site Manager | 100 | 51 | 22 | 13 | 7
485 | 1.2.3.3.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 486 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Timber Floorer | 100 | 30 | 24 | 84 | 51
486 | 1.2.3.3.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 485 | 487 | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Timber Floorer | 100 | 68 | 32 | 57 | 34
487 | 1.2.3.3.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 486 | 488 | 4 December 2024 8:00 AM | 2025-01-06 17:00 | 2 | Joiner | 100 | 75 | 21 | 52 | 7
488 | 1.2.3.3.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 487 |  | 6 January 2025 8:00 AM | 2025-02-01 17:00 | 5 | Floor Sealer | 100 | 27 | 21 | 33 | 29
489 | 1.2.3.3.2 | Lvl 2 | 44 | 16 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | 16 December 2024 8:00 AM | 2025-02-14 17:00 | 0 | Project Manager | 100 | 40 | 22 | 72 | 57
490 | 1.2.3.3.2.1 | Survey & Setout | 1 | 16 December 2024 8:00 AM | 16 December 2024 5:00 PM | 331 | 491 | 16 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Hoarding | 100 | 46 | 20 | 49 | 11
491 | 1.2.3.3.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 17 December 2024 8:00 AM | 21 December 2024 5:00 PM | 490 | 492 | 17 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Electrician | 100 | 55 | 31 | 23 | 14
492 | 1.2.3.3.2.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 491 | 493 | 23 December 2024 8:00 AM | 2025-01-26 17:00 | 3 | Tiler | 100 | 49 | 27 | 33 | 47
493 | 1.2.3.3.2.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 492 |  | 24 January 2025 8:00 AM | 2025-02-15 17:00 | 1 | Window | 100 | 35 | 35 | 100 | 52
494 | 1.2.3.3.3 | Lvl 3 | 42 | 21 December 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | 21 December 2024 8:00 AM | 2025-02-22 17:00 | 4 | Waterproofer | 100 | 66 | 14 | 80 | 32
495 | 1.2.3.3.3.1 | Survey & Setout | 1 | 21 December 2024 8:00 AM | 21 December 2024 5:00 PM | 343 | 496FS-1d | 21 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Excavation | 100 | 50 | 14 | 72 | 14
496 | 1.2.3.3.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 21 December 2024 8:00 AM | 3 January 2025 5:00 PM | 495FS-1d | 497 | 21 December 2024 8:00 AM | 2025-01-03 17:00 | 0 | Stone Mason | 100 | 90 | 22 | 53 | 3
497 | 1.2.3.3.3.3 | Façade & External Walls | 20 | 4 January 2025 8:00 AM | 28 January 2025 5:00 PM | 496 | 498 | 4 January 2025 8:00 AM | 2025-01-30 17:00 | 2 | Waterproofer | 100 | 12 | 29 | 40 | 4
498 | 1.2.3.3.3.4 | Windows Install | 18 | 29 January 2025 8:00 AM | 18 February 2025 5:00 PM | 497 | 2654FS-6d | 29 January 2025 8:00 AM | 2025-02-20 17:00 | 2 | Tiler | 100 | 82 | 24 | 98 | 38
499 | 1.2.3.3.4 | Lvl 4 | 42 | 18 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-02-18 17:00 | 4 | Admin | 100 | 56 | 13 | 19 | 58
500 | 1.2.3.3.4.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 355 | 501FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Carpenter | 100 | 80 | 33 | 92 | 50
501 | 1.2.3.3.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 500FS-1d | 502 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Timber Floorer | 100 | 17 | 33 | 94 | 51
502 | 1.2.3.3.4.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 501 | 503 | 23 December 2024 8:00 AM | 2025-01-26 17:00 | 3 | Development Manager | 100 | 56 | 35 | 78 | 59
503 | 1.2.3.3.4.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 502 | 3151FS-6d,7 | 24 January 2025 8:00 AM | 2025-02-15 17:00 | 1 | Cleaner | 100 | 10 | 26 | 50 | 22
504 | 1.2.3.4 | Building D | 62 | 27 November 2024 8:00 AM | 17 February 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-02-17 17:00 | 0 | Landscaper | 100 | 67 | 12 | 11 | 54
505 | 1.2.3.4.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-01-29 17:00 | 2 | Electrician | 100 | 74 | 21 | 86 | 30
506 | 1.2.3.4.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 507 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Mechanical | 100 | 66 | 24 | 83 | 49
507 | 1.2.3.4.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 506 | 508,3361 | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Stone Mason | 100 | 76 | 13 | 96 | 10
508 | 1.2.3.4.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 507 | 509 | 4 December 2024 8:00 AM | 2025-01-05 17:00 | 1 | Electrician | 100 | 66 | 16 | 70 | 26
509 | 1.2.3.4.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 508 |  | 6 January 2025 8:00 AM | 2025-01-30 17:00 | 3 | Tiler | 100 | 14 | 19 | 78 | 58
510 | 1.2.3.4.2 | Lvl 2 | 44 | 2 December 2024 8:00 AM | 31 January 2025 5:00 PM |  |  | 2 December 2024 8:00 AM | 2025-02-05 17:00 | 5 | Admin | 100 | 20 | 30 | 80 | 28
511 | 1.2.3.4.2.1 | Survey & Setout | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 385 | 512 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Cleaner | 100 | 18 | 11 | 72 | 41
512 | 1.2.3.4.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 3 December 2024 8:00 AM | 7 December 2024 5:00 PM | 511 | 513,3388 | 3 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Tiler | 100 | 21 | 11 | 94 | 35
513 | 1.2.3.4.2.3 | Façade & External Walls | 20 | 9 December 2024 8:00 AM | 9 January 2025 5:00 PM | 512 | 514 | 9 December 2024 8:00 AM | 2025-01-13 17:00 | 4 | Subcontractor | 100 | 67 | 16 | 12 | 3
514 | 1.2.3.4.2.4 | Windows Install | 18 | 10 January 2025 8:00 AM | 31 January 2025 5:00 PM | 513 |  | 10 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Mechanical | 100 | 91 | 20 | 6 | 26
515 | 1.2.3.4.3 | Lvl 3 | 37 | 4 January 2025 8:00 AM | 17 February 2025 5:00 PM |  |  | 4 January 2025 8:00 AM | 2025-02-20 17:00 | 3 | Fire | 100 | 49 | 16 | 38 | 19
516 | 1.2.3.4.3.1 | Survey & Setout | 1 | 4 January 2025 8:00 AM | 4 January 2025 5:00 PM | 396 | 517FS-1d | 4 January 2025 8:00 AM | 2025-01-04 17:00 | 0 | Development Manager | 100 | 44 | 15 | 71 | 31
517 | 1.2.3.4.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 3 | 4 January 2025 8:00 AM | 7 January 2025 5:00 PM | 516FS-1d | 518,3415 | 4 January 2025 8:00 AM | 2025-01-07 17:00 | 0 | Hoarding | 100 | 47 | 28 | 91 | 6
518 | 1.2.3.4.3.3 | Façade & External Walls | 18 | 8 January 2025 8:00 AM | 29 January 2025 5:00 PM | 517 | 519 | 8 January 2025 8:00 AM | 2025-01-31 17:00 | 2 | Excavation | 100 | 71 | 16 | 93 | 52
519 | 1.2.3.4.3.4 | Windows Install | 16 | 30 January 2025 8:00 AM | 17 February 2025 5:00 PM | 518 | 3421FS-6d,8 | 30 January 2025 8:00 AM | 2025-02-17 17:00 | 0 | Carpenter | 100 | 85 | 28 | 29 | 43
520 | 1.2.4 | FIT-OUT WORKS | 185 | 13 September 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 13 September 2024 8:00 AM | 2025-05-06 17:00 | 1 | Hoarding | 100 | 11 | 17 | 61 | 51
521 | 1.2.4.1 | Basement 2 - Services & Fitoff | 140 | 13 September 2024 8:00 AM | 7 March 2025 5:00 PM |  |  | 13 September 2024 8:00 AM | 2025-03-12 17:00 | 5 | Landscaper | 100 | 43 | 27 | 67 | 13
522 | 1.2.4.1.1 | Services rough in | 60 | 13 September 2024 8:00 AM | 23 November 2024 5:00 PM | 107 | 523 | 13 September 2024 8:00 AM | 2024-11-23 17:00 | 0 | Plumber | 100 | 58 | 33 | 81 | 31
523 | 1.2.4.1.2 | Block walls (Metal Door Frames) | 6 | 25 November 2024 8:00 AM | 30 November 2024 5:00 PM | 522 | 524,525 | 25 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Window | 100 | 57 | 31 | 65 | 10
524 | 1.2.4.1.3 | Render works as specified | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 527 | 2 December 2024 8:00 AM | 2024-12-19 17:00 | 5 | Reinforcement Fixer | 100 | 39 | 27 | 92 | 16
525 | 1.2.4.1.4 | Carpentry fitoff | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 526 | 2 December 2024 8:00 AM | 2024-12-18 17:00 | 4 | Painter | 100 | 79 | 13 | 2 | 50
526 | 1.2.4.1.5 | Services Plant & Equipment Install | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 525 |  | 16 December 2024 8:00 AM | 2025-01-11 17:00 | 4 | Post Tension | 100 | 54 | 24 | 59 | 3
527 | 1.2.4.1.6 | Doors & Hardware | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 524 | 528 | 16 December 2024 8:00 AM | 2025-01-11 17:00 | 4 | Carpet | 100 | 34 | 34 | 93 | 12
528 | 1.2.4.1.7 | Services Fitoff | 12 | 8 January 2025 8:00 AM | 21 January 2025 5:00 PM | 527 | 529 | 8 January 2025 8:00 AM | 2025-01-25 17:00 | 4 | Carpet | 100 | 11 | 35 | 69 | 33
529 | 1.2.4.1.8 | Finishes & Painting | 12 | 22 January 2025 8:00 AM | 5 February 2025 5:00 PM | 528 | 530 | 22 January 2025 8:00 AM | 2025-02-07 17:00 | 2 | Carpet | 100 | 81 | 23 | 76 | 58
530 | 1.2.4.1.9 | Metalwork Items | 8 | 6 February 2025 8:00 AM | 14 February 2025 5:00 PM | 529 | 531 | 6 February 2025 8:00 AM | 2025-02-19 17:00 | 5 | Carpet | 100 | 27 | 26 | 22 | 18
531 | 1.2.4.1.10 | Builders Clean | 6 | 15 February 2025 8:00 AM | 21 February 2025 5:00 PM | 530 | 532 | 15 February 2025 8:00 AM | 2025-02-22 17:00 | 1 | Painter | 100 | 61 | 20 | 60 | 9
532 | 1.2.4.1.11 | Car Park Clean, Patch and Floor Sealer | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 531 | 533 | 22 February 2025 8:00 AM | 2025-03-04 17:00 | 1 | Waterproofer | 100 | 72 | 31 | 23 | 38
533 | 1.2.4.1.12 | Line Marking | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 532 |  | 4 March 2025 8:00 AM | 2025-03-07 17:00 | 0 | Excavation | 100 | 93 | 31 | 3 | 27
534 | 1.2.4.2 | Basement 1 - Services & Fitoff | 140 | 1 October 2024 8:00 AM | 25 March 2025 5:00 PM |  |  | 1 October 2024 8:00 AM | 2025-03-29 17:00 | 4 | Painter | 100 | 47 | 22 | 79 | 3
535 | 1.2.4.2.1 | Services rough in | 60 | 1 October 2024 8:00 AM | 11 December 2024 5:00 PM | 119 | 536 | 1 October 2024 8:00 AM | 2024-12-11 17:00 | 0 | Electrician | 100 | 89 | 18 | 24 | 34
536 | 1.2.4.2.2 | Block walls (Metal Door Frames) | 6 | 12 December 2024 8:00 AM | 18 December 2024 5:00 PM | 535 | 537,538 | 12 December 2024 8:00 AM | 2024-12-20 17:00 | 2 | Plasterboarder | 100 | 81 | 24 | 44 | 31
537 | 1.2.4.2.3 | Render works as specified | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 540 | 19 December 2024 8:00 AM | 2025-01-13 17:00 | 3 | Carpet | 100 | 40 | 20 | 22 | 15
538 | 1.2.4.2.4 | Carpentry fitoff | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 539 | 19 December 2024 8:00 AM | 2025-01-14 17:00 | 4 | Timber Floorer | 100 | 46 | 22 | 0 | 41
539 | 1.2.4.2.5 | Services Plant & Equipment Install | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 538 |  | 11 January 2025 8:00 AM | 2025-01-27 17:00 | 3 | Subcontractor | 100 | 67 | 16 | 77 | 36
540 | 1.2.4.2.6 | Doors & Hardware | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 537 | 541 | 11 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Joiner | 100 | 83 | 32 | 11 | 27
541 | 1.2.4.2.7 | Services Fitoff | 12 | 27 January 2025 8:00 AM | 8 February 2025 5:00 PM | 540 | 542 | 27 January 2025 8:00 AM | 2025-02-11 17:00 | 3 | Hoarding | 100 | 92 | 14 | 63 | 43
542 | 1.2.4.2.8 | Finishes & Painting | 12 | 10 February 2025 8:00 AM | 22 February 2025 5:00 PM | 541 | 543 | 10 February 2025 8:00 AM | 2025-02-27 17:00 | 5 | Head Contractor | 100 | 59 | 22 | 30 | 11
543 | 1.2.4.2.9 | Metalwork Items | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 542 | 544 | 24 February 2025 8:00 AM | 2025-03-05 17:00 | 1 | Concretor | 100 | 100 | 19 | 7 | 53
544 | 1.2.4.2.10 | Builders Clean | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 543 | 545 | 5 March 2025 8:00 AM | 2025-03-13 17:00 | 2 | Reinforcement Fixer | 100 | 99 | 33 | 94 | 29
545 | 1.2.4.2.11 | Car Park Clean, Patch and Floor Sealer | 8 | 12 March 2025 8:00 AM | 20 March 2025 5:00 PM | 544 | 546 | 12 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Concretor | 100 | 93 | 33 | 72 | 28
546 | 1.2.4.2.12 | Line Marking | 4 | 21 March 2025 8:00 AM | 25 March 2025 5:00 PM | 545 |  | 21 March 2025 8:00 AM | 2025-03-25 17:00 | 0 | Electrician | 100 | 67 | 20 | 100 | 35
547 | 1.2.4.3 | Building A | 155 | 21 October 2024 8:00 AM | 5 May 2025 5:00 PM |  | 3440 | 21 October 2024 8:00 AM | 2025-05-10 17:00 | 5 | Tiler | 100 | 83 | 19 | 61 | 32
548 | 1.2.4.3.1 | Lvl 1 - Services & Finishes | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-14 17:00 | 1 | Metal Work | 100 | 73 | 13 | 48 | 17
549 | 1.2.4.3.1.1 | Internal Works | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-15 17:00 | 2 | Scaffolder | 100 | 83 | 34 | 44 | 35
550 | 1.2.4.3.1.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 150 | 551FS-2d | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Site Manager | 100 | 59 | 35 | 31 | 51
551 | 1.2.4.3.1.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 550FS-2d | 552 | 21 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Landscaper | 100 | 75 | 12 | 67 | 49
552 | 1.2.4.3.1.1.3 | Internal Wall Framing | 10 | 1 November 2024 8:00 AM | 12 November 2024 5:00 PM | 551 | 554,553 | 1 November 2024 8:00 AM | 2024-11-16 17:00 | 4 | Floor Sealer | 100 | 22 | 22 | 76 | 45
553 | 1.2.4.3.1.1.4 | Sheet one side of walls | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 556,555 | 13 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Excavation | 100 | 53 | 28 | 29 | 24
554 | 1.2.4.3.1.1.5 | Service Rough-In | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 555 | 13 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Cleaner | 100 | 47 | 28 | 97 | 26
555 | 1.2.4.3.1.1.6 | ITP for services in the walls | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 553,554 | 556,562 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Reinforcement Fixer | 100 | 73 | 29 | 73 | 42
556 | 1.2.4.3.1.1.7 | Sheet other side of walls | 8 | 25 November 2024 8:00 AM | 3 December 2024 5:00 PM | 553,555 | 557 | 25 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Stone Mason | 100 | 70 | 15 | 12 | 40
557 | 1.2.4.3.1.1.8 | Frame & Sheet Ceilings | 8 | 4 December 2024 8:00 AM | 12 December 2024 5:00 PM | 556 | 558 | 4 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Excavation | 100 | 76 | 34 | 73 | 3
558 | 1.2.4.3.1.1.9 | Sheet, Set & Sand Ceilings | 8 | 13 December 2024 8:00 AM | 21 December 2024 5:00 PM | 557,405 | 559 | 13 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Formworker | 100 | 51 | 27 | 13 | 4
559 | 1.2.4.3.1.1.10 | Paint undercoat | 4 | 23 December 2024 8:00 AM | 4 January 2025 5:00 PM | 558 | 560 | 23 December 2024 8:00 AM | 2025-01-04 17:00 | 0 | Window | 100 | 84 | 27 | 82 | 10
560 | 1.2.4.3.1.1.11 | Floor Levelling and Floor Finish | 6 | 6 January 2025 8:00 AM | 11 January 2025 5:00 PM | 559 | 561 | 6 January 2025 8:00 AM | 2025-01-14 17:00 | 3 | Hoarding | 100 | 51 | 20 | 38 | 39
561 | 1.2.4.3.1.1.12 | Timber Flooring | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 560 | 567,568,563 | 13 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Line Market | 100 | 81 | 24 | 88 | 18
562 | 1.2.4.3.1.1.13 | Measure & Manufacture Joinery | 40 | 25 November 2024 8:00 AM | 18 January 2025 5:00 PM | 555 | 563 | 25 November 2024 8:00 AM | 2025-01-21 17:00 | 3 | Mechanical | 100 | 57 | 17 | 8 | 20
563 | 1.2.4.3.1.1.14 | Install Joinery | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 561,562 | 565 | 22 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Cleaner | 100 | 91 | 27 | 64 | 6
564 | 1.2.4.3.1.1.15 | Measure & Manufacture Stone Benchtops | 12 | 17 January 2025 8:00 AM | 1 February 2025 8:00 AM | 565SF |  | 17 January 2025 8:00 AM | 2025-02-04 08:00 | 3 | Project Manager | 100 | 59 | 16 | 15 | 52
565 | 1.2.4.3.1.1.16 | Install Stone Benchtops | 5 | 1 February 2025 8:00 AM | 6 February 2025 5:00 PM | 563 | 564SF,566 | 1 February 2025 8:00 AM | 2025-02-06 17:00 | 0 | Contract Administrator | 100 | 43 | 30 | 30 | 29
566 | 1.2.4.3.1.1.17 | Fixtures & Fittings Fit-off | 3 | 7 February 2025 8:00 AM | 10 February 2025 5:00 PM | 565 | 574 | 7 February 2025 8:00 AM | 2025-02-10 17:00 | 0 | Surveyor | 100 | 44 | 30 | 46 | 13
567 | 1.2.4.3.1.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 561 | 569 | 22 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Cleaner | 100 | 83 | 15 | 32 | 27
568 | 1.2.4.3.1.1.19 | Lighting Fit-off | 3 | 22 January 2025 8:00 AM | 24 January 2025 5:00 PM | 561 | 569 | 22 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Site Manager | 100 | 35 | 23 | 18 | 57
569 | 1.2.4.3.1.1.20 | Setting Defects | 4 | 28 January 2025 8:00 AM | 31 January 2025 5:00 PM | 567,568 | 570 | 28 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Landscaper | 100 | 90 | 31 | 80 | 7
570 | 1.2.4.3.1.1.21 | Paint Finish Coat | 4 | 1 February 2025 8:00 AM | 5 February 2025 5:00 PM | 569 | 573,571 | 1 February 2025 8:00 AM | 2025-02-05 17:00 | 0 | Development Manager | 100 | 16 | 34 | 94 | 22
571 | 1.2.4.3.1.1.22 | Carpet | 3 | 6 February 2025 8:00 AM | 8 February 2025 5:00 PM | 570 | 572 | 6 February 2025 8:00 AM | 2025-02-08 17:00 | 0 | Head Contractor | 100 | 26 | 29 | 74 | 55
572 | 1.2.4.3.1.1.23 | Final Clean & Commissioning | 4 | 10 February 2025 8:00 AM | 13 February 2025 5:00 PM | 571 |  | 10 February 2025 8:00 AM | 2025-02-13 17:00 | 0 | Cleaner | 100 | 23 | 31 | 0 | 10
573 | 1.2.4.3.1.1.24 | Defects Inspections & Rectifications | 6 | 6 February 2025 8:00 AM | 12 February 2025 5:00 PM | 570 | 574 | 6 February 2025 8:00 AM | 2025-02-13 17:00 | 1 | Carpenter | 100 | 48 | 15 | 56 | 10
574 | 1.2.4.3.1.2 | LVL 1 - FITOUT COMPLETE | 0 | 12 February 2025 5:00 PM | 12 February 2025 5:00 PM | 566,573 |  | 12 February 2025 5:00 PM | 2025-02-12 17:00 | 0 | Project Manager | 100 | 40 | 22 | 65 | 37
575 | 1.2.4.3.2 | Lvl 2 - Services & Finishes | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-11 17:00 | 5 | Window | 100 | 18 | 28 | 79 | 12
576 | 1.2.4.3.2.1 | Internal Works | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-10 17:00 | 4 | Plumber | 100 | 27 | 19 | 42 | 60
577 | 1.2.4.3.2.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 408,150 | 578FS-2d | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Fire | 100 | 67 | 20 | 94 | 20
578 | 1.2.4.3.2.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 577FS-2d | 579 | 21 October 2024 8:00 AM | 2024-11-02 17:00 | 2 | Hoarding | 100 | 31 | 14 | 67 | 34
579 | 1.2.4.3.2.1.3 | Internal Wall Framing | 8 | 1 November 2024 8:00 AM | 9 November 2024 5:00 PM | 578 | 581,580 | 1 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Carpet | 100 | 79 | 19 | 63 | 33
580 | 1.2.4.3.2.1.4 | Sheet one side of walls | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 583,582 | 11 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Contract Administrator | 100 | 91 | 30 | 89 | 25
581 | 1.2.4.3.2.1.5 | Service Rough-In | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 582 | 11 November 2024 8:00 AM | 2024-11-21 17:00 | 2 | Carpenter | 100 | 73 | 12 | 13 | 40
582 | 1.2.4.3.2.1.6 | ITP for services in the walls | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 580,581 | 583,589 | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Mechanical | 100 | 66 | 22 | 30 | 39
583 | 1.2.4.3.2.1.7 | Sheet other side of walls | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 580,582 | 584 | 22 November 2024 8:00 AM | 2024-12-03 17:00 | 3 | Contract Administrator | 100 | 66 | 34 | 18 | 45
584 | 1.2.4.3.2.1.8 | Frame & Sheet Ceilings | 8 | 2 December 2024 8:00 AM | 10 December 2024 5:00 PM | 583 | 585 | 2 December 2024 8:00 AM | 2024-12-12 17:00 | 2 | Head Contractor | 100 | 80 | 23 | 70 | 7
585 | 1.2.4.3.2.1.9 | Sheet, Set & Sand Ceilings | 8 | 11 December 2024 8:00 AM | 19 December 2024 5:00 PM | 584,411 | 586 | 11 December 2024 8:00 AM | 2024-12-21 17:00 | 2 | Line Market | 100 | 61 | 18 | 62 | 31
586 | 1.2.4.3.2.1.10 | Paint undercoat | 4 | 20 December 2024 8:00 AM | 24 December 2024 5:00 PM | 585 | 587 | 20 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Foreman | 100 | 80 | 12 | 26 | 8
587 | 1.2.4.3.2.1.11 | Floor Levelling and Floor Finish | 6 | 3 January 2025 8:00 AM | 9 January 2025 5:00 PM | 586 | 588 | 3 January 2025 8:00 AM | 2025-01-12 17:00 | 3 | Concretor | 100 | 72 | 30 | 38 | 38
588 | 1.2.4.3.2.1.12 | Timber Flooring | 6 | 10 January 2025 8:00 AM | 16 January 2025 5:00 PM | 587 | 594,595,590 | 10 January 2025 8:00 AM | 2025-01-16 17:00 | 0 | Head Contractor | 100 | 44 | 32 | 67 | 10
589 | 1.2.4.3.2.1.13 | Measure & Manufacture Joinery | 40 | 22 November 2024 8:00 AM | 16 January 2025 5:00 PM | 582 | 590 | 22 November 2024 8:00 AM | 2025-01-18 17:00 | 2 | Hoarding | 100 | 44 | 10 | 45 | 49
590 | 1.2.4.3.2.1.14 | Install Joinery | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 588,589 | 592 | 17 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Plumber | 100 | 25 | 29 | 85 | 19
591 | 1.2.4.3.2.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 January 2025 8:00 AM | 28 January 2025 8:00 AM | 592SF |  | 13 January 2025 8:00 AM | 2025-01-28 08:00 | 0 | Metal Work | 100 | 66 | 24 | 95 | 25
592 | 1.2.4.3.2.1.16 | Install Stone Benchtops | 5 | 28 January 2025 8:00 AM | 1 February 2025 5:00 PM | 590 | 591SF,593 | 28 January 2025 8:00 AM | 2025-02-01 17:00 | 0 | Concretor | 100 | 36 | 11 | 73 | 44
593 | 1.2.4.3.2.1.17 | Fixtures & Fittings Fit-off | 3 | 3 February 2025 8:00 AM | 5 February 2025 5:00 PM | 592 | 601 | 3 February 2025 8:00 AM | 2025-02-05 17:00 | 0 | Plumber | 100 | 59 | 22 | 44 | 18
594 | 1.2.4.3.2.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 17 January 2025 8:00 AM | 21 January 2025 5:00 PM | 588 | 596 | 17 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Formworker | 100 | 36 | 13 | 27 | 48
595 | 1.2.4.3.2.1.19 | Lighting Fit-off | 3 | 17 January 2025 8:00 AM | 20 January 2025 5:00 PM | 588 | 596 | 17 January 2025 8:00 AM | 2025-01-20 17:00 | 0 | Painter | 100 | 96 | 15 | 29 | 31
596 | 1.2.4.3.2.1.20 | Setting Defects | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 594,595 | 597 | 22 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Formworker | 100 | 33 | 33 | 86 | 9
597 | 1.2.4.3.2.1.21 | Paint Finish Coat | 3 | 28 January 2025 8:00 AM | 30 January 2025 5:00 PM | 596 | 600,598 | 28 January 2025 8:00 AM | 2025-01-30 17:00 | 0 | Electrician | 100 | 40 | 19 | 61 | 5
598 | 1.2.4.3.2.1.22 | Carpet | 2 | 31 January 2025 8:00 AM | 1 February 2025 5:00 PM | 597 | 599 | 31 January 2025 8:00 AM | 2025-02-01 17:00 | 0 | Post Tension | 100 | 58 | 20 | 17 | 47
599 | 1.2.4.3.2.1.23 | Final Clean & Commissioning | 4 | 3 February 2025 8:00 AM | 6 February 2025 5:00 PM | 598 |  | 3 February 2025 8:00 AM | 2025-02-06 17:00 | 0 | Waterproofer | 100 | 27 | 32 | 89 | 27
600 | 1.2.4.3.2.1.24 | Defects Inspections & Rectifications | 6 | 31 January 2025 8:00 AM | 6 February 2025 5:00 PM | 597 | 601 | 31 January 2025 8:00 AM | 2025-02-08 17:00 | 2 | Plasterboarder | 100 | 75 | 21 | 82 | 32
601 | 1.2.4.3.2.2 | LVL 2 - FITOUT COMPLETE | 0 | 6 February 2025 5:00 PM | 6 February 2025 5:00 PM | 593,600 |  | 6 February 2025 5:00 PM | 2025-02-06 17:00 | 0 | Carpenter | 100 | 92 | 34 | 14 | 53
602 | 1.2.4.3.3 | Lvl 3 - Services & Finishes | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | 25 November 2024 8:00 AM | 2025-03-21 17:00 | 4 | Scaffolder | 100 | 92 | 27 | 92 | 7
603 | 1.2.4.3.3.1 | Internal Works | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | 25 November 2024 8:00 AM | 2025-03-22 17:00 | 5 | Foreman | 100 | 24 | 27 | 76 | 22
604 | 1.2.4.3.3.1.1 | Pre-load Levels | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 174 | 605FS-2d | 25 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Carpenter | 100 | 70 | 21 | 11 | 60
605 | 1.2.4.3.3.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 25 November 2024 8:00 AM | 5 December 2024 5:00 PM | 604FS-2d | 606 | 25 November 2024 8:00 AM | 2024-12-08 17:00 | 3 | Stone Mason | 100 | 36 | 27 | 51 | 47
606 | 1.2.4.3.3.1.3 | Internal Wall Framing | 8 | 6 December 2024 8:00 AM | 14 December 2024 5:00 PM | 605 | 608,607 | 6 December 2024 8:00 AM | 2024-12-14 17:00 | 0 | Surveyor | 100 | 28 | 30 | 2 | 15
607 | 1.2.4.3.3.1.4 | Sheet one side of walls | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 610,609 | 16 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Renderer | 100 | 59 | 19 | 60 | 60
608 | 1.2.4.3.3.1.5 | Service Rough-In | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 609 | 16 December 2024 8:00 AM | 2024-12-25 17:00 | 1 | Carpet | 100 | 82 | 14 | 10 | 17
609 | 1.2.4.3.3.1.6 | ITP for services in the walls | 2 | 3 January 2025 8:00 AM | 4 January 2025 5:00 PM | 607,608 | 610,616 | 3 January 2025 8:00 AM | 2025-01-04 17:00 | 0 | Subcontractor | 100 | 85 | 15 | 41 | 46
610 | 1.2.4.3.3.1.7 | Sheet other side of walls | 8 | 6 January 2025 8:00 AM | 14 January 2025 5:00 PM | 607,609,416FS-6d | 611 | 6 January 2025 8:00 AM | 2025-01-15 17:00 | 1 | Fire | 100 | 97 | 19 | 28 | 22
611 | 1.2.4.3.3.1.8 | Frame & Sheet Ceilings | 8 | 15 January 2025 8:00 AM | 23 January 2025 5:00 PM | 610 | 612 | 15 January 2025 8:00 AM | 2025-01-24 17:00 | 1 | Reinforcement Fixer | 100 | 91 | 29 | 19 | 19
612 | 1.2.4.3.3.1.9 | Sheet, Set & Sand Ceilings | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 611,417 | 613 | 24 January 2025 8:00 AM | 2025-02-05 17:00 | 2 | Fire | 100 | 38 | 26 | 2 | 39
613 | 1.2.4.3.3.1.10 | Paint undercoat | 4 | 4 February 2025 8:00 AM | 7 February 2025 5:00 PM | 612 | 614 | 4 February 2025 8:00 AM | 2025-02-07 17:00 | 0 | Mechanical | 100 | 94 | 13 | 3 | 59
614 | 1.2.4.3.3.1.11 | Floor Levelling and Floor Finish | 7 | 8 February 2025 8:00 AM | 15 February 2025 5:00 PM | 613 | 615 | 8 February 2025 8:00 AM | 2025-02-16 17:00 | 1 | Surveyor | 100 | 80 | 34 | 75 | 48
615 | 1.2.4.3.3.1.12 | Timber Flooring | 6 | 17 February 2025 8:00 AM | 22 February 2025 5:00 PM | 614 | 621,622,617 | 17 February 2025 8:00 AM | 2025-02-22 17:00 | 0 | Plasterboarder | 100 | 63 | 24 | 42 | 51
616 | 1.2.4.3.3.1.13 | Measure & Manufacture Joinery | 40 | 6 January 2025 8:00 AM | 21 February 2025 5:00 PM | 609 | 617 | 6 January 2025 8:00 AM | 2025-02-21 17:00 | 0 | Metal Work | 100 | 91 | 11 | 40 | 36
617 | 1.2.4.3.3.1.14 | Install Joinery | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 615,616 | 619 | 24 February 2025 8:00 AM | 2025-03-04 17:00 | 0 | Renderer | 100 | 15 | 32 | 55 | 14
618 | 1.2.4.3.3.1.15 | Measure & Manufacture Stone Benchtops | 12 | 19 February 2025 8:00 AM | 5 March 2025 8:00 AM | 619SF |  | 19 February 2025 8:00 AM | 2025-03-07 08:00 | 2 | Carpet | 100 | 77 | 34 | 38 | 29
619 | 1.2.4.3.3.1.16 | Install Stone Benchtops | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 617 | 618SF,620 | 5 March 2025 8:00 AM | 2025-03-11 17:00 | 0 | Tiler | 100 | 99 | 31 | 51 | 44
620 | 1.2.4.3.3.1.17 | Fixtures & Fittings Fit-off | 3 | 12 March 2025 8:00 AM | 14 March 2025 5:00 PM | 619 | 628 | 12 March 2025 8:00 AM | 2025-03-14 17:00 | 0 | Foreman | 100 | 10 | 28 | 2 | 14
621 | 1.2.4.3.3.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 24 February 2025 8:00 AM | 27 February 2025 5:00 PM | 615 | 623 | 24 February 2025 8:00 AM | 2025-02-27 17:00 | 0 | Head Contractor | 100 | 15 | 16 | 80 | 23
622 | 1.2.4.3.3.1.19 | Lighting Fit-off | 3 | 24 February 2025 8:00 AM | 26 February 2025 5:00 PM | 615 | 623 | 24 February 2025 8:00 AM | 2025-02-26 17:00 | 0 | Formworker | 100 | 43 | 34 | 89 | 35
623 | 1.2.4.3.3.1.20 | Setting Defects | 4 | 28 February 2025 8:00 AM | 4 March 2025 5:00 PM | 621,622 | 624 | 28 February 2025 8:00 AM | 2025-03-04 17:00 | 0 | Concretor | 100 | 43 | 16 | 75 | 19
624 | 1.2.4.3.3.1.21 | Paint Finish Coat | 3 | 5 March 2025 8:00 AM | 7 March 2025 5:00 PM | 623 | 627,625 | 5 March 2025 8:00 AM | 2025-03-07 17:00 | 0 | Plasterboarder | 100 | 68 | 30 | 22 | 46
625 | 1.2.4.3.3.1.22 | Carpet | 2 | 8 March 2025 8:00 AM | 10 March 2025 5:00 PM | 624 | 626 | 8 March 2025 8:00 AM | 2025-03-10 17:00 | 0 | Plumber | 100 | 29 | 21 | 10 | 52
626 | 1.2.4.3.3.1.23 | Final Clean & Commissioning | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 625 |  | 11 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Hoarding | 100 | 50 | 11 | 93 | 48
627 | 1.2.4.3.3.1.24 | Defects Inspections & Rectifications | 8 | 8 March 2025 8:00 AM | 17 March 2025 5:00 PM | 624 | 628 | 8 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Head Contractor | 100 | 40 | 10 | 75 | 23
628 | 1.2.4.3.3.2 | LVL 3 - FITOUT COMPLETE | 0 | 17 March 2025 5:00 PM | 17 March 2025 5:00 PM | 620,627 | 753 | 17 March 2025 5:00 PM | 2025-03-17 17:00 | 0 | Project Manager | 100 | 24 | 13 | 28 | 40
629 | 1.2.4.3.4 | Lvl 4 - Services & Finishes | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | 11 December 2024 8:00 AM | 2025-04-25 17:00 | 3 | Renderer | 100 | 14 | 34 | 100 | 22
630 | 1.2.4.3.4.1 | Internal Works | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | 11 December 2024 8:00 AM | 2025-04-22 17:00 | 0 | Renderer | 100 | 82 | 18 | 41 | 26
631 | 1.2.4.3.4.1.1 | Pre-load Levels | 2 | 11 December 2024 8:00 AM | 12 December 2024 5:00 PM | 186 | 632FS-2d | 11 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Tiler | 100 | 13 | 31 | 12 | 31
632 | 1.2.4.3.4.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 11 December 2024 8:00 AM | 21 December 2024 5:00 PM | 631FS-2d | 633 | 11 December 2024 8:00 AM | 2024-12-24 17:00 | 3 | Renderer | 100 | 31 | 21 | 15 | 12
633 | 1.2.4.3.4.1.3 | Internal Wall Framing | 8 | 23 December 2024 8:00 AM | 9 January 2025 5:00 PM | 632 | 635,634 | 23 December 2024 8:00 AM | 2025-01-11 17:00 | 2 | Waterproofer | 100 | 64 | 33 | 14 | 24
634 | 1.2.4.3.4.1.4 | Sheet one side of walls | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 637,636 | 10 January 2025 8:00 AM | 2025-01-18 17:00 | 0 | Reinforcement Fixer | 100 | 98 | 18 | 56 | 44
635 | 1.2.4.3.4.1.5 | Service Rough-In | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 636 | 10 January 2025 8:00 AM | 2025-01-18 17:00 | 0 | Development Manager | 100 | 20 | 10 | 7 | 17
636 | 1.2.4.3.4.1.6 | ITP for services in the walls | 2 | 20 January 2025 8:00 AM | 21 January 2025 5:00 PM | 634,635 | 637,643 | 20 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Renderer | 100 | 23 | 28 | 56 | 25
637 | 1.2.4.3.4.1.7 | Sheet other side of walls | 8 | 10 February 2025 8:00 AM | 18 February 2025 5:00 PM | 634,636,422FS-6d | 638 | 10 February 2025 8:00 AM | 2025-02-18 17:00 | 0 | Concretor | 100 | 100 | 22 | 22 | 51
638 | 1.2.4.3.4.1.8 | Frame & Sheet Ceilings | 8 | 19 February 2025 8:00 AM | 27 February 2025 5:00 PM | 637 | 639 | 19 February 2025 8:00 AM | 2025-02-27 17:00 | 0 | Carpenter | 100 | 79 | 12 | 63 | 20
639 | 1.2.4.3.4.1.9 | Sheet, Set & Sand Ceilings | 8 | 28 February 2025 8:00 AM | 8 March 2025 5:00 PM | 638,423 | 640 | 28 February 2025 8:00 AM | 2025-03-11 17:00 | 3 | Timber Floorer | 100 | 25 | 16 | 9 | 38
640 | 1.2.4.3.4.1.10 | Paint undercoat | 4 | 10 March 2025 8:00 AM | 13 March 2025 5:00 PM | 639 | 641 | 10 March 2025 8:00 AM | 2025-03-13 17:00 | 0 | Tiler | 100 | 34 | 26 | 56 | 52
641 | 1.2.4.3.4.1.11 | Floor Levelling and Floor Finish | 6 | 14 March 2025 8:00 AM | 20 March 2025 5:00 PM | 640 | 642 | 14 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Post Tension | 100 | 70 | 28 | 21 | 49
642 | 1.2.4.3.4.1.12 | Timber Flooring | 6 | 21 March 2025 8:00 AM | 27 March 2025 5:00 PM | 641 | 648,649,644 | 21 March 2025 8:00 AM | 2025-03-27 17:00 | 0 | Electrician | 100 | 27 | 20 | 3 | 14
643 | 1.2.4.3.4.1.13 | Measure & Manufacture Joinery | 40 | 22 January 2025 8:00 AM | 10 March 2025 5:00 PM | 636 | 644 | 22 January 2025 8:00 AM | 2025-03-15 17:00 | 5 | Carpet | 100 | 26 | 30 | 28 | 29
644 | 1.2.4.3.4.1.14 | Install Joinery | 8 | 28 March 2025 8:00 AM | 5 April 2025 5:00 PM | 642,643 | 646 | 28 March 2025 8:00 AM | 2025-04-05 17:00 | 0 | Mechanical | 100 | 49 | 31 | 60 | 48
645 | 1.2.4.3.4.1.15 | Measure & Manufacture Stone Benchtops | 12 | 24 March 2025 8:00 AM | 7 April 2025 8:00 AM | 646SF |  | 24 March 2025 8:00 AM | 2025-04-10 08:00 | 3 | Development Manager | 100 | 17 | 34 | 30 | 47
646 | 1.2.4.3.4.1.16 | Install Stone Benchtops | 6 | 7 April 2025 8:00 AM | 12 April 2025 5:00 PM | 644 | 645SF,647 | 7 April 2025 8:00 AM | 2025-04-14 17:00 | 2 | Fire | 100 | 26 | 31 | 58 | 39
647 | 1.2.4.3.4.1.17 | Fixtures & Fittings Fit-off | 3 | 14 April 2025 8:00 AM | 16 April 2025 5:00 PM | 646 | 655 | 14 April 2025 8:00 AM | 2025-04-16 17:00 | 0 | Plumber | 100 | 55 | 19 | 34 | 25
648 | 1.2.4.3.4.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 28 March 2025 8:00 AM | 1 April 2025 5:00 PM | 642 | 650 | 28 March 2025 8:00 AM | 2025-04-01 17:00 | 0 | Metal Work | 100 | 59 | 17 | 67 | 54
649 | 1.2.4.3.4.1.19 | Lighting Fit-off | 3 | 28 March 2025 8:00 AM | 31 March 2025 5:00 PM | 642 | 650 | 28 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Electrician | 100 | 42 | 11 | 43 | 46
650 | 1.2.4.3.4.1.20 | Setting Defects | 4 | 2 April 2025 8:00 AM | 5 April 2025 5:00 PM | 648,649 | 651 | 2 April 2025 8:00 AM | 2025-04-05 17:00 | 0 | Plasterboarder | 100 | 19 | 28 | 75 | 54
651 | 1.2.4.3.4.1.21 | Paint Finish Coat | 3 | 7 April 2025 8:00 AM | 9 April 2025 5:00 PM | 650 | 654,652 | 7 April 2025 8:00 AM | 2025-04-09 17:00 | 0 | Subcontractor | 100 | 65 | 26 | 87 | 54
652 | 1.2.4.3.4.1.22 | Carpet | 2 | 10 April 2025 8:00 AM | 11 April 2025 5:00 PM | 651 | 653 | 10 April 2025 8:00 AM | 2025-04-11 17:00 | 0 | Cleaner | 100 | 77 | 11 | 66 | 5
653 | 1.2.4.3.4.1.23 | Final Clean & Commissioning | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 652 |  | 12 April 2025 8:00 AM | 2025-04-23 17:00 | 1 | Metal Work | 100 | 92 | 31 | 33 | 43
654 | 1.2.4.3.4.1.24 | Defects Inspections & Rectifications | 8 | 10 April 2025 8:00 AM | 22 April 2025 5:00 PM | 651 | 655 | 10 April 2025 8:00 AM | 2025-04-22 17:00 | 0 | Concretor | 100 | 68 | 19 | 96 | 23
655 | 1.2.4.3.4.2 | LVL 4 - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 647,654 | 753 | 22 April 2025 5:00 PM | 2025-04-22 17:00 | 0 | Timber Floorer | 100 | 13 | 30 | 94 | 45
656 | 1.2.4.3.5 | Lvl 5 - Services & Finishes | 100 | 12 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | 12 December 2024 8:00 AM | 2025-04-19 17:00 | 2 | Development Manager | 100 | 70 | 19 | 59 | 10
657 | 1.2.4.3.5.1 | Survey & Setout | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 289,198 | 658FS-1d | 12 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Landscaper | 100 | 95 | 16 | 42 | 25
658 | 1.2.4.3.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 657FS-1d | 660,663 | 12 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Scaffolder | 100 | 57 | 13 | 46 | 39
659 | 1.2.4.3.5.3 | External Works | 34 | 17 December 2024 8:00 AM | 4 February 2025 5:00 PM |  |  | 17 December 2024 8:00 AM | 2025-02-08 17:00 | 4 | Project Manager | 100 | 45 | 13 | 9 | 23
660 | 1.2.4.3.5.3.1 | Façade & External Walls | 18 | 17 December 2024 8:00 AM | 15 January 2025 5:00 PM | 658 | 661 | 17 December 2024 8:00 AM | 2025-01-16 17:00 | 1 | Electrician | 100 | 89 | 18 | 89 | 35
661 | 1.2.4.3.5.3.2 | Windows Install | 16 | 16 January 2025 8:00 AM | 4 February 2025 5:00 PM | 660 | 669FS-6d | 16 January 2025 8:00 AM | 2025-02-07 17:00 | 3 | Surveyor | 100 | 91 | 24 | 92 | 50
662 | 1.2.4.3.5.4 | Internal Works | 91 | 23 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-04-18 17:00 | 1 | Painter | 100 | 10 | 26 | 28 | 39
663 | 1.2.4.3.5.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 658,426 | 664FS-2d | 23 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Project Manager | 100 | 25 | 25 | 33 | 17
664 | 1.2.4.3.5.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 663FS-2d | 665 | 23 December 2024 8:00 AM | 2025-01-14 17:00 | 3 | Joiner | 100 | 95 | 23 | 52 | 17
665 | 1.2.4.3.5.4.3 | Internal Wall Framing | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 664 | 667,666 | 13 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Mechanical | 100 | 25 | 17 | 54 | 3
666 | 1.2.4.3.5.4.4 | Sheet one side of walls | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 669,668 | 22 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Window | 100 | 48 | 33 | 18 | 58
667 | 1.2.4.3.5.4.5 | Service Rough-In | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 668 | 22 January 2025 8:00 AM | 2025-02-03 17:00 | 3 | Landscaper | 100 | 26 | 20 | 86 | 54
668 | 1.2.4.3.5.4.6 | ITP for services in the walls | 2 | 1 February 2025 8:00 AM | 3 February 2025 5:00 PM | 666,667 | 669,675 | 1 February 2025 8:00 AM | 2025-02-03 17:00 | 0 | Cleaner | 100 | 32 | 24 | 85 | 55
669 | 1.2.4.3.5.4.7 | Sheet other side of walls | 8 | 4 February 2025 8:00 AM | 12 February 2025 5:00 PM | 661FS-6d,666,668,428FS-6d | 670 | 4 February 2025 8:00 AM | 2025-02-12 17:00 | 0 | Stone Mason | 100 | 98 | 28 | 22 | 31
670 | 1.2.4.3.5.4.8 | Frame & Sheet Ceilings | 8 | 13 February 2025 8:00 AM | 21 February 2025 5:00 PM | 669 | 671 | 13 February 2025 8:00 AM | 2025-02-23 17:00 | 2 | Hoarding | 100 | 72 | 33 | 21 | 18
671 | 1.2.4.3.5.4.9 | Sheet, Set & Sand Ceilings | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 670,429 | 672 | 22 February 2025 8:00 AM | 2025-03-03 17:00 | 0 | Waterproofer | 100 | 94 | 28 | 34 | 18
672 | 1.2.4.3.5.4.10 | Paint undercoat | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 671 | 673 | 4 March 2025 8:00 AM | 2025-03-07 17:00 | 0 | Renderer | 100 | 56 | 12 | 56 | 51
673 | 1.2.4.3.5.4.11 | Floor Levelling and Floor Finish | 6 | 8 March 2025 8:00 AM | 14 March 2025 5:00 PM | 672 | 674 | 8 March 2025 8:00 AM | 2025-03-17 17:00 | 3 | Excavation | 100 | 36 | 22 | 100 | 60
674 | 1.2.4.3.5.4.12 | Timber Flooring | 6 | 15 March 2025 8:00 AM | 21 March 2025 5:00 PM | 673 | 680,681,676 | 15 March 2025 8:00 AM | 2025-03-21 17:00 | 0 | Plumber | 100 | 72 | 35 | 60 | 40
675 | 1.2.4.3.5.4.13 | Measure & Manufacture Joinery | 40 | 4 February 2025 8:00 AM | 21 March 2025 5:00 PM | 668 | 676 | 4 February 2025 8:00 AM | 2025-03-24 17:00 | 3 | Window | 100 | 27 | 15 | 20 | 5
676 | 1.2.4.3.5.4.14 | Install Joinery | 8 | 22 March 2025 8:00 AM | 31 March 2025 5:00 PM | 674,675 | 678 | 22 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Site Manager | 100 | 93 | 10 | 6 | 26
677 | 1.2.4.3.5.4.15 | Measure & Manufacture Stone Benchtops | 15 | 14 March 2025 8:00 AM | 1 April 2025 8:00 AM | 678SF | 687 | 14 March 2025 8:00 AM | 2025-04-06 08:00 | 5 | Foreman | 100 | 22 | 28 | 88 | 43
678 | 1.2.4.3.5.4.16 | Install Stone Benchtops | 6 | 1 April 2025 8:00 AM | 7 April 2025 5:00 PM | 676 | 677SF,679 | 1 April 2025 8:00 AM | 2025-04-08 17:00 | 1 | Scaffolder | 100 | 77 | 11 | 97 | 41
679 | 1.2.4.3.5.4.17 | Fixtures & Fittings Fit-off | 8 | 8 April 2025 8:00 AM | 16 April 2025 5:00 PM | 678 | 687 | 8 April 2025 8:00 AM | 2025-04-16 17:00 | 0 | Head Contractor | 100 | 20 | 32 | 99 | 3
680 | 1.2.4.3.5.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 674 | 682 | 22 March 2025 8:00 AM | 2025-03-26 17:00 | 0 | Waterproofer | 100 | 93 | 21 | 9 | 37
681 | 1.2.4.3.5.4.19 | Lighting Fit-off | 3 | 22 March 2025 8:00 AM | 25 March 2025 5:00 PM | 674 | 682 | 22 March 2025 8:00 AM | 2025-03-25 17:00 | 0 | Contract Administrator | 100 | 26 | 19 | 42 | 28
682 | 1.2.4.3.5.4.20 | Setting Defects | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 680,681 | 683 | 27 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Tiler | 100 | 60 | 32 | 59 | 17
683 | 1.2.4.3.5.4.21 | Paint Finish Coat | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 682 | 686,684 | 1 April 2025 8:00 AM | 2025-04-03 17:00 | 0 | Painter | 100 | 58 | 24 | 14 | 36
684 | 1.2.4.3.5.4.22 | Carpet | 2 | 4 April 2025 8:00 AM | 5 April 2025 5:00 PM | 683 | 685 | 4 April 2025 8:00 AM | 2025-04-05 17:00 | 0 | Head Contractor | 100 | 51 | 13 | 28 | 38
685 | 1.2.4.3.5.4.23 | Final Clean & Commissioning | 10 | 7 April 2025 8:00 AM | 17 April 2025 5:00 PM | 684 | 687 | 7 April 2025 8:00 AM | 2025-04-20 17:00 | 3 | Plasterboarder | 100 | 76 | 32 | 42 | 13
686 | 1.2.4.3.5.4.24 | Defects Inspections & Rectifications | 8 | 4 April 2025 8:00 AM | 12 April 2025 5:00 PM | 683 | 687 | 4 April 2025 8:00 AM | 2025-04-15 17:00 | 3 | Waterproofer | 100 | 12 | 34 | 47 | 13
687 | 1.2.4.3.5.5 | LVL 5 - FITOUT COMPLETE | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 679,686,685,677 |  | 17 April 2025 5:00 PM | 2025-04-17 17:00 | 0 | Site Manager | 100 | 58 | 34 | 96 | 20
688 | 1.2.4.3.6 | Lvl 6 - Services & Finishes | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-04-18 17:00 | 3 | Head Contractor | 100 | 75 | 26 | 38 | 12
689 | 1.2.4.3.6.1 | Internal Works | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-04-17 17:00 | 2 | Excavation | 100 | 50 | 11 | 43 | 24
690 | 1.2.4.3.6.1.1 | Pre-load Levels | 2 | 18 December 2024 8:00 AM | 19 December 2024 5:00 PM | 432,210 | 691FS-2d | 18 December 2024 8:00 AM | 2024-12-19 17:00 | 0 | Project Manager | 100 | 11 | 11 | 31 | 44
691 | 1.2.4.3.6.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 18 December 2024 8:00 AM | 7 January 2025 5:00 PM | 690FS-2d | 692 | 18 December 2024 8:00 AM | 2025-01-07 17:00 | 0 | Carpet | 100 | 59 | 20 | 63 | 37
692 | 1.2.4.3.6.1.3 | Internal Wall Framing | 8 | 8 January 2025 8:00 AM | 16 January 2025 5:00 PM | 691 | 694,693 | 8 January 2025 8:00 AM | 2025-01-16 17:00 | 0 | Plumber | 100 | 67 | 29 | 3 | 59
693 | 1.2.4.3.6.1.4 | Sheet one side of walls | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 696,695 | 17 January 2025 8:00 AM | 2025-01-29 17:00 | 2 | Subcontractor | 100 | 17 | 16 | 36 | 24
694 | 1.2.4.3.6.1.5 | Service Rough-In | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 695 | 17 January 2025 8:00 AM | 2025-01-30 17:00 | 3 | Waterproofer | 100 | 56 | 33 | 28 | 49
695 | 1.2.4.3.6.1.6 | ITP for services in the walls | 2 | 28 January 2025 8:00 AM | 29 January 2025 5:00 PM | 693,694 | 696,702 | 28 January 2025 8:00 AM | 2025-01-29 17:00 | 0 | Foreman | 100 | 82 | 22 | 59 | 46
696 | 1.2.4.3.6.1.7 | Sheet other side of walls | 8 | 30 January 2025 8:00 AM | 7 February 2025 5:00 PM | 693,695,434FS-6d | 697 | 30 January 2025 8:00 AM | 2025-02-07 17:00 | 0 | Subcontractor | 100 | 39 | 13 | 97 | 6
697 | 1.2.4.3.6.1.8 | Frame & Sheet Ceilings | 8 | 8 February 2025 8:00 AM | 17 February 2025 5:00 PM | 696 | 698 | 8 February 2025 8:00 AM | 2025-02-20 17:00 | 3 | Scaffolder | 100 | 33 | 20 | 78 | 15
698 | 1.2.4.3.6.1.9 | Sheet, Set & Sand Ceilings | 8 | 18 February 2025 8:00 AM | 26 February 2025 5:00 PM | 697,435 | 699 | 18 February 2025 8:00 AM | 2025-02-27 17:00 | 1 | Stone Mason | 100 | 59 | 16 | 74 | 48
699 | 1.2.4.3.6.1.10 | Paint undercoat | 4 | 27 February 2025 8:00 AM | 3 March 2025 5:00 PM | 698 | 700 | 27 February 2025 8:00 AM | 2025-03-03 17:00 | 0 | Floor Sealer | 100 | 86 | 17 | 47 | 59
700 | 1.2.4.3.6.1.11 | Floor Levelling and Floor Finish | 6 | 4 March 2025 8:00 AM | 10 March 2025 5:00 PM | 699 | 701 | 4 March 2025 8:00 AM | 2025-03-12 17:00 | 2 | Renderer | 100 | 86 | 20 | 62 | 39
701 | 1.2.4.3.6.1.12 | Timber Flooring | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 700 | 707,708,703 | 11 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Carpet | 100 | 18 | 30 | 38 | 34
702 | 1.2.4.3.6.1.13 | Measure & Manufacture Joinery | 40 | 30 January 2025 8:00 AM | 17 March 2025 5:00 PM | 695 | 703 | 30 January 2025 8:00 AM | 2025-03-21 17:00 | 4 | Project Manager | 100 | 17 | 30 | 51 | 11
703 | 1.2.4.3.6.1.14 | Install Joinery | 8 | 18 March 2025 8:00 AM | 26 March 2025 5:00 PM | 701,702 | 705 | 18 March 2025 8:00 AM | 2025-03-28 17:00 | 2 | Metal Work | 100 | 22 | 25 | 29 | 58
704 | 1.2.4.3.6.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 March 2025 8:00 AM | 27 March 2025 8:00 AM | 705SF |  | 13 March 2025 8:00 AM | 2025-03-28 08:00 | 1 | Reinforcement Fixer | 100 | 49 | 18 | 92 | 14
705 | 1.2.4.3.6.1.16 | Install Stone Benchtops | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 703 | 704SF,706 | 27 March 2025 8:00 AM | 2025-04-02 17:00 | 0 | Metal Work | 100 | 35 | 13 | 97 | 55
706 | 1.2.4.3.6.1.17 | Fixtures & Fittings Fit-off | 7 | 3 April 2025 8:00 AM | 10 April 2025 5:00 PM | 705 | 714 | 3 April 2025 8:00 AM | 2025-04-12 17:00 | 2 | Formworker | 100 | 18 | 26 | 72 | 56
707 | 1.2.4.3.6.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 18 March 2025 8:00 AM | 21 March 2025 5:00 PM | 701 | 709 | 18 March 2025 8:00 AM | 2025-03-21 17:00 | 0 | Post Tension | 100 | 49 | 24 | 9 | 8
708 | 1.2.4.3.6.1.19 | Lighting Fit-off | 3 | 18 March 2025 8:00 AM | 20 March 2025 5:00 PM | 701 | 709 | 18 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Development Manager | 100 | 63 | 24 | 48 | 24
709 | 1.2.4.3.6.1.20 | Setting Defects | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 707,708 | 710 | 22 March 2025 8:00 AM | 2025-03-26 17:00 | 0 | Waterproofer | 100 | 42 | 10 | 85 | 34
710 | 1.2.4.3.6.1.21 | Paint Finish Coat | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 709 | 713,711 | 27 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Subcontractor | 100 | 50 | 14 | 7 | 10
711 | 1.2.4.3.6.1.22 | Carpet | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 710 | 712 | 1 April 2025 8:00 AM | 2025-04-03 17:00 | 0 | Admin | 100 | 30 | 13 | 22 | 28
712 | 1.2.4.3.6.1.23 | Final Clean & Commissioning | 10 | 4 April 2025 8:00 AM | 15 April 2025 5:00 PM | 711 |  | 4 April 2025 8:00 AM | 2025-04-15 17:00 | 0 | Development Manager | 100 | 94 | 12 | 39 | 9
713 | 1.2.4.3.6.1.24 | Defects Inspections & Rectifications | 8 | 1 April 2025 8:00 AM | 9 April 2025 5:00 PM | 710 | 714 | 1 April 2025 8:00 AM | 2025-04-10 17:00 | 1 | Waterproofer | 100 | 76 | 24 | 75 | 35
714 | 1.2.4.3.6.2 | LVL 6 - FITOUT COMPLETE | 0 | 10 April 2025 5:00 PM | 10 April 2025 5:00 PM | 706,713 | 5 | 10 April 2025 5:00 PM | 2025-04-10 17:00 | 0 | Surveyor | 100 | 95 | 34 | 44 | 9
715 | 1.2.4.3.7 | Lvl 7 - Services & Finishes | 105 | 18 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-05-08 17:00 | 3 | Development Manager | 100 | 69 | 33 | 76 | 3
716 | 1.2.4.3.7.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 301,223 | 717FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Window | 100 | 34 | 23 | 7 | 12
717 | 1.2.4.3.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 716FS-1d | 719,722 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Plumber | 100 | 48 | 26 | 48 | 29
718 | 1.2.4.3.7.3 | External Works | 34 | 23 December 2024 8:00 AM | 10 February 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-02-11 17:00 | 1 | Site Manager | 100 | 96 | 31 | 23 | 51
719 | 1.2.4.3.7.3.1 | Façade & External Walls | 18 | 23 December 2024 8:00 AM | 21 January 2025 5:00 PM | 717 | 720 | 23 December 2024 8:00 AM | 2025-01-22 17:00 | 1 | Metal Work | 100 | 96 | 27 | 72 | 51
720 | 1.2.4.3.7.3.2 | Windows Install | 16 | 22 January 2025 8:00 AM | 10 February 2025 5:00 PM | 719 | 728FS-6d | 22 January 2025 8:00 AM | 2025-02-15 17:00 | 5 | Window | 100 | 70 | 30 | 88 | 53
721 | 1.2.4.3.7.4 | Internal Works | 101 | 23 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-05-05 17:00 | 0 | Hoarding | 100 | 32 | 14 | 26 | 58
722 | 1.2.4.3.7.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 717,438 | 723FS-2d | 23 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Reinforcement Fixer | 100 | 77 | 20 | 86 | 58
723 | 1.2.4.3.7.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 722FS-2d | 724 | 23 December 2024 8:00 AM | 2025-01-13 17:00 | 2 | Carpet | 100 | 81 | 18 | 41 | 60
724 | 1.2.4.3.7.4.3 | Internal Wall Framing | 10 | 13 January 2025 8:00 AM | 23 January 2025 5:00 PM | 723 | 726,725 | 13 January 2025 8:00 AM | 2025-01-28 17:00 | 5 | Foreman | 100 | 30 | 12 | 89 | 43
725 | 1.2.4.3.7.4.4 | Sheet one side of walls | 9 | 24 January 2025 8:00 AM | 4 February 2025 5:00 PM | 724 | 728,727 | 24 January 2025 8:00 AM | 2025-02-05 17:00 | 1 | Head Contractor | 100 | 37 | 18 | 82 | 13
726 | 1.2.4.3.7.4.5 | Service Rough-In | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 724 | 727 | 24 January 2025 8:00 AM | 2025-02-03 17:00 | 0 | Stone Mason | 100 | 50 | 24 | 18 | 56
727 | 1.2.4.3.7.4.6 | ITP for services in the walls | 2 | 5 February 2025 8:00 AM | 6 February 2025 5:00 PM | 725,726 | 728,734 | 5 February 2025 8:00 AM | 2025-02-06 17:00 | 0 | Painter | 100 | 77 | 17 | 86 | 47
728 | 1.2.4.3.7.4.7 | Sheet other side of walls | 8 | 15 February 2025 8:00 AM | 24 February 2025 5:00 PM | 720FS-6d,725,727,440FS-6d | 729 | 15 February 2025 8:00 AM | 2025-02-24 17:00 | 0 | Metal Work | 100 | 57 | 17 | 25 | 58
729 | 1.2.4.3.7.4.8 | Frame & Sheet Ceilings | 8 | 25 February 2025 8:00 AM | 5 March 2025 5:00 PM | 728 | 730 | 25 February 2025 8:00 AM | 2025-03-06 17:00 | 1 | Tiler | 100 | 50 | 19 | 25 | 51
730 | 1.2.4.3.7.4.9 | Sheet, Set & Sand Ceilings | 8 | 6 March 2025 8:00 AM | 14 March 2025 5:00 PM | 729,441 | 731 | 6 March 2025 8:00 AM | 2025-03-15 17:00 | 1 | Concretor | 100 | 91 | 33 | 1 | 57
731 | 1.2.4.3.7.4.10 | Paint undercoat | 4 | 15 March 2025 8:00 AM | 19 March 2025 5:00 PM | 730 | 732 | 15 March 2025 8:00 AM | 2025-03-19 17:00 | 0 | Tiler | 100 | 31 | 27 | 87 | 30
732 | 1.2.4.3.7.4.11 | Floor Levelling and Floor Finish | 6 | 20 March 2025 8:00 AM | 26 March 2025 5:00 PM | 731 | 733 | 20 March 2025 8:00 AM | 2025-03-28 17:00 | 2 | Stone Mason | 100 | 11 | 17 | 42 | 35
733 | 1.2.4.3.7.4.12 | Timber Flooring | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 732 | 739,740,735 | 27 March 2025 8:00 AM | 2025-04-05 17:00 | 3 | Subcontractor | 100 | 38 | 17 | 63 | 56
734 | 1.2.4.3.7.4.13 | Measure & Manufacture Joinery | 40 | 7 February 2025 8:00 AM | 25 March 2025 5:00 PM | 727 | 735 | 7 February 2025 8:00 AM | 2025-03-27 17:00 | 2 | Surveyor | 100 | 47 | 18 | 68 | 3
735 | 1.2.4.3.7.4.14 | Install Joinery | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733,734 | 737 | 3 April 2025 8:00 AM | 2025-04-13 17:00 | 2 | Metal Work | 100 | 64 | 34 | 18 | 26
736 | 1.2.4.3.7.4.15 | Measure & Manufacture Stone Benchtops | 12 | 29 March 2025 8:00 AM | 12 April 2025 8:00 AM | 737SF | 746 | 29 March 2025 8:00 AM | 2025-04-17 08:00 | 5 | Contract Administrator | 100 | 29 | 17 | 24 | 36
737 | 1.2.4.3.7.4.16 | Install Stone Benchtops | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 735 | 736SF,738 | 12 April 2025 8:00 AM | 2025-04-22 17:00 | 0 | Renderer | 100 | 98 | 34 | 94 | 13
738 | 1.2.4.3.7.4.17 | Fixtures & Fittings Fit-off | 7 | 23 April 2025 8:00 AM | 2 May 2025 5:00 PM | 737 | 746 | 23 April 2025 8:00 AM | 2025-05-05 17:00 | 3 | Foreman | 100 | 18 | 26 | 40 | 24
739 | 1.2.4.3.7.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733 | 741 | 3 April 2025 8:00 AM | 2025-04-13 17:00 | 2 | Mechanical | 100 | 32 | 34 | 96 | 55
740 | 1.2.4.3.7.4.19 | Lighting Fit-off | 5 | 3 April 2025 8:00 AM | 8 April 2025 5:00 PM | 733 | 741 | 3 April 2025 8:00 AM | 2025-04-08 17:00 | 0 | Hoarding | 100 | 41 | 27 | 65 | 20
741 | 1.2.4.3.7.4.20 | Setting Defects | 4 | 12 April 2025 8:00 AM | 16 April 2025 5:00 PM | 739,740 | 742 | 12 April 2025 8:00 AM | 2025-04-16 17:00 | 0 | Cleaner | 100 | 46 | 27 | 81 | 59
742 | 1.2.4.3.7.4.21 | Paint Finish Coat | 4 | 17 April 2025 8:00 AM | 24 April 2025 5:00 PM | 741 | 745,743 | 17 April 2025 8:00 AM | 2025-04-24 17:00 | 0 | Cleaner | 100 | 40 | 31 | 56 | 23
743 | 1.2.4.3.7.4.22 | Carpet | 3 | 28 April 2025 8:00 AM | 30 April 2025 5:00 PM | 742 | 744 | 28 April 2025 8:00 AM | 2025-04-30 17:00 | 0 | Contract Administrator | 100 | 60 | 24 | 92 | 22
744 | 1.2.4.3.7.4.23 | Final Clean & Commissioning | 4 | 1 May 2025 8:00 AM | 5 May 2025 5:00 PM | 743 | 746 | 1 May 2025 8:00 AM | 2025-05-06 17:00 | 1 | Painter | 100 | 21 | 14 | 10 | 5
745 | 1.2.4.3.7.4.24 | Defects Inspections & Rectifications | 6 | 28 April 2025 8:00 AM | 3 May 2025 5:00 PM | 742 | 746 | 28 April 2025 8:00 AM | 2025-05-06 17:00 | 3 | Window | 100 | 75 | 11 | 92 | 36
746 | 1.2.4.3.7.5 | LVL 7 - FITOUT COMPLETE | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 738,745,744,736 | 5,754 | 5 May 2025 5:00 PM | 2025-05-06 17:00 | 1 | Tiler | 100 | 91 | 16 | 37 | 46
747 | 1.2.4.3.8 | Lvl 8 (Roof) - Services | 96 | 7 January 2025 8:00 AM | 5 May 2025 5:00 PM |  |  | 7 January 2025 8:00 AM | 2025-05-05 17:00 | 0 | Concretor | 100 | 62 | 35 | 34 | 55
748 | 1.2.4.3.8.1 | Survey & Setout | 1 | 7 January 2025 8:00 AM | 7 January 2025 5:00 PM | 301FS+24d | 749FS-1d | 7 January 2025 8:00 AM | 2025-01-07 17:00 | 0 | Tiler | 100 | 41 | 11 | 98 | 58
749 | 1.2.4.3.8.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 7 January 2025 8:00 AM | 10 January 2025 5:00 PM | 748FS-1d | 751 | 7 January 2025 8:00 AM | 2025-01-10 17:00 | 0 | Plasterboarder | 100 | 65 | 17 | 27 | 3
750 | 1.2.4.3.8.3 | External Services (Plant) | 56 | 11 January 2025 8:00 AM | 18 March 2025 5:00 PM |  |  | 11 January 2025 8:00 AM | 2025-03-25 17:00 | 7 | Excavation | 100 | 60 | 26 | 27 | 19
751 | 1.2.4.3.8.3.1 | Heat Pumps & Associated Services | 32 | 11 January 2025 8:00 AM | 18 February 2025 5:00 PM | 749 | 752 | 11 January 2025 8:00 AM | 2025-02-23 17:00 | 5 | Reinforcement Fixer | 100 | 95 | 29 | 53 | 54
752 | 1.2.4.3.8.3.2 | Louvres, Balustrades & Roof Safety System | 24 | 19 February 2025 8:00 AM | 18 March 2025 5:00 PM | 751 | 753 | 19 February 2025 8:00 AM | 2025-03-19 17:00 | 1 | Subcontractor | 100 | 31 | 25 | 38 | 47
753 | 1.2.4.3.8.4 | LVL 8 (ROOF) - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 752,655,628 | 5,754 | 22 April 2025 5:00 PM | 2025-04-22 17:00 | 0 | Fire | 100 | 33 | 19 | 1 | 35
754 | 1.2.4.3.8.5 | Building A Fitout Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 753,746 |  | 5 May 2025 5:00 PM | 2025-05-05 17:00 | 0 | Head Contractor | 100 | 97 | 13 | 52 | 6
755 | 1.2.4.4 | Building B | 135 | 14 October 2024 8:00 AM | 29 March 2025 5:00 PM |  | 3440 | 14 October 2024 8:00 AM | 2025-03-29 17:00 | 0 | Stone Mason | 100 | 13 | 24 | 92 | 10
756 | 1.2.4.4.1 | Level 1 | 52 | 14 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | 14 October 2024 8:00 AM | 2024-12-13 17:00 | 1 | Carpet | 100 | 66 | 33 | 49 | 52
757 | 1.2.4.4.1.1 | Apartment B010 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | 14 October 2024 8:00 AM | 2024-12-05 17:00 | 0 | Renderer | 100 | 32 | 12 | 22 | 36
758 | 1.2.4.4.1.1.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 759,762,763,830 | 14 October 2024 8:00 AM | 2024-10-20 17:00 | 5 | Electrician | 100 | 85 | 16 | 54 | 39
759 | 1.2.4.4.1.1.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 758 | 761,760 | 16 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Painter | 100 | 87 | 11 | 1 | 41
760 | 1.2.4.4.1.1.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 759 |  | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Metal Work | 100 | 92 | 18 | 75 | 46
761 | 1.2.4.4.1.1.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 759 | 764 | 17 October 2024 8:00 AM | 2024-10-24 17:00 | 5 | Project Manager | 100 | 99 | 19 | 12 | 8
762 | 1.2.4.4.1.1.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 771 | 16 October 2024 8:00 AM | 2024-10-23 17:00 | 5 | Carpenter | 100 | 22 | 27 | 2 | 16
763 | 1.2.4.4.1.1.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 834 | 16 October 2024 8:00 AM | 2024-10-25 17:00 | 7 | Development Manager | 100 | 30 | 21 | 82 | 25
764 | 1.2.4.4.1.1.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 761 | 765,766,767,768,769 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Contract Administrator | 100 | 38 | 31 | 91 | 7
765 | 1.2.4.4.1.1.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Development Manager | 100 | 68 | 30 | 71 | 34
766 | 1.2.4.4.1.1.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769,833 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Timber Floorer | 100 | 18 | 29 | 92 | 18
767 | 1.2.4.4.1.1.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 832 | 23 October 2024 8:00 AM | 2024-10-26 17:00 | 2 | Foreman | 100 | 14 | 23 | 47 | 25
768 | 1.2.4.4.1.1.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 |  | 23 October 2024 8:00 AM | 2024-10-29 17:00 | 5 | Waterproofer | 100 | 27 | 21 | 49 | 51
769 | 1.2.4.4.1.1.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 764,765,766 | 770 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Timber Floorer | 100 | 78 | 23 | 87 | 16
770 | 1.2.4.4.1.1.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 769 | 771 | 26 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Tiler | 100 | 44 | 10 | 63 | 44
771 | 1.2.4.4.1.1.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 762,770 | 772,773,774,775,777,779 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Contract Administrator | 100 | 29 | 13 | 81 | 33
772 | 1.2.4.4.1.1.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 776,779 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Stone Mason | 100 | 92 | 20 | 44 | 19
773 | 1.2.4.4.1.1.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 779 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Scaffolder | 100 | 99 | 32 | 73 | 32
774 | 1.2.4.4.1.1.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 778,779 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Foreman | 100 | 65 | 11 | 81 | 18
775 | 1.2.4.4.1.1.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Surveyor | 100 | 21 | 26 | 49 | 39
776 | 1.2.4.4.1.1.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 772 | 779 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Cleaner | 100 | 14 | 29 | 62 | 24
777 | 1.2.4.4.1.1.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Fire | 100 | 31 | 28 | 89 | 18
778 | 1.2.4.4.1.1.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 774 | 779 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Foreman | 100 | 81 | 12 | 96 | 15
779 | 1.2.4.4.1.1.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 771,772,773,774,775,776,777,778 | 780 | 4 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Post Tension | 100 | 90 | 14 | 88 | 32
780 | 1.2.4.4.1.1.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 779 | 781 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Joiner | 100 | 38 | 24 | 55 | 48
781 | 1.2.4.4.1.1.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 780 | 782,799,816 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Floor Sealer | 100 | 22 | 30 | 15 | 33
782 | 1.2.4.4.1.1.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 783 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Waterproofer | 100 | 77 | 25 | 2 | 58
783 | 1.2.4.4.1.1.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 782 | 784 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Head Contractor | 100 | 62 | 35 | 25 | 13
784 | 1.2.4.4.1.1.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 783 | 785 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Carpet | 100 | 68 | 22 | 63 | 56
785 | 1.2.4.4.1.1.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 784 | 786 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Hoarding | 100 | 23 | 11 | 97 | 19
786 | 1.2.4.4.1.1.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 785 | 787,788 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Landscaper | 100 | 54 | 31 | 76 | 3
787 | 1.2.4.4.1.1.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 786 | 791 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Window | 100 | 81 | 20 | 66 | 18
788 | 1.2.4.4.1.1.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 786 | 789 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Metal Work | 100 | 41 | 24 | 2 | 57
789 | 1.2.4.4.1.1.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 788 | 790 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Painter | 100 | 10 | 26 | 55 | 60
790 | 1.2.4.4.1.1.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 789 |  | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Development Manager | 100 | 92 | 26 | 36 | 21
791 | 1.2.4.4.1.1.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 787 | 792,793,794,795,796 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Site Manager | 100 | 46 | 15 | 77 | 46
792 | 1.2.4.4.1.1.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 791 |  | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Renderer | 100 | 93 | 30 | 80 | 45
793 | 1.2.4.4.1.1.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Plumber | 100 | 71 | 24 | 58 | 5
794 | 1.2.4.4.1.1.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Floor Sealer | 100 | 100 | 23 | 41 | 4
795 | 1.2.4.4.1.1.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Waterproofer | 100 | 80 | 13 | 16 | 58
796 | 1.2.4.4.1.1.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Stone Mason | 100 | 36 | 14 | 99 | 23
797 | 1.2.4.4.1.1.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 847 | 9 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Electrician | 100 | 25 | 35 | 34 | 36
798 | 1.2.4.4.1.1.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Hoarding | 100 | 90 | 28 | 90 | 32
799 | 1.2.4.4.1.1.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 800 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Window | 100 | 97 | 27 | 14 | 10
800 | 1.2.4.4.1.1.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 799 | 801 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Concretor | 100 | 15 | 24 | 52 | 9
801 | 1.2.4.4.1.1.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 800 | 802 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Mechanical | 100 | 67 | 19 | 84 | 29
802 | 1.2.4.4.1.1.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 801 | 803 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Scaffolder | 100 | 13 | 27 | 48 | 47
803 | 1.2.4.4.1.1.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 802 | 804 | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Excavation | 100 | 10 | 19 | 19 | 26
804 | 1.2.4.4.1.1.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 803 | 805 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Plumber | 100 | 26 | 15 | 76 | 17
805 | 1.2.4.4.1.1.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 804 | 806 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Waterproofer | 100 | 58 | 24 | 36 | 46
806 | 1.2.4.4.1.1.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 805 | 807 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Window | 100 | 35 | 20 | 92 | 7
807 | 1.2.4.4.1.1.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 806 | 808 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Tiler | 100 | 70 | 19 | 69 | 51
808 | 1.2.4.4.1.1.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 807 | 809 | 25 November 2024 8:00 AM | 2024-12-01 17:00 | 6 | Timber Floorer | 100 | 72 | 30 | 56 | 15
809 | 1.2.4.4.1.1.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 808 | 810 | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 4 | Project Manager | 100 | 50 | 27 | 44 | 11
810 | 1.2.4.4.1.1.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 809 | 814,811,812,813 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Landscaper | 100 | 83 | 22 | 90 | 7
811 | 1.2.4.4.1.1.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Plumber | 100 | 97 | 29 | 7 | 5
812 | 1.2.4.4.1.1.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Admin | 100 | 72 | 29 | 94 | 42
813 | 1.2.4.4.1.1.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Excavation | 100 | 40 | 15 | 83 | 22
814 | 1.2.4.4.1.1.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 810,811,812,813 |  | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Hoarding | 100 | 12 | 14 | 17 | 51
815 | 1.2.4.4.1.1.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Renderer | 100 | 13 | 25 | 64 | 40
816 | 1.2.4.4.1.1.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 817 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Hoarding | 100 | 31 | 19 | 79 | 54
817 | 1.2.4.4.1.1.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 816 | 818 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Development Manager | 100 | 15 | 25 | 4 | 49
818 | 1.2.4.4.1.1.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 817 | 819 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Waterproofer | 100 | 64 | 34 | 24 | 34
819 | 1.2.4.4.1.1.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 818 | 820 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Reinforcement Fixer | 100 | 55 | 22 | 68 | 14
820 | 1.2.4.4.1.1.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 819 | 821 | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Window | 100 | 84 | 18 | 61 | 58
821 | 1.2.4.4.1.1.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 820 | 822 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Site Manager | 100 | 16 | 25 | 74 | 46
822 | 1.2.4.4.1.1.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 821 | 823 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Floor Sealer | 100 | 18 | 26 | 65 | 32
823 | 1.2.4.4.1.1.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 822 | 824,825,826,827 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Mechanical | 100 | 56 | 22 | 1 | 25
824 | 1.2.4.4.1.1.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Tiler | 100 | 43 | 24 | 42 | 50
825 | 1.2.4.4.1.1.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Concretor | 100 | 100 | 10 | 96 | 49
826 | 1.2.4.4.1.1.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-28 17:00 | 3 | Head Contractor | 100 | 54 | 34 | 25 | 17
827 | 1.2.4.4.1.1.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Carpenter | 100 | 92 | 27 | 75 | 43
828 | 1.2.4.4.1.1.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 824,825,826,827 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Cleaner | 100 | 70 | 14 | 96 | 27
829 | 1.2.4.4.1.1.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-11-11 17:00 | 0 | Renderer | 100 | 59 | 11 | 42 | 28
830 | 1.2.4.4.1.1.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 758 | 831 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Contract Administrator | 100 | 41 | 27 | 76 | 31
831 | 1.2.4.4.1.1.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 830 |  | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Site Manager | 100 | 78 | 29 | 100 | 6
832 | 1.2.4.4.1.1.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 767 | 835 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Stone Mason | 100 | 12 | 24 | 2 | 60
833 | 1.2.4.4.1.1.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 766 | 835 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Contract Administrator | 100 | 21 | 28 | 24 | 57
834 | 1.2.4.4.1.1.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 763 | 835 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Renderer | 100 | 83 | 35 | 56 | 23
835 | 1.2.4.4.1.1.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 832,833,834 | 836 | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Fire | 100 | 82 | 18 | 43 | 25
836 | 1.2.4.4.1.1.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 835 | 837 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Admin | 100 | 84 | 14 | 34 | 28
837 | 1.2.4.4.1.1.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 836 | 838 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Line Market | 100 | 84 | 23 | 79 | 51
838 | 1.2.4.4.1.1.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 837 | 839 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Contract Administrator | 100 | 52 | 32 | 36 | 27
839 | 1.2.4.4.1.1.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 838 | 840 | 1 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Scaffolder | 100 | 78 | 26 | 17 | 18
840 | 1.2.4.4.1.1.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 839 | 841 | 4 November 2024 8:00 AM | 2024-11-12 17:00 | 7 | Window | 100 | 26 | 35 | 87 | 41
841 | 1.2.4.4.1.1.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 840 | 842 | 6 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Formworker | 100 | 32 | 32 | 93 | 41
842 | 1.2.4.4.1.1.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 841 | 843,844,845,846 | 7 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Renderer | 100 | 23 | 17 | 93 | 13
843 | 1.2.4.4.1.1.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Stone Mason | 100 | 83 | 18 | 41 | 35
844 | 1.2.4.4.1.1.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Carpet | 100 | 12 | 24 | 34 | 7
845 | 1.2.4.4.1.1.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Stone Mason | 100 | 81 | 29 | 7 | 24
846 | 1.2.4.4.1.1.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Timber Floorer | 100 | 89 | 10 | 58 | 49
847 | 1.2.4.4.1.1.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 793,794,795,796,797 | 848 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Plumber | 100 | 26 | 20 | 23 | 22
848 | 1.2.4.4.1.1.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 847 | 849 | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Foreman | 100 | 67 | 20 | 68 | 55
849 | 1.2.4.4.1.1.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 848 | 850 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Fire | 100 | 18 | 30 | 34 | 29
850 | 1.2.4.4.1.1.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 849 |  | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Plasterboarder | 100 | 22 | 11 | 71 | 18
851 | 1.2.4.4.1.2 | Apartment B011 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | 14 October 2024 8:00 AM | 2024-12-05 17:00 | 0 | Formworker | 100 | 42 | 30 | 68 | 27
852 | 1.2.4.4.1.2.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 853,856,857,924 | 14 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Subcontractor | 100 | 73 | 33 | 49 | 59
853 | 1.2.4.4.1.2.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 852 | 855,854 | 16 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Line Market | 100 | 34 | 16 | 57 | 25
854 | 1.2.4.4.1.2.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 853 |  | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Formworker | 100 | 72 | 14 | 22 | 9
855 | 1.2.4.4.1.2.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 853 | 858 | 17 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Development Manager | 100 | 50 | 24 | 19 | 48
856 | 1.2.4.4.1.2.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 865 | 16 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Post Tension | 100 | 26 | 26 | 19 | 44
857 | 1.2.4.4.1.2.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 928 | 16 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Subcontractor | 100 | 71 | 10 | 26 | 20
858 | 1.2.4.4.1.2.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 855 | 859,860,861,862,863 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Landscaper | 100 | 10 | 35 | 1 | 45
859 | 1.2.4.4.1.2.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Carpet | 100 | 86 | 13 | 34 | 25
860 | 1.2.4.4.1.2.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863,927 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Line Market | 100 | 34 | 35 | 73 | 22
861 | 1.2.4.4.1.2.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 926 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Site Manager | 100 | 34 | 17 | 74 | 28
862 | 1.2.4.4.1.2.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 |  | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 1 | Surveyor | 100 | 42 | 28 | 68 | 39
863 | 1.2.4.4.1.2.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 858,859,860 | 864 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Project Manager | 100 | 47 | 15 | 21 | 2
864 | 1.2.4.4.1.2.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 863 | 865 | 26 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Site Manager | 100 | 53 | 11 | 99 | 41
865 | 1.2.4.4.1.2.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 856,864 | 866,867,868,869,871,873 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Hoarding | 100 | 87 | 12 | 46 | 36
866 | 1.2.4.4.1.2.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 870,873 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Admin | 100 | 68 | 35 | 73 | 4
867 | 1.2.4.4.1.2.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 873 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Plasterboarder | 100 | 28 | 20 | 20 | 3
868 | 1.2.4.4.1.2.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 872,873 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Stone Mason | 100 | 18 | 21 | 37 | 39
869 | 1.2.4.4.1.2.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Waterproofer | 100 | 91 | 17 | 7 | 45
870 | 1.2.4.4.1.2.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 866 | 873 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Scaffolder | 100 | 13 | 24 | 8 | 3
871 | 1.2.4.4.1.2.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Waterproofer | 100 | 83 | 16 | 76 | 25
872 | 1.2.4.4.1.2.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 868 | 873 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Surveyor | 100 | 84 | 11 | 12 | 24
873 | 1.2.4.4.1.2.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 865,866,867,868,869,870,871,872 | 874 | 4 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Hoarding | 100 | 100 | 33 | 18 | 27
874 | 1.2.4.4.1.2.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 873 | 875 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Contract Administrator | 100 | 95 | 28 | 85 | 32
875 | 1.2.4.4.1.2.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 874 | 876,893,910 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Fire | 100 | 92 | 14 | 100 | 23
876 | 1.2.4.4.1.2.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 877 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Excavation | 100 | 35 | 14 | 60 | 38
877 | 1.2.4.4.1.2.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 876 | 878 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Development Manager | 100 | 40 | 24 | 95 | 24
878 | 1.2.4.4.1.2.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 877 | 879 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Fire | 100 | 60 | 24 | 8 | 8
879 | 1.2.4.4.1.2.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 878 | 880 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Head Contractor | 100 | 44 | 15 | 34 | 24
880 | 1.2.4.4.1.2.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 879 | 881,882 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Stone Mason | 100 | 78 | 22 | 87 | 58
881 | 1.2.4.4.1.2.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 880 | 885 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Post Tension | 100 | 24 | 14 | 81 | 17
882 | 1.2.4.4.1.2.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 880 | 883 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Plumber | 100 | 96 | 14 | 63 | 58
883 | 1.2.4.4.1.2.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 882 | 884 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Waterproofer | 100 | 91 | 27 | 11 | 3
884 | 1.2.4.4.1.2.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 883 |  | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Reinforcement Fixer | 100 | 57 | 16 | 97 | 17
885 | 1.2.4.4.1.2.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 881 | 886,887,888,889,890 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Head Contractor | 100 | 34 | 13 | 67 | 52
886 | 1.2.4.4.1.2.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 885 |  | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Hoarding | 100 | 36 | 11 | 70 | 6
887 | 1.2.4.4.1.2.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Tiler | 100 | 68 | 22 | 70 | 37
888 | 1.2.4.4.1.2.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Surveyor | 100 | 28 | 31 | 30 | 40
889 | 1.2.4.4.1.2.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Site Manager | 100 | 48 | 24 | 66 | 6
890 | 1.2.4.4.1.2.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Renderer | 100 | 67 | 33 | 28 | 22
891 | 1.2.4.4.1.2.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 941 | 9 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Carpenter | 100 | 81 | 23 | 75 | 50
892 | 1.2.4.4.1.2.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Floor Sealer | 100 | 27 | 26 | 71 | 7
893 | 1.2.4.4.1.2.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 894 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Contract Administrator | 100 | 29 | 11 | 93 | 22
894 | 1.2.4.4.1.2.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 893 | 895 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Site Manager | 100 | 45 | 26 | 28 | 12
895 | 1.2.4.4.1.2.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 894 | 896 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Foreman | 100 | 55 | 20 | 92 | 58
896 | 1.2.4.4.1.2.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 895 | 897 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Scaffolder | 100 | 88 | 25 | 20 | 19
897 | 1.2.4.4.1.2.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 896 | 898 | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Development Manager | 100 | 52 | 18 | 18 | 6
898 | 1.2.4.4.1.2.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 897 | 899 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Project Manager | 100 | 27 | 21 | 24 | 41
899 | 1.2.4.4.1.2.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 898 | 900 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Plumber | 100 | 41 | 14 | 79 | 10
900 | 1.2.4.4.1.2.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 899 | 901 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Head Contractor | 100 | 46 | 11 | 89 | 52
901 | 1.2.4.4.1.2.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 900 | 902 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Hoarding | 100 | 30 | 25 | 35 | 3
902 | 1.2.4.4.1.2.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 901 | 903 | 25 November 2024 8:00 AM | 2024-11-29 17:00 | 4 | Electrician | 100 | 53 | 18 | 44 | 36
903 | 1.2.4.4.1.2.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 902 | 904 | 26 November 2024 8:00 AM | 2024-12-01 17:00 | 5 | Carpet | 100 | 66 | 13 | 94 | 40
904 | 1.2.4.4.1.2.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 903 | 908,905,906,907 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Landscaper | 100 | 46 | 17 | 65 | 50
905 | 1.2.4.4.1.2.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Scaffolder | 100 | 78 | 24 | 14 | 14
906 | 1.2.4.4.1.2.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Stone Mason | 100 | 38 | 24 | 8 | 37
907 | 1.2.4.4.1.2.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Painter | 100 | 57 | 16 | 10 | 41
908 | 1.2.4.4.1.2.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 904,905,906,907 |  | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Line Market | 100 | 94 | 26 | 8 | 53
909 | 1.2.4.4.1.2.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Mechanical | 100 | 96 | 15 | 31 | 42
910 | 1.2.4.4.1.2.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 911 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Scaffolder | 100 | 70 | 34 | 81 | 27
911 | 1.2.4.4.1.2.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 910 | 912 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Line Market | 100 | 10 | 31 | 53 | 46
912 | 1.2.4.4.1.2.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 911 | 913 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Joiner | 100 | 19 | 34 | 27 | 60
913 | 1.2.4.4.1.2.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 912 | 914 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Line Market | 100 | 14 | 28 | 65 | 48
914 | 1.2.4.4.1.2.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 913 | 915 | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Surveyor | 100 | 33 | 24 | 0 | 14
915 | 1.2.4.4.1.2.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 914 | 916 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Renderer | 100 | 54 | 12 | 75 | 30
916 | 1.2.4.4.1.2.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 915 | 917 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Carpet | 100 | 17 | 19 | 39 | 56
917 | 1.2.4.4.1.2.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 916 | 918,919,920,921 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Cleaner | 100 | 48 | 12 | 41 | 33
918 | 1.2.4.4.1.2.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Tiler | 100 | 81 | 16 | 67 | 53
919 | 1.2.4.4.1.2.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Surveyor | 100 | 51 | 16 | 8 | 28
920 | 1.2.4.4.1.2.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Tiler | 100 | 11 | 10 | 62 | 10
921 | 1.2.4.4.1.2.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Reinforcement Fixer | 100 | 48 | 17 | 82 | 26
922 | 1.2.4.4.1.2.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 918,919,920,921 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Stone Mason | 100 | 33 | 10 | 88 | 60
923 | 1.2.4.4.1.2.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-11-11 17:00 | 0 | Project Manager | 100 | 48 | 32 | 94 | 30
924 | 1.2.4.4.1.2.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 852 | 925 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Plasterboarder | 100 | 23 | 20 | 13 | 57
925 | 1.2.4.4.1.2.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 924 |  | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Formworker | 100 | 98 | 30 | 88 | 14
926 | 1.2.4.4.1.2.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 861 | 929 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Renderer | 100 | 75 | 27 | 60 | 44
927 | 1.2.4.4.1.2.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 860 | 929 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Carpenter | 100 | 71 | 35 | 79 | 42
928 | 1.2.4.4.1.2.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 857 | 929 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Timber Floorer | 100 | 92 | 19 | 28 | 36
929 | 1.2.4.4.1.2.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 926,927,928 | 930 | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Line Market | 100 | 38 | 11 | 62 | 50
930 | 1.2.4.4.1.2.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 929 | 931 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Joiner | 100 | 15 | 24 | 65 | 6
931 | 1.2.4.4.1.2.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 930 | 932 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Concretor | 100 | 26 | 29 | 74 | 12
932 | 1.2.4.4.1.2.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 931 | 933 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Timber Floorer | 100 | 45 | 21 | 28 | 38
933 | 1.2.4.4.1.2.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 932 | 934 | 1 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Stone Mason | 100 | 38 | 18 | 1 | 55
934 | 1.2.4.4.1.2.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 933 | 935 | 4 November 2024 8:00 AM | 2024-11-12 17:00 | 7 | Development Manager | 100 | 16 | 10 | 47 | 29
935 | 1.2.4.4.1.2.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 934 | 936 | 6 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Floor Sealer | 100 | 27 | 33 | 98 | 6
936 | 1.2.4.4.1.2.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 935 | 937,938,939,940 | 7 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Hoarding | 100 | 50 | 29 | 24 | 15
937 | 1.2.4.4.1.2.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Formworker | 100 | 67 | 16 | 6 | 31
938 | 1.2.4.4.1.2.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Hoarding | 100 | 37 | 14 | 59 | 10
939 | 1.2.4.4.1.2.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Concretor | 100 | 37 | 20 | 91 | 6
940 | 1.2.4.4.1.2.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Joiner | 100 | 20 | 33 | 64 | 19
941 | 1.2.4.4.1.2.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 887,888,889,890,891 | 942 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Timber Floorer | 100 | 87 | 16 | 30 | 44
942 | 1.2.4.4.1.2.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 941 | 943 | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Tiler | 100 | 48 | 26 | 45 | 7
943 | 1.2.4.4.1.2.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 942 | 944 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Renderer | 100 | 89 | 14 | 34 | 15
944 | 1.2.4.4.1.2.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 943 |  | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Contract Administrator | 100 | 42 | 11 | 66 | 37
945 | 1.2.4.4.1.3 | Apartment B012 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-12-07 17:00 | 0 | Waterproofer | 100 | 77 | 14 | 33 | 17
946 | 1.2.4.4.1.3.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 947,950,951,1018 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Carpet | 100 | 26 | 25 | 71 | 49
947 | 1.2.4.4.1.3.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 946 | 949,948 | 18 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Waterproofer | 100 | 83 | 20 | 77 | 38
948 | 1.2.4.4.1.3.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 947 |  | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Surveyor | 100 | 26 | 24 | 88 | 40
949 | 1.2.4.4.1.3.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 947 | 952 | 19 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Subcontractor | 100 | 42 | 31 | 97 | 4
950 | 1.2.4.4.1.3.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 959 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Scaffolder | 100 | 74 | 20 | 73 | 13
951 | 1.2.4.4.1.3.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 1022 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Electrician | 100 | 41 | 28 | 74 | 57
952 | 1.2.4.4.1.3.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 949 | 953,954,955,956,957 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Fire | 100 | 21 | 34 | 13 | 33
953 | 1.2.4.4.1.3.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Landscaper | 100 | 86 | 24 | 38 | 21
954 | 1.2.4.4.1.3.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957,1021 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Electrician | 100 | 62 | 22 | 90 | 19
955 | 1.2.4.4.1.3.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 1020 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Landscaper | 100 | 37 | 19 | 2 | 56
956 | 1.2.4.4.1.3.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 |  | 25 October 2024 8:00 AM | 2024-10-30 17:00 | 4 | Line Market | 100 | 19 | 31 | 22 | 10
957 | 1.2.4.4.1.3.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 952,953,954 | 958 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Fire | 100 | 65 | 25 | 97 | 41
958 | 1.2.4.4.1.3.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 957 | 959 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Floor Sealer | 100 | 56 | 16 | 33 | 39
959 | 1.2.4.4.1.3.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 950,958 | 960,961,962,963,965,967 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Electrician | 100 | 72 | 31 | 25 | 45
960 | 1.2.4.4.1.3.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 964,967 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Line Market | 100 | 86 | 29 | 14 | 30
961 | 1.2.4.4.1.3.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 967 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Admin | 100 | 34 | 29 | 43 | 10
962 | 1.2.4.4.1.3.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 966,967 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Electrician | 100 | 99 | 13 | 39 | 9
963 | 1.2.4.4.1.3.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Plasterboarder | 100 | 46 | 13 | 61 | 13
964 | 1.2.4.4.1.3.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 960 | 967 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Reinforcement Fixer | 100 | 84 | 13 | 66 | 56
965 | 1.2.4.4.1.3.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Scaffolder | 100 | 32 | 12 | 34 | 23
966 | 1.2.4.4.1.3.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 962 | 967 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Concretor | 100 | 42 | 35 | 81 | 34
967 | 1.2.4.4.1.3.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 959,960,961,962,963,964,965,966 | 968 | 6 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Hoarding | 100 | 64 | 33 | 76 | 17
968 | 1.2.4.4.1.3.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 967 | 969 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Site Manager | 100 | 94 | 33 | 88 | 22
969 | 1.2.4.4.1.3.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 968 | 970,987,1004 | 8 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Cleaner | 100 | 75 | 29 | 17 | 18
970 | 1.2.4.4.1.3.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 971 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Tiler | 100 | 66 | 14 | 42 | 42
971 | 1.2.4.4.1.3.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 970 | 972 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Subcontractor | 100 | 49 | 14 | 46 | 58
972 | 1.2.4.4.1.3.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 971 | 973 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Plasterboarder | 100 | 56 | 10 | 68 | 6
973 | 1.2.4.4.1.3.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 972 | 974 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Excavation | 100 | 34 | 20 | 30 | 46
974 | 1.2.4.4.1.3.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 973 | 975,976 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Mechanical | 100 | 16 | 32 | 93 | 55
975 | 1.2.4.4.1.3.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 974 | 979 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Fire | 100 | 42 | 34 | 39 | 55
976 | 1.2.4.4.1.3.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 974 | 977 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Timber Floorer | 100 | 52 | 10 | 86 | 20
977 | 1.2.4.4.1.3.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 976 | 978 | 20 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Subcontractor | 100 | 59 | 29 | 16 | 25
978 | 1.2.4.4.1.3.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 977 |  | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Excavation | 100 | 91 | 27 | 49 | 5
979 | 1.2.4.4.1.3.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 975 | 980,981,982,983,984 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Metal Work | 100 | 86 | 33 | 75 | 41
980 | 1.2.4.4.1.3.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 979 |  | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Carpenter | 100 | 37 | 26 | 4 | 8
981 | 1.2.4.4.1.3.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Contract Administrator | 100 | 44 | 28 | 75 | 7
982 | 1.2.4.4.1.3.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Carpet | 100 | 43 | 17 | 41 | 50
983 | 1.2.4.4.1.3.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Concretor | 100 | 74 | 35 | 45 | 59
984 | 1.2.4.4.1.3.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Carpet | 100 | 91 | 15 | 98 | 28
985 | 1.2.4.4.1.3.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1035 | 12 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Waterproofer | 100 | 29 | 29 | 71 | 27
986 | 1.2.4.4.1.3.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | 12 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Renderer | 100 | 40 | 27 | 69 | 55
987 | 1.2.4.4.1.3.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 988 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Site Manager | 100 | 16 | 11 | 14 | 21
988 | 1.2.4.4.1.3.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 987 | 989 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Admin | 100 | 81 | 25 | 75 | 27
989 | 1.2.4.4.1.3.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 988 | 990 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Foreman | 100 | 75 | 12 | 26 | 60
990 | 1.2.4.4.1.3.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 989 | 991 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Formworker | 100 | 12 | 31 | 40 | 41
991 | 1.2.4.4.1.3.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 990 | 992 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Formworker | 100 | 53 | 17 | 68 | 19
992 | 1.2.4.4.1.3.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 991 | 993 | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Subcontractor | 100 | 77 | 31 | 35 | 56
993 | 1.2.4.4.1.3.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 992 | 994 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Timber Floorer | 100 | 38 | 35 | 61 | 43
994 | 1.2.4.4.1.3.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 993 | 995 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Concretor | 100 | 41 | 24 | 10 | 28
995 | 1.2.4.4.1.3.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 994 | 996 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Metal Work | 100 | 22 | 18 | 14 | 50
996 | 1.2.4.4.1.3.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 995 | 997 | 27 November 2024 8:00 AM | 2024-11-30 17:00 | 3 | Joiner | 100 | 61 | 27 | 31 | 30
997 | 1.2.4.4.1.3.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 996 | 998 | 28 November 2024 8:00 AM | 2024-12-01 17:00 | 3 | Post Tension | 100 | 33 | 25 | 7 | 5
998 | 1.2.4.4.1.3.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 997 | 1002,999,1000,1001 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Subcontractor | 100 | 78 | 27 | 97 | 52
999 | 1.2.4.4.1.3.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Timber Floorer | 100 | 57 | 35 | 11 | 42
1000 | 1.2.4.4.1.3.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Mechanical | 100 | 24 | 10 | 62 | 56
1001 | 1.2.4.4.1.3.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Reinforcement Fixer | 100 | 77 | 18 | 100 | 6
1002 | 1.2.4.4.1.3.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 998,999,1000,1001 |  | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Cleaner | 100 | 86 | 35 | 71 | 50
1003 | 1.2.4.4.1.3.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | 12 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Fire | 100 | 56 | 12 | 79 | 18
1004 | 1.2.4.4.1.3.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 1005 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Admin | 100 | 39 | 25 | 66 | 31
1005 | 1.2.4.4.1.3.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1004 | 1006 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Admin | 100 | 96 | 28 | 85 | 29
1006 | 1.2.4.4.1.3.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1005 | 1007 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Mechanical | 100 | 56 | 29 | 32 | 39
1007 | 1.2.4.4.1.3.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1006 | 1008 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Excavation | 100 | 30 | 27 | 31 | 43
1008 | 1.2.4.4.1.3.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1007 | 1009 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Contract Administrator | 100 | 24 | 13 | 84 | 38
1009 | 1.2.4.4.1.3.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1008 | 1010 | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Floor Sealer | 100 | 77 | 21 | 92 | 11
1010 | 1.2.4.4.1.3.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1009 | 1011 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Electrician | 100 | 88 | 28 | 70 | 30
1011 | 1.2.4.4.1.3.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1010 | 1012,1013,1014,1015 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Development Manager | 100 | 27 | 32 | 28 | 26
1012 | 1.2.4.4.1.3.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Subcontractor | 100 | 93 | 13 | 29 | 6
1013 | 1.2.4.4.1.3.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Reinforcement Fixer | 100 | 40 | 15 | 48 | 52
1014 | 1.2.4.4.1.3.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 3 | Head Contractor | 100 | 27 | 21 | 14 | 9
1015 | 1.2.4.4.1.3.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Painter | 100 | 28 | 34 | 94 | 24
1016 | 1.2.4.4.1.3.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1012,1013,1014,1015 |  | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Renderer | 100 | 67 | 32 | 97 | 32
1017 | 1.2.4.4.1.3.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | 18 October 2024 8:00 AM | 2024-11-13 17:00 | 0 | Metal Work | 100 | 80 | 10 | 26 | 46
1018 | 1.2.4.4.1.3.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 946 | 1019 | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Carpenter | 100 | 44 | 17 | 93 | 31
1019 | 1.2.4.4.1.3.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1018 |  | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Reinforcement Fixer | 100 | 53 | 28 | 21 | 13
1020 | 1.2.4.4.1.3.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 955 | 1023 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Site Manager | 100 | 72 | 13 | 58 | 3
1021 | 1.2.4.4.1.3.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 954 | 1023 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Site Manager | 100 | 20 | 23 | 35 | 8
1022 | 1.2.4.4.1.3.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 951 | 1023 | 22 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Floor Sealer | 100 | 60 | 32 | 27 | 46
1023 | 1.2.4.4.1.3.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1020,1021,1022 | 1024 | 29 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Post Tension | 100 | 91 | 16 | 21 | 22
1024 | 1.2.4.4.1.3.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1023 | 1025 | 30 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Joiner | 100 | 16 | 12 | 99 | 23
1025 | 1.2.4.4.1.3.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1024 | 1026 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Scaffolder | 100 | 38 | 10 | 96 | 18
1026 | 1.2.4.4.1.3.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1025 | 1027 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Contract Administrator | 100 | 100 | 27 | 17 | 21
1027 | 1.2.4.4.1.3.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1026 | 1028 | 4 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Stone Mason | 100 | 14 | 30 | 79 | 22
1028 | 1.2.4.4.1.3.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1027 | 1029 | 6 November 2024 8:00 AM | 2024-11-12 17:00 | 5 | Excavation | 100 | 69 | 17 | 77 | 11
1029 | 1.2.4.4.1.3.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1028 | 1030 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Line Market | 100 | 28 | 17 | 58 | 38
1030 | 1.2.4.4.1.3.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1029 | 1031,1032,1033,1034 | 9 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Concretor | 100 | 95 | 31 | 89 | 56
1031 | 1.2.4.4.1.3.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Concretor | 100 | 60 | 17 | 5 | 27
1032 | 1.2.4.4.1.3.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Landscaper | 100 | 83 | 18 | 86 | 60
1033 | 1.2.4.4.1.3.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Project Manager | 100 | 46 | 26 | 32 | 47
1034 | 1.2.4.4.1.3.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Stone Mason | 100 | 17 | 11 | 0 | 56
1035 | 1.2.4.4.1.3.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 981,982,983,984,985 | 1036 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Post Tension | 100 | 69 | 21 | 48 | 51
1036 | 1.2.4.4.1.3.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1035 | 1037 | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Landscaper | 100 | 73 | 16 | 92 | 42
1037 | 1.2.4.4.1.3.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1036 | 1038 | 6 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Tiler | 100 | 19 | 20 | 54 | 45
1038 | 1.2.4.4.1.3.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1037 |  | 7 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Renderer | 100 | 55 | 18 | 47 | 13
1039 | 1.2.4.4.1.4 | Apartment B013 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-12-07 17:00 | 0 | Head Contractor | 100 | 25 | 35 | 22 | 42
1040 | 1.2.4.4.1.4.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 1041,1044,1045,1112 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Fire | 100 | 85 | 34 | 10 | 12
1041 | 1.2.4.4.1.4.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 1040 | 1043,1042 | 18 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Contract Administrator | 100 | 95 | 16 | 54 | 23
1042 | 1.2.4.4.1.4.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1041 |  | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Carpet | 100 | 79 | 11 | 96 | 54
1043 | 1.2.4.4.1.4.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1041 | 1046 | 19 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Joiner | 100 | 94 | 15 | 5 | 47
1044 | 1.2.4.4.1.4.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1053 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Reinforcement Fixer | 100 | 59 | 25 | 82 | 55
1045 | 1.2.4.4.1.4.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1116 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Surveyor | 100 | 57 | 18 | 84 | 19
1046 | 1.2.4.4.1.4.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1043 | 1047,1048,1049,1050,1051 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Carpenter | 100 | 49 | 13 | 8 | 41
1047 | 1.2.4.4.1.4.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Development Manager | 100 | 47 | 20 | 61 | 45
1048 | 1.2.4.4.1.4.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051,1115 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Tiler | 100 | 20 | 23 | 75 | 33
1049 | 1.2.4.4.1.4.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1114 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Plumber | 100 | 78 | 15 | 66 | 28
1050 | 1.2.4.4.1.4.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 |  | 25 October 2024 8:00 AM | 2024-11-01 17:00 | 6 | Scaffolder | 100 | 38 | 32 | 6 | 45
1051 | 1.2.4.4.1.4.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1046,1047,1048 | 1052 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Carpet | 100 | 89 | 31 | 44 | 4
1052 | 1.2.4.4.1.4.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1051 | 1053 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Head Contractor | 100 | 96 | 12 | 16 | 38
1053 | 1.2.4.4.1.4.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1044,1052 | 1054,1055,1056,1057,1059,1061 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Carpet | 100 | 71 | 24 | 14 | 6
1054 | 1.2.4.4.1.4.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1058,1061 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Landscaper | 100 | 34 | 24 | 2 | 20
1055 | 1.2.4.4.1.4.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1061 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Contract Administrator | 100 | 67 | 18 | 58 | 27
1056 | 1.2.4.4.1.4.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1060,1061 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Metal Work | 100 | 93 | 13 | 70 | 36
1057 | 1.2.4.4.1.4.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Surveyor | 0 | 40 | 13 | 24 | 55
1058 | 1.2.4.4.1.4.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1054 | 1061 | - | - | 0 | Window | 0 | 52 | 24 | 89 | 46
1059 | 1.2.4.4.1.4.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | - | - | 0 | Contract Administrator | 0 | 81 | 23 | 2 | 3
1060 | 1.2.4.4.1.4.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1056 | 1061 | - | - | 0 | Cleaner | 0 | 20 | 24 | 94 | 39
1061 | 1.2.4.4.1.4.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1053,1054,1055,1056,1057,1058,1059,1060 | 1062 | - | - | 0 | Reinforcement Fixer | 0 | 23 | 19 | 87 | 52
1062 | 1.2.4.4.1.4.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1061 | 1063 | - | - | 0 | Development Manager | 0 | 54 | 35 | 66 | 36
1063 | 1.2.4.4.1.4.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1062 | 1064,1081,1098 | - | - | 0 | Development Manager | 0 | 77 | 15 | 54 | 55
1064 | 1.2.4.4.1.4.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1065 | - | - | 0 | Renderer | 0 | 61 | 31 | 70 | 2
1065 | 1.2.4.4.1.4.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1064 | 1066 | - | - | 0 | Plasterboarder | 0 | 12 | 27 | 83 | 40
1066 | 1.2.4.4.1.4.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1065 | 1067 | - | - | 0 | Post Tension | 0 | 40 | 25 | 69 | 26
1067 | 1.2.4.4.1.4.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1066 | 1068 | - | - | 0 | Carpet | 0 | 16 | 20 | 20 | 45
1068 | 1.2.4.4.1.4.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1067 | 1069,1070 | - | - | 0 | Electrician | 0 | 68 | 17 | 82 | 60
1069 | 1.2.4.4.1.4.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1068 | 1073 | - | - | 0 | Joiner | 0 | 80 | 35 | 22 | 23
1070 | 1.2.4.4.1.4.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1068 | 1071 | - | - | 0 | Reinforcement Fixer | 0 | 40 | 17 | 31 | 24
1071 | 1.2.4.4.1.4.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1070 | 1072 | - | - | 0 | Waterproofer | 0 | 48 | 17 | 53 | 3
1072 | 1.2.4.4.1.4.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1071 |  | - | - | 0 | Window | 0 | 26 | 21 | 5 | 43
1073 | 1.2.4.4.1.4.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1069 | 1074,1075,1076,1077,1078 | - | - | 0 | Line Market | 0 | 54 | 33 | 90 | 35
1074 | 1.2.4.4.1.4.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1073 |  | - | - | 0 | Line Market | 0 | 79 | 11 | 13 | 37
1075 | 1.2.4.4.1.4.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Reinforcement Fixer | 0 | 49 | 24 | 92 | 33
1076 | 1.2.4.4.1.4.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Electrician | 0 | 44 | 27 | 41 | 53
1077 | 1.2.4.4.1.4.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Post Tension | 0 | 45 | 16 | 26 | 42
1078 | 1.2.4.4.1.4.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | - | - | 0 | Plumber | 0 | 99 | 21 | 51 | 54
1079 | 1.2.4.4.1.4.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1129 | - | - | 0 | Floor Sealer | 0 | 89 | 35 | 46 | 12
1080 | 1.2.4.4.1.4.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Timber Floorer | 0 | 98 | 22 | 80 | 36
1081 | 1.2.4.4.1.4.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1082 | - | - | 0 | Admin | 0 | 92 | 14 | 0 | 53
1082 | 1.2.4.4.1.4.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1081 | 1083 | - | - | 0 | Line Market | 0 | 82 | 22 | 75 | 34
1083 | 1.2.4.4.1.4.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1082 | 1084 | - | - | 0 | Joiner | 0 | 17 | 13 | 98 | 24
1084 | 1.2.4.4.1.4.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1083 | 1085 | - | - | 0 | Waterproofer | 0 | 77 | 13 | 16 | 26
1085 | 1.2.4.4.1.4.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1084 | 1086 | - | - | 0 | Plasterboarder | 0 | 60 | 26 | 29 | 7
1086 | 1.2.4.4.1.4.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1085 | 1087 | - | - | 0 | Subcontractor | 0 | 48 | 33 | 62 | 17
1087 | 1.2.4.4.1.4.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1086 | 1088 | - | - | 0 | Metal Work | 0 | 13 | 32 | 71 | 13
1088 | 1.2.4.4.1.4.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1087 | 1089 | - | - | 0 | Renderer | 0 | 19 | 31 | 84 | 54
1089 | 1.2.4.4.1.4.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1088 | 1090 | - | - | 0 | Carpenter | 0 | 17 | 27 | 46 | 8
1090 | 1.2.4.4.1.4.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1089 | 1091 | - | - | 0 | Timber Floorer | 0 | 68 | 21 | 78 | 22
1091 | 1.2.4.4.1.4.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1090 | 1092 | - | - | 0 | Site Manager | 0 | 43 | 12 | 5 | 43
1092 | 1.2.4.4.1.4.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1091 | 1096,1093,1094,1095 | - | - | 0 | Head Contractor | 0 | 31 | 22 | 53 | 13
1093 | 1.2.4.4.1.4.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Admin | 0 | 27 | 27 | 54 | 10
1094 | 1.2.4.4.1.4.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Hoarding | 0 | 81 | 12 | 17 | 60
1095 | 1.2.4.4.1.4.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | - | - | 0 | Window | 0 | 80 | 31 | 3 | 16
1096 | 1.2.4.4.1.4.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1092,1093,1094,1095 |  | - | - | 0 | Post Tension | 0 | 64 | 30 | 51 | 25
1097 | 1.2.4.4.1.4.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | - | - | 0 | Development Manager | 0 | 35 | 30 | 38 | 6
1098 | 1.2.4.4.1.4.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1099 | - | - | 0 | Tiler | 0 | 58 | 34 | 16 | 9
1099 | 1.2.4.4.1.4.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1098 | 1100 | - | - | 0 | Project Manager | 0 | 60 | 19 | 77 | 33
1100 | 1.2.4.4.1.4.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1099 | 1101 | - | - | 0 | Painter | 0 | 29 | 18 | 71 | 17
1101 | 1.2.4.4.1.4.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1100 | 1102 | - | - | 0 | Contract Administrator | 0 | 16 | 22 | 9 | 30
1102 | 1.2.4.4.1.4.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1101 | 1103 | - | - | 0 | Plumber | 0 | 12 | 33 | 61 | 17
1103 | 1.2.4.4.1.4.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1102 | 1104 | - | - | 0 | Stone Mason | 0 | 91 | 15 | 73 | 28
1104 | 1.2.4.4.1.4.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1103 | 1105 | - | - | 0 | Landscaper | 0 | 81 | 11 | 20 | 17
1105 | 1.2.4.4.1.4.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1104 | 1106,1107,1108,1109 | - | - | 0 | Foreman | 0 | 12 | 26 | 83 | 7
1106 | 1.2.4.4.1.4.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Post Tension | 0 | 62 | 20 | 33 | 29
1107 | 1.2.4.4.1.4.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Hoarding | 0 | 36 | 24 | 59 | 37
1108 | 1.2.4.4.1.4.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Excavation | 0 | 93 | 25 | 10 | 26
1109 | 1.2.4.4.1.4.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | - | - | 0 | Painter | 0 | 19 | 30 | 94 | 7
1110 | 1.2.4.4.1.4.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1106,1107,1108,1109 |  | - | - | 0 | Development Manager | 0 | 81 | 14 | 45 | 10
1111 | 1.2.4.4.1.4.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | - | - | 0 | Landscaper | 0 | 92 | 35 | 4 | 10
1112 | 1.2.4.4.1.4.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 1040 | 1113 | - | - | 0 | Electrician | 0 | 51 | 30 | 80 | 10
1113 | 1.2.4.4.1.4.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1112 |  | - | - | 0 | Development Manager | 0 | 63 | 34 | 74 | 36
1114 | 1.2.4.4.1.4.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1049 | 1117 | - | - | 0 | Post Tension | 0 | 49 | 34 | 71 | 9
1115 | 1.2.4.4.1.4.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1048 | 1117 | - | - | 0 | Post Tension | 0 | 11 | 27 | 60 | 36
1116 | 1.2.4.4.1.4.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1045 | 1117 | - | - | 0 | Electrician | 0 | 45 | 18 | 38 | 12
1117 | 1.2.4.4.1.4.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1114,1115,1116 | 1118 | - | - | 0 | Surveyor | 0 | 59 | 22 | 65 | 24
1118 | 1.2.4.4.1.4.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1117 | 1119 | - | - | 0 | Renderer | 0 | 91 | 29 | 20 | 13
1119 | 1.2.4.4.1.4.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1118 | 1120 | - | - | 0 | Subcontractor | 0 | 60 | 26 | 97 | 60
1120 | 1.2.4.4.1.4.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1119 | 1121 | - | - | 0 | Post Tension | 0 | 57 | 29 | 2 | 32
1121 | 1.2.4.4.1.4.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1120 | 1122 | - | - | 0 | Plumber | 0 | 67 | 26 | 12 | 20
1122 | 1.2.4.4.1.4.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1121 | 1123 | - | - | 0 | Hoarding | 0 | 27 | 31 | 61 | 36
1123 | 1.2.4.4.1.4.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1122 | 1124 | - | - | 0 | Contract Administrator | 0 | 12 | 28 | 41 | 37
1124 | 1.2.4.4.1.4.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1123 | 1125,1126,1127,1128 | - | - | 0 | Floor Sealer | 0 | 33 | 34 | 34 | 18
1125 | 1.2.4.4.1.4.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Mechanical | 0 | 11 | 33 | 7 | 31
1126 | 1.2.4.4.1.4.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Window | 0 | 80 | 30 | 52 | 24
1127 | 1.2.4.4.1.4.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Painter | 0 | 22 | 23 | 79 | 3
1128 | 1.2.4.4.1.4.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | - | - | 0 | Subcontractor | 0 | 70 | 31 | 6 | 60
1129 | 1.2.4.4.1.4.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1075,1076,1077,1078,1079 | 1130 | - | - | 0 | Plasterboarder | 0 | 72 | 23 | 81 | 39
1130 | 1.2.4.4.1.4.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1129 | 1131 | - | - | 0 | Renderer | 0 | 13 | 23 | 59 | 45
1131 | 1.2.4.4.1.4.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1130 | 1132 | - | - | 0 | Foreman | 0 | 17 | 20 | 100 | 21
1132 | 1.2.4.4.1.4.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1131 |  | - | - | 0 | Renderer | 0 | 75 | 14 | 23 | 50
1133 | 1.2.4.4.1.5 | Apartment B014 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | - | - | 0 | Joiner | 0 | 96 | 22 | 18 | 47
1134 | 1.2.4.4.1.5.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1135,1138,1139,1206 | - | - | 0 | Contract Administrator | 0 | 73 | 12 | 76 | 37
1135 | 1.2.4.4.1.5.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1134 | 1137,1136 | - | - | 0 | Formworker | 0 | 97 | 12 | 53 | 47
1136 | 1.2.4.4.1.5.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1135 |  | - | - | 0 | Project Manager | 0 | 17 | 10 | 54 | 29
1137 | 1.2.4.4.1.5.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1135 | 1140 | - | - | 0 | Line Market | 0 | 50 | 26 | 13 | 50
1138 | 1.2.4.4.1.5.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1147 | - | - | 0 | Reinforcement Fixer | 0 | 38 | 17 | 19 | 30
1139 | 1.2.4.4.1.5.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1210 | - | - | 0 | Site Manager | 0 | 45 | 18 | 63 | 37
1140 | 1.2.4.4.1.5.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1137 | 1141,1142,1143,1144,1145 | - | - | 0 | Renderer | 0 | 36 | 13 | 62 | 32
1141 | 1.2.4.4.1.5.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145 | - | - | 0 | Hoarding | 0 | 80 | 33 | 33 | 25
1142 | 1.2.4.4.1.5.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145,1209 | - | - | 0 | Project Manager | 0 | 47 | 20 | 87 | 48
1143 | 1.2.4.4.1.5.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1208 | - | - | 0 | Hoarding | 0 | 74 | 16 | 94 | 33
1144 | 1.2.4.4.1.5.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 |  | - | - | 0 | Scaffolder | 0 | 77 | 20 | 41 | 40
1145 | 1.2.4.4.1.5.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1140,1141,1142 | 1146 | - | - | 0 | Timber Floorer | 0 | 100 | 25 | 96 | 37
1146 | 1.2.4.4.1.5.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1145 | 1147 | - | - | 0 | Electrician | 0 | 54 | 29 | 33 | 48
1147 | 1.2.4.4.1.5.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1138,1146 | 1148,1149,1150,1151,1153,1155 | - | - | 0 | Cleaner | 0 | 56 | 17 | 58 | 41
1148 | 1.2.4.4.1.5.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1152,1155 | - | - | 0 | Site Manager | 0 | 59 | 13 | 30 | 18
1149 | 1.2.4.4.1.5.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Electrician | 0 | 44 | 25 | 20 | 20
1150 | 1.2.4.4.1.5.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1154,1155 | - | - | 0 | Project Manager | 0 | 84 | 17 | 5 | 56
1151 | 1.2.4.4.1.5.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Waterproofer | 0 | 24 | 32 | 34 | 29
1152 | 1.2.4.4.1.5.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1148 | 1155 | - | - | 0 | Plumber | 0 | 79 | 25 | 93 | 43
1153 | 1.2.4.4.1.5.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | - | - | 0 | Stone Mason | 0 | 73 | 35 | 56 | 46
1154 | 1.2.4.4.1.5.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1150 | 1155 | - | - | 0 | Hoarding | 0 | 68 | 29 | 38 | 21
1155 | 1.2.4.4.1.5.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1147,1148,1149,1150,1151,1152,1153,1154 | 1156 | - | - | 0 | Waterproofer | 0 | 77 | 31 | 20 | 46
1156 | 1.2.4.4.1.5.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1155 | 1157 | - | - | 0 | Admin | 0 | 33 | 13 | 58 | 36
1157 | 1.2.4.4.1.5.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1156 | 1158,1175,1192 | - | - | 0 | Electrician | 0 | 97 | 21 | 26 | 45
1158 | 1.2.4.4.1.5.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1159 | - | - | 0 | Contract Administrator | 0 | 24 | 14 | 66 | 55
1159 | 1.2.4.4.1.5.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1158 | 1160 | - | - | 0 | Admin | 0 | 52 | 34 | 24 | 39
1160 | 1.2.4.4.1.5.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1159 | 1161 | - | - | 0 | Fire | 0 | 38 | 21 | 75 | 15
1161 | 1.2.4.4.1.5.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1160 | 1162 | - | - | 0 | Plasterboarder | 0 | 88 | 29 | 27 | 47
1162 | 1.2.4.4.1.5.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1161 | 1163,1164 | - | - | 0 | Formworker | 0 | 29 | 21 | 100 | 32
1163 | 1.2.4.4.1.5.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1162 | 1167 | - | - | 0 | Scaffolder | 0 | 49 | 14 | 83 | 19
1164 | 1.2.4.4.1.5.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1162 | 1165 | - | - | 0 | Contract Administrator | 0 | 98 | 30 | 15 | 39
1165 | 1.2.4.4.1.5.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1164 | 1166 | - | - | 0 | Development Manager | 0 | 71 | 30 | 37 | 23
1166 | 1.2.4.4.1.5.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1165 |  | - | - | 0 | Project Manager | 0 | 35 | 10 | 60 | 9
1167 | 1.2.4.4.1.5.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1163 | 1168,1169,1170,1171,1172 | - | - | 0 | Admin | 0 | 88 | 28 | 74 | 12
1168 | 1.2.4.4.1.5.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1167 |  | - | - | 0 | Admin | 0 | 55 | 29 | 3 | 37
1169 | 1.2.4.4.1.5.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Admin | 0 | 66 | 13 | 81 | 53
1170 | 1.2.4.4.1.5.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Joiner | 0 | 43 | 24 | 30 | 33
1171 | 1.2.4.4.1.5.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Cleaner | 0 | 35 | 14 | 73 | 8
1172 | 1.2.4.4.1.5.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | - | - | 0 | Foreman | 0 | 99 | 14 | 72 | 55
1173 | 1.2.4.4.1.5.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1223 | - | - | 0 | Fire | 0 | 46 | 19 | 94 | 48
1174 | 1.2.4.4.1.5.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Plumber | 0 | 89 | 28 | 26 | 33
1175 | 1.2.4.4.1.5.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1176 | - | - | 0 | Renderer | 0 | 14 | 26 | 7 | 37
1176 | 1.2.4.4.1.5.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1175 | 1177 | - | - | 0 | Formworker | 0 | 88 | 11 | 22 | 3
1177 | 1.2.4.4.1.5.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1176 | 1178 | - | - | 0 | Plumber | 0 | 34 | 24 | 16 | 34
1178 | 1.2.4.4.1.5.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1177 | 1179 | - | - | 0 | Subcontractor | 0 | 77 | 26 | 71 | 3
1179 | 1.2.4.4.1.5.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1178 | 1180 | - | - | 0 | Carpenter | 0 | 87 | 30 | 35 | 51
1180 | 1.2.4.4.1.5.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1179 | 1181 | - | - | 0 | Timber Floorer | 0 | 68 | 30 | 93 | 48
1181 | 1.2.4.4.1.5.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1180 | 1182 | - | - | 0 | Carpenter | 0 | 56 | 29 | 80 | 42
1182 | 1.2.4.4.1.5.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1181 | 1183 | - | - | 0 | Renderer | 0 | 59 | 35 | 81 | 49
1183 | 1.2.4.4.1.5.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1182 | 1184 | - | - | 0 | Floor Sealer | 0 | 47 | 23 | 48 | 15
1184 | 1.2.4.4.1.5.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1183 | 1185 | - | - | 0 | Head Contractor | 0 | 29 | 23 | 45 | 8
1185 | 1.2.4.4.1.5.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1184 | 1186 | - | - | 0 | Development Manager | 0 | 86 | 27 | 28 | 9
1186 | 1.2.4.4.1.5.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1185 | 1190,1187,1188,1189 | - | - | 0 | Painter | 0 | 90 | 33 | 60 | 20
1187 | 1.2.4.4.1.5.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Development Manager | 0 | 87 | 13 | 81 | 34
1188 | 1.2.4.4.1.5.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Concretor | 0 | 39 | 14 | 73 | 15
1189 | 1.2.4.4.1.5.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | - | - | 0 | Reinforcement Fixer | 0 | 28 | 32 | 96 | 3
1190 | 1.2.4.4.1.5.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1186,1187,1188,1189 |  | - | - | 0 | Admin | 0 | 88 | 20 | 83 | 51
1191 | 1.2.4.4.1.5.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Timber Floorer | 0 | 93 | 11 | 57 | 9
1192 | 1.2.4.4.1.5.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1193 | - | - | 0 | Painter | 0 | 59 | 27 | 36 | 33
1193 | 1.2.4.4.1.5.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1192 | 1194 | - | - | 0 | Subcontractor | 0 | 79 | 35 | 49 | 48
1194 | 1.2.4.4.1.5.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1193 | 1195 | - | - | 0 | Surveyor | 0 | 35 | 15 | 95 | 45
1195 | 1.2.4.4.1.5.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1194 | 1196 | - | - | 0 | Landscaper | 0 | 94 | 11 | 74 | 29
1196 | 1.2.4.4.1.5.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1195 | 1197 | - | - | 0 | Concretor | 0 | 86 | 19 | 3 | 2
1197 | 1.2.4.4.1.5.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1196 | 1198 | - | - | 0 | Foreman | 0 | 72 | 25 | 19 | 34
1198 | 1.2.4.4.1.5.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1197 | 1199 | - | - | 0 | Stone Mason | 0 | 97 | 33 | 48 | 22
1199 | 1.2.4.4.1.5.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1198 | 1200,1201,1202,1203 | - | - | 0 | Head Contractor | 0 | 11 | 31 | 22 | 45
1200 | 1.2.4.4.1.5.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Surveyor | 0 | 44 | 31 | 56 | 4
1201 | 1.2.4.4.1.5.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Project Manager | 0 | 42 | 34 | 54 | 11
1202 | 1.2.4.4.1.5.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Waterproofer | 0 | 59 | 13 | 94 | 23
1203 | 1.2.4.4.1.5.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | - | - | 0 | Concretor | 0 | 78 | 26 | 49 | 3
1204 | 1.2.4.4.1.5.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1200,1201,1202,1203 |  | - | - | 0 | Post Tension | 0 | 59 | 24 | 84 | 27
1205 | 1.2.4.4.1.5.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | - | - | 0 | Mechanical | 0 | 25 | 33 | 53 | 4
1206 | 1.2.4.4.1.5.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1134 | 1207 | - | - | 0 | Excavation | 0 | 69 | 30 | 67 | 45
1207 | 1.2.4.4.1.5.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1206 |  | - | - | 0 | Reinforcement Fixer | 0 | 27 | 31 | 42 | 23
1208 | 1.2.4.4.1.5.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1143 | 1211 | - | - | 0 | Renderer | 0 | 19 | 10 | 2 | 32
1209 | 1.2.4.4.1.5.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1142 | 1211 | - | - | 0 | Joiner | 0 | 98 | 34 | 97 | 5
1210 | 1.2.4.4.1.5.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1139 | 1211 | - | - | 0 | Contract Administrator | 0 | 20 | 25 | 61 | 2
1211 | 1.2.4.4.1.5.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1208,1209,1210 | 1212 | - | - | 0 | Tiler | 0 | 38 | 26 | 4 | 34
1212 | 1.2.4.4.1.5.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1211 | 1213 | - | - | 0 | Mechanical | 0 | 46 | 14 | 30 | 3
1213 | 1.2.4.4.1.5.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1212 | 1214 | - | - | 0 | Site Manager | 0 | 42 | 32 | 33 | 13
1214 | 1.2.4.4.1.5.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1213 | 1215 | - | - | 0 | Site Manager | 0 | 35 | 13 | 22 | 53
1215 | 1.2.4.4.1.5.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1214 | 1216 | - | - | 0 | Carpenter | 0 | 58 | 14 | 41 | 59
1216 | 1.2.4.4.1.5.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1215 | 1217 | - | - | 0 | Surveyor | 0 | 70 | 29 | 4 | 20
1217 | 1.2.4.4.1.5.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1216 | 1218 | - | - | 0 | Formworker | 0 | 59 | 30 | 32 | 38
1218 | 1.2.4.4.1.5.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1217 | 1219,1220,1221,1222 | - | - | 0 | Line Market | 0 | 30 | 18 | 6 | 6
1219 | 1.2.4.4.1.5.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Site Manager | 0 | 99 | 34 | 30 | 13
1220 | 1.2.4.4.1.5.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Landscaper | 0 | 40 | 15 | 9 | 51
1221 | 1.2.4.4.1.5.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Post Tension | 0 | 66 | 29 | 91 | 33
1222 | 1.2.4.4.1.5.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | - | - | 0 | Metal Work | 0 | 34 | 27 | 83 | 15
1223 | 1.2.4.4.1.5.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1169,1170,1171,1172,1173 | 1224 | - | - | 0 | Window | 0 | 59 | 30 | 49 | 49
1224 | 1.2.4.4.1.5.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1223 | 1225 | - | - | 0 | Electrician | 0 | 85 | 29 | 44 | 19
1225 | 1.2.4.4.1.5.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1224 | 1226 | - | - | 0 | Excavation | 0 | 60 | 10 | 49 | 33
1226 | 1.2.4.4.1.5.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1225 |  | - | - | 0 | Surveyor | 0 | 36 | 19 | 33 | 24
1227 | 1.2.4.4.1.6 | Apartment B015 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | - | - | 0 | Window | 0 | 46 | 29 | 35 | 41
1228 | 1.2.4.4.1.6.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1229,1232,1233,1300 | - | - | 0 | Subcontractor | 0 | 23 | 25 | 76 | 23
1229 | 1.2.4.4.1.6.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1228 | 1231,1230 | - | - | 0 | Landscaper | 0 | 34 | 27 | 97 | 33
1230 | 1.2.4.4.1.6.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1229 |  | - | - | 0 | Painter | 0 | 25 | 22 | 12 | 59
1231 | 1.2.4.4.1.6.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1229 | 1234 | - | - | 0 | Site Manager | 0 | 29 | 10 | 59 | 28
1232 | 1.2.4.4.1.6.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1241 | - | - | 0 | Metal Work | 0 | 92 | 22 | 94 | 48
1233 | 1.2.4.4.1.6.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1304 | - | - | 0 | Head Contractor | 0 | 56 | 29 | 33 | 26
1234 | 1.2.4.4.1.6.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1231 | 1235,1236,1237,1238,1239 | - | - | 0 | Scaffolder | 0 | 12 | 19 | 38 | 57
1235 | 1.2.4.4.1.6.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239 | - | - | 0 | Window | 0 | 51 | 18 | 59 | 50
1236 | 1.2.4.4.1.6.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239,1303 | - | - | 0 | Development Manager | 0 | 10 | 16 | 52 | 36
1237 | 1.2.4.4.1.6.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1302 | - | - | 0 | Concretor | 0 | 31 | 32 | 69 | 17
1238 | 1.2.4.4.1.6.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 |  | - | - | 0 | Admin | 0 | 32 | 32 | 45 | 28
1239 | 1.2.4.4.1.6.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1234,1235,1236 | 1240 | - | - | 0 | Joiner | 0 | 64 | 29 | 44 | 20
1240 | 1.2.4.4.1.6.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1239 | 1241 | - | - | 0 | Stone Mason | 0 | 80 | 30 | 97 | 41
1241 | 1.2.4.4.1.6.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1232,1240 | 1242,1243,1244,1245,1247,1249 | - | - | 0 | Plumber | 0 | 13 | 26 | 17 | 12
1242 | 1.2.4.4.1.6.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1246,1249 | - | - | 0 | Stone Mason | 0 | 61 | 13 | 19 | 21
1243 | 1.2.4.4.1.6.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Carpet | 0 | 61 | 27 | 11 | 9
1244 | 1.2.4.4.1.6.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1248,1249 | - | - | 0 | Waterproofer | 0 | 99 | 10 | 98 | 19
1245 | 1.2.4.4.1.6.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Plumber | 0 | 92 | 33 | 40 | 39
1246 | 1.2.4.4.1.6.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1242 | 1249 | - | - | 0 | Project Manager | 0 | 96 | 14 | 51 | 3
1247 | 1.2.4.4.1.6.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | - | - | 0 | Concretor | 0 | 99 | 18 | 83 | 2
1248 | 1.2.4.4.1.6.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1244 | 1249 | - | - | 0 | Cleaner | 0 | 17 | 28 | 20 | 42
1249 | 1.2.4.4.1.6.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1241,1242,1243,1244,1245,1246,1247,1248 | 1250 | - | - | 0 | Tiler | 0 | 41 | 35 | 90 | 19
1250 | 1.2.4.4.1.6.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1249 | 1251 | - | - | 0 | Hoarding | 0 | 86 | 27 | 25 | 50
1251 | 1.2.4.4.1.6.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1250 | 1252,1269,1286 | - | - | 0 | Surveyor | 0 | 84 | 20 | 84 | 8
1252 | 1.2.4.4.1.6.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1253 | - | - | 0 | Post Tension | 0 | 71 | 24 | 55 | 50
1253 | 1.2.4.4.1.6.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1252 | 1254 | - | - | 0 | Site Manager | 0 | 72 | 25 | 45 | 43
1254 | 1.2.4.4.1.6.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1253 | 1255 | - | - | 0 | Foreman | 0 | 72 | 28 | 94 | 59
1255 | 1.2.4.4.1.6.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1254 | 1256 | - | - | 0 | Joiner | 0 | 67 | 34 | 51 | 34
1256 | 1.2.4.4.1.6.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1255 | 1257,1258 | - | - | 0 | Contract Administrator | 0 | 42 | 34 | 97 | 6
1257 | 1.2.4.4.1.6.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1256 | 1261 | - | - | 0 | Joiner | 0 | 10 | 35 | 91 | 5
1258 | 1.2.4.4.1.6.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1256 | 1259 | - | - | 0 | Post Tension | 0 | 100 | 23 | 87 | 51
1259 | 1.2.4.4.1.6.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1258 | 1260 | - | - | 0 | Renderer | 0 | 16 | 16 | 70 | 21
1260 | 1.2.4.4.1.6.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1259 |  | - | - | 0 | Scaffolder | 0 | 42 | 23 | 62 | 57
1261 | 1.2.4.4.1.6.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1257 | 1262,1263,1264,1265,1266 | - | - | 0 | Joiner | 0 | 40 | 24 | 37 | 32
1262 | 1.2.4.4.1.6.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1261 |  | - | - | 0 | Line Market | 0 | 11 | 28 | 5 | 36
1263 | 1.2.4.4.1.6.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Tiler | 0 | 27 | 30 | 68 | 39
1264 | 1.2.4.4.1.6.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Post Tension | 0 | 74 | 11 | 22 | 48
1265 | 1.2.4.4.1.6.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Admin | 0 | 93 | 14 | 85 | 33
1266 | 1.2.4.4.1.6.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | - | - | 0 | Metal Work | 0 | 21 | 15 | 57 | 24
1267 | 1.2.4.4.1.6.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1317 | - | - | 0 | Post Tension | 0 | 68 | 32 | 77 | 19
1268 | 1.2.4.4.1.6.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | - | - | 0 | Renderer | 0 | 45 | 19 | 8 | 20
1269 | 1.2.4.4.1.6.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1270 | - | - | 0 | Excavation | 0 | 38 | 12 | 2 | 50
1270 | 1.2.4.4.1.6.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1269 | 1271 | - | - | 0 | Project Manager | 0 | 34 | 21 | 76 | 16
1271 | 1.2.4.4.1.6.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1270 | 1272 | - | - | 0 | Development Manager | 0 | 85 | 31 | 87 | 36
1272 | 1.2.4.4.1.6.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1271 | 1273 | - | - | 0 | Renderer | 0 | 14 | 19 | 70 | 30
1273 | 1.2.4.4.1.6.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1272 | 1274 | - | - | 0 | Foreman | 0 | 69 | 34 | 0 | 20
1274 | 1.2.4.4.1.6.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1273 | 1275 | - | - | 0 | Floor Sealer | 0 | 93 | 25 | 73 | 20
1275 | 1.2.4.4.1.6.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1274 | 1276 | - | - | 0 | Surveyor | 0 | 30 | 22 | 15 | 2
1276 | 1.2.4.4.1.6.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1275 | 1277 | - | - | 0 | Subcontractor | 0 | 39 | 32 | 46 | 4
1277 | 1.2.4.4.1.6.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1276 | 1278 | - | - | 0 | Line Market | 0 | 66 | 11 | 68 | 32
1278 | 1.2.4.4.1.6.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1277 | 1279 | - | - | 0 | Stone Mason | 0 | 12 | 20 | 100 | 15
1279 | 1.2.4.4.1.6.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1278 | 1280 | - | - | 0 | Carpet | 0 | 55 | 13 | 81 | 32
1280 | 1.2.4.4.1.6.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1279 | 1284,1281,1282,1283 | - | - | 0 | Admin | 0 | 63 | 29 | 91 | 5
1281 | 1.2.4.4.1.6.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Scaffolder | 0 | 80 | 35 | 40 | 44
1282 | 1.2.4.4.1.6.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Landscaper | 0 | 97 | 12 | 99 | 57
1283 | 1.2.4.4.1.6.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | - | - | 0 | Landscaper | 0 | 49 | 17 | 95 | 3
1284 | 1.2.4.4.1.6.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1280,1281,1282,1283 |  | - | - | 0 | Subcontractor | 0 | 42 | 33 | 15 | 7
1285 | 1.2.4.4.1.6.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | - | - | 0 | Metal Work | 0 | 80 | 18 | 2 | 60
1286 | 1.2.4.4.1.6.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1287 | - | - | 0 | Concretor | 0 | 59 | 15 | 35 | 50
1287 | 1.2.4.4.1.6.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1286 | 1288 | - | - | 0 | Timber Floorer | 0 | 37 | 28 | 2 | 20
1288 | 1.2.4.4.1.6.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1287 | 1289 | - | - | 0 | Waterproofer | 0 | 67 | 32 | 72 | 29
1289 | 1.2.4.4.1.6.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1288 | 1290 | - | - | 0 | Head Contractor | 0 | 44 | 12 | 20 | 28
1290 | 1.2.4.4.1.6.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1289 | 1291 | - | - | 0 | Landscaper | 0 | 64 | 20 | 6 | 14
1291 | 1.2.4.4.1.6.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1290 | 1292 | - | - | 0 | Development Manager | 0 | 87 | 32 | 87 | 33
1292 | 1.2.4.4.1.6.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1291 | 1293 | - | - | 0 | Metal Work | 0 | 49 | 18 | 98 | 43
1293 | 1.2.4.4.1.6.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1292 | 1294,1295,1296,1297 | - | - | 0 | Stone Mason | 0 | 64 | 12 | 32 | 49
1294 | 1.2.4.4.1.6.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Plasterboarder | 0 | 81 | 14 | 50 | 18
1295 | 1.2.4.4.1.6.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Post Tension | 0 | 89 | 30 | 46 | 11
1296 | 1.2.4.4.1.6.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Scaffolder | 0 | 34 | 33 | 89 | 12
1297 | 1.2.4.4.1.6.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | - | - | 0 | Contract Administrator | 0 | 84 | 35 | 28 | 46
1298 | 1.2.4.4.1.6.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1294,1295,1296,1297 |  | - | - | 0 | Renderer | 0 | 14 | 35 | 10 | 22
1299 | 1.2.4.4.1.6.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | - | - | 0 | Formworker | 0 | 50 | 24 | 38 | 54
1300 | 1.2.4.4.1.6.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1228 | 1301 | - | - | 0 | Landscaper | 0 | 47 | 27 | 31 | 29
1301 | 1.2.4.4.1.6.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1300 |  | - | - | 0 | Concretor | 0 | 61 | 33 | 36 | 31
1302 | 1.2.4.4.1.6.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1237 | 1305 | - | - | 0 | Formworker | 0 | 64 | 17 | 71 | 13
1303 | 1.2.4.4.1.6.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1236 | 1305 | - | - | 0 | Waterproofer | 0 | 78 | 17 | 90 | 44
1304 | 1.2.4.4.1.6.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1233 | 1305 | - | - | 0 | Painter | 0 | 75 | 20 | 10 | 6
1305 | 1.2.4.4.1.6.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1302,1303,1304 | 1306 | - | - | 0 | Carpenter | 0 | 50 | 27 | 95 | 27
1306 | 1.2.4.4.1.6.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1305 | 1307 | - | - | 0 | Post Tension | 0 | 19 | 22 | 85 | 3
1307 | 1.2.4.4.1.6.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1306 | 1308 | - | - | 0 | Concretor | 0 | 94 | 28 | 17 | 46
1308 | 1.2.4.4.1.6.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1307 | 1309 | - | - | 0 | Mechanical | 0 | 26 | 34 | 54 | 28
1309 | 1.2.4.4.1.6.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1308 | 1310 | - | - | 0 | Development Manager | 0 | 45 | 21 | 46 | 60
1310 | 1.2.4.4.1.6.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1309 | 1311 | - | - | 0 | Hoarding | 0 | 56 | 25 | 19 | 7
1311 | 1.2.4.4.1.6.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1310 | 1312 | - | - | 0 | Subcontractor | 0 | 88 | 23 | 3 | 50
1312 | 1.2.4.4.1.6.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1311 | 1313,1314,1315,1316 | - | - | 0 | Plasterboarder | 0 | 37 | 32 | 12 | 57
1313 | 1.2.4.4.1.6.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Plumber | 0 | 38 | 11 | 76 | 44
1314 | 1.2.4.4.1.6.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Mechanical | 0 | 28 | 13 | 26 | 23
1315 | 1.2.4.4.1.6.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Electrician | 0 | 21 | 22 | 15 | 42
1316 | 1.2.4.4.1.6.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | - | - | 0 | Plumber | 0 | 34 | 14 | 12 | 38
1317 | 1.2.4.4.1.6.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1263,1264,1265,1266,1267 | 1318 | - | - | 0 | Timber Floorer | 0 | 89 | 27 | 100 | 53
1318 | 1.2.4.4.1.6.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1317 | 1319 | - | - | 0 | Excavation | 0 | 53 | 11 | 26 | 51
1319 | 1.2.4.4.1.6.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1318 | 1320 | - | - | 0 | Project Manager | 0 | 46 | 29 | 2 | 59
1320 | 1.2.4.4.1.6.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1319 |  | - | - | 0 | Reinforcement Fixer | 0 | 99 | 35 | 4 | 22
1321 | 1.2.4.4.1.7 | Apartment B016 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Floor Sealer | 0 | 37 | 17 | 59 | 20
1322 | 1.2.4.4.1.7.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1323,1326,1327,1394 | - | - | 0 | Window | 0 | 98 | 14 | 12 | 35
1323 | 1.2.4.4.1.7.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1322 | 1325,1324 | - | - | 0 | Electrician | 0 | 74 | 11 | 78 | 22
1324 | 1.2.4.4.1.7.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1323 |  | - | - | 0 | Subcontractor | 0 | 73 | 35 | 87 | 22
1325 | 1.2.4.4.1.7.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1323 | 1328 | - | - | 0 | Mechanical | 0 | 10 | 12 | 56 | 31
1326 | 1.2.4.4.1.7.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1335 | - | - | 0 | Scaffolder | 0 | 82 | 17 | 39 | 56
1327 | 1.2.4.4.1.7.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1398 | - | - | 0 | Tiler | 0 | 54 | 11 | 91 | 19
1328 | 1.2.4.4.1.7.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1325 | 1329,1330,1331,1332,1333 | - | - | 0 | Post Tension | 0 | 95 | 31 | 11 | 28
1329 | 1.2.4.4.1.7.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333 | - | - | 0 | Timber Floorer | 0 | 40 | 11 | 11 | 48
1330 | 1.2.4.4.1.7.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333,1397 | - | - | 0 | Joiner | 0 | 28 | 21 | 28 | 30
1331 | 1.2.4.4.1.7.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1396 | - | - | 0 | Excavation | 0 | 55 | 16 | 45 | 21
1332 | 1.2.4.4.1.7.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 |  | - | - | 0 | Line Market | 0 | 51 | 20 | 49 | 12
1333 | 1.2.4.4.1.7.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1328,1329,1330 | 1334 | - | - | 0 | Metal Work | 0 | 20 | 10 | 100 | 14
1334 | 1.2.4.4.1.7.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1333 | 1335 | - | - | 0 | Hoarding | 0 | 81 | 16 | 18 | 30
1335 | 1.2.4.4.1.7.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1326,1334 | 1336,1337,1338,1339,1341,1343 | - | - | 0 | Carpet | 0 | 75 | 23 | 69 | 7
1336 | 1.2.4.4.1.7.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1340,1343 | - | - | 0 | Subcontractor | 0 | 32 | 27 | 3 | 10
1337 | 1.2.4.4.1.7.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Subcontractor | 0 | 100 | 27 | 47 | 2
1338 | 1.2.4.4.1.7.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1342,1343 | - | - | 0 | Hoarding | 0 | 59 | 13 | 97 | 4
1339 | 1.2.4.4.1.7.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Excavation | 0 | 43 | 24 | 53 | 24
1340 | 1.2.4.4.1.7.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1336 | 1343 | - | - | 0 | Tiler | 0 | 77 | 33 | 22 | 51
1341 | 1.2.4.4.1.7.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | - | - | 0 | Post Tension | 0 | 97 | 35 | 87 | 6
1342 | 1.2.4.4.1.7.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1338 | 1343 | - | - | 0 | Formworker | 0 | 90 | 10 | 46 | 36
1343 | 1.2.4.4.1.7.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1335,1336,1337,1338,1339,1340,1341,1342 | 1344 | - | - | 0 | Site Manager | 0 | 32 | 16 | 21 | 6
1344 | 1.2.4.4.1.7.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1343 | 1345 | - | - | 0 | Site Manager | 0 | 84 | 20 | 3 | 15
1345 | 1.2.4.4.1.7.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1344 | 1346,1363,1380 | - | - | 0 | Mechanical | 0 | 36 | 32 | 54 | 19
1346 | 1.2.4.4.1.7.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1347 | - | - | 0 | Reinforcement Fixer | 0 | 50 | 35 | 77 | 54
1347 | 1.2.4.4.1.7.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1346 | 1348 | - | - | 0 | Window | 0 | 18 | 13 | 52 | 27
1348 | 1.2.4.4.1.7.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1347 | 1349 | - | - | 0 | Hoarding | 0 | 51 | 28 | 12 | 15
1349 | 1.2.4.4.1.7.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1348 | 1350 | - | - | 0 | Joiner | 0 | 40 | 19 | 90 | 32
1350 | 1.2.4.4.1.7.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1349 | 1351,1352 | - | - | 0 | Excavation | 0 | 38 | 23 | 47 | 31
1351 | 1.2.4.4.1.7.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1350 | 1355 | - | - | 0 | Contract Administrator | 0 | 74 | 15 | 49 | 13
1352 | 1.2.4.4.1.7.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1350 | 1353 | - | - | 0 | Foreman | 0 | 67 | 28 | 19 | 23
1353 | 1.2.4.4.1.7.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1352 | 1354 | - | - | 0 | Site Manager | 0 | 45 | 18 | 0 | 5
1354 | 1.2.4.4.1.7.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1353 |  | - | - | 0 | Plasterboarder | 0 | 29 | 19 | 40 | 51
1355 | 1.2.4.4.1.7.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1351 | 1356,1357,1358,1359,1360 | - | - | 0 | Painter | 0 | 91 | 22 | 70 | 41
1356 | 1.2.4.4.1.7.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1355 |  | - | - | 0 | Landscaper | 0 | 79 | 27 | 25 | 9
1357 | 1.2.4.4.1.7.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Tiler | 0 | 76 | 17 | 78 | 5
1358 | 1.2.4.4.1.7.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Electrician | 0 | 18 | 31 | 99 | 27
1359 | 1.2.4.4.1.7.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Contract Administrator | 0 | 20 | 11 | 66 | 27
1360 | 1.2.4.4.1.7.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | - | - | 0 | Joiner | 0 | 88 | 15 | 36 | 26
1361 | 1.2.4.4.1.7.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1411 | - | - | 0 | Foreman | 0 | 54 | 20 | 41 | 25
1362 | 1.2.4.4.1.7.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 55 | 27 | 89 | 36
1363 | 1.2.4.4.1.7.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1364 | - | - | 0 | Joiner | 0 | 64 | 28 | 59 | 43
1364 | 1.2.4.4.1.7.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1363 | 1365 | - | - | 0 | Project Manager | 0 | 82 | 34 | 43 | 36
1365 | 1.2.4.4.1.7.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1364 | 1366 | - | - | 0 | Landscaper | 0 | 70 | 24 | 29 | 19
1366 | 1.2.4.4.1.7.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1365 | 1367 | - | - | 0 | Hoarding | 0 | 67 | 23 | 43 | 58
1367 | 1.2.4.4.1.7.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1366 | 1368 | - | - | 0 | Contract Administrator | 0 | 31 | 16 | 14 | 43
1368 | 1.2.4.4.1.7.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1367 | 1369 | - | - | 0 | Line Market | 0 | 44 | 12 | 69 | 33
1369 | 1.2.4.4.1.7.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1368 | 1370 | - | - | 0 | Hoarding | 0 | 59 | 21 | 10 | 53
1370 | 1.2.4.4.1.7.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1369 | 1371 | - | - | 0 | Hoarding | 0 | 90 | 29 | 79 | 35
1371 | 1.2.4.4.1.7.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1370 | 1372 | - | - | 0 | Tiler | 0 | 59 | 14 | 62 | 16
1372 | 1.2.4.4.1.7.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1371 | 1373 | - | - | 0 | Line Market | 0 | 86 | 27 | 86 | 13
1373 | 1.2.4.4.1.7.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1372 | 1374 | - | - | 0 | Electrician | 0 | 66 | 35 | 1 | 23
1374 | 1.2.4.4.1.7.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1373 | 1378,1375,1376,1377 | - | - | 0 | Development Manager | 0 | 96 | 30 | 78 | 52
1375 | 1.2.4.4.1.7.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Project Manager | 0 | 90 | 34 | 51 | 14
1376 | 1.2.4.4.1.7.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Site Manager | 0 | 46 | 21 | 6 | 46
1377 | 1.2.4.4.1.7.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | - | - | 0 | Joiner | 0 | 31 | 22 | 59 | 40
1378 | 1.2.4.4.1.7.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1374,1375,1376,1377 |  | - | - | 0 | Admin | 0 | 27 | 33 | 39 | 37
1379 | 1.2.4.4.1.7.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Electrician | 0 | 20 | 13 | 51 | 37
1380 | 1.2.4.4.1.7.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1381 | - | - | 0 | Subcontractor | 0 | 78 | 34 | 19 | 3
1381 | 1.2.4.4.1.7.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1380 | 1382 | - | - | 0 | Painter | 0 | 52 | 34 | 97 | 2
1382 | 1.2.4.4.1.7.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1381 | 1383 | - | - | 0 | Metal Work | 0 | 24 | 28 | 62 | 59
1383 | 1.2.4.4.1.7.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1382 | 1384 | - | - | 0 | Post Tension | 0 | 26 | 29 | 14 | 11
1384 | 1.2.4.4.1.7.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1383 | 1385 | - | - | 0 | Landscaper | 0 | 98 | 35 | 58 | 39
1385 | 1.2.4.4.1.7.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1384 | 1386 | - | - | 0 | Electrician | 0 | 78 | 14 | 55 | 39
1386 | 1.2.4.4.1.7.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1385 | 1387 | - | - | 0 | Scaffolder | 0 | 69 | 34 | 66 | 27
1387 | 1.2.4.4.1.7.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1386 | 1388,1389,1390,1391 | - | - | 0 | Floor Sealer | 0 | 89 | 34 | 62 | 42
1388 | 1.2.4.4.1.7.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Head Contractor | 0 | 56 | 21 | 28 | 35
1389 | 1.2.4.4.1.7.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Carpet | 0 | 60 | 28 | 4 | 21
1390 | 1.2.4.4.1.7.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Scaffolder | 0 | 25 | 30 | 45 | 30
1391 | 1.2.4.4.1.7.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | - | - | 0 | Carpet | 0 | 22 | 18 | 22 | 39
1392 | 1.2.4.4.1.7.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1388,1389,1390,1391 |  | - | - | 0 | Tiler | 0 | 68 | 18 | 100 | 57
1393 | 1.2.4.4.1.7.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | - | - | 0 | Excavation | 0 | 53 | 22 | 49 | 2
1394 | 1.2.4.4.1.7.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1322 | 1395 | - | - | 0 | Scaffolder | 0 | 62 | 30 | 48 | 8
1395 | 1.2.4.4.1.7.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1394 |  | - | - | 0 | Tiler | 0 | 29 | 15 | 35 | 4
1396 | 1.2.4.4.1.7.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1331 | 1399 | - | - | 0 | Surveyor | 0 | 74 | 35 | 19 | 48
1397 | 1.2.4.4.1.7.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1330 | 1399 | - | - | 0 | Plasterboarder | 0 | 17 | 15 | 40 | 57
1398 | 1.2.4.4.1.7.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1327 | 1399 | - | - | 0 | Line Market | 0 | 81 | 21 | 84 | 42
1399 | 1.2.4.4.1.7.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1396,1397,1398 | 1400 | - | - | 0 | Hoarding | 0 | 37 | 21 | 90 | 53
1400 | 1.2.4.4.1.7.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1399 | 1401 | - | - | 0 | Contract Administrator | 0 | 66 | 35 | 53 | 39
1401 | 1.2.4.4.1.7.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1400 | 1402 | - | - | 0 | Project Manager | 0 | 23 | 13 | 43 | 50
1402 | 1.2.4.4.1.7.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1401 | 1403 | - | - | 0 | Waterproofer | 0 | 76 | 19 | 57 | 26
1403 | 1.2.4.4.1.7.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1402 | 1404 | - | - | 0 | Line Market | 0 | 83 | 19 | 41 | 22
1404 | 1.2.4.4.1.7.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1403 | 1405 | - | - | 0 | Tiler | 0 | 47 | 29 | 37 | 7
1405 | 1.2.4.4.1.7.41.12 | Grout | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1404 | 1406 | - | - | 0 | Cleaner | 0 | 11 | 21 | 26 | 44
1406 | 1.2.4.4.1.7.41.13 | Paint/Cladding | 3 | 14 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1405 | 1407,1408,1409,1410 | - | - | 0 | Landscaper | 0 | 44 | 35 | 49 | 58
1407 | 1.2.4.4.1.7.41.14 | Silicone | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Reinforcement Fixer | 0 | 51 | 26 | 75 | 24
1408 | 1.2.4.4.1.7.41.15 | Hydraulic Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Subcontractor | 0 | 17 | 30 | 14 | 22
1409 | 1.2.4.4.1.7.41.16 | Electrical Fit Off | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Development Manager | 0 | 83 | 30 | 51 | 15
1410 | 1.2.4.4.1.7.41.17 | Fit Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | - | - | 0 | Waterproofer | 0 | 83 | 16 | 100 | 22
1411 | 1.2.4.4.1.7.42 | Carpet Install | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1357,1358,1359,1360,1361 | 1412 | - | - | 0 | Admin | 0 | 100 | 26 | 97 | 41
1412 | 1.2.4.4.1.7.43 | Paint (FINAL Coat) | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1411 | 1413 | - | - | 0 | Carpenter | 0 | 75 | 26 | 74 | 7
1413 | 1.2.4.4.1.7.44 | FINAL CLEAN | 1 | 11 December 2024 8:00 AM | 11 December 2024 5:00 PM | 1412 | 1414 | - | - | 0 | Site Manager | 0 | 51 | 18 | 17 | 46
1414 | 1.2.4.4.1.7.45 | UNIT LOCKED | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 1413 |  | - | - | 0 | Subcontractor | 0 | 64 | 14 | 63 | 54
1415 | 1.2.4.4.1.8 | Apartment B017 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | - | - | 0 | Post Tension | 0 | 12 | 30 | 70 | 37
1416 | 1.2.4.4.1.8.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1417,1420,1421,1488 | - | - | 0 | Surveyor | 0 | 46 | 20 | 32 | 26
1417 | 1.2.4.4.1.8.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1416 | 1419,1418 | - | - | 0 | Waterproofer | 0 | 95 | 18 | 10 | 50
1418 | 1.2.4.4.1.8.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1417 |  | - | - | 0 | Tiler | 0 | 49 | 19 | 91 | 39
1419 | 1.2.4.4.1.8.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1417 | 1422 | - | - | 0 | Cleaner | 0 | 24 | 34 | 87 | 38
1420 | 1.2.4.4.1.8.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1429 | - | - | 0 | Site Manager | 0 | 76 | 29 | 83 | 39
1421 | 1.2.4.4.1.8.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1492 | - | - | 0 | Formworker | 0 | 44 | 27 | 13 | 32
1422 | 1.2.4.4.1.8.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1419 | 1423,1424,1425,1426,1427 | - | - | 0 | Formworker | 0 | 62 | 11 | 56 | 34
1423 | 1.2.4.4.1.8.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427 | - | - | 0 | Formworker | 0 | 27 | 26 | 33 | 18
1424 | 1.2.4.4.1.8.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427,1491 | - | - | 0 | Post Tension | 0 | 21 | 15 | 52 | 22
1425 | 1.2.4.4.1.8.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1490 | - | - | 0 | Fire | 0 | 21 | 35 | 89 | 30
1426 | 1.2.4.4.1.8.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 |  | - | - | 0 | Carpet | 0 | 36 | 35 | 11 | 54
1427 | 1.2.4.4.1.8.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1422,1423,1424 | 1428 | - | - | 0 | Formworker | 0 | 64 | 24 | 29 | 8
1428 | 1.2.4.4.1.8.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1427 | 1429 | - | - | 0 | Plasterboarder | 0 | 76 | 14 | 55 | 15
1429 | 1.2.4.4.1.8.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1420,1428 | 1430,1431,1432,1433,1435,1437 | - | - | 0 | Metal Work | 0 | 11 | 27 | 91 | 45
1430 | 1.2.4.4.1.8.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1434,1437 | - | - | 0 | Hoarding | 0 | 50 | 33 | 56 | 40
1431 | 1.2.4.4.1.8.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Carpet | 0 | 33 | 34 | 29 | 31
1432 | 1.2.4.4.1.8.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1436,1437 | - | - | 0 | Stone Mason | 0 | 73 | 31 | 54 | 19
1433 | 1.2.4.4.1.8.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Renderer | 0 | 95 | 19 | 48 | 8
1434 | 1.2.4.4.1.8.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1430 | 1437 | - | - | 0 | Foreman | 0 | 28 | 24 | 43 | 50
1435 | 1.2.4.4.1.8.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | - | - | 0 | Tiler | 0 | 39 | 30 | 8 | 8
1436 | 1.2.4.4.1.8.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1432 | 1437 | - | - | 0 | Timber Floorer | 0 | 80 | 25 | 83 | 58
1437 | 1.2.4.4.1.8.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1429,1430,1431,1432,1433,1434,1435,1436 | 1438 | - | - | 0 | Mechanical | 0 | 64 | 21 | 98 | 23
1438 | 1.2.4.4.1.8.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1437 | 1439 | - | - | 0 | Stone Mason | 0 | 83 | 28 | 42 | 4
1439 | 1.2.4.4.1.8.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1438 | 1440,1457,1474 | - | - | 0 | Foreman | 0 | 42 | 32 | 97 | 37
1440 | 1.2.4.4.1.8.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1441 | - | - | 0 | Contract Administrator | 0 | 56 | 25 | 62 | 31
1441 | 1.2.4.4.1.8.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1440 | 1442 | - | - | 0 | Carpet | 0 | 43 | 30 | 66 | 57
1442 | 1.2.4.4.1.8.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1441 | 1443 | - | - | 0 | Floor Sealer | 0 | 11 | 17 | 80 | 17
1443 | 1.2.4.4.1.8.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1442 | 1444 | - | - | 0 | Reinforcement Fixer | 0 | 39 | 25 | 10 | 58
1444 | 1.2.4.4.1.8.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1443 | 1445,1446 | - | - | 0 | Line Market | 0 | 47 | 26 | 15 | 35
1445 | 1.2.4.4.1.8.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1444 | 1449 | - | - | 0 | Hoarding | 0 | 95 | 31 | 28 | 17
1446 | 1.2.4.4.1.8.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1444 | 1447 | - | - | 0 | Development Manager | 0 | 80 | 16 | 18 | 5
1447 | 1.2.4.4.1.8.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1446 | 1448 | - | - | 0 | Head Contractor | 0 | 45 | 30 | 41 | 56
1448 | 1.2.4.4.1.8.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1447 |  | - | - | 0 | Renderer | 0 | 15 | 18 | 80 | 50
1449 | 1.2.4.4.1.8.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1445 | 1450,1451,1452,1453,1454 | - | - | 0 | Surveyor | 0 | 91 | 28 | 80 | 51
1450 | 1.2.4.4.1.8.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1449 |  | - | - | 0 | Cleaner | 0 | 24 | 27 | 94 | 15
1451 | 1.2.4.4.1.8.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Floor Sealer | 0 | 15 | 18 | 98 | 11
1452 | 1.2.4.4.1.8.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Subcontractor | 0 | 62 | 20 | 89 | 45
1453 | 1.2.4.4.1.8.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Renderer | 0 | 54 | 33 | 34 | 36
1454 | 1.2.4.4.1.8.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | - | - | 0 | Cleaner | 0 | 92 | 22 | 79 | 19
1455 | 1.2.4.4.1.8.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1505 | - | - | 0 | Mechanical | 0 | 97 | 15 | 23 | 48
1456 | 1.2.4.4.1.8.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | - | - | 0 | Carpet | 0 | 70 | 26 | 87 | 54
1457 | 1.2.4.4.1.8.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1458 | - | - | 0 | Mechanical | 0 | 36 | 27 | 5 | 34
1458 | 1.2.4.4.1.8.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1457 | 1459 | - | - | 0 | Foreman | 0 | 15 | 33 | 9 | 8
1459 | 1.2.4.4.1.8.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1458 | 1460 | - | - | 0 | Waterproofer | 0 | 34 | 17 | 34 | 32
1460 | 1.2.4.4.1.8.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1459 | 1461 | - | - | 0 | Project Manager | 0 | 86 | 31 | 34 | 21
1461 | 1.2.4.4.1.8.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1460 | 1462 | - | - | 0 | Carpet | 0 | 11 | 18 | 71 | 39
1462 | 1.2.4.4.1.8.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1461 | 1463 | - | - | 0 | Admin | 0 | 87 | 10 | 72 | 34
1463 | 1.2.4.4.1.8.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1462 | 1464 | - | - | 0 | Scaffolder | 0 | 36 | 23 | 54 | 24
1464 | 1.2.4.4.1.8.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1463 | 1465 | - | - | 0 | Joiner | 0 | 11 | 32 | 15 | 49
1465 | 1.2.4.4.1.8.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1464 | 1466 | - | - | 0 | Painter | 0 | 98 | 24 | 73 | 27
1466 | 1.2.4.4.1.8.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1465 | 1467 | - | - | 0 | Foreman | 0 | 13 | 18 | 12 | 35
1467 | 1.2.4.4.1.8.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1466 | 1468 | - | - | 0 | Plasterboarder | 0 | 54 | 13 | 69 | 17
1468 | 1.2.4.4.1.8.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1467 | 1472,1469,1470,1471 | - | - | 0 | Plasterboarder | 0 | 71 | 19 | 11 | 33
1469 | 1.2.4.4.1.8.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Window | 0 | 15 | 30 | 98 | 49
1470 | 1.2.4.4.1.8.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Electrician | 0 | 10 | 15 | 69 | 48
1471 | 1.2.4.4.1.8.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | - | - | 0 | Reinforcement Fixer | 0 | 41 | 11 | 54 | 54
1472 | 1.2.4.4.1.8.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1468,1469,1470,1471 |  | - | - | 0 | Carpenter | 0 | 72 | 17 | 87 | 41
1473 | 1.2.4.4.1.8.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | - | - | 0 | Project Manager | 0 | 92 | 24 | 69 | 59
1474 | 1.2.4.4.1.8.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1475 | - | - | 0 | Metal Work | 0 | 61 | 23 | 53 | 9
1475 | 1.2.4.4.1.8.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1474 | 1476 | - | - | 0 | Formworker | 0 | 12 | 25 | 65 | 34
1476 | 1.2.4.4.1.8.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1475 | 1477 | - | - | 0 | Landscaper | 0 | 59 | 33 | 26 | 23
1477 | 1.2.4.4.1.8.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1476 | 1478 | - | - | 0 | Fire | 0 | 64 | 31 | 27 | 12
1478 | 1.2.4.4.1.8.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1477 | 1479 | - | - | 0 | Head Contractor | 0 | 42 | 33 | 82 | 56
1479 | 1.2.4.4.1.8.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1478 | 1480 | - | - | 0 | Contract Administrator | 0 | 66 | 28 | 67 | 51
1480 | 1.2.4.4.1.8.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1479 | 1481 | - | - | 0 | Project Manager | 0 | 52 | 12 | 49 | 16
1481 | 1.2.4.4.1.8.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1480 | 1482,1483,1484,1485 | - | - | 0 | Window | 0 | 41 | 33 | 15 | 7
1482 | 1.2.4.4.1.8.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Timber Floorer | 0 | 20 | 27 | 10 | 8
1483 | 1.2.4.4.1.8.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Renderer | 0 | 81 | 14 | 37 | 6
1484 | 1.2.4.4.1.8.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Painter | 0 | 16 | 30 | 64 | 37
1485 | 1.2.4.4.1.8.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | - | - | 0 | Plasterboarder | 0 | 59 | 29 | 91 | 10
1486 | 1.2.4.4.1.8.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1482,1483,1484,1485 |  | - | - | 0 | Project Manager | 0 | 62 | 33 | 86 | 23
1487 | 1.2.4.4.1.8.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | - | - | 0 | Head Contractor | 0 | 48 | 26 | 37 | 20
1488 | 1.2.4.4.1.8.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1416 | 1489 | - | - | 0 | Floor Sealer | 0 | 51 | 16 | 32 | 56
1489 | 1.2.4.4.1.8.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1488 |  | - | - | 0 | Joiner | 0 | 50 | 21 | 65 | 53
1490 | 1.2.4.4.1.8.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1425 | 1493 | - | - | 0 | Admin | 0 | 24 | 26 | 85 | 48
1491 | 1.2.4.4.1.8.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1424 | 1493 | - | - | 0 | Line Market | 0 | 79 | 11 | 90 | 30
1492 | 1.2.4.4.1.8.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1421 | 1493 | - | - | 0 | Scaffolder | 0 | 31 | 12 | 80 | 59
1493 | 1.2.4.4.1.8.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1490,1491,1492 | 1494 | - | - | 0 | Surveyor | 0 | 63 | 24 | 38 | 55
1494 | 1.2.4.4.1.8.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1493 | 1495 | - | - | 0 | Concretor | 0 | 73 | 22 | 82 | 44
1495 | 1.2.4.4.1.8.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1494 | 1496 | - | - | 0 | Waterproofer | 0 | 99 | 25 | 9 | 24
1496 | 1.2.4.4.1.8.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1495 | 1497 | - | - | 0 | Development Manager | 0 | 13 | 35 | 65 | 56
1497 | 1.2.4.4.1.8.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1496 | 1498 | - | - | 0 | Scaffolder | 0 | 28 | 19 | 44 | 15
1498 | 1.2.4.4.1.8.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1497 | 1499 | - | - | 0 | Surveyor | 0 | 86 | 31 | 94 | 60

## Progress 100%
ID | Outline_Number | Name | Duration | Start_Date | Finish_Date | Predecessors | Successors | Actual_Start | Actual_End | Delay | Trade | Progress | Worker_Score | Temp | Rain_Probability | Wind_Speed
2 | 1.1 | MILESTONES / KEY DATES | 633 | 17 April 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 17 April 2023 7:00 AM | - | 869 |  | 100 | - | - | - | -
3 | 1.1.1 | Site Establishment | 0 | 5 June 2023 7:00 AM | 5 June 2023 7:00 AM |  | 25SS | 5 June 2023 7:00 AM | 2023-06-05 07:00 | 0 | Plasterboarder | 100 | 33 | 30 | 69 | 19
4 | 1.1.2 | Basement Completed (B2) | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 88 |  | 2 May 2024 5:00 PM | 2024-05-02 17:00 | 0 | Timber Floorer | 100 | 93 | 24 | 2 | 16
5 | 1.1.3 | Building A Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 444,753,746,714 | 3466,9 | 5 May 2025 5:00 PM | 2025-05-05 17:00 | 0 | Floor Sealer | 100 | 72 | 30 | 36 | 57
6 | 1.1.4 | Building B Complete | 0 | 29 March 2025 5:00 PM | 29 March 2025 5:00 PM | 228,482,306,1737 | 3466,9 | 29 March 2025 5:00 PM | 2025-03-29 17:00 | 0 | Scaffolder | 100 | 89 | 22 | 78 | 33
7 | 1.1.5 | Building C Complete | 0 | 16 April 2025 5:00 PM | 16 April 2025 5:00 PM | 306,360,503,3169 | 3466,9 | 16 April 2025 5:00 PM | 2025-04-16 17:00 | 0 | Painter | 100 | 19 | 14 | 44 | 60
8 | 1.1.6 | Building D Complete | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 360,396,519,3439 | 3466,9 | 17 April 2025 5:00 PM | 2025-04-17 17:00 | 0 | Post Tension | 100 | 72 | 18 | 31 | 43
9 | 1.1.7 | Practical Completion (Net) | 0 | 28 May 2025 5:00 PM | 28 May 2025 5:00 PM | 3465,3440,5,3460,6,7,8 |  | 28 May 2025 5:00 PM | 2025-05-28 17:00 | 0 | Admin | 100 | 56 | 30 | 35 | 39
10 | 1.1.8 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | 28 July 2023 8:00 AM | 2023-08-15 17:00 | 0 | Plasterboarder | 100 | 34 | 14 | 40 | 35
11 | 1.1.9 | Inclement Weatherallowed (Spent) | 19 | 29 May 2025 8:00 AM | 21 June 2025 5:00 PM | 3466 | 12 | 29 May 2025 8:00 AM | 2025-06-23 17:00 | 2 | Subcontractor | 100 | 15 | 12 | 75 | 32
12 | 1.1.10 | Inclement Weatherallowed (Remaining) | 1 | 23 June 2025 8:00 AM | 23 June 2025 5:00 PM | 11 | 3469 | 23 June 2025 8:00 AM | 2025-06-23 17:00 | 0 | Painter | 100 | 50 | 33 | 73 | 35
13 | 1.1.11 | Practical Completion (Gross) - Building Handover | 0 | 23 June 2025 5:00 PM | 23 June 2025 5:00 PM | 3469 |  | 23 June 2025 5:00 PM | 2025-06-23 17:00 | 0 | Contract Administrator | 100 | 88 | 22 | 67 | 45
14 | 1.1.12 | PRE CONSTRUCTION WORKS | 210.13 | 17 April 2023 7:00 AM | 16 January 2024 5:00 PM |  |  | 17 April 2023 7:00 AM | 2024-01-16 17:00 | 0 | Stone Mason | 100 | 70 | 22 | 98 | 35
15 | 1.1.12.1 | Authority Approvals, (Access Deeds by Client etc (Ultra to assist in coordination) These are qualifying causes of delay resulting in EOT time & costs) | 372 | 17 April 2023 7:00 AM | 1 August 2024 5:00 PM |  |  | 17 April 2023 7:00 AM | 2024-08-04 17:00 | 3 | Scaffolder | 100 | 19 | 24 | 60 | 26
16 | 1.1.12.1.1 | Section 73 - BPA Design & Stormwater Works | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Mechanical | 100 | 85 | 35 | 39 | 22
17 | 1.1.12.1.2 | Rail Approval | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Scaffolder | 100 | 63 | 17 | 5 | 5
18 | 1.1.12.1.3 | CC1 - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  | 25,19 | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Electrician | 100 | 93 | 19 | 7 | 35
19 | 1.1.12.1.4 | CC1a - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM | 18 | 25,20 | 17 April 2023 7:00 AM | 2023-04-17 07:00 | 0 | Post Tension | 100 | 60 | 35 | 80 | 46
20 | 1.1.12.1.5 | CC2 - Structure (SoG - Podium) | 120 | 17 April 2023 8:00 AM | 12 September 2023 5:00 PM | 19 | 21 | 17 April 2023 8:00 AM | 2023-09-13 17:00 | 1 | Floor Sealer | 100 | 75 | 15 | 51 | 10
21 | 1.1.12.1.6 | CC3 - Structure (Podium - Roof) + Facade | 156 | 13 September 2023 8:00 AM | 8 April 2024 5:00 PM | 20 | 22 | 13 September 2023 8:00 AM | 2024-04-13 17:00 | 5 | Window | 100 | 13 | 24 | 47 | 16
22 | 1.1.12.1.7 | CC4 - Services & Fit Out | 60 | 9 April 2024 8:00 AM | 20 June 2024 5:00 PM | 21 | 23 | 9 April 2024 8:00 AM | 2024-06-21 17:00 | 1 | Plumber | 100 | 71 | 25 | 85 | 39
23 | 1.1.12.1.8 | CC5 - External Works and Public Domain | 36 | 21 June 2024 8:00 AM | 1 August 2024 5:00 PM | 22 |  | 21 June 2024 8:00 AM | 2024-08-04 17:00 | 3 | Development Manager | 100 | 46 | 24 | 87 | 24
24 | 1.1.12.2 | SITE ESTABLISHMENT | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM |  |  | 26 June 2023 8:00 AM | 2023-06-30 17:00 | 0 | Head Contractor | 100 | 85 | 10 | 99 | 53
25 | 1.1.12.2.1 | Site Establishment, Enviro Protection, Survey Set out & Hoardings | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM | 18,3SS,19 | 28 | 26 June 2023 8:00 AM | 2023-06-30 17:00 | 0 | Painter | 100 | 22 | 30 | 48 | 39
26 | 1.2 | CONSTRUCTION WORKS | 571 | 3 July 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 3 July 2023 7:00 AM | 2025-06-24 17:00 | 1 | Mechanical | 100 | 65 | 11 | 2 | 33
27 | 1.2.1 | EARTHWORKS, PILING - BASEMENT | 234 | 3 July 2023 7:00 AM | 2 May 2024 5:00 PM |  |  | 3 July 2023 7:00 AM | 2024-05-06 17:00 | 4 | Contract Administrator | 100 | 25 | 23 | 51 | 8
28 | 1.2.1.1 | Demolition, Clear & Cut/Level Site | 6 | 3 July 2023 7:00 AM | 8 July 2023 5:00 PM | 25 | 10SS,29SS | 3 July 2023 7:00 AM | 2023-07-08 17:00 | 0 | Plasterboarder | 100 | 22 | 25 | 82 | 58
29 | 1.2.1.2 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | 28 July 2023 8:00 AM | 2023-08-15 17:00 | 0 | Head Contractor | 100 | 26 | 29 | 29 | 19
30 | 1.2.1.3 | Install Piling Matt | 12 | 16 August 2023 8:00 AM | 30 August 2023 5:00 PM | 10,29 | 34FS-6d | 16 August 2023 8:00 AM | 2023-09-03 17:00 | 4 | Tiler | 100 | 11 | 21 | 74 | 41
31 | 1.2.1.4 | Crane Base Ex, Piles & FRP | 8 | 18 December 2023 8:00 AM | 5 January 2024 5:00 PM | 53 | 3442FS+8d | 18 December 2023 8:00 AM | 2024-01-08 17:00 | 3 | Cleaner | 100 | 44 | 29 | 28 | 18
32 | 1.2.1.5 | Piling and Capping Beam | 58 | 28 August 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | 28 August 2023 8:00 AM | 2023-11-13 17:00 | 4 | Concretor | 100 | 14 | 26 | 34 | 47
33 | 1.2.1.5.1 | Buildings A | 28 | 28 August 2023 8:00 AM | 3 October 2023 5:00 PM |  |  | 28 August 2023 8:00 AM | 2023-10-03 17:00 | 0 | Formworker | 100 | 45 | 22 | 36 | 9
34 | 1.2.1.5.1.1 | Perimeter Piling (75 Piles) | 16 | 28 August 2023 8:00 AM | 15 September 2023 5:00 PM | 30FS-6d | 35FS-6d,37,46 | 28 August 2023 8:00 AM | 2023-09-20 17:00 | 5 | Electrician | 100 | 54 | 20 | 97 | 34
35 | 1.2.1.5.1.2 | Capping Beam - Detailed Excavation & FRP | 18 | 9 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34FS-6d |  | 9 September 2023 8:00 AM | 2023-10-06 17:00 | 3 | Metal Work | 100 | 74 | 14 | 48 | 11
36 | 1.2.1.5.2 | Buildings B | 24 | 16 September 2023 8:00 AM | 17 October 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-10-21 17:00 | 4 | Renderer | 100 | 40 | 32 | 55 | 50
37 | 1.2.1.5.2.1 | Perimeter Piling (56 Piles) | 12 | 16 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34 | 38FS-6d,40 | 16 September 2023 8:00 AM | 2023-10-08 17:00 | 5 | Carpenter | 100 | 71 | 11 | 93 | 37
38 | 1.2.1.5.2.2 | Capping Beam - Detailed Excavation & FRP | 18 | 25 September 2023 8:00 AM | 17 October 2023 5:00 PM | 37FS-6d | 56 | 25 September 2023 8:00 AM | 2023-10-22 17:00 | 5 | Development Manager | 100 | 88 | 10 | 11 | 60
39 | 1.2.1.5.3 | Buildings C & D | 30 | 4 October 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | 4 October 2023 8:00 AM | 2023-11-09 17:00 | 0 | Foreman | 100 | 16 | 11 | 37 | 11
40 | 1.2.1.5.3.1 | Foundation Piling (Gnd Lvl) - (17 Piles) | 6 | 4 October 2023 8:00 AM | 10 October 2023 5:00 PM | 37 | 41 | 4 October 2023 8:00 AM | 2023-10-10 17:00 | 0 | Cleaner | 100 | 70 | 34 | 70 | 4
41 | 1.2.1.5.3.2 | Perimeter Piling (82 Piles) | 18 | 11 October 2023 8:00 AM | 1 November 2023 5:00 PM | 40 | 42FS-6d | 11 October 2023 8:00 AM | 2023-11-03 17:00 | 2 | Reinforcement Fixer | 100 | 79 | 19 | 79 | 48
42 | 1.2.1.5.3.3 | Capping Beam - Detailed Excavation & FRP | 12 | 26 October 2023 8:00 AM | 9 November 2023 5:00 PM | 41FS-6d | 66 | 26 October 2023 8:00 AM | 2023-11-10 17:00 | 1 | Excavation | 100 | 30 | 35 | 30 | 58
43 | 1.2.1.6 | Bulk Excavation & Shotcrete | 142 | 16 September 2023 8:00 AM | 22 March 2024 5:00 PM |  |  | 16 September 2023 8:00 AM | 2024-03-22 17:00 | 0 | Reinforcement Fixer | 100 | 32 | 10 | 20 | 3
44 | 1.2.1.6.1 | Building A | 70 | 16 September 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-12-16 17:00 | 0 | Carpet | 100 | 47 | 27 | 11 | 3
45 | 1.2.1.6.1.1 | Excavate - Gnd - B1 | 57 | 16 September 2023 8:00 AM | 28 November 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-11-28 17:00 | 0 | Hoarding | 100 | 31 | 18 | 47 | 57
46 | 1.2.1.6.1.1.1 | Excavation | 21 | 16 September 2023 8:00 AM | 13 October 2023 5:00 PM | 34 | 47,56,51,71 | 16 September 2023 8:00 AM | 2023-10-18 17:00 | 5 | Carpet | 100 | 94 | 28 | 49 | 30
47 | 1.2.1.6.1.1.2 | Installation of Anchors | 8 | 20 October 2023 8:00 AM | 30 October 2023 5:00 PM | 46 | 48,49SS+11d | 20 October 2023 8:00 AM | 2023-11-01 17:00 | 2 | Plumber | 100 | 37 | 26 | 54 | 53
48 | 1.2.1.6.1.1.3 | Install Bracing | 4 | 31 October 2023 8:00 AM | 3 November 2023 5:00 PM | 47 |  | 31 October 2023 8:00 AM | 2023-11-03 17:00 | 0 | Project Manager | 100 | 95 | 14 | 28 | 46
49 | 1.2.1.6.1.1.4 | Shotcrete | 20 | 3 November 2023 8:00 AM | 28 November 2023 5:00 PM | 47SS+11d |  | 3 November 2023 8:00 AM | 2023-11-28 17:00 | 0 | Painter | 100 | 29 | 12 | 72 | 3
50 | 1.2.1.6.1.2 | Excavate - B1-B2 | 44 | 20 October 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | 20 October 2023 8:00 AM | 2023-12-16 17:00 | 0 | Carpet | 100 | 28 | 16 | 21 | 7
51 | 1.2.1.6.1.2.1 | Excavation | 14 | 20 October 2023 8:00 AM | 7 November 2023 5:00 PM | 46 | 52,53,56,71 | 20 October 2023 8:00 AM | 2023-11-10 17:00 | 3 | Electrician | 100 | 77 | 15 | 71 | 59
52 | 1.2.1.6.1.2.2 | Shotcrete | 16 | 15 November 2023 8:00 AM | 7 December 2023 5:00 PM | 51 | 53 | 15 November 2023 8:00 AM | 2023-12-12 17:00 | 5 | Fire | 100 | 45 | 28 | 74 | 4
53 | 1.2.1.6.1.2.3 | Foundation Piling (Basement 2 Lvl) - (35 Piles) | 8 | 8 December 2023 8:00 AM | 16 December 2023 5:00 PM | 51,52 | 63,31 | 8 December 2023 8:00 AM | 2023-12-16 17:00 | 0 | Formworker | 100 | 71 | 27 | 59 | 40
54 | 1.2.1.6.2 | Building B | 66 | 15 November 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | 15 November 2023 8:00 AM | 2024-02-16 17:00 | 0 | Site Manager | 100 | 77 | 28 | 81 | 47
55 | 1.2.1.6.2.1 | Excavate - Gnd - B1 | 46 | 15 November 2023 8:00 AM | 22 January 2024 5:00 PM |  |  | 15 November 2023 8:00 AM | 2024-01-26 17:00 | 4 | Plumber | 100 | 34 | 23 | 60 | 57
56 | 1.2.1.6.2.1.1 | Excavation | 22 | 15 November 2023 8:00 AM | 14 December 2023 5:00 PM | 38,46,51 | 57,59,61,71 | 15 November 2023 8:00 AM | 2023-12-16 17:00 | 2 | Excavation | 100 | 69 | 18 | 68 | 16
57 | 1.2.1.6.2.1.2 | Installation of Anchors | 8 | 20 December 2023 8:00 AM | 8 January 2024 5:00 PM | 56 | 58 | 20 December 2023 8:00 AM | 2024-01-09 17:00 | 1 | Cleaner | 100 | 62 | 31 | 70 | 45
58 | 1.2.1.6.2.1.3 | Install Bracing | 4 | 9 January 2024 8:00 AM | 12 January 2024 5:00 PM | 57 | 59 | 9 January 2024 8:00 AM | 2024-01-12 17:00 | 0 | Head Contractor | 100 | 21 | 14 | 72 | 38
59 | 1.2.1.6.2.1.4 | Shotcrete | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,58 | 61 | 20 December 2023 8:00 AM | 2024-01-23 17:00 | 1 | Floor Sealer | 100 | 52 | 13 | 62 | 23
60 | 1.2.1.6.2.2 | Excavate - B1-B2 | 40 | 20 December 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | 20 December 2023 8:00 AM | 2024-02-20 17:00 | 4 | Fire | 100 | 61 | 24 | 64 | 15
61 | 1.2.1.6.2.2.1 | Excavation | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,59 | 66,63,71,62 | 20 December 2023 8:00 AM | 2024-01-27 17:00 | 5 | Metal Work | 100 | 66 | 19 | 85 | 18
62 | 1.2.1.6.2.2.2 | Shotcrete | 10 | 1 February 2024 8:00 AM | 12 February 2024 5:00 PM | 61 | 63 | 1 February 2024 8:00 AM | 2024-02-12 17:00 | 0 | Contract Administrator | 100 | 56 | 26 | 17 | 44
63 | 1.2.1.6.2.2.3 | Foundation Piling (Basement 2 Lvl) - (23 Piles) | 4 | 13 February 2024 8:00 AM | 16 February 2024 5:00 PM | 61,53,62 | 74 | 13 February 2024 8:00 AM | 2024-02-16 17:00 | 0 | Stone Mason | 100 | 88 | 13 | 37 | 14
64 | 1.2.1.6.3 | Buildings C & D | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | 23 January 2024 8:00 AM | 2024-03-22 17:00 | 0 | Mechanical | 100 | 61 | 21 | 14 | 43
65 | 1.2.1.6.3.1 | Excavate - Gnd - B2 | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | 23 January 2024 8:00 AM | 2024-03-27 17:00 | 5 | Foreman | 100 | 20 | 13 | 44 | 37
66 | 1.2.1.6.3.1.1 | Excavation | 30 | 23 January 2024 8:00 AM | 28 February 2024 5:00 PM | 42,61 | 67,71 | 23 January 2024 8:00 AM | 2024-03-01 17:00 | 2 | Plumber | 100 | 61 | 32 | 20 | 2
67 | 1.2.1.6.3.1.2 | Installation of Anchors | 8 | 29 February 2024 8:00 AM | 8 March 2024 5:00 PM | 66 | 68 | 29 February 2024 8:00 AM | 2024-03-08 17:00 | 0 | Site Manager | 100 | 84 | 28 | 71 | 35
68 | 1.2.1.6.3.1.3 | Install Bracing | 4 | 9 March 2024 8:00 AM | 13 March 2024 5:00 PM | 67 | 69 | 9 March 2024 8:00 AM | 2024-03-13 17:00 | 0 | Fire | 100 | 64 | 12 | 34 | 26
69 | 1.2.1.6.3.1.4 | Shotcrete | 6 | 14 March 2024 8:00 AM | 20 March 2024 5:00 PM | 68 | 70,84 | 14 March 2024 8:00 AM | 2024-03-20 17:00 | 0 | Contract Administrator | 100 | 83 | 31 | 66 | 32
70 | 1.2.1.6.3.1.5 | Foundation Piling (Basement 2 Lvl) - (5 Piles) | 2 | 21 March 2024 8:00 AM | 22 March 2024 5:00 PM | 69 | 86 | 21 March 2024 8:00 AM | 2024-03-22 17:00 | 0 | Mechanical | 100 | 46 | 14 | 21 | 20
71 | 1.2.1.6.4 | Complete Bulk Exacavation | 0 | 28 February 2024 5:00 PM | 28 February 2024 5:00 PM | 46,51,56,61,66 |  | 28 February 2024 5:00 PM | 2024-02-28 17:00 | 0 | Admin | 100 | 78 | 19 | 72 | 21
72 | 1.2.1.7 | Detail Excavation, Services & Base course | 61 | 17 February 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | 17 February 2024 8:00 AM | 2024-05-07 17:00 | 5 | Window | 100 | 97 | 11 | 6 | 28
73 | 1.2.1.7.1 | Stage 1 (Building A) | 32 | 17 February 2024 8:00 AM | 25 March 2024 5:00 PM |  |  | 17 February 2024 8:00 AM | 2024-03-29 17:00 | 4 | Concretor | 100 | 46 | 20 | 55 | 55
74 | 1.2.1.7.1.1 | Detailed Excavation | 11 | 17 February 2024 8:00 AM | 29 February 2024 5:00 PM | 63 | 75,79 | 17 February 2024 8:00 AM | 2024-03-02 17:00 | 2 | Formworker | 100 | 63 | 10 | 29 | 2
75 | 1.2.1.7.1.2 | In-Ground Services | 8 | 1 March 2024 8:00 AM | 9 March 2024 5:00 PM | 74 | 76 | 1 March 2024 8:00 AM | 2024-03-12 17:00 | 3 | Plumber | 100 | 63 | 27 | 4 | 44
76 | 1.2.1.7.1.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 11 March 2024 8:00 AM | 15 March 2024 5:00 PM | 75 | 77 | 11 March 2024 8:00 AM | 2024-03-15 17:00 | 0 | Foreman | 100 | 66 | 35 | 9 | 4
77 | 1.2.1.7.1.4 | Base Course to Basement | 8 | 16 March 2024 8:00 AM | 25 March 2024 5:00 PM | 76 | 88 | 16 March 2024 8:00 AM | 2024-03-25 17:00 | 0 | Metal Work | 100 | 99 | 31 | 70 | 35
78 | 1.2.1.7.2 | Stage 2 (Building B) | 32 | 1 March 2024 8:00 AM | 10 April 2024 5:00 PM |  |  | 1 March 2024 8:00 AM | 2024-04-15 17:00 | 5 | Reinforcement Fixer | 100 | 81 | 25 | 57 | 46
79 | 1.2.1.7.2.1 | Detailed Excavation | 12 | 1 March 2024 8:00 AM | 14 March 2024 5:00 PM | 74 | 80 | 1 March 2024 8:00 AM | 2024-03-17 17:00 | 3 | Surveyor | 100 | 75 | 13 | 36 | 59
80 | 1.2.1.7.2.2 | In-Ground Services | 9 | 15 March 2024 8:00 AM | 25 March 2024 5:00 PM | 79 | 81 | 15 March 2024 8:00 AM | 2024-03-27 17:00 | 2 | Surveyor | 100 | 57 | 16 | 68 | 31
81 | 1.2.1.7.2.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 6 | 26 March 2024 8:00 AM | 4 April 2024 5:00 PM | 80 | 82 | 26 March 2024 8:00 AM | 2024-04-05 17:00 | 1 | Metal Work | 100 | 84 | 33 | 87 | 55
82 | 1.2.1.7.2.4 | Base Course to Basement | 5 | 5 April 2024 8:00 AM | 10 April 2024 5:00 PM | 81 | 93 | 5 April 2024 8:00 AM | 2024-04-10 17:00 | 0 | Window | 100 | 74 | 23 | 47 | 26
83 | 1.2.1.7.3 | Stage 3 (Buildings C&D) | 33 | 21 March 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | 21 March 2024 8:00 AM | 2024-05-03 17:00 | 1 | Development Manager | 100 | 58 | 16 | 40 | 18
84 | 1.2.1.7.3.1 | Detailed Excavation | 12 | 21 March 2024 8:00 AM | 6 April 2024 5:00 PM | 69 | 85 | 21 March 2024 8:00 AM | 2024-04-09 17:00 | 3 | Floor Sealer | 100 | 83 | 24 | 55 | 42
85 | 1.2.1.7.3.2 | In-Ground Services | 8 | 8 April 2024 8:00 AM | 16 April 2024 5:00 PM | 84 | 86 | 8 April 2024 8:00 AM | 2024-04-16 17:00 | 0 | Carpenter | 100 | 49 | 29 | 96 | 44
86 | 1.2.1.7.3.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 17 April 2024 8:00 AM | 22 April 2024 5:00 PM | 85,70 | 87 | 17 April 2024 8:00 AM | 2024-04-22 17:00 | 0 | Line Market | 100 | 56 | 21 | 86 | 21
87 | 1.2.1.7.3.4 | Base Course to Basement | 8 | 23 April 2024 8:00 AM | 2 May 2024 5:00 PM | 86 | 88 | 23 April 2024 8:00 AM | 2024-05-04 17:00 | 2 | Painter | 100 | 69 | 24 | 95 | 20
88 | 1.2.1.7.4 | Basement Earthworks and Piling Complete | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 87,77 | 122,4 | 2 May 2024 5:00 PM | 2024-05-02 17:00 | 0 | Concretor | 100 | 33 | 29 | 65 | 33
89 | 1.2.2 | STRUCTURE WORKS | 217 | 11 April 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 11 April 2024 8:00 AM | 2025-01-04 17:00 | 1 | Metal Work | 100 | 93 | 29 | 22 | 38
90 | 1.2.2.1 | CC2 - Basement to Podium L1 - A, B, C, D | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  |  | 11 April 2024 8:00 AM | 2024-10-04 17:00 | 4 | Line Market | 100 | 70 | 28 | 43 | 3
91 | 1.2.2.1.1 | Basement to Podium (Level 1 - A & B ) | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | 11 April 2024 8:00 AM | 2024-10-01 17:00 | 1 | Development Manager | 100 | 91 | 25 | 80 | 35
92 | 1.2.2.1.1.1 | Basement 2 - FRP - SoG | 23 | 11 April 2024 8:00 AM | 8 May 2024 5:00 PM |  |  | 11 April 2024 8:00 AM | 2024-05-11 17:00 | 3 | Cleaner | 100 | 34 | 10 | 40 | 32
93 | 1.2.2.1.1.1.1 | Reinforcement Fix | 13 | 11 April 2024 8:00 AM | 26 April 2024 5:00 PM | 82 | 94 | 11 April 2024 8:00 AM | 2024-04-27 17:00 | 1 | Plumber | 100 | 37 | 26 | 87 | 37
94 | 1.2.2.1.1.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 9 | 27 April 2024 8:00 AM | 7 May 2024 5:00 PM | 93 | 95 | 27 April 2024 8:00 AM | 2024-05-07 17:00 | 0 | Stone Mason | 100 | 60 | 20 | 3 | 24
95 | 1.2.2.1.1.1.3 | Pour | 1 | 8 May 2024 8:00 AM | 8 May 2024 5:00 PM | 94 | 97 | 8 May 2024 8:00 AM | 2024-05-08 17:00 | 0 | Landscaper | 100 | 98 | 22 | 82 | 45
96 | 1.2.2.1.1.2 | Basement 1 - FRP - Suspended Slab | 25 | 9 May 2024 8:00 AM | 6 June 2024 5:00 PM |  |  | 9 May 2024 8:00 AM | 2024-06-07 17:00 | 1 | Hoarding | 100 | 75 | 17 | 82 | 59
97 | 1.2.2.1.1.2.1 | Scaffold Stair Removal/Adjustment | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 95 | 98SS | 9 May 2024 8:00 AM | 2024-05-10 17:00 | 0 | Subcontractor | 100 | 51 | 34 | 11 | 7
98 | 1.2.2.1.1.2.2 | Setout and Install Lift/Stair Formwork | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 97SS | 99 | 9 May 2024 8:00 AM | 2024-05-10 17:00 | 0 | Plasterboarder | 100 | 96 | 21 | 14 | 41
99 | 1.2.2.1.1.2.3 | Formworker setout, drop material and 80% Deck | 9 | 11 May 2024 8:00 AM | 21 May 2024 5:00 PM | 98 | 100FS-1d,101 | 11 May 2024 8:00 AM | 2024-05-21 17:00 | 0 | Formworker | 100 | 12 | 19 | 62 | 33
100 | 1.2.2.1.1.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 21 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99FS-1d | 102,103 | 21 May 2024 8:00 AM | 2024-05-24 17:00 | 0 | Plumber | 100 | 10 | 19 | 40 | 37
101 | 1.2.2.1.1.2.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 22 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99 |  | 22 May 2024 8:00 AM | 2024-05-24 17:00 | 0 | Painter | 100 | 61 | 13 | 13 | 59
102 | 1.2.2.1.1.2.6 | Services | 4 | 25 May 2024 8:00 AM | 29 May 2024 5:00 PM | 100 | 104FS-1d | 25 May 2024 8:00 AM | 2024-05-29 17:00 | 0 | Reinforcement Fixer | 100 | 88 | 28 | 69 | 29
103 | 1.2.2.1.1.2.7 | Post Tension | 3 | 25 May 2024 8:00 AM | 28 May 2024 5:00 PM | 100 | 104FS-1d | 25 May 2024 8:00 AM | 2024-05-28 17:00 | 0 | Plasterboarder | 100 | 79 | 33 | 69 | 19
104 | 1.2.2.1.1.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 29 May 2024 8:00 AM | 31 May 2024 5:00 PM | 102FS-1d,103FS-1d | 105 | 29 May 2024 8:00 AM | 2024-05-31 17:00 | 0 | Admin | 100 | 45 | 32 | 46 | 47
105 | 1.2.2.1.1.2.9 | Formworker setdowns and edge boards | 4 | 1 June 2024 8:00 AM | 5 June 2024 5:00 PM | 104 | 106 | 1 June 2024 8:00 AM | 2024-06-05 17:00 | 0 | Window | 100 | 27 | 12 | 89 | 21
106 | 1.2.2.1.1.2.10 | Pour | 1 | 6 June 2024 8:00 AM | 6 June 2024 5:00 PM | 105 | 109 | 6 June 2024 8:00 AM | 2024-06-06 17:00 | 0 | Mechanical | 100 | 99 | 23 | 73 | 48
107 | 1.2.2.1.1.3 | Strip Formwork - Basement 1 | 5 | 7 September 2024 8:00 AM | 12 September 2024 5:00 PM | 161FS+5d | 522 | 7 September 2024 8:00 AM | 2024-09-12 17:00 | 0 | Contract Administrator | 100 | 99 | 26 | 5 | 2
108 | 1.2.2.1.1.4 | Lvl 1 - FRP - Suspended Slab | 28 | 7 June 2024 8:00 AM | 11 July 2024 5:00 PM |  |  | 7 June 2024 8:00 AM | 2024-07-14 17:00 | 3 | Plasterboarder | 100 | 26 | 32 | 4 | 10
109 | 1.2.2.1.1.4.1 | Scaffold Stair Removal/Adjustment | 1 | 7 June 2024 8:00 AM | 7 June 2024 5:00 PM | 106 | 110SS | 7 June 2024 8:00 AM | 2024-06-07 17:00 | 0 | Surveyor | 100 | 68 | 27 | 6 | 52
110 | 1.2.2.1.1.4.2 | Setout and Install Lift/Stair Formwork | 3 | 7 June 2024 8:00 AM | 12 June 2024 5:00 PM | 109SS | 111 | 7 June 2024 8:00 AM | 2024-06-12 17:00 | 0 | Metal Work | 100 | 36 | 18 | 80 | 49
111 | 1.2.2.1.1.4.3 | Formworker setout, drop material and 80% Deck | 10 | 13 June 2024 8:00 AM | 24 June 2024 5:00 PM | 110 | 112FS-1d,113,128 | 13 June 2024 8:00 AM | 2024-06-24 17:00 | 0 | Project Manager | 100 | 24 | 10 | 65 | 53
112 | 1.2.2.1.1.4.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 6 | 24 June 2024 8:00 AM | 29 June 2024 5:00 PM | 111FS-1d | 114,115 | 24 June 2024 8:00 AM | 2024-06-29 17:00 | 0 | Renderer | 100 | 24 | 12 | 4 | 18
113 | 1.2.2.1.1.4.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 25 June 2024 8:00 AM | 28 June 2024 5:00 PM | 111 | 118 | 25 June 2024 8:00 AM | 2024-06-28 17:00 | 0 | Tiler | 100 | 77 | 13 | 3 | 4
114 | 1.2.2.1.1.4.6 | Services | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 112 | 116FS-1d | 1 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Carpet | 100 | 45 | 11 | 23 | 33
115 | 1.2.2.1.1.4.7 | Post Tension | 4 | 1 July 2024 8:00 AM | 4 July 2024 5:00 PM | 112 | 116FS-1d | 1 July 2024 8:00 AM | 2024-07-04 17:00 | 0 | Reinforcement Fixer | 100 | 69 | 14 | 14 | 45
116 | 1.2.2.1.1.4.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 114FS-1d,115FS-1d | 117,401FS+5d | 4 July 2024 8:00 AM | 2024-07-06 17:00 | 0 | Carpet | 100 | 54 | 32 | 56 | 47
117 | 1.2.2.1.1.4.9 | Formworker setdowns and edge boards | 3 | 8 July 2024 8:00 AM | 10 July 2024 5:00 PM | 116 | 118 | 8 July 2024 8:00 AM | 2024-07-10 17:00 | 0 | Carpenter | 100 | 47 | 27 | 60 | 5
118 | 1.2.2.1.1.4.10 | Pour | 1 | 11 July 2024 8:00 AM | 11 July 2024 5:00 PM | 117,113 | 140 | 11 July 2024 8:00 AM | 2024-07-11 17:00 | 0 | Carpet | 100 | 52 | 13 | 56 | 16
119 | 1.2.2.1.1.5 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d | 535 | 25 September 2024 8:00 AM | 2024-09-30 17:00 | 0 | Painter | 100 | 99 | 22 | 40 | 25
120 | 1.2.2.1.2 | Basement to Podium (Level 1 - C & D) | 127 | 3 May 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | 3 May 2024 8:00 AM | 2024-10-03 17:00 | 3 | Concretor | 100 | 80 | 34 | 63 | 14
121 | 1.2.2.1.2.1 | Basement 2 - FRP - SoG | 12 | 3 May 2024 8:00 AM | 16 May 2024 5:00 PM |  |  | 3 May 2024 8:00 AM | 2024-05-19 17:00 | 3 | Subcontractor | 100 | 28 | 23 | 64 | 48
122 | 1.2.2.1.2.1.1 | Reinforcement Fix | 6 | 3 May 2024 8:00 AM | 9 May 2024 5:00 PM | 88 | 123 | 3 May 2024 8:00 AM | 2024-05-09 17:00 | 0 | Cleaner | 100 | 44 | 26 | 11 | 5
123 | 1.2.2.1.2.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 5 | 10 May 2024 8:00 AM | 15 May 2024 5:00 PM | 122 | 124 | 10 May 2024 8:00 AM | 2024-05-15 17:00 | 0 | Line Market | 100 | 53 | 21 | 24 | 48
124 | 1.2.2.1.2.1.3 | Pour | 1 | 16 May 2024 8:00 AM | 16 May 2024 5:00 PM | 123 | 126 | 16 May 2024 8:00 AM | 2024-05-16 17:00 | 0 | Stone Mason | 100 | 39 | 27 | 43 | 48
125 | 1.2.2.1.2.2 | Lvl 1 - FRP - Suspended Slab | 48 | 17 May 2024 8:00 AM | 13 July 2024 5:00 PM |  |  | 17 May 2024 8:00 AM | 2024-07-13 17:00 | 0 | Plasterboarder | 100 | 18 | 25 | 20 | 29
126 | 1.2.2.1.2.2.1 | Scaffold Stair Removal/Adjustment | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 124 | 127SS | 17 May 2024 8:00 AM | 2024-05-17 17:00 | 0 | Foreman | 100 | 82 | 25 | 6 | 25
127 | 1.2.2.1.2.2.2 | Setout and Install Lift/Stair Formwork | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 126SS | 128 | 17 May 2024 8:00 AM | 2024-05-17 17:00 | 0 | Plasterboarder | 100 | 82 | 10 | 14 | 31
128 | 1.2.2.1.2.2.3 | Formworker setout, drop material and 80% Deck | 6 | 25 June 2024 8:00 AM | 1 July 2024 5:00 PM | 127,111 | 129FS-1d,130 | 25 June 2024 8:00 AM | 2024-07-01 17:00 | 0 | Electrician | 100 | 13 | 32 | 94 | 17
129 | 1.2.2.1.2.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128FS-1d | 131,132 | 1 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Project Manager | 100 | 63 | 18 | 49 | 36
130 | 1.2.2.1.2.2.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128 |  | 2 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Waterproofer | 100 | 37 | 23 | 9 | 37
131 | 1.2.2.1.2.2.6 | Services | 2 | 4 July 2024 8:00 AM | 5 July 2024 5:00 PM | 129 | 133FS-1d | 4 July 2024 8:00 AM | 2024-07-05 17:00 | 0 | Window | 100 | 26 | 32 | 43 | 18
132 | 1.2.2.1.2.2.7 | Post Tension | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 129 | 133FS-1d | 4 July 2024 8:00 AM | 2024-07-06 17:00 | 0 | Line Market | 100 | 31 | 29 | 60 | 39
133 | 1.2.2.1.2.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 6 July 2024 8:00 AM | 9 July 2024 5:00 PM | 131FS-1d,132FS-1d | 134 | 6 July 2024 8:00 AM | 2024-07-09 17:00 | 0 | Line Market | 100 | 24 | 13 | 97 | 51
134 | 1.2.2.1.2.2.9 | Formworker setdowns and edge boards | 3 | 10 July 2024 8:00 AM | 12 July 2024 5:00 PM | 133 | 135 | 10 July 2024 8:00 AM | 2024-07-12 17:00 | 0 | Concretor | 100 | 76 | 31 | 78 | 40
135 | 1.2.2.1.2.2.10 | Pour | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 134 | 309,233 | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Cleaner | 100 | 60 | 25 | 97 | 51
136 | 1.2.2.1.2.3 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d |  | 25 September 2024 8:00 AM | 2024-09-30 17:00 | 0 | Mechanical | 100 | 87 | 20 | 70 | 35
137 | 1.2.2.2 | CC3 - Remainder of Structure | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 12 July 2024 8:00 AM | 2025-01-06 17:00 | 3 | Head Contractor | 100 | 11 | 12 | 74 | 43
138 | 1.2.2.2.1 | Building A | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | 12 July 2024 8:00 AM | 2025-01-07 17:00 | 4 | Landscaper | 100 | 73 | 35 | 83 | 56
139 | 1.2.2.2.1.1 | Lvl 2 - FRP - Suspended Slab | 26 | 12 July 2024 8:00 AM | 10 August 2024 5:00 PM |  |  | 12 July 2024 8:00 AM | 2024-08-14 17:00 | 4 | Reinforcement Fixer | 100 | 12 | 14 | 16 | 47
140 | 1.2.2.2.1.1.1 | Scaffold Perimeter Protection | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 118 | 141SS | 12 July 2024 8:00 AM | 2024-07-16 17:00 | 0 | Tiler | 100 | 71 | 20 | 3 | 30
141 | 1.2.2.2.1.1.2 | Setout and Install Lift/Stair Formwork | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 140SS | 142 | 12 July 2024 8:00 AM | 2024-07-16 17:00 | 0 | Reinforcement Fixer | 100 | 14 | 28 | 59 | 28
142 | 1.2.2.2.1.1.3 | Formworker setout, drop material and 80% Deck | 6 | 17 July 2024 8:00 AM | 23 July 2024 5:00 PM | 141 | 143FS-1d,144 | 17 July 2024 8:00 AM | 2024-07-23 17:00 | 0 | Painter | 100 | 95 | 28 | 48 | 32
143 | 1.2.2.2.1.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 23 July 2024 8:00 AM | 26 July 2024 5:00 PM | 142FS-1d | 145,146 | 23 July 2024 8:00 AM | 2024-07-26 17:00 | 0 | Window | 100 | 44 | 17 | 30 | 18
144 | 1.2.2.2.1.1.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 24 July 2024 8:00 AM | 27 July 2024 5:00 PM | 142 | 146 | 24 July 2024 8:00 AM | 2024-07-27 17:00 | 0 | Post Tension | 100 | 33 | 15 | 46 | 15
145 | 1.2.2.2.1.1.6 | Services | 3 | 27 July 2024 8:00 AM | 30 July 2024 5:00 PM | 143 | 147FS-1d | 27 July 2024 8:00 AM | 2024-07-30 17:00 | 0 | Painter | 100 | 53 | 18 | 21 | 10
146 | 1.2.2.2.1.1.7 | Post Tension | 3 | 29 July 2024 8:00 AM | 31 July 2024 5:00 PM | 143,144 | 147FS-1d | 29 July 2024 8:00 AM | 2024-07-31 17:00 | 0 | Window | 100 | 84 | 29 | 22 | 37
147 | 1.2.2.2.1.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 5 | 31 July 2024 8:00 AM | 5 August 2024 5:00 PM | 145FS-1d,146FS-1d | 148 | 31 July 2024 8:00 AM | 2024-08-05 17:00 | 0 | Foreman | 100 | 72 | 23 | 63 | 47
148 | 1.2.2.2.1.1.9 | Formworker setdowns and edge boards | 4 | 6 August 2024 8:00 AM | 9 August 2024 5:00 PM | 147 | 149 | 6 August 2024 8:00 AM | 2024-08-09 17:00 | 0 | Excavation | 100 | 16 | 12 | 86 | 43
149 | 1.2.2.2.1.1.10 | Pour | 1 | 10 August 2024 8:00 AM | 10 August 2024 5:00 PM | 148 | 152,407FS+5d | 10 August 2024 8:00 AM | 2024-08-10 17:00 | 0 | Fire | 100 | 26 | 31 | 7 | 44
150 | 1.2.2.2.1.2 | Strip Formwork - Lvl 2 | 5 | 15 October 2024 8:00 AM | 19 October 2024 5:00 PM | 185FS+5d | 577,550,409FS-10d | 15 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Window | 100 | 21 | 32 | 33 | 50
151 | 1.2.2.2.1.3 | Lvl 3 - FRP - Suspended Slab | 18 | 12 August 2024 8:00 AM | 31 August 2024 5:00 PM |  |  | 12 August 2024 8:00 AM | 2024-09-03 17:00 | 3 | Hoarding | 100 | 54 | 21 | 84 | 43
152 | 1.2.2.2.1.3.1 | Scaffold Perimeter Protection | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 149 | 153SS | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 0 | Project Manager | 100 | 73 | 26 | 14 | 53
153 | 1.2.2.2.1.3.2 | Setout and Install Lift/Stair Formwork | 1 | 12 August 2024 8:00 AM | 12 August 2024 5:00 PM | 152SS | 154 | 12 August 2024 8:00 AM | 2024-08-12 17:00 | 0 | Waterproofer | 100 | 58 | 15 | 65 | 49
154 | 1.2.2.2.1.3.3 | Formworker setout, drop material and 80% Deck | 6 | 13 August 2024 8:00 AM | 19 August 2024 5:00 PM | 153 | 155FS-1d,156 | 13 August 2024 8:00 AM | 2024-08-19 17:00 | 0 | Formworker | 100 | 67 | 27 | 20 | 11
155 | 1.2.2.2.1.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 19 August 2024 8:00 AM | 22 August 2024 5:00 PM | 154FS-1d | 157,158 | 19 August 2024 8:00 AM | 2024-08-22 17:00 | 0 | Tiler | 100 | 53 | 28 | 80 | 13
156 | 1.2.2.2.1.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 August 2024 8:00 AM | 21 August 2024 5:00 PM | 154 |  | 20 August 2024 8:00 AM | 2024-08-21 17:00 | 0 | Hoarding | 100 | 21 | 13 | 70 | 55
157 | 1.2.2.2.1.3.6 | Services | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | 23 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Mechanical | 100 | 92 | 26 | 26 | 24
158 | 1.2.2.2.1.3.7 | Post Tension | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | 23 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Development Manager | 100 | 15 | 22 | 3 | 14
159 | 1.2.2.2.1.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 24 August 2024 8:00 AM | 27 August 2024 5:00 PM | 157FS-1d,158FS-1d | 160 | 24 August 2024 8:00 AM | 2024-08-27 17:00 | 0 | Cleaner | 100 | 66 | 20 | 3 | 40
160 | 1.2.2.2.1.3.9 | Formworker setdowns and edge boards | 3 | 28 August 2024 8:00 AM | 30 August 2024 5:00 PM | 159 | 161 | 28 August 2024 8:00 AM | 2024-08-30 17:00 | 0 | Electrician | 100 | 93 | 10 | 18 | 18
161 | 1.2.2.2.1.3.10 | Pour | 1 | 31 August 2024 8:00 AM | 31 August 2024 5:00 PM | 160 | 164,3445,107FS+5d | 31 August 2024 8:00 AM | 2024-08-31 17:00 | 0 | Floor Sealer | 100 | 31 | 34 | 93 | 35
162 | 1.2.2.2.1.4 | Strip Formwork - Lvl 3 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d |  | 19 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Timber Floorer | 100 | 39 | 21 | 97 | 12
163 | 1.2.2.2.1.5 | Lvl 4 - FRP - Suspended Slab | 15 | 2 September 2024 8:00 AM | 18 September 2024 5:00 PM |  |  | 2 September 2024 8:00 AM | 2024-09-19 17:00 | 1 | Window | 100 | 68 | 18 | 31 | 45
164 | 1.2.2.2.1.5.1 | Scaffold Perimeter Protection | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 161 | 165SS | 2 September 2024 8:00 AM | 2024-09-02 17:00 | 0 | Joiner | 100 | 10 | 20 | 38 | 32
165 | 1.2.2.2.1.5.2 | Setout and Install Lift/Stair Formwork | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 164SS | 166FS-1d | 2 September 2024 8:00 AM | 2024-09-02 17:00 | 0 | Foreman | 100 | 66 | 15 | 38 | 18
166 | 1.2.2.2.1.5.3 | Formworker setout, drop material and 80% Deck | 6 | 2 September 2024 8:00 AM | 7 September 2024 5:00 PM | 165FS-1d | 167FS-1d,168 | 2 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Head Contractor | 100 | 58 | 28 | 78 | 49
167 | 1.2.2.2.1.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 7 September 2024 8:00 AM | 11 September 2024 5:00 PM | 166FS-1d | 169,170 | 7 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Landscaper | 100 | 76 | 13 | 63 | 35
168 | 1.2.2.2.1.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 9 September 2024 8:00 AM | 10 September 2024 5:00 PM | 166 |  | 9 September 2024 8:00 AM | 2024-09-10 17:00 | 0 | Timber Floorer | 100 | 98 | 12 | 53 | 38
169 | 1.2.2.2.1.5.6 | Services | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | 12 September 2024 8:00 AM | 2024-09-13 17:00 | 0 | Surveyor | 100 | 17 | 11 | 21 | 54
170 | 1.2.2.2.1.5.7 | Post Tension | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | 12 September 2024 8:00 AM | 2024-09-13 17:00 | 0 | Reinforcement Fixer | 100 | 25 | 20 | 49 | 38
171 | 1.2.2.2.1.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 13 September 2024 8:00 AM | 14 September 2024 5:00 PM | 169FS-1d,170FS-1d | 172 | 13 September 2024 8:00 AM | 2024-09-14 17:00 | 0 | Fire | 100 | 35 | 30 | 29 | 49
172 | 1.2.2.2.1.5.9 | Formworker setdowns and edge boards | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 171 | 173 | 16 September 2024 8:00 AM | 2024-09-17 17:00 | 0 | Floor Sealer | 100 | 27 | 30 | 28 | 15
173 | 1.2.2.2.1.5.10 | Pour | 1 | 18 September 2024 8:00 AM | 18 September 2024 5:00 PM | 172 | 176,119FS+5d,136FS+5d | 18 September 2024 8:00 AM | 2024-09-18 17:00 | 0 | Surveyor | 100 | 57 | 28 | 17 | 22
174 | 1.2.2.2.1.6 | Strip Formwork - Lvl 4 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d | 413FS+5d,604,415FS-10d | 19 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Window | 100 | 35 | 12 | 75 | 30
175 | 1.2.2.2.1.7 | Lvl 5 - FRP - Suspended Slab | 15 | 19 September 2024 8:00 AM | 8 October 2024 5:00 PM |  |  | 19 September 2024 8:00 AM | 2024-10-11 17:00 | 3 | Site Manager | 100 | 26 | 15 | 40 | 9
176 | 1.2.2.2.1.7.1 | Scaffold Perimeter Protection | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 173 | 177SS | 19 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Joiner | 100 | 73 | 35 | 64 | 7
177 | 1.2.2.2.1.7.2 | Setout and Install Lift/Stair Formwork | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 176SS | 178FS-1d | 19 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Tiler | 100 | 57 | 35 | 77 | 60
178 | 1.2.2.2.1.7.3 | Formworker setout, drop material and 80% Deck | 6 | 19 September 2024 8:00 AM | 25 September 2024 5:00 PM | 177FS-1d | 179FS-1d,180 | 19 September 2024 8:00 AM | 2024-09-25 17:00 | 0 | Post Tension | 100 | 69 | 28 | 4 | 37
179 | 1.2.2.2.1.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 25 September 2024 8:00 AM | 28 September 2024 5:00 PM | 178FS-1d | 181,182 | 25 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Tiler | 100 | 82 | 23 | 80 | 49
180 | 1.2.2.2.1.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 26 September 2024 8:00 AM | 27 September 2024 5:00 PM | 178 |  | 26 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Floor Sealer | 100 | 20 | 20 | 13 | 34
181 | 1.2.2.2.1.7.6 | Services | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | 30 September 2024 8:00 AM | 2024-10-01 17:00 | 0 | Landscaper | 100 | 68 | 32 | 14 | 18
182 | 1.2.2.2.1.7.7 | Post Tension | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | 30 September 2024 8:00 AM | 2024-10-01 17:00 | 0 | Electrician | 100 | 47 | 25 | 79 | 6
183 | 1.2.2.2.1.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 1 October 2024 8:00 AM | 2 October 2024 5:00 PM | 181FS-1d,182FS-1d | 184 | 1 October 2024 8:00 AM | 2024-10-02 17:00 | 0 | Painter | 100 | 57 | 35 | 71 | 3
184 | 1.2.2.2.1.7.9 | Formworker setdowns and edge boards | 2 | 3 October 2024 8:00 AM | 4 October 2024 5:00 PM | 183 | 185 | 3 October 2024 8:00 AM | 2024-10-04 17:00 | 0 | Concretor | 100 | 44 | 21 | 46 | 43
185 | 1.2.2.2.1.7.10 | Pour | 1 | 8 October 2024 8:00 AM | 8 October 2024 5:00 PM | 184 | 188,150FS+5d | 8 October 2024 8:00 AM | 2024-10-08 17:00 | 0 | Subcontractor | 100 | 40 | 28 | 7 | 21
186 | 1.2.2.2.1.8 | Strip Formwork - Lvl 5 | 5 | 5 December 2024 8:00 AM | 10 December 2024 5:00 PM | 221FS+5d | 631,421FS-10d,419FS+5d | 5 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Carpet | 100 | 89 | 33 | 25 | 12
187 | 1.2.2.2.1.9 | Lvl 6 - FRP - Suspended Slab | 15 | 9 October 2024 8:00 AM | 25 October 2024 5:00 PM |  |  | 9 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Carpet | 100 | 76 | 24 | 22 | 41
188 | 1.2.2.2.1.9.1 | Scaffold Perimeter Protection | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 185 | 189SS | 9 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Contract Administrator | 100 | 80 | 11 | 28 | 60
189 | 1.2.2.2.1.9.2 | Setout and Install Lift/Stair Formwork | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 188SS | 190FS-1d | 9 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Mechanical | 100 | 34 | 19 | 68 | 34
190 | 1.2.2.2.1.9.3 | Formworker setout, drop material and 80% Deck | 6 | 9 October 2024 8:00 AM | 15 October 2024 5:00 PM | 189FS-1d | 191FS-1d,192 | 9 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Concretor | 100 | 84 | 24 | 74 | 20
191 | 1.2.2.2.1.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 October 2024 8:00 AM | 18 October 2024 5:00 PM | 190FS-1d | 193,194 | 15 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Carpenter | 100 | 24 | 23 | 15 | 58
192 | 1.2.2.2.1.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 190 |  | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Waterproofer | 100 | 80 | 33 | 92 | 10
193 | 1.2.2.2.1.9.6 | Services | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Floor Sealer | 100 | 62 | 13 | 93 | 12
194 | 1.2.2.2.1.9.7 | Post Tension | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Landscaper | 100 | 10 | 13 | 44 | 45
195 | 1.2.2.2.1.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 193FS-1d,194FS-1d | 196 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Contract Administrator | 100 | 62 | 20 | 76 | 15
196 | 1.2.2.2.1.9.9 | Formworker setdowns and edge boards | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 195 | 197 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Reinforcement Fixer | 100 | 79 | 25 | 61 | 55
197 | 1.2.2.2.1.9.10 | Pour | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 196 | 200 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Electrician | 100 | 11 | 23 | 50 | 58
198 | 1.2.2.2.1.10 | Strip Formwork - Lvl 6 | 5 | 6 December 2024 8:00 AM | 11 December 2024 5:00 PM | 225 | 657,425FS+5d,427FS-10d | 6 December 2024 8:00 AM | 2024-12-11 17:00 | 0 | Hoarding | 100 | 71 | 25 | 70 | 38
199 | 1.2.2.2.1.11 | Lvl 7 - FRP - Suspended Slab | 15 | 26 October 2024 8:00 AM | 12 November 2024 5:00 PM |  |  | 26 October 2024 8:00 AM | 2024-11-16 17:00 | 4 | Subcontractor | 100 | 19 | 30 | 10 | 19
200 | 1.2.2.2.1.11.1 | Scaffold Perimeter Protection | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 197 | 201SS | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Metal Work | 100 | 36 | 21 | 71 | 55
201 | 1.2.2.2.1.11.2 | Setout and Install Lift/Stair Formwork | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 200SS | 202FS-1d | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Concretor | 100 | 62 | 30 | 36 | 14
202 | 1.2.2.2.1.11.3 | Formworker setout, drop material and 80% Deck | 6 | 26 October 2024 8:00 AM | 1 November 2024 5:00 PM | 201FS-1d | 203FS-1d,204 | 26 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Concretor | 100 | 93 | 27 | 83 | 45
203 | 1.2.2.2.1.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 1 November 2024 8:00 AM | 5 November 2024 5:00 PM | 202FS-1d | 205,206 | 1 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Project Manager | 100 | 20 | 35 | 85 | 35
204 | 1.2.2.2.1.11.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 202 |  | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Painter | 100 | 59 | 20 | 40 | 17
205 | 1.2.2.2.1.11.6 | Services | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Plasterboarder | 100 | 67 | 31 | 58 | 14
206 | 1.2.2.2.1.11.7 | Post Tension | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Admin | 100 | 58 | 31 | 82 | 23
207 | 1.2.2.2.1.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 205FS-1d,206FS-1d | 208 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Excavation | 100 | 100 | 17 | 22 | 16
208 | 1.2.2.2.1.11.9 | Formworker setdowns and edge boards | 2 | 9 November 2024 8:00 AM | 11 November 2024 5:00 PM | 207 | 209 | 9 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Subcontractor | 100 | 11 | 14 | 24 | 9
209 | 1.2.2.2.1.11.10 | Pour | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 208 | 212,162FS+5d,174FS+5d,431FS+5d | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Carpenter | 100 | 31 | 22 | 62 | 46
210 | 1.2.2.2.1.12 | Strip Formwork - Lvl 7 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 225FS+5d | 690,432FS-10d | 12 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Concretor | 100 | 70 | 20 | 35 | 15
211 | 1.2.2.2.1.13 | Lvl 8 (Roof) - FRP - Suspended Slab | 14 | 13 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | 13 November 2024 8:00 AM | 2024-12-01 17:00 | 3 | Formworker | 100 | 56 | 10 | 95 | 37
212 | 1.2.2.2.1.13.1 | Scaffold Perimeter Protection | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 209 | 213SS | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Electrician | 100 | 10 | 17 | 73 | 54
213 | 1.2.2.2.1.13.2 | Setout and Install Lift/Stair Formwork | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 212SS | 214FS-1d | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Joiner | 100 | 50 | 21 | 64 | 35
214 | 1.2.2.2.1.13.3 | Formworker setout, drop material and 80% Deck | 6 | 13 November 2024 8:00 AM | 19 November 2024 5:00 PM | 213FS-1d | 215FS-1d,216 | 13 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Cleaner | 100 | 85 | 11 | 3 | 54
215 | 1.2.2.2.1.13.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214FS-1d | 217,218 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Timber Floorer | 100 | 10 | 22 | 18 | 31
216 | 1.2.2.2.1.13.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214 |  | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Mechanical | 100 | 47 | 25 | 6 | 48
217 | 1.2.2.2.1.13.6 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Contract Administrator | 100 | 90 | 13 | 59 | 43
218 | 1.2.2.2.1.13.7 | Post Tension | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Stone Mason | 100 | 87 | 12 | 15 | 58
219 | 1.2.2.2.1.13.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 217FS-1d,218FS-1d | 220 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Surveyor | 100 | 68 | 28 | 31 | 3
220 | 1.2.2.2.1.13.9 | Formworker setdowns and edge boards | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 219 | 221 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Renderer | 100 | 36 | 10 | 44 | 53
221 | 1.2.2.2.1.13.10 | Pour - Structure Top Out | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 220 | 223FS+12d,222,225,186FS+5d,437FS+5d | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Admin | 100 | 50 | 23 | 37 | 5
222 | 1.2.2.2.1.13.11 | Structure Top Out | 0 | 28 November 2024 5:00 PM | 28 November 2024 5:00 PM | 221 |  | 28 November 2024 5:00 PM | 2024-11-28 17:00 | 0 | Head Contractor | 100 | 92 | 22 | 2 | 16
223 | 1.2.2.2.1.14 | Strip Formwork - Lvl 8 | 4 | 13 December 2024 8:00 AM | 17 December 2024 5:00 PM | 221FS+12d | 716,439FS+10d | 13 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Development Manager | 100 | 46 | 11 | 45 | 57
224 | 1.2.2.2.1.15 | Lift Shaft | 23 | 29 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 29 November 2024 8:00 AM | 2025-01-08 17:00 | 5 | Plasterboarder | 100 | 69 | 14 | 89 | 28
225 | 1.2.2.2.1.15.1 | FRP Lift Over-run | 6 | 29 November 2024 8:00 AM | 5 December 2024 5:00 PM | 221 | 226FS+5d,228,198,210FS+5d | 29 November 2024 8:00 AM | 2024-12-08 17:00 | 3 | Cleaner | 100 | 88 | 16 | 77 | 14
226 | 1.2.2.2.1.15.2 | Strip Lift Shaft Formwork | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 225FS+5d | 227 | 12 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Contract Administrator | 100 | 31 | 32 | 89 | 37
227 | 1.2.2.2.1.15.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 17 December 2024 8:00 AM | 3 January 2025 5:00 PM | 226 | 3451 | 17 December 2024 8:00 AM | 2025-01-05 17:00 | 2 | Timber Floorer | 100 | 84 | 21 | 61 | 25
228 | 1.2.2.2.1.15.4 | Building A Structure Complete | 0 | 5 December 2024 5:00 PM | 5 December 2024 5:00 PM | 225 | 6 | 5 December 2024 5:00 PM | 2024-12-05 17:00 | 0 | Reinforcement Fixer | 100 | 25 | 33 | 88 | 26
229 | 1.2.2.2.2 | Building B | 119 | 13 July 2024 8:00 AM | 30 November 2024 5:00 PM |  | 397 | 13 July 2024 8:00 AM | 2024-11-30 17:00 | 0 | Head Contractor | 100 | 77 | 13 | 22 | 10
230 | 1.2.2.2.2.1 | Lvl 2 - FRP - Suspended Slab | 18 | 13 July 2024 8:00 AM | 2 August 2024 5:00 PM |  |  | 13 July 2024 8:00 AM | 2024-08-02 17:00 | 0 | Plumber | 100 | 87 | 16 | 16 | 19
231 | 1.2.2.2.2.1.1 | Scaffold Perimeter Protection | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 232SS |  | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Window | 100 | 85 | 14 | 22 | 16
232 | 1.2.2.2.2.1.2 | Setout and Install Lift/Stair Formwork | 1 | 13 July 2024 8:00 AM | 15 July 2024 8:00 AM | 233SF | 231SS | 13 July 2024 8:00 AM | 2024-07-15 08:00 | 0 | Plumber | 100 | 42 | 23 | 34 | 45
233 | 1.2.2.2.2.1.3 | Formworker setout, drop material and 80% Deck | 6 | 15 July 2024 8:00 AM | 20 July 2024 5:00 PM | 135 | 234FS-1d,235,232SF | 15 July 2024 8:00 AM | 2024-07-20 17:00 | 0 | Joiner | 100 | 74 | 21 | 8 | 18
234 | 1.2.2.2.2.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 20 July 2024 8:00 AM | 24 July 2024 5:00 PM | 233FS-1d | 236,237 | 20 July 2024 8:00 AM | 2024-07-24 17:00 | 0 | Subcontractor | 100 | 14 | 23 | 99 | 27
235 | 1.2.2.2.2.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 22 July 2024 8:00 AM | 23 July 2024 5:00 PM | 233 |  | 22 July 2024 8:00 AM | 2024-07-23 17:00 | 0 | Floor Sealer | 100 | 86 | 32 | 8 | 43
236 | 1.2.2.2.2.1.6 | Services | 2 | 25 July 2024 8:00 AM | 26 July 2024 5:00 PM | 234 | 238FS-1d | 25 July 2024 8:00 AM | 2024-07-26 17:00 | 0 | Excavation | 100 | 81 | 28 | 46 | 3
237 | 1.2.2.2.2.1.7 | Post Tension | 3 | 25 July 2024 8:00 AM | 27 July 2024 5:00 PM | 234 | 238FS-1d | 25 July 2024 8:00 AM | 2024-07-27 17:00 | 0 | Floor Sealer | 100 | 16 | 12 | 9 | 57
238 | 1.2.2.2.2.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 27 July 2024 8:00 AM | 29 July 2024 5:00 PM | 236FS-1d,237FS-1d | 239 | 27 July 2024 8:00 AM | 2024-07-29 17:00 | 0 | Plumber | 100 | 18 | 35 | 80 | 35
239 | 1.2.2.2.2.1.9 | Formworker setdowns and edge boards | 3 | 30 July 2024 8:00 AM | 1 August 2024 5:00 PM | 238 | 240 | 30 July 2024 8:00 AM | 2024-08-01 17:00 | 0 | Hoarding | 100 | 71 | 33 | 37 | 2
240 | 1.2.2.2.2.1.10 | Pour | 1 | 2 August 2024 8:00 AM | 2 August 2024 5:00 PM | 239 | 243,309FS+30d | 2 August 2024 8:00 AM | 2024-08-02 17:00 | 0 | Hoarding | 100 | 51 | 13 | 53 | 60
241 | 1.2.2.2.2.2 | Strip Formwork - Lvl 2 | 5 | 28 September 2024 8:00 AM | 3 October 2024 5:00 PM | 276 | 447 | 28 September 2024 8:00 AM | 2024-10-03 17:00 | 0 | Excavation | 100 | 46 | 22 | 79 | 17
242 | 1.2.2.2.2.3 | Lvl 3 - FRP - Suspended Slab | 18 | 3 August 2024 8:00 AM | 23 August 2024 5:00 PM |  |  | 3 August 2024 8:00 AM | 2024-08-24 17:00 | 1 | Head Contractor | 100 | 29 | 17 | 51 | 21
243 | 1.2.2.2.2.3.1 | Scaffold Perimeter Protection | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 240 | 244SS | 3 August 2024 8:00 AM | 2024-08-03 17:00 | 0 | Concretor | 100 | 80 | 10 | 4 | 48
244 | 1.2.2.2.2.3.2 | Setout and Install Lift/Stair Formwork | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 243SS | 245 | 3 August 2024 8:00 AM | 2024-08-03 17:00 | 0 | Surveyor | 100 | 66 | 32 | 67 | 54
245 | 1.2.2.2.2.3.3 | Formworker setout, drop material and 80% Deck | 6 | 5 August 2024 8:00 AM | 10 August 2024 5:00 PM | 244 | 246FS-1d,247 | 5 August 2024 8:00 AM | 2024-08-12 17:00 | 2 | Admin | 100 | 79 | 17 | 61 | 51
246 | 1.2.2.2.2.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 10 August 2024 8:00 AM | 14 August 2024 5:00 PM | 245FS-1d | 248,249 | 10 August 2024 8:00 AM | 2024-08-14 17:00 | 0 | Carpenter | 100 | 11 | 32 | 17 | 27
247 | 1.2.2.2.2.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 245 |  | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 0 | Floor Sealer | 100 | 96 | 23 | 80 | 13
248 | 1.2.2.2.2.3.6 | Services | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | 15 August 2024 8:00 AM | 2024-08-16 17:00 | 0 | Carpet | 100 | 11 | 12 | 82 | 25
249 | 1.2.2.2.2.3.7 | Post Tension | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | 15 August 2024 8:00 AM | 2024-08-16 17:00 | 0 | Concretor | 100 | 11 | 13 | 70 | 46
250 | 1.2.2.2.2.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 16 August 2024 8:00 AM | 19 August 2024 5:00 PM | 248FS-1d,249FS-1d | 251 | 16 August 2024 8:00 AM | 2024-08-19 17:00 | 0 | Admin | 100 | 89 | 25 | 72 | 5
251 | 1.2.2.2.2.3.9 | Formworker setdowns and edge boards | 3 | 20 August 2024 8:00 AM | 22 August 2024 5:00 PM | 250 | 252 | 20 August 2024 8:00 AM | 2024-08-22 17:00 | 0 | Plumber | 100 | 62 | 24 | 40 | 50
252 | 1.2.2.2.2.3.10 | Pour | 1 | 23 August 2024 8:00 AM | 23 August 2024 5:00 PM | 251 | 255,3447 | 23 August 2024 8:00 AM | 2024-08-23 17:00 | 0 | Fire | 100 | 61 | 12 | 16 | 54
253 | 1.2.2.2.2.4 | Strip Formwork - Lvl 3 | 5 | 21 October 2024 8:00 AM | 25 October 2024 5:00 PM | 288 | 453,1605 | 21 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Scaffolder | 100 | 77 | 24 | 57 | 27
254 | 1.2.2.2.2.5 | Lvl 4 - FRP - Suspended Slab | 15 | 24 August 2024 8:00 AM | 10 September 2024 5:00 PM |  |  | 24 August 2024 8:00 AM | 2024-09-15 17:00 | 5 | Metal Work | 100 | 12 | 14 | 47 | 13
255 | 1.2.2.2.2.5.1 | Scaffold Perimeter Protection | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 252 | 256SS | 24 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Foreman | 100 | 89 | 31 | 19 | 29
256 | 1.2.2.2.2.5.2 | Setout and Install Lift/Stair Formwork | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 255SS | 257FS-1d | 24 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Project Manager | 100 | 10 | 25 | 31 | 6
257 | 1.2.2.2.2.5.3 | Formworker setout, drop material and 80% Deck | 6 | 24 August 2024 8:00 AM | 30 August 2024 5:00 PM | 256FS-1d | 258FS-1d,259 | 24 August 2024 8:00 AM | 2024-09-01 17:00 | 2 | Excavation | 100 | 85 | 19 | 29 | 5
258 | 1.2.2.2.2.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 30 August 2024 8:00 AM | 3 September 2024 5:00 PM | 257FS-1d | 260,261 | 30 August 2024 8:00 AM | 2024-09-03 17:00 | 0 | Fire | 100 | 29 | 11 | 0 | 12
259 | 1.2.2.2.2.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 31 August 2024 8:00 AM | 2 September 2024 5:00 PM | 257 |  | 31 August 2024 8:00 AM | 2024-09-02 17:00 | 0 | Plumber | 100 | 50 | 33 | 57 | 59
260 | 1.2.2.2.2.5.6 | Services | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | 4 September 2024 8:00 AM | 2024-09-05 17:00 | 0 | Foreman | 100 | 27 | 10 | 80 | 55
261 | 1.2.2.2.2.5.7 | Post Tension | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | 4 September 2024 8:00 AM | 2024-09-05 17:00 | 0 | Waterproofer | 100 | 44 | 23 | 67 | 32
262 | 1.2.2.2.2.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 5 September 2024 8:00 AM | 6 September 2024 5:00 PM | 260FS-1d,261FS-1d | 263 | 5 September 2024 8:00 AM | 2024-09-06 17:00 | 0 | Admin | 100 | 23 | 10 | 1 | 20
263 | 1.2.2.2.2.5.9 | Formworker setdowns and edge boards | 2 | 7 September 2024 8:00 AM | 9 September 2024 5:00 PM | 262 | 264 | 7 September 2024 8:00 AM | 2024-09-09 17:00 | 0 | Window | 100 | 27 | 14 | 19 | 15
264 | 1.2.2.2.2.5.10 | Pour | 1 | 10 September 2024 8:00 AM | 10 September 2024 5:00 PM | 263 | 267 | 10 September 2024 8:00 AM | 2024-09-10 17:00 | 0 | Plasterboarder | 100 | 30 | 26 | 100 | 18
265 | 1.2.2.2.2.6 | Strip Formwork - Lvl 4 | 5 | 11 November 2024 8:00 AM | 15 November 2024 5:00 PM | 300 | 459,1632 | 11 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Carpet | 100 | 55 | 27 | 95 | 24
266 | 1.2.2.2.2.7 | Lvl 5 - FRP - Suspended Slab | 15 | 11 September 2024 8:00 AM | 27 September 2024 5:00 PM |  |  | 11 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Plasterboarder | 100 | 41 | 16 | 55 | 29
267 | 1.2.2.2.2.7.1 | Scaffold Perimeter Protection | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 264 | 268SS | 11 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Carpet | 100 | 81 | 28 | 82 | 12
268 | 1.2.2.2.2.7.2 | Setout and Install Lift/Stair Formwork | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 267SS | 269FS-1d | 11 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Floor Sealer | 100 | 80 | 28 | 59 | 25
269 | 1.2.2.2.2.7.3 | Formworker setout, drop material and 80% Deck | 6 | 11 September 2024 8:00 AM | 17 September 2024 5:00 PM | 268FS-1d | 270FS-1d,271 | 11 September 2024 8:00 AM | 2024-09-18 17:00 | 1 | Excavation | 100 | 78 | 21 | 94 | 36
270 | 1.2.2.2.2.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 17 September 2024 8:00 AM | 20 September 2024 5:00 PM | 269FS-1d | 272,273 | 17 September 2024 8:00 AM | 2024-09-20 17:00 | 0 | Floor Sealer | 100 | 97 | 13 | 12 | 11
271 | 1.2.2.2.2.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 18 September 2024 8:00 AM | 19 September 2024 5:00 PM | 269 |  | 18 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Line Market | 100 | 16 | 21 | 10 | 43
272 | 1.2.2.2.2.7.6 | Services | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Carpenter | 100 | 30 | 17 | 80 | 15
273 | 1.2.2.2.2.7.7 | Post Tension | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Admin | 100 | 41 | 29 | 5 | 11
274 | 1.2.2.2.2.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 September 2024 8:00 AM | 24 September 2024 5:00 PM | 272FS-1d,273FS-1d | 275 | 23 September 2024 8:00 AM | 2024-09-24 17:00 | 0 | Plumber | 100 | 92 | 22 | 98 | 18
275 | 1.2.2.2.2.7.9 | Formworker setdowns and edge boards | 2 | 25 September 2024 8:00 AM | 26 September 2024 5:00 PM | 274 | 276 | 25 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Timber Floorer | 100 | 78 | 16 | 63 | 34
276 | 1.2.2.2.2.7.10 | Pour | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 275 | 279,241 | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Site Manager | 100 | 89 | 22 | 17 | 56
277 | 1.2.2.2.2.8 | Strip Formwork - Lvl 5 | 5 | 18 November 2024 8:00 AM | 22 November 2024 5:00 PM | 303 | 465,1659 | 18 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Hoarding | 100 | 38 | 13 | 66 | 5
278 | 1.2.2.2.2.9 | Lvl 6 - FRP - Suspended Slab | 17 | 28 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | 28 September 2024 8:00 AM | 2024-10-22 17:00 | 3 | Joiner | 100 | 28 | 29 | 86 | 2
279 | 1.2.2.2.2.9.1 | Scaffold Perimeter Protection | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 276 | 280SS | 28 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Post Tension | 100 | 70 | 24 | 6 | 18
280 | 1.2.2.2.2.9.2 | Setout and Install Lift/Stair Formwork | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 279SS | 281FS-1d | 28 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Electrician | 100 | 19 | 31 | 15 | 47
281 | 1.2.2.2.2.9.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 280FS-1d | 282FS-1d,283 | 28 September 2024 8:00 AM | 2024-10-05 17:00 | 1 | Site Manager | 100 | 31 | 12 | 42 | 51
282 | 1.2.2.2.2.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 281FS-1d | 284,285 | 4 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Cleaner | 100 | 42 | 28 | 32 | 26
283 | 1.2.2.2.2.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 281 |  | 8 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Admin | 100 | 47 | 10 | 55 | 40
284 | 1.2.2.2.2.9.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Concretor | 100 | 63 | 32 | 3 | 58
285 | 1.2.2.2.2.9.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Mechanical | 100 | 80 | 33 | 84 | 46
286 | 1.2.2.2.2.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 284FS-1d,285FS-1d | 287 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Development Manager | 100 | 99 | 27 | 100 | 60
287 | 1.2.2.2.2.9.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 286 | 288 | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Concretor | 100 | 37 | 21 | 13 | 42
288 | 1.2.2.2.2.9.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 287 | 291,253 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Head Contractor | 100 | 87 | 13 | 86 | 53
289 | 1.2.2.2.2.10 | Strip Formwork - Lvl 6 | 5 | 20 November 2024 8:00 AM | 25 November 2024 5:00 PM | 300FS+8d | 657,471,1686 | 20 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Window | 100 | 26 | 23 | 2 | 29
290 | 1.2.2.2.2.11 | Lvl 7 (Roof) - FRP - Suspended Slab | 18 | 21 October 2024 8:00 AM | 9 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-13 17:00 | 4 | Stone Mason | 100 | 35 | 25 | 64 | 32
291 | 1.2.2.2.2.11.1 | Scaffold Perimeter Protection | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 288 | 292SS | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Surveyor | 100 | 44 | 26 | 32 | 29
292 | 1.2.2.2.2.11.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 291SS | 293FS-1d | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Carpenter | 100 | 23 | 12 | 54 | 58
293 | 1.2.2.2.2.11.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 292FS-1d | 294FS-1d,295 | 21 October 2024 8:00 AM | 2024-10-27 17:00 | 1 | Fire | 100 | 37 | 13 | 35 | 6
294 | 1.2.2.2.2.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293FS-1d | 296,297 | 26 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Foreman | 100 | 78 | 32 | 87 | 51
295 | 1.2.2.2.2.11.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 28 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293 |  | 28 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Plasterboarder | 100 | 96 | 29 | 13 | 42
296 | 1.2.2.2.2.11.6 | Services | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Formworker | 100 | 17 | 19 | 46 | 16
297 | 1.2.2.2.2.11.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Line Market | 100 | 25 | 30 | 95 | 16
298 | 1.2.2.2.2.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 296FS-1d,297FS-1d | 299 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Plasterboarder | 100 | 91 | 18 | 39 | 11
299 | 1.2.2.2.2.11.9 | Formworker setdowns and edge boards | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 298 | 300 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Electrician | 100 | 60 | 22 | 61 | 28
300 | 1.2.2.2.2.11.10 | Pour | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 299 | 303,289FS+8d,301FS+12d,1739FS+24d,265 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Carpenter | 100 | 47 | 13 | 42 | 57
301 | 1.2.2.2.2.12 | Strip Formwork - Lvl 7 | 5 | 25 November 2024 8:00 AM | 29 November 2024 5:00 PM | 300FS+12d | 716,748FS+24d,477,1713 | 25 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Head Contractor | 100 | 73 | 12 | 92 | 46
302 | 1.2.2.2.2.13 | Lift Shaft | 18 | 11 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 11 November 2024 8:00 AM | 2024-12-04 17:00 | 4 | Electrician | 100 | 28 | 12 | 83 | 39
303 | 1.2.2.2.2.13.1 | FRP Lift Over-run | 6 | 11 November 2024 8:00 AM | 16 November 2024 5:00 PM | 300 | 304,277 | 11 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Carpet | 100 | 25 | 12 | 12 | 19
304 | 1.2.2.2.2.13.2 | Strip Lift Shaft Formwork | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 303 | 305 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Waterproofer | 100 | 100 | 10 | 61 | 48
305 | 1.2.2.2.2.13.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 304 | 3452,306 | 22 November 2024 8:00 AM | 2024-12-02 17:00 | 2 | Post Tension | 100 | 30 | 12 | 4 | 34
306 | 1.2.2.2.2.13.4 | Building B Structure Complete | 0 | 30 November 2024 5:00 PM | 30 November 2024 5:00 PM | 305 | 7,6 | 30 November 2024 5:00 PM | 2024-11-30 17:00 | 0 | Electrician | 100 | 15 | 19 | 24 | 31
307 | 1.2.2.2.3 | Building C | 90 | 7 September 2024 8:00 AM | 23 December 2024 5:00 PM |  | 397 | 7 September 2024 8:00 AM | 2024-12-27 17:00 | 4 | Metal Work | 100 | 12 | 25 | 39 | 11
308 | 1.2.2.2.3.1 | Lvl 2 - FRP - Suspended Slab | 17 | 7 September 2024 8:00 AM | 26 September 2024 5:00 PM |  |  | 7 September 2024 8:00 AM | 2024-09-29 17:00 | 3 | Joiner | 100 | 25 | 33 | 86 | 59
309 | 1.2.2.2.3.1.1 | Scaffold Stair Removal/Adjustment | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 135,240FS+30d | 310SS | 7 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Line Market | 100 | 67 | 31 | 25 | 59
310 | 1.2.2.2.3.1.2 | Setout and Install Lift/Stair Formwork | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 309SS | 311 | 7 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Plasterboarder | 100 | 56 | 13 | 4 | 45
311 | 1.2.2.2.3.1.3 | Formworker setout, drop material and 80% Deck | 6 | 9 September 2024 8:00 AM | 14 September 2024 5:00 PM | 310 | 312FS-1d,313,365FS+10d | 9 September 2024 8:00 AM | 2024-09-14 17:00 | 0 | Plasterboarder | 100 | 78 | 29 | 77 | 3
312 | 1.2.2.2.3.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 14 September 2024 8:00 AM | 18 September 2024 5:00 PM | 311FS-1d | 314,315 | 14 September 2024 8:00 AM | 2024-09-18 17:00 | 0 | Excavation | 100 | 12 | 13 | 66 | 25
313 | 1.2.2.2.3.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 311 |  | 16 September 2024 8:00 AM | 2024-09-17 17:00 | 0 | Development Manager | 100 | 31 | 33 | 72 | 21
314 | 1.2.2.2.3.1.6 | Services | 2 | 19 September 2024 8:00 AM | 20 September 2024 5:00 PM | 312 | 316FS-1d | 19 September 2024 8:00 AM | 2024-09-20 17:00 | 0 | Carpet | 100 | 48 | 22 | 4 | 24
315 | 1.2.2.2.3.1.7 | Post Tension | 3 | 19 September 2024 8:00 AM | 21 September 2024 5:00 PM | 312 | 316FS-1d | 19 September 2024 8:00 AM | 2024-09-21 17:00 | 0 | Project Manager | 100 | 13 | 11 | 9 | 49
316 | 1.2.2.2.3.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 314FS-1d,315FS-1d | 317 | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Project Manager | 100 | 18 | 24 | 94 | 28
317 | 1.2.2.2.3.1.9 | Formworker setdowns and edge boards | 2 | 24 September 2024 8:00 AM | 25 September 2024 5:00 PM | 316 | 318 | 24 September 2024 8:00 AM | 2024-09-25 17:00 | 0 | Stone Mason | 100 | 11 | 16 | 64 | 18
318 | 1.2.2.2.3.1.10 | Pour | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 317 | 321 | 26 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Head Contractor | 100 | 75 | 29 | 52 | 48
319 | 1.2.2.2.3.2 | Strip Formwork - Lvl 2 | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 354 | 331FS+5d | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Carpet | 100 | 57 | 31 | 81 | 35
320 | 1.2.2.2.3.3 | Lvl 3 - FRP - Suspended Slab | 17 | 27 September 2024 8:00 AM | 18 October 2024 5:00 PM |  |  | 27 September 2024 8:00 AM | 2024-10-21 17:00 | 3 | Surveyor | 100 | 28 | 17 | 25 | 10
321 | 1.2.2.2.3.3.1 | Scaffold Stair Removal/Adjustment | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 318 | 322SS | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Post Tension | 100 | 42 | 35 | 66 | 28
322 | 1.2.2.2.3.3.2 | Setout and Install Lift/Stair Formwork | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 321SS | 323 | 27 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Timber Floorer | 100 | 10 | 33 | 88 | 5
323 | 1.2.2.2.3.3.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 322 | 324FS-1d,325 | 28 September 2024 8:00 AM | 2024-10-08 17:00 | 4 | Post Tension | 100 | 56 | 31 | 18 | 40
324 | 1.2.2.2.3.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 323FS-1d | 326,327 | 4 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Plasterboarder | 100 | 27 | 33 | 100 | 40
325 | 1.2.2.2.3.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 323 |  | 8 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Formworker | 100 | 89 | 12 | 11 | 50
326 | 1.2.2.2.3.3.6 | Services | 2 | 11 October 2024 8:00 AM | 12 October 2024 5:00 PM | 324 | 328FS-1d | 11 October 2024 8:00 AM | 2024-10-12 17:00 | 0 | Line Market | 100 | 100 | 35 | 91 | 46
327 | 1.2.2.2.3.3.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 324 | 328FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Reinforcement Fixer | 100 | 80 | 23 | 63 | 58
328 | 1.2.2.2.3.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 326FS-1d,327FS-1d | 329 | 14 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Metal Work | 100 | 48 | 31 | 80 | 56
329 | 1.2.2.2.3.3.9 | Formworker setdowns and edge boards | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 328 | 330 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Waterproofer | 100 | 24 | 22 | 11 | 24
330 | 1.2.2.2.3.3.10 | Pour | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 329 | 333 | 18 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Excavation | 100 | 99 | 16 | 69 | 16
331 | 1.2.2.2.3.4 | Strip Formwork - Lvl 3 | 5 | 10 December 2024 8:00 AM | 14 December 2024 5:00 PM | 319FS+5d | 490,1748,2151,1774,2177FS+5d | 10 December 2024 8:00 AM | 2024-12-14 17:00 | 0 | Line Market | 100 | 53 | 10 | 24 | 52
332 | 1.2.2.2.3.5 | Lvl 4 - FRP - Suspended Slab | 17 | 19 October 2024 8:00 AM | 7 November 2024 5:00 PM |  |  | 19 October 2024 8:00 AM | 2024-11-08 17:00 | 1 | Hoarding | 100 | 20 | 20 | 8 | 48
333 | 1.2.2.2.3.5.1 | Scaffold Stair Removal/Adjustment | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 330 | 334SS | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Contract Administrator | 100 | 86 | 10 | 45 | 39
334 | 1.2.2.2.3.5.2 | Setout and Install Lift/Stair Formwork | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 333SS | 335 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Site Manager | 100 | 55 | 27 | 13 | 30
335 | 1.2.2.2.3.5.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 334 | 336FS-1d,337 | 21 October 2024 8:00 AM | 2024-10-29 17:00 | 3 | Cleaner | 100 | 78 | 27 | 31 | 53
336 | 1.2.2.2.3.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 335FS-1d | 338,339 | 26 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Plumber | 100 | 66 | 24 | 13 | 2
337 | 1.2.2.2.3.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 335 |  | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Project Manager | 100 | 37 | 16 | 2 | 25
338 | 1.2.2.2.3.5.6 | Services | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 336 | 340FS-1d | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Concretor | 100 | 54 | 11 | 23 | 48
339 | 1.2.2.2.3.5.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 336 | 340FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Carpenter | 100 | 34 | 30 | 11 | 31
340 | 1.2.2.2.3.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 338FS-1d,339FS-1d | 341 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Head Contractor | 100 | 24 | 22 | 94 | 59
341 | 1.2.2.2.3.5.9 | Formworker setdowns and edge boards | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 340 | 342 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Mechanical | 100 | 20 | 28 | 46 | 30
342 | 1.2.2.2.3.5.10 | Pour | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 341 | 345 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Surveyor | 100 | 13 | 27 | 50 | 2
343 | 1.2.2.2.3.6 | Strip Formwork - Lvl 4 | 5 | 16 December 2024 8:00 AM | 20 December 2024 5:00 PM | 354FS+15d | 495,2648,2674FS+5d | 16 December 2024 8:00 AM | 2024-12-20 17:00 | 0 | Plasterboarder | 100 | 44 | 25 | 20 | 49
344 | 1.2.2.2.3.7 | Lvl 5 (Roof) - FRP - Suspended Slab | 17 | 8 November 2024 8:00 AM | 27 November 2024 5:00 PM |  |  | 8 November 2024 8:00 AM | 2024-11-29 17:00 | 2 | Hoarding | 100 | 41 | 16 | 65 | 59
345 | 1.2.2.2.3.7.1 | Scaffold Stair Removal/Adjustment | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 342 | 346SS | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Waterproofer | 100 | 94 | 20 | 29 | 45
346 | 1.2.2.2.3.7.2 | Setout and Install Lift/Stair Formwork | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 345SS | 347 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Renderer | 100 | 45 | 13 | 45 | 15
347 | 1.2.2.2.3.7.3 | Formworker setout, drop material and 80% Deck | 6 | 9 November 2024 8:00 AM | 15 November 2024 5:00 PM | 346 | 348FS-1d,349 | 9 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Excavation | 100 | 86 | 23 | 90 | 17
348 | 1.2.2.2.3.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 November 2024 8:00 AM | 19 November 2024 5:00 PM | 347FS-1d | 350,351 | 15 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Carpet | 100 | 62 | 31 | 0 | 48
349 | 1.2.2.2.3.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 347 |  | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Timber Floorer | 100 | 50 | 33 | 21 | 58
350 | 1.2.2.2.3.7.6 | Services | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 348 | 352FS-1d | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 100 | 48 | 23 | 91 | 43
351 | 1.2.2.2.3.7.7 | Post Tension | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 348 | 352FS-1d | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Carpet | 100 | 15 | 16 | 45 | 5
352 | 1.2.2.2.3.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 350FS-1d,351FS-1d | 353 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Fire | 100 | 81 | 25 | 7 | 10
353 | 1.2.2.2.3.7.9 | Formworker setdowns and edge boards | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 352 | 354 | 25 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Contract Administrator | 100 | 62 | 14 | 26 | 39
354 | 1.2.2.2.3.7.10 | Pour | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 353 | 357,355FS+12d,343FS+15d,360,319 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Admin | 100 | 90 | 32 | 90 | 5
355 | 1.2.2.2.3.8 | Strip Formwork - Lvl 5 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 354FS+12d | 500,3145,3171FS+5d | 12 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Renderer | 100 | 77 | 28 | 95 | 22
356 | 1.2.2.2.3.9 | Lift Shaft | 22 | 28 November 2024 8:00 AM | 23 December 2024 5:00 PM |  |  | 28 November 2024 8:00 AM | 2024-12-24 17:00 | 1 | Plasterboarder | 100 | 76 | 18 | 87 | 33
357 | 1.2.2.2.3.9.1 | FRP Lift Over-run | 10 | 28 November 2024 8:00 AM | 9 December 2024 5:00 PM | 354 | 358 | 28 November 2024 8:00 AM | 2024-12-13 17:00 | 4 | Plumber | 100 | 87 | 34 | 41 | 50
358 | 1.2.2.2.3.9.2 | Strip Lift Shaft Formwork | 4 | 10 December 2024 8:00 AM | 13 December 2024 5:00 PM | 357 | 359 | 10 December 2024 8:00 AM | 2024-12-13 17:00 | 0 | Project Manager | 100 | 64 | 22 | 33 | 50
359 | 1.2.2.2.3.9.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 14 December 2024 8:00 AM | 23 December 2024 5:00 PM | 358 | 3453,360 | 14 December 2024 8:00 AM | 2024-12-25 17:00 | 2 | Head Contractor | 100 | 79 | 31 | 19 | 15
360 | 1.2.2.2.3.10 | Building C Structure Complete | 0 | 23 December 2024 5:00 PM | 23 December 2024 5:00 PM | 354,359 | 8,7 | 23 December 2024 5:00 PM | 2024-12-23 17:00 | 0 | Excavation | 100 | 42 | 15 | 38 | 18
361 | 1.2.2.2.4 | Building D | 76 | 26 September 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | 26 September 2024 8:00 AM | 2025-01-06 17:00 | 3 | Landscaper | 100 | 21 | 24 | 58 | 35
362 | 1.2.2.2.4.1 | Lvl 2 - FRP - Suspended Slab | 19 | 26 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | 26 September 2024 8:00 AM | 2024-10-23 17:00 | 4 | Joiner | 100 | 75 | 22 | 86 | 50
363 | 1.2.2.2.4.1.1 | Scaffold Stair Removal/Adjustment | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 364SS |  | 26 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Tiler | 100 | 57 | 12 | 77 | 24
364 | 1.2.2.2.4.1.2 | Setout and Install Lift/Stair Formwork | 1 | 26 September 2024 8:00 AM | 27 September 2024 8:00 AM | 365SF | 363SS | 26 September 2024 8:00 AM | 2024-09-27 08:00 | 0 | Fire | 100 | 28 | 15 | 96 | 13
365 | 1.2.2.2.4.1.3 | Formworker setout, drop material and 80% Deck | 6 | 27 September 2024 8:00 AM | 3 October 2024 5:00 PM | 311FS+10d | 366FS-1d,367,364SF | 27 September 2024 8:00 AM | 2024-10-04 17:00 | 1 | Cleaner | 100 | 68 | 23 | 31 | 35
366 | 1.2.2.2.4.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 3 October 2024 8:00 AM | 10 October 2024 5:00 PM | 365FS-1d | 368,369 | 3 October 2024 8:00 AM | 2024-10-10 17:00 | 0 | Joiner | 100 | 54 | 19 | 41 | 54
367 | 1.2.2.2.4.1.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 4 October 2024 8:00 AM | 9 October 2024 5:00 PM | 365 |  | 4 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Head Contractor | 100 | 59 | 15 | 80 | 12
368 | 1.2.2.2.4.1.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Line Market | 100 | 49 | 32 | 36 | 58
369 | 1.2.2.2.4.1.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Admin | 100 | 49 | 26 | 41 | 31
370 | 1.2.2.2.4.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 368FS-1d,369FS-1d | 371 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Formworker | 100 | 82 | 14 | 37 | 43
371 | 1.2.2.2.4.1.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 370 | 372 | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Site Manager | 100 | 83 | 26 | 63 | 13
372 | 1.2.2.2.4.1.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 371 | 375 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Post Tension | 100 | 88 | 25 | 45 | 5
373 | 1.2.2.2.4.2 | Strip Formwork - Lvl 2 | 5 | 21 November 2024 8:00 AM | 26 November 2024 5:00 PM | 384FS+8d | 485,506 | 21 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Tiler | 100 | 100 | 17 | 91 | 44
374 | 1.2.2.2.4.3 | Lvl 3 - FRP - Suspended Slab | 19 | 21 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-16 17:00 | 5 | Timber Floorer | 100 | 38 | 15 | 46 | 60
375 | 1.2.2.2.4.3.1 | Scaffold Stair Removal/Adjustment | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 372 | 376SS | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Foreman | 100 | 88 | 14 | 31 | 6
376 | 1.2.2.2.4.3.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 375SS | 377 | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Project Manager | 100 | 22 | 14 | 84 | 29
377 | 1.2.2.2.4.3.3 | Formworker setout, drop material and 80% Deck | 6 | 22 October 2024 8:00 AM | 28 October 2024 5:00 PM | 376 | 378FS-1d,379 | 22 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Fire | 100 | 18 | 29 | 29 | 52
378 | 1.2.2.2.4.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 377FS-1d | 380,381 | 28 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Contract Administrator | 100 | 24 | 35 | 11 | 26
379 | 1.2.2.2.4.3.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 29 October 2024 8:00 AM | 31 October 2024 5:00 PM | 377 |  | 29 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Formworker | 100 | 54 | 33 | 68 | 59
380 | 1.2.2.2.4.3.6 | Services | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Project Manager | 100 | 25 | 32 | 83 | 57
381 | 1.2.2.2.4.3.7 | Post Tension | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Development Manager | 100 | 13 | 10 | 64 | 18
382 | 1.2.2.2.4.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 5 November 2024 8:00 AM | 7 November 2024 5:00 PM | 380FS-1d,381FS-1d | 383 | 5 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Electrician | 100 | 20 | 28 | 19 | 23
383 | 1.2.2.2.4.3.9 | Formworker setdowns and edge boards | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 382 | 384 | 8 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Electrician | 100 | 63 | 25 | 29 | 19
384 | 1.2.2.2.4.3.10 | Pour | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 383 | 385FS+12d,373FS+8d,387 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Contract Administrator | 100 | 62 | 22 | 84 | 16
385 | 1.2.2.2.4.4 | Strip Formwork - Lvl 3 | 5 | 26 November 2024 8:00 AM | 30 November 2024 5:00 PM | 384FS+12d | 511 | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Plasterboarder | 100 | 62 | 21 | 100 | 9
386 | 1.2.2.2.4.5 | L4 Strucutral Steel Roof | 38 | 12 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 12 November 2024 8:00 AM | 2025-01-08 17:00 | 5 | Electrician | 100 | 77 | 15 | 39 | 7
387 | 1.2.2.2.4.5.1 | Scaffold Perimeter Protection | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 384 | 388SS | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Window | 100 | 52 | 23 | 73 | 38
388 | 1.2.2.2.4.5.2 | Setout | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 387SS | 389 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Metal Work | 100 | 48 | 13 | 47 | 47
389 | 1.2.2.2.4.5.3 | Formworker setout, drop material and 80% Walls | 5 | 14 November 2024 8:00 AM | 19 November 2024 5:00 PM | 388 | 390FS-1d | 14 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Line Market | 100 | 21 | 16 | 11 | 22
390 | 1.2.2.2.4.5.4 | Steel Fixer - Walls | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 389FS-1d | 391 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Cleaner | 100 | 63 | 13 | 28 | 24
391 | 1.2.2.2.4.5.5 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 390 | 392 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Floor Sealer | 100 | 18 | 16 | 48 | 13
392 | 1.2.2.2.4.5.6 | Pour | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 391 | 393 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Renderer | 100 | 13 | 14 | 42 | 34
393 | 1.2.2.2.4.5.7 | Strip Formwork | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 392 | 394 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Carpenter | 100 | 17 | 22 | 28 | 56
394 | 1.2.2.2.4.5.8 | Structural Steel Setout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 393 | 395 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Timber Floorer | 100 | 19 | 10 | 30 | 43
395 | 1.2.2.2.4.5.9 | Install Structural Steel | 8 | 29 November 2024 8:00 AM | 7 December 2024 5:00 PM | 394 | 396 | 29 November 2024 8:00 AM | 2024-12-09 17:00 | 2 | Subcontractor | 100 | 57 | 15 | 78 | 52
396 | 1.2.2.2.4.5.10 | Install Metal Deck Roofing | 15 | 9 December 2024 8:00 AM | 3 January 2025 5:00 PM | 395 | 516,8 | 9 December 2024 8:00 AM | 2025-01-08 17:00 | 5 | Joiner | 100 | 13 | 15 | 19 | 29
397 | 1.2.2.3 | Structural Works Complete | 0 | 3 January 2025 5:00 PM | 3 January 2025 5:00 PM | 120,307,361,91,138,229 |  | 3 January 2025 5:00 PM | 2025-01-03 17:00 | 0 | Subcontractor | 100 | 80 | 10 | 40 | 9
398 | 1.2.3 | FAÇADE WORKS | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | 13 July 2024 8:00 AM | 2025-03-23 17:00 | 1 | Landscaper | 100 | 91 | 30 | 47 | 7
399 | 1.2.3.1 | Building A | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | 13 July 2024 8:00 AM | 2025-03-24 17:00 | 2 | Contract Administrator | 100 | 79 | 31 | 16 | 54
400 | 1.2.3.1.1 | Lvl 1 | 44 | 13 July 2024 8:00 AM | 2 September 2024 5:00 PM |  |  | 13 July 2024 8:00 AM | 2024-09-04 17:00 | 2 | Joiner | 100 | 76 | 30 | 37 | 33
401 | 1.2.3.1.1.1 | Survey & Setout | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 116FS+5d | 402 | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Surveyor | 100 | 27 | 20 | 0 | 53
402 | 1.2.3.1.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 15 July 2024 8:00 AM | 19 July 2024 5:00 PM | 401 | 403 | 15 July 2024 8:00 AM | 2024-07-19 17:00 | 0 | Concretor | 100 | 69 | 29 | 46 | 39
403 | 1.2.3.1.1.3 | Façade & External Walls | 20 | 20 July 2024 8:00 AM | 12 August 2024 5:00 PM | 402 | 404 | 20 July 2024 8:00 AM | 2024-08-17 17:00 | 5 | Cleaner | 100 | 33 | 10 | 87 | 8
404 | 1.2.3.1.1.4 | Windows Install | 18 | 13 August 2024 8:00 AM | 2 September 2024 5:00 PM | 403 | 405,411 | 13 August 2024 8:00 AM | 2024-09-04 17:00 | 2 | Subcontractor | 100 | 96 | 15 | 65 | 15
405 | 1.2.3.1.1.5 | Level 1 Weathertight | 0 | 2 September 2024 5:00 PM | 2 September 2024 5:00 PM | 404 | 558 | 2 September 2024 5:00 PM | 2024-09-02 17:00 | 0 | Electrician | 100 | 91 | 19 | 14 | 34
406 | 1.2.3.1.2 | Lvl 2 | 83 | 17 August 2024 8:00 AM | 23 November 2024 5:00 PM |  |  | 17 August 2024 8:00 AM | 2024-11-24 17:00 | 1 | Concretor | 100 | 23 | 10 | 64 | 51
407 | 1.2.3.1.2.1 | Survey & Setout | 1 | 17 August 2024 8:00 AM | 17 August 2024 5:00 PM | 149FS+5d | 408 | 17 August 2024 8:00 AM | 2024-08-17 17:00 | 0 | Concretor | 100 | 57 | 15 | 97 | 38
408 | 1.2.3.1.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 19 August 2024 8:00 AM | 23 August 2024 5:00 PM | 407 | 577 | 19 August 2024 8:00 AM | 2024-08-23 17:00 | 0 | Reinforcement Fixer | 100 | 67 | 16 | 10 | 3
409 | 1.2.3.1.2.3 | Façade & External Walls | 22 | 9 October 2024 8:00 AM | 2 November 2024 5:00 PM | 150FS-10d | 410 | 9 October 2024 8:00 AM | 2024-11-04 17:00 | 2 | Metal Work | 100 | 98 | 22 | 20 | 50
410 | 1.2.3.1.2.4 | Windows Install | 18 | 4 November 2024 8:00 AM | 23 November 2024 5:00 PM | 409 | 411 | 4 November 2024 8:00 AM | 2024-11-25 17:00 | 2 | Painter | 100 | 77 | 31 | 94 | 37
411 | 1.2.3.1.2.5 | Level 2 Weathertight | 0 | 23 November 2024 5:00 PM | 23 November 2024 5:00 PM | 404,410 | 585 | 23 November 2024 5:00 PM | 2024-11-23 17:00 | 0 | Electrician | 100 | 96 | 27 | 20 | 55
412 | 1.2.3.1.3 | Lvl 3 | 40 | 13 November 2024 8:00 AM | 7 January 2025 5:00 PM |  |  | 13 November 2024 8:00 AM | 2025-01-08 17:00 | 1 | Metal Work | 100 | 59 | 24 | 27 | 46
413 | 1.2.3.1.3.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 174FS+5d | 414FS-1d | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Renderer | 100 | 12 | 10 | 90 | 39
414 | 1.2.3.1.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 413FS-1d |  | 30 November 2024 8:00 AM | 2024-12-04 17:00 | 0 | Tiler | 100 | 91 | 14 | 53 | 19
415 | 1.2.3.1.3.3 | Façade & External Walls | 22 | 13 November 2024 8:00 AM | 7 December 2024 5:00 PM | 174FS-10d | 416 | 13 November 2024 8:00 AM | 2024-12-12 17:00 | 5 | Stone Mason | 100 | 37 | 18 | 39 | 29
416 | 1.2.3.1.3.4 | Windows Install | 18 | 9 December 2024 8:00 AM | 7 January 2025 5:00 PM | 415 | 610FS-6d,417 | 9 December 2024 8:00 AM | 2025-01-07 17:00 | 0 | Excavation | 100 | 34 | 14 | 73 | 27
417 | 1.2.3.1.3.5 | Level 3 Weathertight | 0 | 7 January 2025 5:00 PM | 7 January 2025 5:00 PM | 416 | 612,444 | 7 January 2025 5:00 PM | 2025-01-07 17:00 | 0 | Waterproofer | 100 | 96 | 19 | 62 | 46
418 | 1.2.3.1.4 | Lvl 4 | 44 | 17 December 2024 8:00 AM | 15 February 2025 5:00 PM |  |  | 17 December 2024 8:00 AM | 2025-02-17 17:00 | 2 | Site Manager | 100 | 74 | 12 | 20 | 55
419 | 1.2.3.1.4.1 | Survey & Setout | 1 | 17 December 2024 8:00 AM | 17 December 2024 5:00 PM | 186FS+5d | 420FS-1d | 17 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Waterproofer | 100 | 67 | 22 | 67 | 7
420 | 1.2.3.1.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 17 December 2024 8:00 AM | 20 December 2024 5:00 PM | 419FS-1d | 421 | 17 December 2024 8:00 AM | 2024-12-20 17:00 | 0 | Project Manager | 100 | 29 | 14 | 43 | 31
421 | 1.2.3.1.4.3 | Façade & External Walls | 22 | 21 December 2024 8:00 AM | 24 January 2025 5:00 PM | 186FS-10d,420 | 422 | 21 December 2024 8:00 AM | 2025-01-24 17:00 | 0 | Mechanical | 100 | 14 | 33 | 78 | 2
422 | 1.2.3.1.4.4 | Windows Install | 18 | 27 January 2025 8:00 AM | 15 February 2025 5:00 PM | 421 | 637FS-6d,423 | 27 January 2025 8:00 AM | 2025-02-19 17:00 | 4 | Plasterboarder | 100 | 66 | 11 | 41 | 13
423 | 1.2.3.1.4.5 | Level 4 Weathertight | 0 | 15 February 2025 5:00 PM | 15 February 2025 5:00 PM | 422 | 639,444 | 15 February 2025 5:00 PM | 2025-02-15 17:00 | 0 | Landscaper | 100 | 83 | 33 | 19 | 8
424 | 1.2.3.1.5 | Lvl 5 | 40 | 30 November 2024 8:00 AM | 24 January 2025 5:00 PM |  |  | 30 November 2024 8:00 AM | 2025-01-24 17:00 | 0 | Electrician | 100 | 98 | 28 | 100 | 16
425 | 1.2.3.1.5.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 198FS+5d | 426FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Contract Administrator | 100 | 40 | 14 | 30 | 12
426 | 1.2.3.1.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 425FS-1d | 663 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Stone Mason | 100 | 19 | 21 | 28 | 56
427 | 1.2.3.1.5.3 | Façade & External Walls | 22 | 30 November 2024 8:00 AM | 3 January 2025 5:00 PM | 198FS-10d | 428 | 30 November 2024 8:00 AM | 2025-01-04 17:00 | 1 | Site Manager | 100 | 67 | 31 | 12 | 56
428 | 1.2.3.1.5.4 | Windows Install | 18 | 4 January 2025 8:00 AM | 24 January 2025 5:00 PM | 427 | 669FS-6d,429,444 | 4 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Surveyor | 100 | 61 | 19 | 96 | 54
429 | 1.2.3.1.5.5 | Level 5 Weathertight | 0 | 24 January 2025 5:00 PM | 24 January 2025 5:00 PM | 428 | 671 | 24 January 2025 5:00 PM | 2025-01-24 17:00 | 0 | Timber Floorer | 100 | 21 | 14 | 65 | 18
430 | 1.2.3.1.6 | Lvl 6 | 59 | 19 November 2024 8:00 AM | 5 February 2025 5:00 PM |  |  | 19 November 2024 8:00 AM | 2025-02-10 17:00 | 5 | Timber Floorer | 100 | 75 | 31 | 91 | 33
431 | 1.2.3.1.6.1 | Survey & Setout | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 209FS+5d | 432 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Admin | 100 | 80 | 18 | 56 | 36
432 | 1.2.3.1.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 6 December 2024 8:00 AM | 10 December 2024 5:00 PM | 210FS-10d,431 | 433,690 | 6 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Tiler | 100 | 17 | 15 | 95 | 46
433 | 1.2.3.1.6.3 | Façade & External Walls | 22 | 11 December 2024 8:00 AM | 14 January 2025 5:00 PM | 432 | 434 | 11 December 2024 8:00 AM | 2025-01-15 17:00 | 1 | Scaffolder | 100 | 96 | 35 | 91 | 32
434 | 1.2.3.1.6.4 | Windows Install | 18 | 15 January 2025 8:00 AM | 5 February 2025 5:00 PM | 433 | 696FS-6d,435 | 15 January 2025 8:00 AM | 2025-02-06 17:00 | 1 | Contract Administrator | 100 | 87 | 15 | 50 | 22
435 | 1.2.3.1.6.5 | Level 6 Weathertight | 0 | 5 February 2025 5:00 PM | 5 February 2025 5:00 PM | 434 | 698,444 | 5 February 2025 5:00 PM | 2025-02-05 17:00 | 0 | Floor Sealer | 100 | 79 | 32 | 11 | 36
436 | 1.2.3.1.7 | Lvl 7 | 59 | 5 December 2024 8:00 AM | 21 February 2025 5:00 PM |  |  | 5 December 2024 8:00 AM | 2025-02-26 17:00 | 5 | Post Tension | 100 | 27 | 26 | 42 | 43
437 | 1.2.3.1.7.1 | Survey & Setout | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 221FS+5d | 438FS-1d | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Metal Work | 100 | 26 | 27 | 61 | 28
438 | 1.2.3.1.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 5 December 2024 8:00 AM | 9 December 2024 5:00 PM | 437FS-1d | 722 | 5 December 2024 8:00 AM | 2024-12-09 17:00 | 0 | Metal Work | 100 | 94 | 31 | 77 | 46
439 | 1.2.3.1.7.3 | Façade & External Walls | 22 | 8 January 2025 8:00 AM | 3 February 2025 5:00 PM | 223FS+10d | 440 | 8 January 2025 8:00 AM | 2025-02-06 17:00 | 3 | Plasterboarder | 100 | 74 | 29 | 65 | 40
440 | 1.2.3.1.7.4 | Windows Install | 16 | 4 February 2025 8:00 AM | 21 February 2025 5:00 PM | 439 | 728FS-6d,441,3446FS-5d | 4 February 2025 8:00 AM | 2025-02-21 17:00 | 0 | Tiler | 100 | 51 | 20 | 13 | 53
441 | 1.2.3.1.7.5 | Level 7 Weathertight | 0 | 21 February 2025 5:00 PM | 21 February 2025 5:00 PM | 440 | 730,442 | 21 February 2025 5:00 PM | 2025-02-21 17:00 | 0 | Floor Sealer | 100 | 82 | 28 | 52 | 10
442 | 1.2.3.1.8 | Defect Rectification | 15 | 22 February 2025 8:00 AM | 11 March 2025 5:00 PM | 441 | 443 | 22 February 2025 8:00 AM | 2025-03-14 17:00 | 3 | Subcontractor | 100 | 53 | 17 | 30 | 56
443 | 1.2.3.1.9 | Strip Scaffold | 10 | 12 March 2025 8:00 AM | 22 March 2025 5:00 PM | 442 | 444,3456 | 12 March 2025 8:00 AM | 2025-03-25 17:00 | 3 | Reinforcement Fixer | 100 | 74 | 19 | 1 | 11
444 | 1.2.3.1.10 | Building A Façade Complete | 0 | 22 March 2025 5:00 PM | 22 March 2025 5:00 PM | 443,435,428,423,417 | 5 | 22 March 2025 5:00 PM | 2025-03-22 17:00 | 0 | Electrician | 100 | 38 | 11 | 61 | 40
445 | 1.2.3.2 | Building B | 89 | 4 October 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | 4 October 2024 8:00 AM | 2025-02-01 17:00 | 4 | Admin | 100 | 45 | 27 | 52 | 17
446 | 1.2.3.2.1 | Lvl 1 | 44 | 4 October 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 4 October 2024 8:00 AM | 2024-11-30 17:00 | 4 | Window | 100 | 62 | 25 | 58 | 11
447 | 1.2.3.2.1.1 | Survey & Setout | 1 | 4 October 2024 8:00 AM | 4 October 2024 5:00 PM | 241 | 448 | 4 October 2024 8:00 AM | 2024-10-04 17:00 | 0 | Window | 100 | 48 | 20 | 10 | 2
448 | 1.2.3.2.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 8 October 2024 8:00 AM | 12 October 2024 5:00 PM | 447 | 449,758,852,1322FS+6d,1510FS+6d,1416FS+6d,946FS+2d,1040FS+2d,1134FS+4d,1228FS+4d | 8 October 2024 8:00 AM | 2024-10-12 17:00 | 0 | Reinforcement Fixer | 100 | 39 | 11 | 83 | 58
449 | 1.2.3.2.1.3 | Façade & External Walls | 20 | 14 October 2024 8:00 AM | 5 November 2024 5:00 PM | 448 | 450 | 14 October 2024 8:00 AM | 2024-11-10 17:00 | 5 | Project Manager | 100 | 87 | 23 | 59 | 30
450 | 1.2.3.2.1.4 | Windows Install | 18 | 6 November 2024 8:00 AM | 26 November 2024 5:00 PM | 449 | 451 | 6 November 2024 8:00 AM | 2024-11-29 17:00 | 3 | Plumber | 100 | 89 | 22 | 82 | 38
451 | 1.2.3.2.1.5 | Level 1 Weathertight | 0 | 26 November 2024 5:00 PM | 26 November 2024 5:00 PM | 450 | 1640 | 26 November 2024 5:00 PM | 2024-11-26 17:00 | 0 | Electrician | 100 | 75 | 13 | 15 | 59
452 | 1.2.3.2.2 | Lvl 2 | 42 | 26 October 2024 8:00 AM | 13 December 2024 5:00 PM |  |  | 26 October 2024 8:00 AM | 2024-12-14 17:00 | 1 | Concretor | 100 | 31 | 28 | 24 | 10
453 | 1.2.3.2.2.1 | Survey & Setout | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 253 | 454 | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Window | 100 | 33 | 31 | 79 | 40
454 | 1.2.3.2.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 453 | 455 | 28 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Head Contractor | 100 | 16 | 10 | 12 | 59
455 | 1.2.3.2.2.3 | Façade & External Walls | 20 | 2 November 2024 8:00 AM | 25 November 2024 5:00 PM | 454 | 456 | 2 November 2024 8:00 AM | 2024-11-29 17:00 | 4 | Painter | 100 | 10 | 29 | 31 | 8
456 | 1.2.3.2.2.4 | Windows Install | 16 | 26 November 2024 8:00 AM | 13 December 2024 5:00 PM | 455 | 457 | 26 November 2024 8:00 AM | 2024-12-17 17:00 | 4 | Mechanical | 100 | 98 | 30 | 18 | 36
457 | 1.2.3.2.2.5 | Level 2 Weathertight | 0 | 13 December 2024 5:00 PM | 13 December 2024 5:00 PM | 456 |  | 13 December 2024 5:00 PM | 2024-12-13 17:00 | 0 | Excavation | 100 | 64 | 29 | 0 | 22
458 | 1.2.3.2.3 | Lvl 3 | 43 | 16 November 2024 8:00 AM | 14 January 2025 5:00 PM |  |  | 16 November 2024 8:00 AM | 2025-01-15 17:00 | 1 | Renderer | 100 | 61 | 35 | 2 | 14
459 | 1.2.3.2.3.1 | Survey & Setout | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 265 | 460 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Joiner | 100 | 82 | 35 | 42 | 13
460 | 1.2.3.2.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 459 | 461 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 100 | 73 | 11 | 23 | 51
461 | 1.2.3.2.3.3 | Façade & External Walls | 20 | 22 November 2024 8:00 AM | 14 December 2024 5:00 PM | 460 | 462 | 22 November 2024 8:00 AM | 2024-12-15 17:00 | 1 | Contract Administrator | 100 | 10 | 27 | 47 | 3
462 | 1.2.3.2.3.4 | Windows Install | 18 | 16 December 2024 8:00 AM | 14 January 2025 5:00 PM | 461 | 1638FS-6d,463 | 16 December 2024 8:00 AM | 2025-01-19 17:00 | 5 | Reinforcement Fixer | 100 | 56 | 20 | 94 | 39
463 | 1.2.3.2.3.5 | Level 3 Weathertight | 0 | 14 January 2025 5:00 PM | 14 January 2025 5:00 PM | 462 | 1640 | 14 January 2025 5:00 PM | 2025-01-14 17:00 | 0 | Admin | 100 | 88 | 34 | 32 | 37
464 | 1.2.3.2.4 | Lvl 4 | 42 | 23 November 2024 8:00 AM | 20 January 2025 5:00 PM |  |  | 23 November 2024 8:00 AM | 2025-01-23 17:00 | 3 | Formworker | 100 | 10 | 28 | 85 | 56
465 | 1.2.3.2.4.1 | Survey & Setout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 277 | 466FS-1d | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Metal Work | 100 | 67 | 10 | 83 | 24
466 | 1.2.3.2.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 23 November 2024 8:00 AM | 27 November 2024 5:00 PM | 465FS-1d | 467 | 23 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Landscaper | 100 | 16 | 28 | 32 | 10
467 | 1.2.3.2.4.3 | Façade & External Walls | 20 | 28 November 2024 8:00 AM | 20 December 2024 5:00 PM | 466 | 468 | 28 November 2024 8:00 AM | 2024-12-24 17:00 | 4 | Line Market | 100 | 82 | 15 | 4 | 34
468 | 1.2.3.2.4.4 | Windows Install | 18 | 21 December 2024 8:00 AM | 20 January 2025 5:00 PM | 467 | 1665FS-6d,469 | 21 December 2024 8:00 AM | 2025-01-24 17:00 | 4 | Landscaper | 100 | 84 | 31 | 84 | 37
469 | 1.2.3.2.4.5 | Level 4 Weathertight | 0 | 20 January 2025 5:00 PM | 20 January 2025 5:00 PM | 468 | 1665FS-6d | 20 January 2025 5:00 PM | 2025-01-20 17:00 | 0 | Carpet | 100 | 64 | 17 | 59 | 54
470 | 1.2.3.2.5 | Lvl 5 | 42 | 26 November 2024 8:00 AM | 22 January 2025 5:00 PM |  |  | 26 November 2024 8:00 AM | 2025-01-26 17:00 | 4 | Head Contractor | 100 | 18 | 13 | 15 | 57
471 | 1.2.3.2.5.1 | Survey & Setout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 289 | 472FS-1d | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Subcontractor | 100 | 73 | 18 | 44 | 21
472 | 1.2.3.2.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 26 November 2024 8:00 AM | 29 November 2024 5:00 PM | 471FS-1d | 473 | 26 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Window | 100 | 33 | 16 | 0 | 18
473 | 1.2.3.2.5.3 | Façade & External Walls | 20 | 30 November 2024 8:00 AM | 23 December 2024 5:00 PM | 472 | 474 | 30 November 2024 8:00 AM | 2024-12-28 17:00 | 5 | Timber Floorer | 100 | 100 | 35 | 16 | 11
474 | 1.2.3.2.5.4 | Windows Install | 18 | 24 December 2024 8:00 AM | 22 January 2025 5:00 PM | 473 | 475 | 24 December 2024 8:00 AM | 2025-01-27 17:00 | 5 | Surveyor | 100 | 94 | 16 | 53 | 13
475 | 1.2.3.2.5.5 | Level 5 Weathertight | 0 | 22 January 2025 5:00 PM | 22 January 2025 5:00 PM | 474 | 1692FS-4d | 22 January 2025 5:00 PM | 2025-01-22 17:00 | 0 | Foreman | 100 | 67 | 33 | 38 | 8
476 | 1.2.3.2.6 | Lvl 6 | 42 | 30 November 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | 30 November 2024 8:00 AM | 2025-01-28 17:00 | 0 | Renderer | 100 | 37 | 25 | 13 | 3
477 | 1.2.3.2.6.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 301 | 478FS-1d | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Concretor | 100 | 77 | 27 | 46 | 8
478 | 1.2.3.2.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 477FS-1d | 479 | 30 November 2024 8:00 AM | 2024-12-04 17:00 | 0 | Fire | 100 | 57 | 14 | 10 | 17
479 | 1.2.3.2.6.3 | Façade & External Walls | 20 | 5 December 2024 8:00 AM | 6 January 2025 5:00 PM | 478 | 480 | 5 December 2024 8:00 AM | 2025-01-10 17:00 | 4 | Window | 100 | 26 | 30 | 99 | 52
480 | 1.2.3.2.6.4 | Windows Install | 18 | 7 January 2025 8:00 AM | 28 January 2025 5:00 PM | 479 | 481 | 7 January 2025 8:00 AM | 2025-01-29 17:00 | 1 | Painter | 100 | 46 | 22 | 90 | 44
481 | 1.2.3.2.6.5 | Level 6 Weathertight | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 480 | 1719FS-6d,482 | 28 January 2025 5:00 PM | 2025-01-28 17:00 | 0 | Excavation | 100 | 63 | 14 | 80 | 9
482 | 1.2.3.2.6.6 | Building B Façade Complete | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 481 | 6 | 28 January 2025 5:00 PM | 2025-01-28 17:00 | 0 | Landscaper | 100 | 59 | 23 | 12 | 56
483 | 1.2.3.3 | Building C | 63 | 27 November 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-02-21 17:00 | 3 | Formworker | 100 | 52 | 24 | 76 | 2
484 | 1.2.3.3.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-01-28 17:00 | 1 | Site Manager | 100 | 51 | 22 | 13 | 7
485 | 1.2.3.3.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 486 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Timber Floorer | 100 | 30 | 24 | 84 | 51
486 | 1.2.3.3.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 485 | 487 | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Timber Floorer | 100 | 68 | 32 | 57 | 34
487 | 1.2.3.3.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 486 | 488 | 4 December 2024 8:00 AM | 2025-01-06 17:00 | 2 | Joiner | 100 | 75 | 21 | 52 | 7
488 | 1.2.3.3.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 487 |  | 6 January 2025 8:00 AM | 2025-02-01 17:00 | 5 | Floor Sealer | 100 | 27 | 21 | 33 | 29
489 | 1.2.3.3.2 | Lvl 2 | 44 | 16 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | 16 December 2024 8:00 AM | 2025-02-14 17:00 | 0 | Project Manager | 100 | 40 | 22 | 72 | 57
490 | 1.2.3.3.2.1 | Survey & Setout | 1 | 16 December 2024 8:00 AM | 16 December 2024 5:00 PM | 331 | 491 | 16 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Hoarding | 100 | 46 | 20 | 49 | 11
491 | 1.2.3.3.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 17 December 2024 8:00 AM | 21 December 2024 5:00 PM | 490 | 492 | 17 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Electrician | 100 | 55 | 31 | 23 | 14
492 | 1.2.3.3.2.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 491 | 493 | 23 December 2024 8:00 AM | 2025-01-26 17:00 | 3 | Tiler | 100 | 49 | 27 | 33 | 47
493 | 1.2.3.3.2.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 492 |  | 24 January 2025 8:00 AM | 2025-02-15 17:00 | 1 | Window | 100 | 35 | 35 | 100 | 52
494 | 1.2.3.3.3 | Lvl 3 | 42 | 21 December 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | 21 December 2024 8:00 AM | 2025-02-22 17:00 | 4 | Waterproofer | 100 | 66 | 14 | 80 | 32
495 | 1.2.3.3.3.1 | Survey & Setout | 1 | 21 December 2024 8:00 AM | 21 December 2024 5:00 PM | 343 | 496FS-1d | 21 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Excavation | 100 | 50 | 14 | 72 | 14
496 | 1.2.3.3.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 21 December 2024 8:00 AM | 3 January 2025 5:00 PM | 495FS-1d | 497 | 21 December 2024 8:00 AM | 2025-01-03 17:00 | 0 | Stone Mason | 100 | 90 | 22 | 53 | 3
497 | 1.2.3.3.3.3 | Façade & External Walls | 20 | 4 January 2025 8:00 AM | 28 January 2025 5:00 PM | 496 | 498 | 4 January 2025 8:00 AM | 2025-01-30 17:00 | 2 | Waterproofer | 100 | 12 | 29 | 40 | 4
498 | 1.2.3.3.3.4 | Windows Install | 18 | 29 January 2025 8:00 AM | 18 February 2025 5:00 PM | 497 | 2654FS-6d | 29 January 2025 8:00 AM | 2025-02-20 17:00 | 2 | Tiler | 100 | 82 | 24 | 98 | 38
499 | 1.2.3.3.4 | Lvl 4 | 42 | 18 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-02-18 17:00 | 4 | Admin | 100 | 56 | 13 | 19 | 58
500 | 1.2.3.3.4.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 355 | 501FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Carpenter | 100 | 80 | 33 | 92 | 50
501 | 1.2.3.3.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 500FS-1d | 502 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Timber Floorer | 100 | 17 | 33 | 94 | 51
502 | 1.2.3.3.4.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 501 | 503 | 23 December 2024 8:00 AM | 2025-01-26 17:00 | 3 | Development Manager | 100 | 56 | 35 | 78 | 59
503 | 1.2.3.3.4.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 502 | 3151FS-6d,7 | 24 January 2025 8:00 AM | 2025-02-15 17:00 | 1 | Cleaner | 100 | 10 | 26 | 50 | 22
504 | 1.2.3.4 | Building D | 62 | 27 November 2024 8:00 AM | 17 February 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-02-17 17:00 | 0 | Landscaper | 100 | 67 | 12 | 11 | 54
505 | 1.2.3.4.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-01-29 17:00 | 2 | Electrician | 100 | 74 | 21 | 86 | 30
506 | 1.2.3.4.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 507 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Mechanical | 100 | 66 | 24 | 83 | 49
507 | 1.2.3.4.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 506 | 508,3361 | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Stone Mason | 100 | 76 | 13 | 96 | 10
508 | 1.2.3.4.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 507 | 509 | 4 December 2024 8:00 AM | 2025-01-05 17:00 | 1 | Electrician | 100 | 66 | 16 | 70 | 26
509 | 1.2.3.4.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 508 |  | 6 January 2025 8:00 AM | 2025-01-30 17:00 | 3 | Tiler | 100 | 14 | 19 | 78 | 58
510 | 1.2.3.4.2 | Lvl 2 | 44 | 2 December 2024 8:00 AM | 31 January 2025 5:00 PM |  |  | 2 December 2024 8:00 AM | 2025-02-05 17:00 | 5 | Admin | 100 | 20 | 30 | 80 | 28
511 | 1.2.3.4.2.1 | Survey & Setout | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 385 | 512 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Cleaner | 100 | 18 | 11 | 72 | 41
512 | 1.2.3.4.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 3 December 2024 8:00 AM | 7 December 2024 5:00 PM | 511 | 513,3388 | 3 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Tiler | 100 | 21 | 11 | 94 | 35
513 | 1.2.3.4.2.3 | Façade & External Walls | 20 | 9 December 2024 8:00 AM | 9 January 2025 5:00 PM | 512 | 514 | 9 December 2024 8:00 AM | 2025-01-13 17:00 | 4 | Subcontractor | 100 | 67 | 16 | 12 | 3
514 | 1.2.3.4.2.4 | Windows Install | 18 | 10 January 2025 8:00 AM | 31 January 2025 5:00 PM | 513 |  | 10 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Mechanical | 100 | 91 | 20 | 6 | 26
515 | 1.2.3.4.3 | Lvl 3 | 37 | 4 January 2025 8:00 AM | 17 February 2025 5:00 PM |  |  | 4 January 2025 8:00 AM | 2025-02-20 17:00 | 3 | Fire | 100 | 49 | 16 | 38 | 19
516 | 1.2.3.4.3.1 | Survey & Setout | 1 | 4 January 2025 8:00 AM | 4 January 2025 5:00 PM | 396 | 517FS-1d | 4 January 2025 8:00 AM | 2025-01-04 17:00 | 0 | Development Manager | 100 | 44 | 15 | 71 | 31
517 | 1.2.3.4.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 3 | 4 January 2025 8:00 AM | 7 January 2025 5:00 PM | 516FS-1d | 518,3415 | 4 January 2025 8:00 AM | 2025-01-07 17:00 | 0 | Hoarding | 100 | 47 | 28 | 91 | 6
518 | 1.2.3.4.3.3 | Façade & External Walls | 18 | 8 January 2025 8:00 AM | 29 January 2025 5:00 PM | 517 | 519 | 8 January 2025 8:00 AM | 2025-01-31 17:00 | 2 | Excavation | 100 | 71 | 16 | 93 | 52
519 | 1.2.3.4.3.4 | Windows Install | 16 | 30 January 2025 8:00 AM | 17 February 2025 5:00 PM | 518 | 3421FS-6d,8 | 30 January 2025 8:00 AM | 2025-02-17 17:00 | 0 | Carpenter | 100 | 85 | 28 | 29 | 43
520 | 1.2.4 | FIT-OUT WORKS | 185 | 13 September 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 13 September 2024 8:00 AM | 2025-05-06 17:00 | 1 | Hoarding | 100 | 11 | 17 | 61 | 51
521 | 1.2.4.1 | Basement 2 - Services & Fitoff | 140 | 13 September 2024 8:00 AM | 7 March 2025 5:00 PM |  |  | 13 September 2024 8:00 AM | 2025-03-12 17:00 | 5 | Landscaper | 100 | 43 | 27 | 67 | 13
522 | 1.2.4.1.1 | Services rough in | 60 | 13 September 2024 8:00 AM | 23 November 2024 5:00 PM | 107 | 523 | 13 September 2024 8:00 AM | 2024-11-23 17:00 | 0 | Plumber | 100 | 58 | 33 | 81 | 31
523 | 1.2.4.1.2 | Block walls (Metal Door Frames) | 6 | 25 November 2024 8:00 AM | 30 November 2024 5:00 PM | 522 | 524,525 | 25 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Window | 100 | 57 | 31 | 65 | 10
524 | 1.2.4.1.3 | Render works as specified | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 527 | 2 December 2024 8:00 AM | 2024-12-19 17:00 | 5 | Reinforcement Fixer | 100 | 39 | 27 | 92 | 16
525 | 1.2.4.1.4 | Carpentry fitoff | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 526 | 2 December 2024 8:00 AM | 2024-12-18 17:00 | 4 | Painter | 100 | 79 | 13 | 2 | 50
526 | 1.2.4.1.5 | Services Plant & Equipment Install | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 525 |  | 16 December 2024 8:00 AM | 2025-01-11 17:00 | 4 | Post Tension | 100 | 54 | 24 | 59 | 3
527 | 1.2.4.1.6 | Doors & Hardware | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 524 | 528 | 16 December 2024 8:00 AM | 2025-01-11 17:00 | 4 | Carpet | 100 | 34 | 34 | 93 | 12
528 | 1.2.4.1.7 | Services Fitoff | 12 | 8 January 2025 8:00 AM | 21 January 2025 5:00 PM | 527 | 529 | 8 January 2025 8:00 AM | 2025-01-25 17:00 | 4 | Carpet | 100 | 11 | 35 | 69 | 33
529 | 1.2.4.1.8 | Finishes & Painting | 12 | 22 January 2025 8:00 AM | 5 February 2025 5:00 PM | 528 | 530 | 22 January 2025 8:00 AM | 2025-02-07 17:00 | 2 | Carpet | 100 | 81 | 23 | 76 | 58
530 | 1.2.4.1.9 | Metalwork Items | 8 | 6 February 2025 8:00 AM | 14 February 2025 5:00 PM | 529 | 531 | 6 February 2025 8:00 AM | 2025-02-19 17:00 | 5 | Carpet | 100 | 27 | 26 | 22 | 18
531 | 1.2.4.1.10 | Builders Clean | 6 | 15 February 2025 8:00 AM | 21 February 2025 5:00 PM | 530 | 532 | 15 February 2025 8:00 AM | 2025-02-22 17:00 | 1 | Painter | 100 | 61 | 20 | 60 | 9
532 | 1.2.4.1.11 | Car Park Clean, Patch and Floor Sealer | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 531 | 533 | 22 February 2025 8:00 AM | 2025-03-04 17:00 | 1 | Waterproofer | 100 | 72 | 31 | 23 | 38
533 | 1.2.4.1.12 | Line Marking | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 532 |  | 4 March 2025 8:00 AM | 2025-03-07 17:00 | 0 | Excavation | 100 | 93 | 31 | 3 | 27
534 | 1.2.4.2 | Basement 1 - Services & Fitoff | 140 | 1 October 2024 8:00 AM | 25 March 2025 5:00 PM |  |  | 1 October 2024 8:00 AM | 2025-03-29 17:00 | 4 | Painter | 100 | 47 | 22 | 79 | 3
535 | 1.2.4.2.1 | Services rough in | 60 | 1 October 2024 8:00 AM | 11 December 2024 5:00 PM | 119 | 536 | 1 October 2024 8:00 AM | 2024-12-11 17:00 | 0 | Electrician | 100 | 89 | 18 | 24 | 34
536 | 1.2.4.2.2 | Block walls (Metal Door Frames) | 6 | 12 December 2024 8:00 AM | 18 December 2024 5:00 PM | 535 | 537,538 | 12 December 2024 8:00 AM | 2024-12-20 17:00 | 2 | Plasterboarder | 100 | 81 | 24 | 44 | 31
537 | 1.2.4.2.3 | Render works as specified | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 540 | 19 December 2024 8:00 AM | 2025-01-13 17:00 | 3 | Carpet | 100 | 40 | 20 | 22 | 15
538 | 1.2.4.2.4 | Carpentry fitoff | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 539 | 19 December 2024 8:00 AM | 2025-01-14 17:00 | 4 | Timber Floorer | 100 | 46 | 22 | 0 | 41
539 | 1.2.4.2.5 | Services Plant & Equipment Install | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 538 |  | 11 January 2025 8:00 AM | 2025-01-27 17:00 | 3 | Subcontractor | 100 | 67 | 16 | 77 | 36
540 | 1.2.4.2.6 | Doors & Hardware | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 537 | 541 | 11 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Joiner | 100 | 83 | 32 | 11 | 27
541 | 1.2.4.2.7 | Services Fitoff | 12 | 27 January 2025 8:00 AM | 8 February 2025 5:00 PM | 540 | 542 | 27 January 2025 8:00 AM | 2025-02-11 17:00 | 3 | Hoarding | 100 | 92 | 14 | 63 | 43
542 | 1.2.4.2.8 | Finishes & Painting | 12 | 10 February 2025 8:00 AM | 22 February 2025 5:00 PM | 541 | 543 | 10 February 2025 8:00 AM | 2025-02-27 17:00 | 5 | Head Contractor | 100 | 59 | 22 | 30 | 11
543 | 1.2.4.2.9 | Metalwork Items | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 542 | 544 | 24 February 2025 8:00 AM | 2025-03-05 17:00 | 1 | Concretor | 100 | 100 | 19 | 7 | 53
544 | 1.2.4.2.10 | Builders Clean | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 543 | 545 | 5 March 2025 8:00 AM | 2025-03-13 17:00 | 2 | Reinforcement Fixer | 100 | 99 | 33 | 94 | 29
545 | 1.2.4.2.11 | Car Park Clean, Patch and Floor Sealer | 8 | 12 March 2025 8:00 AM | 20 March 2025 5:00 PM | 544 | 546 | 12 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Concretor | 100 | 93 | 33 | 72 | 28
546 | 1.2.4.2.12 | Line Marking | 4 | 21 March 2025 8:00 AM | 25 March 2025 5:00 PM | 545 |  | 21 March 2025 8:00 AM | 2025-03-25 17:00 | 0 | Electrician | 100 | 67 | 20 | 100 | 35
547 | 1.2.4.3 | Building A | 155 | 21 October 2024 8:00 AM | 5 May 2025 5:00 PM |  | 3440 | 21 October 2024 8:00 AM | 2025-05-10 17:00 | 5 | Tiler | 100 | 83 | 19 | 61 | 32
548 | 1.2.4.3.1 | Lvl 1 - Services & Finishes | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-14 17:00 | 1 | Metal Work | 100 | 73 | 13 | 48 | 17
549 | 1.2.4.3.1.1 | Internal Works | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-15 17:00 | 2 | Scaffolder | 100 | 83 | 34 | 44 | 35
550 | 1.2.4.3.1.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 150 | 551FS-2d | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Site Manager | 100 | 59 | 35 | 31 | 51
551 | 1.2.4.3.1.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 550FS-2d | 552 | 21 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Landscaper | 100 | 75 | 12 | 67 | 49
552 | 1.2.4.3.1.1.3 | Internal Wall Framing | 10 | 1 November 2024 8:00 AM | 12 November 2024 5:00 PM | 551 | 554,553 | 1 November 2024 8:00 AM | 2024-11-16 17:00 | 4 | Floor Sealer | 100 | 22 | 22 | 76 | 45
553 | 1.2.4.3.1.1.4 | Sheet one side of walls | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 556,555 | 13 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Excavation | 100 | 53 | 28 | 29 | 24
554 | 1.2.4.3.1.1.5 | Service Rough-In | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 555 | 13 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Cleaner | 100 | 47 | 28 | 97 | 26
555 | 1.2.4.3.1.1.6 | ITP for services in the walls | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 553,554 | 556,562 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Reinforcement Fixer | 100 | 73 | 29 | 73 | 42
556 | 1.2.4.3.1.1.7 | Sheet other side of walls | 8 | 25 November 2024 8:00 AM | 3 December 2024 5:00 PM | 553,555 | 557 | 25 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Stone Mason | 100 | 70 | 15 | 12 | 40
557 | 1.2.4.3.1.1.8 | Frame & Sheet Ceilings | 8 | 4 December 2024 8:00 AM | 12 December 2024 5:00 PM | 556 | 558 | 4 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Excavation | 100 | 76 | 34 | 73 | 3
558 | 1.2.4.3.1.1.9 | Sheet, Set & Sand Ceilings | 8 | 13 December 2024 8:00 AM | 21 December 2024 5:00 PM | 557,405 | 559 | 13 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Formworker | 100 | 51 | 27 | 13 | 4
559 | 1.2.4.3.1.1.10 | Paint undercoat | 4 | 23 December 2024 8:00 AM | 4 January 2025 5:00 PM | 558 | 560 | 23 December 2024 8:00 AM | 2025-01-04 17:00 | 0 | Window | 100 | 84 | 27 | 82 | 10
560 | 1.2.4.3.1.1.11 | Floor Levelling and Floor Finish | 6 | 6 January 2025 8:00 AM | 11 January 2025 5:00 PM | 559 | 561 | 6 January 2025 8:00 AM | 2025-01-14 17:00 | 3 | Hoarding | 100 | 51 | 20 | 38 | 39
561 | 1.2.4.3.1.1.12 | Timber Flooring | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 560 | 567,568,563 | 13 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Line Market | 100 | 81 | 24 | 88 | 18
562 | 1.2.4.3.1.1.13 | Measure & Manufacture Joinery | 40 | 25 November 2024 8:00 AM | 18 January 2025 5:00 PM | 555 | 563 | 25 November 2024 8:00 AM | 2025-01-21 17:00 | 3 | Mechanical | 100 | 57 | 17 | 8 | 20
563 | 1.2.4.3.1.1.14 | Install Joinery | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 561,562 | 565 | 22 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Cleaner | 100 | 91 | 27 | 64 | 6
564 | 1.2.4.3.1.1.15 | Measure & Manufacture Stone Benchtops | 12 | 17 January 2025 8:00 AM | 1 February 2025 8:00 AM | 565SF |  | 17 January 2025 8:00 AM | 2025-02-04 08:00 | 3 | Project Manager | 100 | 59 | 16 | 15 | 52
565 | 1.2.4.3.1.1.16 | Install Stone Benchtops | 5 | 1 February 2025 8:00 AM | 6 February 2025 5:00 PM | 563 | 564SF,566 | 1 February 2025 8:00 AM | 2025-02-06 17:00 | 0 | Contract Administrator | 100 | 43 | 30 | 30 | 29
566 | 1.2.4.3.1.1.17 | Fixtures & Fittings Fit-off | 3 | 7 February 2025 8:00 AM | 10 February 2025 5:00 PM | 565 | 574 | 7 February 2025 8:00 AM | 2025-02-10 17:00 | 0 | Surveyor | 100 | 44 | 30 | 46 | 13
567 | 1.2.4.3.1.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 561 | 569 | 22 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Cleaner | 100 | 83 | 15 | 32 | 27
568 | 1.2.4.3.1.1.19 | Lighting Fit-off | 3 | 22 January 2025 8:00 AM | 24 January 2025 5:00 PM | 561 | 569 | 22 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Site Manager | 100 | 35 | 23 | 18 | 57
569 | 1.2.4.3.1.1.20 | Setting Defects | 4 | 28 January 2025 8:00 AM | 31 January 2025 5:00 PM | 567,568 | 570 | 28 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Landscaper | 100 | 90 | 31 | 80 | 7
570 | 1.2.4.3.1.1.21 | Paint Finish Coat | 4 | 1 February 2025 8:00 AM | 5 February 2025 5:00 PM | 569 | 573,571 | 1 February 2025 8:00 AM | 2025-02-05 17:00 | 0 | Development Manager | 100 | 16 | 34 | 94 | 22
571 | 1.2.4.3.1.1.22 | Carpet | 3 | 6 February 2025 8:00 AM | 8 February 2025 5:00 PM | 570 | 572 | 6 February 2025 8:00 AM | 2025-02-08 17:00 | 0 | Head Contractor | 100 | 26 | 29 | 74 | 55
572 | 1.2.4.3.1.1.23 | Final Clean & Commissioning | 4 | 10 February 2025 8:00 AM | 13 February 2025 5:00 PM | 571 |  | 10 February 2025 8:00 AM | 2025-02-13 17:00 | 0 | Cleaner | 100 | 23 | 31 | 0 | 10
573 | 1.2.4.3.1.1.24 | Defects Inspections & Rectifications | 6 | 6 February 2025 8:00 AM | 12 February 2025 5:00 PM | 570 | 574 | 6 February 2025 8:00 AM | 2025-02-13 17:00 | 1 | Carpenter | 100 | 48 | 15 | 56 | 10
574 | 1.2.4.3.1.2 | LVL 1 - FITOUT COMPLETE | 0 | 12 February 2025 5:00 PM | 12 February 2025 5:00 PM | 566,573 |  | 12 February 2025 5:00 PM | 2025-02-12 17:00 | 0 | Project Manager | 100 | 40 | 22 | 65 | 37
575 | 1.2.4.3.2 | Lvl 2 - Services & Finishes | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-11 17:00 | 5 | Window | 100 | 18 | 28 | 79 | 12
576 | 1.2.4.3.2.1 | Internal Works | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-10 17:00 | 4 | Plumber | 100 | 27 | 19 | 42 | 60
577 | 1.2.4.3.2.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 408,150 | 578FS-2d | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Fire | 100 | 67 | 20 | 94 | 20
578 | 1.2.4.3.2.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 577FS-2d | 579 | 21 October 2024 8:00 AM | 2024-11-02 17:00 | 2 | Hoarding | 100 | 31 | 14 | 67 | 34
579 | 1.2.4.3.2.1.3 | Internal Wall Framing | 8 | 1 November 2024 8:00 AM | 9 November 2024 5:00 PM | 578 | 581,580 | 1 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Carpet | 100 | 79 | 19 | 63 | 33
580 | 1.2.4.3.2.1.4 | Sheet one side of walls | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 583,582 | 11 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Contract Administrator | 100 | 91 | 30 | 89 | 25
581 | 1.2.4.3.2.1.5 | Service Rough-In | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 582 | 11 November 2024 8:00 AM | 2024-11-21 17:00 | 2 | Carpenter | 100 | 73 | 12 | 13 | 40
582 | 1.2.4.3.2.1.6 | ITP for services in the walls | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 580,581 | 583,589 | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Mechanical | 100 | 66 | 22 | 30 | 39
583 | 1.2.4.3.2.1.7 | Sheet other side of walls | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 580,582 | 584 | 22 November 2024 8:00 AM | 2024-12-03 17:00 | 3 | Contract Administrator | 100 | 66 | 34 | 18 | 45
584 | 1.2.4.3.2.1.8 | Frame & Sheet Ceilings | 8 | 2 December 2024 8:00 AM | 10 December 2024 5:00 PM | 583 | 585 | 2 December 2024 8:00 AM | 2024-12-12 17:00 | 2 | Head Contractor | 100 | 80 | 23 | 70 | 7
585 | 1.2.4.3.2.1.9 | Sheet, Set & Sand Ceilings | 8 | 11 December 2024 8:00 AM | 19 December 2024 5:00 PM | 584,411 | 586 | 11 December 2024 8:00 AM | 2024-12-21 17:00 | 2 | Line Market | 100 | 61 | 18 | 62 | 31
586 | 1.2.4.3.2.1.10 | Paint undercoat | 4 | 20 December 2024 8:00 AM | 24 December 2024 5:00 PM | 585 | 587 | 20 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Foreman | 100 | 80 | 12 | 26 | 8
587 | 1.2.4.3.2.1.11 | Floor Levelling and Floor Finish | 6 | 3 January 2025 8:00 AM | 9 January 2025 5:00 PM | 586 | 588 | 3 January 2025 8:00 AM | 2025-01-12 17:00 | 3 | Concretor | 100 | 72 | 30 | 38 | 38
588 | 1.2.4.3.2.1.12 | Timber Flooring | 6 | 10 January 2025 8:00 AM | 16 January 2025 5:00 PM | 587 | 594,595,590 | 10 January 2025 8:00 AM | 2025-01-16 17:00 | 0 | Head Contractor | 100 | 44 | 32 | 67 | 10
589 | 1.2.4.3.2.1.13 | Measure & Manufacture Joinery | 40 | 22 November 2024 8:00 AM | 16 January 2025 5:00 PM | 582 | 590 | 22 November 2024 8:00 AM | 2025-01-18 17:00 | 2 | Hoarding | 100 | 44 | 10 | 45 | 49
590 | 1.2.4.3.2.1.14 | Install Joinery | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 588,589 | 592 | 17 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Plumber | 100 | 25 | 29 | 85 | 19
591 | 1.2.4.3.2.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 January 2025 8:00 AM | 28 January 2025 8:00 AM | 592SF |  | 13 January 2025 8:00 AM | 2025-01-28 08:00 | 0 | Metal Work | 100 | 66 | 24 | 95 | 25
592 | 1.2.4.3.2.1.16 | Install Stone Benchtops | 5 | 28 January 2025 8:00 AM | 1 February 2025 5:00 PM | 590 | 591SF,593 | 28 January 2025 8:00 AM | 2025-02-01 17:00 | 0 | Concretor | 100 | 36 | 11 | 73 | 44
593 | 1.2.4.3.2.1.17 | Fixtures & Fittings Fit-off | 3 | 3 February 2025 8:00 AM | 5 February 2025 5:00 PM | 592 | 601 | 3 February 2025 8:00 AM | 2025-02-05 17:00 | 0 | Plumber | 100 | 59 | 22 | 44 | 18
594 | 1.2.4.3.2.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 17 January 2025 8:00 AM | 21 January 2025 5:00 PM | 588 | 596 | 17 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Formworker | 100 | 36 | 13 | 27 | 48
595 | 1.2.4.3.2.1.19 | Lighting Fit-off | 3 | 17 January 2025 8:00 AM | 20 January 2025 5:00 PM | 588 | 596 | 17 January 2025 8:00 AM | 2025-01-20 17:00 | 0 | Painter | 100 | 96 | 15 | 29 | 31
596 | 1.2.4.3.2.1.20 | Setting Defects | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 594,595 | 597 | 22 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Formworker | 100 | 33 | 33 | 86 | 9
597 | 1.2.4.3.2.1.21 | Paint Finish Coat | 3 | 28 January 2025 8:00 AM | 30 January 2025 5:00 PM | 596 | 600,598 | 28 January 2025 8:00 AM | 2025-01-30 17:00 | 0 | Electrician | 100 | 40 | 19 | 61 | 5
598 | 1.2.4.3.2.1.22 | Carpet | 2 | 31 January 2025 8:00 AM | 1 February 2025 5:00 PM | 597 | 599 | 31 January 2025 8:00 AM | 2025-02-01 17:00 | 0 | Post Tension | 100 | 58 | 20 | 17 | 47
599 | 1.2.4.3.2.1.23 | Final Clean & Commissioning | 4 | 3 February 2025 8:00 AM | 6 February 2025 5:00 PM | 598 |  | 3 February 2025 8:00 AM | 2025-02-06 17:00 | 0 | Waterproofer | 100 | 27 | 32 | 89 | 27
600 | 1.2.4.3.2.1.24 | Defects Inspections & Rectifications | 6 | 31 January 2025 8:00 AM | 6 February 2025 5:00 PM | 597 | 601 | 31 January 2025 8:00 AM | 2025-02-08 17:00 | 2 | Plasterboarder | 100 | 75 | 21 | 82 | 32
601 | 1.2.4.3.2.2 | LVL 2 - FITOUT COMPLETE | 0 | 6 February 2025 5:00 PM | 6 February 2025 5:00 PM | 593,600 |  | 6 February 2025 5:00 PM | 2025-02-06 17:00 | 0 | Carpenter | 100 | 92 | 34 | 14 | 53
602 | 1.2.4.3.3 | Lvl 3 - Services & Finishes | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | 25 November 2024 8:00 AM | 2025-03-21 17:00 | 4 | Scaffolder | 100 | 92 | 27 | 92 | 7
603 | 1.2.4.3.3.1 | Internal Works | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | 25 November 2024 8:00 AM | 2025-03-22 17:00 | 5 | Foreman | 100 | 24 | 27 | 76 | 22
604 | 1.2.4.3.3.1.1 | Pre-load Levels | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 174 | 605FS-2d | 25 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Carpenter | 100 | 70 | 21 | 11 | 60
605 | 1.2.4.3.3.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 25 November 2024 8:00 AM | 5 December 2024 5:00 PM | 604FS-2d | 606 | 25 November 2024 8:00 AM | 2024-12-08 17:00 | 3 | Stone Mason | 100 | 36 | 27 | 51 | 47
606 | 1.2.4.3.3.1.3 | Internal Wall Framing | 8 | 6 December 2024 8:00 AM | 14 December 2024 5:00 PM | 605 | 608,607 | 6 December 2024 8:00 AM | 2024-12-14 17:00 | 0 | Surveyor | 100 | 28 | 30 | 2 | 15
607 | 1.2.4.3.3.1.4 | Sheet one side of walls | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 610,609 | 16 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Renderer | 100 | 59 | 19 | 60 | 60
608 | 1.2.4.3.3.1.5 | Service Rough-In | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 609 | 16 December 2024 8:00 AM | 2024-12-25 17:00 | 1 | Carpet | 100 | 82 | 14 | 10 | 17
609 | 1.2.4.3.3.1.6 | ITP for services in the walls | 2 | 3 January 2025 8:00 AM | 4 January 2025 5:00 PM | 607,608 | 610,616 | 3 January 2025 8:00 AM | 2025-01-04 17:00 | 0 | Subcontractor | 100 | 85 | 15 | 41 | 46
610 | 1.2.4.3.3.1.7 | Sheet other side of walls | 8 | 6 January 2025 8:00 AM | 14 January 2025 5:00 PM | 607,609,416FS-6d | 611 | 6 January 2025 8:00 AM | 2025-01-15 17:00 | 1 | Fire | 100 | 97 | 19 | 28 | 22
611 | 1.2.4.3.3.1.8 | Frame & Sheet Ceilings | 8 | 15 January 2025 8:00 AM | 23 January 2025 5:00 PM | 610 | 612 | 15 January 2025 8:00 AM | 2025-01-24 17:00 | 1 | Reinforcement Fixer | 100 | 91 | 29 | 19 | 19
612 | 1.2.4.3.3.1.9 | Sheet, Set & Sand Ceilings | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 611,417 | 613 | 24 January 2025 8:00 AM | 2025-02-05 17:00 | 2 | Fire | 100 | 38 | 26 | 2 | 39
613 | 1.2.4.3.3.1.10 | Paint undercoat | 4 | 4 February 2025 8:00 AM | 7 February 2025 5:00 PM | 612 | 614 | 4 February 2025 8:00 AM | 2025-02-07 17:00 | 0 | Mechanical | 100 | 94 | 13 | 3 | 59
614 | 1.2.4.3.3.1.11 | Floor Levelling and Floor Finish | 7 | 8 February 2025 8:00 AM | 15 February 2025 5:00 PM | 613 | 615 | 8 February 2025 8:00 AM | 2025-02-16 17:00 | 1 | Surveyor | 100 | 80 | 34 | 75 | 48
615 | 1.2.4.3.3.1.12 | Timber Flooring | 6 | 17 February 2025 8:00 AM | 22 February 2025 5:00 PM | 614 | 621,622,617 | 17 February 2025 8:00 AM | 2025-02-22 17:00 | 0 | Plasterboarder | 100 | 63 | 24 | 42 | 51
616 | 1.2.4.3.3.1.13 | Measure & Manufacture Joinery | 40 | 6 January 2025 8:00 AM | 21 February 2025 5:00 PM | 609 | 617 | 6 January 2025 8:00 AM | 2025-02-21 17:00 | 0 | Metal Work | 100 | 91 | 11 | 40 | 36
617 | 1.2.4.3.3.1.14 | Install Joinery | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 615,616 | 619 | 24 February 2025 8:00 AM | 2025-03-04 17:00 | 0 | Renderer | 100 | 15 | 32 | 55 | 14
618 | 1.2.4.3.3.1.15 | Measure & Manufacture Stone Benchtops | 12 | 19 February 2025 8:00 AM | 5 March 2025 8:00 AM | 619SF |  | 19 February 2025 8:00 AM | 2025-03-07 08:00 | 2 | Carpet | 100 | 77 | 34 | 38 | 29
619 | 1.2.4.3.3.1.16 | Install Stone Benchtops | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 617 | 618SF,620 | 5 March 2025 8:00 AM | 2025-03-11 17:00 | 0 | Tiler | 100 | 99 | 31 | 51 | 44
620 | 1.2.4.3.3.1.17 | Fixtures & Fittings Fit-off | 3 | 12 March 2025 8:00 AM | 14 March 2025 5:00 PM | 619 | 628 | 12 March 2025 8:00 AM | 2025-03-14 17:00 | 0 | Foreman | 100 | 10 | 28 | 2 | 14
621 | 1.2.4.3.3.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 24 February 2025 8:00 AM | 27 February 2025 5:00 PM | 615 | 623 | 24 February 2025 8:00 AM | 2025-02-27 17:00 | 0 | Head Contractor | 100 | 15 | 16 | 80 | 23
622 | 1.2.4.3.3.1.19 | Lighting Fit-off | 3 | 24 February 2025 8:00 AM | 26 February 2025 5:00 PM | 615 | 623 | 24 February 2025 8:00 AM | 2025-02-26 17:00 | 0 | Formworker | 100 | 43 | 34 | 89 | 35
623 | 1.2.4.3.3.1.20 | Setting Defects | 4 | 28 February 2025 8:00 AM | 4 March 2025 5:00 PM | 621,622 | 624 | 28 February 2025 8:00 AM | 2025-03-04 17:00 | 0 | Concretor | 100 | 43 | 16 | 75 | 19
624 | 1.2.4.3.3.1.21 | Paint Finish Coat | 3 | 5 March 2025 8:00 AM | 7 March 2025 5:00 PM | 623 | 627,625 | 5 March 2025 8:00 AM | 2025-03-07 17:00 | 0 | Plasterboarder | 100 | 68 | 30 | 22 | 46
625 | 1.2.4.3.3.1.22 | Carpet | 2 | 8 March 2025 8:00 AM | 10 March 2025 5:00 PM | 624 | 626 | 8 March 2025 8:00 AM | 2025-03-10 17:00 | 0 | Plumber | 100 | 29 | 21 | 10 | 52
626 | 1.2.4.3.3.1.23 | Final Clean & Commissioning | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 625 |  | 11 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Hoarding | 100 | 50 | 11 | 93 | 48
627 | 1.2.4.3.3.1.24 | Defects Inspections & Rectifications | 8 | 8 March 2025 8:00 AM | 17 March 2025 5:00 PM | 624 | 628 | 8 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Head Contractor | 100 | 40 | 10 | 75 | 23
628 | 1.2.4.3.3.2 | LVL 3 - FITOUT COMPLETE | 0 | 17 March 2025 5:00 PM | 17 March 2025 5:00 PM | 620,627 | 753 | 17 March 2025 5:00 PM | 2025-03-17 17:00 | 0 | Project Manager | 100 | 24 | 13 | 28 | 40
629 | 1.2.4.3.4 | Lvl 4 - Services & Finishes | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | 11 December 2024 8:00 AM | 2025-04-25 17:00 | 3 | Renderer | 100 | 14 | 34 | 100 | 22
630 | 1.2.4.3.4.1 | Internal Works | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | 11 December 2024 8:00 AM | 2025-04-22 17:00 | 0 | Renderer | 100 | 82 | 18 | 41 | 26
631 | 1.2.4.3.4.1.1 | Pre-load Levels | 2 | 11 December 2024 8:00 AM | 12 December 2024 5:00 PM | 186 | 632FS-2d | 11 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Tiler | 100 | 13 | 31 | 12 | 31
632 | 1.2.4.3.4.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 11 December 2024 8:00 AM | 21 December 2024 5:00 PM | 631FS-2d | 633 | 11 December 2024 8:00 AM | 2024-12-24 17:00 | 3 | Renderer | 100 | 31 | 21 | 15 | 12
633 | 1.2.4.3.4.1.3 | Internal Wall Framing | 8 | 23 December 2024 8:00 AM | 9 January 2025 5:00 PM | 632 | 635,634 | 23 December 2024 8:00 AM | 2025-01-11 17:00 | 2 | Waterproofer | 100 | 64 | 33 | 14 | 24
634 | 1.2.4.3.4.1.4 | Sheet one side of walls | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 637,636 | 10 January 2025 8:00 AM | 2025-01-18 17:00 | 0 | Reinforcement Fixer | 100 | 98 | 18 | 56 | 44
635 | 1.2.4.3.4.1.5 | Service Rough-In | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 636 | 10 January 2025 8:00 AM | 2025-01-18 17:00 | 0 | Development Manager | 100 | 20 | 10 | 7 | 17
636 | 1.2.4.3.4.1.6 | ITP for services in the walls | 2 | 20 January 2025 8:00 AM | 21 January 2025 5:00 PM | 634,635 | 637,643 | 20 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Renderer | 100 | 23 | 28 | 56 | 25
637 | 1.2.4.3.4.1.7 | Sheet other side of walls | 8 | 10 February 2025 8:00 AM | 18 February 2025 5:00 PM | 634,636,422FS-6d | 638 | 10 February 2025 8:00 AM | 2025-02-18 17:00 | 0 | Concretor | 100 | 100 | 22 | 22 | 51
638 | 1.2.4.3.4.1.8 | Frame & Sheet Ceilings | 8 | 19 February 2025 8:00 AM | 27 February 2025 5:00 PM | 637 | 639 | 19 February 2025 8:00 AM | 2025-02-27 17:00 | 0 | Carpenter | 100 | 79 | 12 | 63 | 20
639 | 1.2.4.3.4.1.9 | Sheet, Set & Sand Ceilings | 8 | 28 February 2025 8:00 AM | 8 March 2025 5:00 PM | 638,423 | 640 | 28 February 2025 8:00 AM | 2025-03-11 17:00 | 3 | Timber Floorer | 100 | 25 | 16 | 9 | 38
640 | 1.2.4.3.4.1.10 | Paint undercoat | 4 | 10 March 2025 8:00 AM | 13 March 2025 5:00 PM | 639 | 641 | 10 March 2025 8:00 AM | 2025-03-13 17:00 | 0 | Tiler | 100 | 34 | 26 | 56 | 52
641 | 1.2.4.3.4.1.11 | Floor Levelling and Floor Finish | 6 | 14 March 2025 8:00 AM | 20 March 2025 5:00 PM | 640 | 642 | 14 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Post Tension | 100 | 70 | 28 | 21 | 49
642 | 1.2.4.3.4.1.12 | Timber Flooring | 6 | 21 March 2025 8:00 AM | 27 March 2025 5:00 PM | 641 | 648,649,644 | 21 March 2025 8:00 AM | 2025-03-27 17:00 | 0 | Electrician | 100 | 27 | 20 | 3 | 14
643 | 1.2.4.3.4.1.13 | Measure & Manufacture Joinery | 40 | 22 January 2025 8:00 AM | 10 March 2025 5:00 PM | 636 | 644 | 22 January 2025 8:00 AM | 2025-03-15 17:00 | 5 | Carpet | 100 | 26 | 30 | 28 | 29
644 | 1.2.4.3.4.1.14 | Install Joinery | 8 | 28 March 2025 8:00 AM | 5 April 2025 5:00 PM | 642,643 | 646 | 28 March 2025 8:00 AM | 2025-04-05 17:00 | 0 | Mechanical | 100 | 49 | 31 | 60 | 48
645 | 1.2.4.3.4.1.15 | Measure & Manufacture Stone Benchtops | 12 | 24 March 2025 8:00 AM | 7 April 2025 8:00 AM | 646SF |  | 24 March 2025 8:00 AM | 2025-04-10 08:00 | 3 | Development Manager | 100 | 17 | 34 | 30 | 47
646 | 1.2.4.3.4.1.16 | Install Stone Benchtops | 6 | 7 April 2025 8:00 AM | 12 April 2025 5:00 PM | 644 | 645SF,647 | 7 April 2025 8:00 AM | 2025-04-14 17:00 | 2 | Fire | 100 | 26 | 31 | 58 | 39
647 | 1.2.4.3.4.1.17 | Fixtures & Fittings Fit-off | 3 | 14 April 2025 8:00 AM | 16 April 2025 5:00 PM | 646 | 655 | 14 April 2025 8:00 AM | 2025-04-16 17:00 | 0 | Plumber | 100 | 55 | 19 | 34 | 25
648 | 1.2.4.3.4.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 28 March 2025 8:00 AM | 1 April 2025 5:00 PM | 642 | 650 | 28 March 2025 8:00 AM | 2025-04-01 17:00 | 0 | Metal Work | 100 | 59 | 17 | 67 | 54
649 | 1.2.4.3.4.1.19 | Lighting Fit-off | 3 | 28 March 2025 8:00 AM | 31 March 2025 5:00 PM | 642 | 650 | 28 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Electrician | 100 | 42 | 11 | 43 | 46
650 | 1.2.4.3.4.1.20 | Setting Defects | 4 | 2 April 2025 8:00 AM | 5 April 2025 5:00 PM | 648,649 | 651 | 2 April 2025 8:00 AM | 2025-04-05 17:00 | 0 | Plasterboarder | 100 | 19 | 28 | 75 | 54
651 | 1.2.4.3.4.1.21 | Paint Finish Coat | 3 | 7 April 2025 8:00 AM | 9 April 2025 5:00 PM | 650 | 654,652 | 7 April 2025 8:00 AM | 2025-04-09 17:00 | 0 | Subcontractor | 100 | 65 | 26 | 87 | 54
652 | 1.2.4.3.4.1.22 | Carpet | 2 | 10 April 2025 8:00 AM | 11 April 2025 5:00 PM | 651 | 653 | 10 April 2025 8:00 AM | 2025-04-11 17:00 | 0 | Cleaner | 100 | 77 | 11 | 66 | 5
653 | 1.2.4.3.4.1.23 | Final Clean & Commissioning | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 652 |  | 12 April 2025 8:00 AM | 2025-04-23 17:00 | 1 | Metal Work | 100 | 92 | 31 | 33 | 43
654 | 1.2.4.3.4.1.24 | Defects Inspections & Rectifications | 8 | 10 April 2025 8:00 AM | 22 April 2025 5:00 PM | 651 | 655 | 10 April 2025 8:00 AM | 2025-04-22 17:00 | 0 | Concretor | 100 | 68 | 19 | 96 | 23
655 | 1.2.4.3.4.2 | LVL 4 - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 647,654 | 753 | 22 April 2025 5:00 PM | 2025-04-22 17:00 | 0 | Timber Floorer | 100 | 13 | 30 | 94 | 45
656 | 1.2.4.3.5 | Lvl 5 - Services & Finishes | 100 | 12 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | 12 December 2024 8:00 AM | 2025-04-19 17:00 | 2 | Development Manager | 100 | 70 | 19 | 59 | 10
657 | 1.2.4.3.5.1 | Survey & Setout | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 289,198 | 658FS-1d | 12 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Landscaper | 100 | 95 | 16 | 42 | 25
658 | 1.2.4.3.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 657FS-1d | 660,663 | 12 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Scaffolder | 100 | 57 | 13 | 46 | 39
659 | 1.2.4.3.5.3 | External Works | 34 | 17 December 2024 8:00 AM | 4 February 2025 5:00 PM |  |  | 17 December 2024 8:00 AM | 2025-02-08 17:00 | 4 | Project Manager | 100 | 45 | 13 | 9 | 23
660 | 1.2.4.3.5.3.1 | Façade & External Walls | 18 | 17 December 2024 8:00 AM | 15 January 2025 5:00 PM | 658 | 661 | 17 December 2024 8:00 AM | 2025-01-16 17:00 | 1 | Electrician | 100 | 89 | 18 | 89 | 35
661 | 1.2.4.3.5.3.2 | Windows Install | 16 | 16 January 2025 8:00 AM | 4 February 2025 5:00 PM | 660 | 669FS-6d | 16 January 2025 8:00 AM | 2025-02-07 17:00 | 3 | Surveyor | 100 | 91 | 24 | 92 | 50
662 | 1.2.4.3.5.4 | Internal Works | 91 | 23 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-04-18 17:00 | 1 | Painter | 100 | 10 | 26 | 28 | 39
663 | 1.2.4.3.5.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 658,426 | 664FS-2d | 23 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Project Manager | 100 | 25 | 25 | 33 | 17
664 | 1.2.4.3.5.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 663FS-2d | 665 | 23 December 2024 8:00 AM | 2025-01-14 17:00 | 3 | Joiner | 100 | 95 | 23 | 52 | 17
665 | 1.2.4.3.5.4.3 | Internal Wall Framing | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 664 | 667,666 | 13 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Mechanical | 100 | 25 | 17 | 54 | 3
666 | 1.2.4.3.5.4.4 | Sheet one side of walls | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 669,668 | 22 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Window | 100 | 48 | 33 | 18 | 58
667 | 1.2.4.3.5.4.5 | Service Rough-In | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 668 | 22 January 2025 8:00 AM | 2025-02-03 17:00 | 3 | Landscaper | 100 | 26 | 20 | 86 | 54
668 | 1.2.4.3.5.4.6 | ITP for services in the walls | 2 | 1 February 2025 8:00 AM | 3 February 2025 5:00 PM | 666,667 | 669,675 | 1 February 2025 8:00 AM | 2025-02-03 17:00 | 0 | Cleaner | 100 | 32 | 24 | 85 | 55
669 | 1.2.4.3.5.4.7 | Sheet other side of walls | 8 | 4 February 2025 8:00 AM | 12 February 2025 5:00 PM | 661FS-6d,666,668,428FS-6d | 670 | 4 February 2025 8:00 AM | 2025-02-12 17:00 | 0 | Stone Mason | 100 | 98 | 28 | 22 | 31
670 | 1.2.4.3.5.4.8 | Frame & Sheet Ceilings | 8 | 13 February 2025 8:00 AM | 21 February 2025 5:00 PM | 669 | 671 | 13 February 2025 8:00 AM | 2025-02-23 17:00 | 2 | Hoarding | 100 | 72 | 33 | 21 | 18
671 | 1.2.4.3.5.4.9 | Sheet, Set & Sand Ceilings | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 670,429 | 672 | 22 February 2025 8:00 AM | 2025-03-03 17:00 | 0 | Waterproofer | 100 | 94 | 28 | 34 | 18
672 | 1.2.4.3.5.4.10 | Paint undercoat | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 671 | 673 | 4 March 2025 8:00 AM | 2025-03-07 17:00 | 0 | Renderer | 100 | 56 | 12 | 56 | 51
673 | 1.2.4.3.5.4.11 | Floor Levelling and Floor Finish | 6 | 8 March 2025 8:00 AM | 14 March 2025 5:00 PM | 672 | 674 | 8 March 2025 8:00 AM | 2025-03-17 17:00 | 3 | Excavation | 100 | 36 | 22 | 100 | 60
674 | 1.2.4.3.5.4.12 | Timber Flooring | 6 | 15 March 2025 8:00 AM | 21 March 2025 5:00 PM | 673 | 680,681,676 | 15 March 2025 8:00 AM | 2025-03-21 17:00 | 0 | Plumber | 100 | 72 | 35 | 60 | 40
675 | 1.2.4.3.5.4.13 | Measure & Manufacture Joinery | 40 | 4 February 2025 8:00 AM | 21 March 2025 5:00 PM | 668 | 676 | 4 February 2025 8:00 AM | 2025-03-24 17:00 | 3 | Window | 100 | 27 | 15 | 20 | 5
676 | 1.2.4.3.5.4.14 | Install Joinery | 8 | 22 March 2025 8:00 AM | 31 March 2025 5:00 PM | 674,675 | 678 | 22 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Site Manager | 100 | 93 | 10 | 6 | 26
677 | 1.2.4.3.5.4.15 | Measure & Manufacture Stone Benchtops | 15 | 14 March 2025 8:00 AM | 1 April 2025 8:00 AM | 678SF | 687 | 14 March 2025 8:00 AM | 2025-04-06 08:00 | 5 | Foreman | 100 | 22 | 28 | 88 | 43
678 | 1.2.4.3.5.4.16 | Install Stone Benchtops | 6 | 1 April 2025 8:00 AM | 7 April 2025 5:00 PM | 676 | 677SF,679 | 1 April 2025 8:00 AM | 2025-04-08 17:00 | 1 | Scaffolder | 100 | 77 | 11 | 97 | 41
679 | 1.2.4.3.5.4.17 | Fixtures & Fittings Fit-off | 8 | 8 April 2025 8:00 AM | 16 April 2025 5:00 PM | 678 | 687 | 8 April 2025 8:00 AM | 2025-04-16 17:00 | 0 | Head Contractor | 100 | 20 | 32 | 99 | 3
680 | 1.2.4.3.5.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 674 | 682 | 22 March 2025 8:00 AM | 2025-03-26 17:00 | 0 | Waterproofer | 100 | 93 | 21 | 9 | 37
681 | 1.2.4.3.5.4.19 | Lighting Fit-off | 3 | 22 March 2025 8:00 AM | 25 March 2025 5:00 PM | 674 | 682 | 22 March 2025 8:00 AM | 2025-03-25 17:00 | 0 | Contract Administrator | 100 | 26 | 19 | 42 | 28
682 | 1.2.4.3.5.4.20 | Setting Defects | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 680,681 | 683 | 27 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Tiler | 100 | 60 | 32 | 59 | 17
683 | 1.2.4.3.5.4.21 | Paint Finish Coat | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 682 | 686,684 | 1 April 2025 8:00 AM | 2025-04-03 17:00 | 0 | Painter | 100 | 58 | 24 | 14 | 36
684 | 1.2.4.3.5.4.22 | Carpet | 2 | 4 April 2025 8:00 AM | 5 April 2025 5:00 PM | 683 | 685 | 4 April 2025 8:00 AM | 2025-04-05 17:00 | 0 | Head Contractor | 100 | 51 | 13 | 28 | 38
685 | 1.2.4.3.5.4.23 | Final Clean & Commissioning | 10 | 7 April 2025 8:00 AM | 17 April 2025 5:00 PM | 684 | 687 | 7 April 2025 8:00 AM | 2025-04-20 17:00 | 3 | Plasterboarder | 100 | 76 | 32 | 42 | 13
686 | 1.2.4.3.5.4.24 | Defects Inspections & Rectifications | 8 | 4 April 2025 8:00 AM | 12 April 2025 5:00 PM | 683 | 687 | 4 April 2025 8:00 AM | 2025-04-15 17:00 | 3 | Waterproofer | 100 | 12 | 34 | 47 | 13
687 | 1.2.4.3.5.5 | LVL 5 - FITOUT COMPLETE | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 679,686,685,677 |  | 17 April 2025 5:00 PM | 2025-04-17 17:00 | 0 | Site Manager | 100 | 58 | 34 | 96 | 20
688 | 1.2.4.3.6 | Lvl 6 - Services & Finishes | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-04-18 17:00 | 3 | Head Contractor | 100 | 75 | 26 | 38 | 12
689 | 1.2.4.3.6.1 | Internal Works | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-04-17 17:00 | 2 | Excavation | 100 | 50 | 11 | 43 | 24
690 | 1.2.4.3.6.1.1 | Pre-load Levels | 2 | 18 December 2024 8:00 AM | 19 December 2024 5:00 PM | 432,210 | 691FS-2d | 18 December 2024 8:00 AM | 2024-12-19 17:00 | 0 | Project Manager | 100 | 11 | 11 | 31 | 44
691 | 1.2.4.3.6.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 18 December 2024 8:00 AM | 7 January 2025 5:00 PM | 690FS-2d | 692 | 18 December 2024 8:00 AM | 2025-01-07 17:00 | 0 | Carpet | 100 | 59 | 20 | 63 | 37
692 | 1.2.4.3.6.1.3 | Internal Wall Framing | 8 | 8 January 2025 8:00 AM | 16 January 2025 5:00 PM | 691 | 694,693 | 8 January 2025 8:00 AM | 2025-01-16 17:00 | 0 | Plumber | 100 | 67 | 29 | 3 | 59
693 | 1.2.4.3.6.1.4 | Sheet one side of walls | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 696,695 | 17 January 2025 8:00 AM | 2025-01-29 17:00 | 2 | Subcontractor | 100 | 17 | 16 | 36 | 24
694 | 1.2.4.3.6.1.5 | Service Rough-In | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 695 | 17 January 2025 8:00 AM | 2025-01-30 17:00 | 3 | Waterproofer | 100 | 56 | 33 | 28 | 49
695 | 1.2.4.3.6.1.6 | ITP for services in the walls | 2 | 28 January 2025 8:00 AM | 29 January 2025 5:00 PM | 693,694 | 696,702 | 28 January 2025 8:00 AM | 2025-01-29 17:00 | 0 | Foreman | 100 | 82 | 22 | 59 | 46
696 | 1.2.4.3.6.1.7 | Sheet other side of walls | 8 | 30 January 2025 8:00 AM | 7 February 2025 5:00 PM | 693,695,434FS-6d | 697 | 30 January 2025 8:00 AM | 2025-02-07 17:00 | 0 | Subcontractor | 100 | 39 | 13 | 97 | 6
697 | 1.2.4.3.6.1.8 | Frame & Sheet Ceilings | 8 | 8 February 2025 8:00 AM | 17 February 2025 5:00 PM | 696 | 698 | 8 February 2025 8:00 AM | 2025-02-20 17:00 | 3 | Scaffolder | 100 | 33 | 20 | 78 | 15
698 | 1.2.4.3.6.1.9 | Sheet, Set & Sand Ceilings | 8 | 18 February 2025 8:00 AM | 26 February 2025 5:00 PM | 697,435 | 699 | 18 February 2025 8:00 AM | 2025-02-27 17:00 | 1 | Stone Mason | 100 | 59 | 16 | 74 | 48
699 | 1.2.4.3.6.1.10 | Paint undercoat | 4 | 27 February 2025 8:00 AM | 3 March 2025 5:00 PM | 698 | 700 | 27 February 2025 8:00 AM | 2025-03-03 17:00 | 0 | Floor Sealer | 100 | 86 | 17 | 47 | 59
700 | 1.2.4.3.6.1.11 | Floor Levelling and Floor Finish | 6 | 4 March 2025 8:00 AM | 10 March 2025 5:00 PM | 699 | 701 | 4 March 2025 8:00 AM | 2025-03-12 17:00 | 2 | Renderer | 100 | 86 | 20 | 62 | 39
701 | 1.2.4.3.6.1.12 | Timber Flooring | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 700 | 707,708,703 | 11 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Carpet | 100 | 18 | 30 | 38 | 34
702 | 1.2.4.3.6.1.13 | Measure & Manufacture Joinery | 40 | 30 January 2025 8:00 AM | 17 March 2025 5:00 PM | 695 | 703 | 30 January 2025 8:00 AM | 2025-03-21 17:00 | 4 | Project Manager | 100 | 17 | 30 | 51 | 11
703 | 1.2.4.3.6.1.14 | Install Joinery | 8 | 18 March 2025 8:00 AM | 26 March 2025 5:00 PM | 701,702 | 705 | 18 March 2025 8:00 AM | 2025-03-28 17:00 | 2 | Metal Work | 100 | 22 | 25 | 29 | 58
704 | 1.2.4.3.6.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 March 2025 8:00 AM | 27 March 2025 8:00 AM | 705SF |  | 13 March 2025 8:00 AM | 2025-03-28 08:00 | 1 | Reinforcement Fixer | 100 | 49 | 18 | 92 | 14
705 | 1.2.4.3.6.1.16 | Install Stone Benchtops | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 703 | 704SF,706 | 27 March 2025 8:00 AM | 2025-04-02 17:00 | 0 | Metal Work | 100 | 35 | 13 | 97 | 55
706 | 1.2.4.3.6.1.17 | Fixtures & Fittings Fit-off | 7 | 3 April 2025 8:00 AM | 10 April 2025 5:00 PM | 705 | 714 | 3 April 2025 8:00 AM | 2025-04-12 17:00 | 2 | Formworker | 100 | 18 | 26 | 72 | 56
707 | 1.2.4.3.6.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 18 March 2025 8:00 AM | 21 March 2025 5:00 PM | 701 | 709 | 18 March 2025 8:00 AM | 2025-03-21 17:00 | 0 | Post Tension | 100 | 49 | 24 | 9 | 8
708 | 1.2.4.3.6.1.19 | Lighting Fit-off | 3 | 18 March 2025 8:00 AM | 20 March 2025 5:00 PM | 701 | 709 | 18 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Development Manager | 100 | 63 | 24 | 48 | 24
709 | 1.2.4.3.6.1.20 | Setting Defects | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 707,708 | 710 | 22 March 2025 8:00 AM | 2025-03-26 17:00 | 0 | Waterproofer | 100 | 42 | 10 | 85 | 34
710 | 1.2.4.3.6.1.21 | Paint Finish Coat | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 709 | 713,711 | 27 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Subcontractor | 100 | 50 | 14 | 7 | 10
711 | 1.2.4.3.6.1.22 | Carpet | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 710 | 712 | 1 April 2025 8:00 AM | 2025-04-03 17:00 | 0 | Admin | 100 | 30 | 13 | 22 | 28
712 | 1.2.4.3.6.1.23 | Final Clean & Commissioning | 10 | 4 April 2025 8:00 AM | 15 April 2025 5:00 PM | 711 |  | 4 April 2025 8:00 AM | 2025-04-15 17:00 | 0 | Development Manager | 100 | 94 | 12 | 39 | 9
713 | 1.2.4.3.6.1.24 | Defects Inspections & Rectifications | 8 | 1 April 2025 8:00 AM | 9 April 2025 5:00 PM | 710 | 714 | 1 April 2025 8:00 AM | 2025-04-10 17:00 | 1 | Waterproofer | 100 | 76 | 24 | 75 | 35
714 | 1.2.4.3.6.2 | LVL 6 - FITOUT COMPLETE | 0 | 10 April 2025 5:00 PM | 10 April 2025 5:00 PM | 706,713 | 5 | 10 April 2025 5:00 PM | 2025-04-10 17:00 | 0 | Surveyor | 100 | 95 | 34 | 44 | 9
715 | 1.2.4.3.7 | Lvl 7 - Services & Finishes | 105 | 18 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-05-08 17:00 | 3 | Development Manager | 100 | 69 | 33 | 76 | 3
716 | 1.2.4.3.7.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 301,223 | 717FS-1d | 18 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Window | 100 | 34 | 23 | 7 | 12
717 | 1.2.4.3.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 716FS-1d | 719,722 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Plumber | 100 | 48 | 26 | 48 | 29
718 | 1.2.4.3.7.3 | External Works | 34 | 23 December 2024 8:00 AM | 10 February 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-02-11 17:00 | 1 | Site Manager | 100 | 96 | 31 | 23 | 51
719 | 1.2.4.3.7.3.1 | Façade & External Walls | 18 | 23 December 2024 8:00 AM | 21 January 2025 5:00 PM | 717 | 720 | 23 December 2024 8:00 AM | 2025-01-22 17:00 | 1 | Metal Work | 100 | 96 | 27 | 72 | 51
720 | 1.2.4.3.7.3.2 | Windows Install | 16 | 22 January 2025 8:00 AM | 10 February 2025 5:00 PM | 719 | 728FS-6d | 22 January 2025 8:00 AM | 2025-02-15 17:00 | 5 | Window | 100 | 70 | 30 | 88 | 53
721 | 1.2.4.3.7.4 | Internal Works | 101 | 23 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-05-05 17:00 | 0 | Hoarding | 100 | 32 | 14 | 26 | 58
722 | 1.2.4.3.7.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 717,438 | 723FS-2d | 23 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Reinforcement Fixer | 100 | 77 | 20 | 86 | 58
723 | 1.2.4.3.7.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 722FS-2d | 724 | 23 December 2024 8:00 AM | 2025-01-13 17:00 | 2 | Carpet | 100 | 81 | 18 | 41 | 60
724 | 1.2.4.3.7.4.3 | Internal Wall Framing | 10 | 13 January 2025 8:00 AM | 23 January 2025 5:00 PM | 723 | 726,725 | 13 January 2025 8:00 AM | 2025-01-28 17:00 | 5 | Foreman | 100 | 30 | 12 | 89 | 43
725 | 1.2.4.3.7.4.4 | Sheet one side of walls | 9 | 24 January 2025 8:00 AM | 4 February 2025 5:00 PM | 724 | 728,727 | 24 January 2025 8:00 AM | 2025-02-05 17:00 | 1 | Head Contractor | 100 | 37 | 18 | 82 | 13
726 | 1.2.4.3.7.4.5 | Service Rough-In | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 724 | 727 | 24 January 2025 8:00 AM | 2025-02-03 17:00 | 0 | Stone Mason | 100 | 50 | 24 | 18 | 56
727 | 1.2.4.3.7.4.6 | ITP for services in the walls | 2 | 5 February 2025 8:00 AM | 6 February 2025 5:00 PM | 725,726 | 728,734 | 5 February 2025 8:00 AM | 2025-02-06 17:00 | 0 | Painter | 100 | 77 | 17 | 86 | 47
728 | 1.2.4.3.7.4.7 | Sheet other side of walls | 8 | 15 February 2025 8:00 AM | 24 February 2025 5:00 PM | 720FS-6d,725,727,440FS-6d | 729 | 15 February 2025 8:00 AM | 2025-02-24 17:00 | 0 | Metal Work | 100 | 57 | 17 | 25 | 58
729 | 1.2.4.3.7.4.8 | Frame & Sheet Ceilings | 8 | 25 February 2025 8:00 AM | 5 March 2025 5:00 PM | 728 | 730 | 25 February 2025 8:00 AM | 2025-03-06 17:00 | 1 | Tiler | 100 | 50 | 19 | 25 | 51
730 | 1.2.4.3.7.4.9 | Sheet, Set & Sand Ceilings | 8 | 6 March 2025 8:00 AM | 14 March 2025 5:00 PM | 729,441 | 731 | 6 March 2025 8:00 AM | 2025-03-15 17:00 | 1 | Concretor | 100 | 91 | 33 | 1 | 57
731 | 1.2.4.3.7.4.10 | Paint undercoat | 4 | 15 March 2025 8:00 AM | 19 March 2025 5:00 PM | 730 | 732 | 15 March 2025 8:00 AM | 2025-03-19 17:00 | 0 | Tiler | 100 | 31 | 27 | 87 | 30
732 | 1.2.4.3.7.4.11 | Floor Levelling and Floor Finish | 6 | 20 March 2025 8:00 AM | 26 March 2025 5:00 PM | 731 | 733 | 20 March 2025 8:00 AM | 2025-03-28 17:00 | 2 | Stone Mason | 100 | 11 | 17 | 42 | 35
733 | 1.2.4.3.7.4.12 | Timber Flooring | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 732 | 739,740,735 | 27 March 2025 8:00 AM | 2025-04-05 17:00 | 3 | Subcontractor | 100 | 38 | 17 | 63 | 56
734 | 1.2.4.3.7.4.13 | Measure & Manufacture Joinery | 40 | 7 February 2025 8:00 AM | 25 March 2025 5:00 PM | 727 | 735 | 7 February 2025 8:00 AM | 2025-03-27 17:00 | 2 | Surveyor | 100 | 47 | 18 | 68 | 3
735 | 1.2.4.3.7.4.14 | Install Joinery | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733,734 | 737 | 3 April 2025 8:00 AM | 2025-04-13 17:00 | 2 | Metal Work | 100 | 64 | 34 | 18 | 26
736 | 1.2.4.3.7.4.15 | Measure & Manufacture Stone Benchtops | 12 | 29 March 2025 8:00 AM | 12 April 2025 8:00 AM | 737SF | 746 | 29 March 2025 8:00 AM | 2025-04-17 08:00 | 5 | Contract Administrator | 100 | 29 | 17 | 24 | 36
737 | 1.2.4.3.7.4.16 | Install Stone Benchtops | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 735 | 736SF,738 | 12 April 2025 8:00 AM | 2025-04-22 17:00 | 0 | Renderer | 100 | 98 | 34 | 94 | 13
738 | 1.2.4.3.7.4.17 | Fixtures & Fittings Fit-off | 7 | 23 April 2025 8:00 AM | 2 May 2025 5:00 PM | 737 | 746 | 23 April 2025 8:00 AM | 2025-05-05 17:00 | 3 | Foreman | 100 | 18 | 26 | 40 | 24
739 | 1.2.4.3.7.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733 | 741 | 3 April 2025 8:00 AM | 2025-04-13 17:00 | 2 | Mechanical | 100 | 32 | 34 | 96 | 55
740 | 1.2.4.3.7.4.19 | Lighting Fit-off | 5 | 3 April 2025 8:00 AM | 8 April 2025 5:00 PM | 733 | 741 | 3 April 2025 8:00 AM | 2025-04-08 17:00 | 0 | Hoarding | 100 | 41 | 27 | 65 | 20
741 | 1.2.4.3.7.4.20 | Setting Defects | 4 | 12 April 2025 8:00 AM | 16 April 2025 5:00 PM | 739,740 | 742 | 12 April 2025 8:00 AM | 2025-04-16 17:00 | 0 | Cleaner | 100 | 46 | 27 | 81 | 59
742 | 1.2.4.3.7.4.21 | Paint Finish Coat | 4 | 17 April 2025 8:00 AM | 24 April 2025 5:00 PM | 741 | 745,743 | 17 April 2025 8:00 AM | 2025-04-24 17:00 | 0 | Cleaner | 100 | 40 | 31 | 56 | 23
743 | 1.2.4.3.7.4.22 | Carpet | 3 | 28 April 2025 8:00 AM | 30 April 2025 5:00 PM | 742 | 744 | 28 April 2025 8:00 AM | 2025-04-30 17:00 | 0 | Contract Administrator | 100 | 60 | 24 | 92 | 22
744 | 1.2.4.3.7.4.23 | Final Clean & Commissioning | 4 | 1 May 2025 8:00 AM | 5 May 2025 5:00 PM | 743 | 746 | 1 May 2025 8:00 AM | 2025-05-06 17:00 | 1 | Painter | 100 | 21 | 14 | 10 | 5
745 | 1.2.4.3.7.4.24 | Defects Inspections & Rectifications | 6 | 28 April 2025 8:00 AM | 3 May 2025 5:00 PM | 742 | 746 | 28 April 2025 8:00 AM | 2025-05-06 17:00 | 3 | Window | 100 | 75 | 11 | 92 | 36
746 | 1.2.4.3.7.5 | LVL 7 - FITOUT COMPLETE | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 738,745,744,736 | 5,754 | 5 May 2025 5:00 PM | 2025-05-06 17:00 | 1 | Tiler | 100 | 91 | 16 | 37 | 46
747 | 1.2.4.3.8 | Lvl 8 (Roof) - Services | 96 | 7 January 2025 8:00 AM | 5 May 2025 5:00 PM |  |  | 7 January 2025 8:00 AM | 2025-05-05 17:00 | 0 | Concretor | 100 | 62 | 35 | 34 | 55
748 | 1.2.4.3.8.1 | Survey & Setout | 1 | 7 January 2025 8:00 AM | 7 January 2025 5:00 PM | 301FS+24d | 749FS-1d | 7 January 2025 8:00 AM | 2025-01-07 17:00 | 0 | Tiler | 100 | 41 | 11 | 98 | 58
749 | 1.2.4.3.8.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 7 January 2025 8:00 AM | 10 January 2025 5:00 PM | 748FS-1d | 751 | 7 January 2025 8:00 AM | 2025-01-10 17:00 | 0 | Plasterboarder | 100 | 65 | 17 | 27 | 3
750 | 1.2.4.3.8.3 | External Services (Plant) | 56 | 11 January 2025 8:00 AM | 18 March 2025 5:00 PM |  |  | 11 January 2025 8:00 AM | 2025-03-25 17:00 | 7 | Excavation | 100 | 60 | 26 | 27 | 19
751 | 1.2.4.3.8.3.1 | Heat Pumps & Associated Services | 32 | 11 January 2025 8:00 AM | 18 February 2025 5:00 PM | 749 | 752 | 11 January 2025 8:00 AM | 2025-02-23 17:00 | 5 | Reinforcement Fixer | 100 | 95 | 29 | 53 | 54
752 | 1.2.4.3.8.3.2 | Louvres, Balustrades & Roof Safety System | 24 | 19 February 2025 8:00 AM | 18 March 2025 5:00 PM | 751 | 753 | 19 February 2025 8:00 AM | 2025-03-19 17:00 | 1 | Subcontractor | 100 | 31 | 25 | 38 | 47
753 | 1.2.4.3.8.4 | LVL 8 (ROOF) - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 752,655,628 | 5,754 | 22 April 2025 5:00 PM | 2025-04-22 17:00 | 0 | Fire | 100 | 33 | 19 | 1 | 35
754 | 1.2.4.3.8.5 | Building A Fitout Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 753,746 |  | 5 May 2025 5:00 PM | 2025-05-05 17:00 | 0 | Head Contractor | 100 | 97 | 13 | 52 | 6
755 | 1.2.4.4 | Building B | 135 | 14 October 2024 8:00 AM | 29 March 2025 5:00 PM |  | 3440 | 14 October 2024 8:00 AM | 2025-03-29 17:00 | 0 | Stone Mason | 100 | 13 | 24 | 92 | 10
756 | 1.2.4.4.1 | Level 1 | 52 | 14 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | 14 October 2024 8:00 AM | 2024-12-13 17:00 | 1 | Carpet | 100 | 66 | 33 | 49 | 52
757 | 1.2.4.4.1.1 | Apartment B010 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | 14 October 2024 8:00 AM | 2024-12-05 17:00 | 0 | Renderer | 100 | 32 | 12 | 22 | 36
758 | 1.2.4.4.1.1.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 759,762,763,830 | 14 October 2024 8:00 AM | 2024-10-20 17:00 | 5 | Electrician | 100 | 85 | 16 | 54 | 39
759 | 1.2.4.4.1.1.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 758 | 761,760 | 16 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Painter | 100 | 87 | 11 | 1 | 41
760 | 1.2.4.4.1.1.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 759 |  | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Metal Work | 100 | 92 | 18 | 75 | 46
761 | 1.2.4.4.1.1.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 759 | 764 | 17 October 2024 8:00 AM | 2024-10-24 17:00 | 5 | Project Manager | 100 | 99 | 19 | 12 | 8
762 | 1.2.4.4.1.1.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 771 | 16 October 2024 8:00 AM | 2024-10-23 17:00 | 5 | Carpenter | 100 | 22 | 27 | 2 | 16
763 | 1.2.4.4.1.1.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 834 | 16 October 2024 8:00 AM | 2024-10-25 17:00 | 7 | Development Manager | 100 | 30 | 21 | 82 | 25
764 | 1.2.4.4.1.1.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 761 | 765,766,767,768,769 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Contract Administrator | 100 | 38 | 31 | 91 | 7
765 | 1.2.4.4.1.1.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Development Manager | 100 | 68 | 30 | 71 | 34
766 | 1.2.4.4.1.1.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769,833 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Timber Floorer | 100 | 18 | 29 | 92 | 18
767 | 1.2.4.4.1.1.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 832 | 23 October 2024 8:00 AM | 2024-10-26 17:00 | 2 | Foreman | 100 | 14 | 23 | 47 | 25
768 | 1.2.4.4.1.1.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 |  | 23 October 2024 8:00 AM | 2024-10-29 17:00 | 5 | Waterproofer | 100 | 27 | 21 | 49 | 51
769 | 1.2.4.4.1.1.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 764,765,766 | 770 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Timber Floorer | 100 | 78 | 23 | 87 | 16
770 | 1.2.4.4.1.1.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 769 | 771 | 26 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Tiler | 100 | 44 | 10 | 63 | 44
771 | 1.2.4.4.1.1.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 762,770 | 772,773,774,775,777,779 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Contract Administrator | 100 | 29 | 13 | 81 | 33
772 | 1.2.4.4.1.1.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 776,779 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Stone Mason | 100 | 92 | 20 | 44 | 19
773 | 1.2.4.4.1.1.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 779 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Scaffolder | 100 | 99 | 32 | 73 | 32
774 | 1.2.4.4.1.1.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 778,779 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Foreman | 100 | 65 | 11 | 81 | 18
775 | 1.2.4.4.1.1.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Surveyor | 100 | 21 | 26 | 49 | 39
776 | 1.2.4.4.1.1.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 772 | 779 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Cleaner | 100 | 14 | 29 | 62 | 24
777 | 1.2.4.4.1.1.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Fire | 100 | 31 | 28 | 89 | 18
778 | 1.2.4.4.1.1.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 774 | 779 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Foreman | 100 | 81 | 12 | 96 | 15
779 | 1.2.4.4.1.1.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 771,772,773,774,775,776,777,778 | 780 | 4 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Post Tension | 100 | 90 | 14 | 88 | 32
780 | 1.2.4.4.1.1.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 779 | 781 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Joiner | 100 | 38 | 24 | 55 | 48
781 | 1.2.4.4.1.1.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 780 | 782,799,816 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Floor Sealer | 100 | 22 | 30 | 15 | 33
782 | 1.2.4.4.1.1.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 783 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Waterproofer | 100 | 77 | 25 | 2 | 58
783 | 1.2.4.4.1.1.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 782 | 784 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Head Contractor | 100 | 62 | 35 | 25 | 13
784 | 1.2.4.4.1.1.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 783 | 785 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Carpet | 100 | 68 | 22 | 63 | 56
785 | 1.2.4.4.1.1.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 784 | 786 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Hoarding | 100 | 23 | 11 | 97 | 19
786 | 1.2.4.4.1.1.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 785 | 787,788 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Landscaper | 100 | 54 | 31 | 76 | 3
787 | 1.2.4.4.1.1.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 786 | 791 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Window | 100 | 81 | 20 | 66 | 18
788 | 1.2.4.4.1.1.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 786 | 789 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Metal Work | 100 | 41 | 24 | 2 | 57
789 | 1.2.4.4.1.1.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 788 | 790 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Painter | 100 | 10 | 26 | 55 | 60
790 | 1.2.4.4.1.1.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 789 |  | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Development Manager | 100 | 92 | 26 | 36 | 21
791 | 1.2.4.4.1.1.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 787 | 792,793,794,795,796 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Site Manager | 100 | 46 | 15 | 77 | 46
792 | 1.2.4.4.1.1.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 791 |  | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Renderer | 100 | 93 | 30 | 80 | 45
793 | 1.2.4.4.1.1.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Plumber | 100 | 71 | 24 | 58 | 5
794 | 1.2.4.4.1.1.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Floor Sealer | 100 | 100 | 23 | 41 | 4
795 | 1.2.4.4.1.1.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Waterproofer | 100 | 80 | 13 | 16 | 58
796 | 1.2.4.4.1.1.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Stone Mason | 100 | 36 | 14 | 99 | 23
797 | 1.2.4.4.1.1.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 847 | 9 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Electrician | 100 | 25 | 35 | 34 | 36
798 | 1.2.4.4.1.1.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Hoarding | 100 | 90 | 28 | 90 | 32
799 | 1.2.4.4.1.1.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 800 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Window | 100 | 97 | 27 | 14 | 10
800 | 1.2.4.4.1.1.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 799 | 801 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Concretor | 100 | 15 | 24 | 52 | 9
801 | 1.2.4.4.1.1.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 800 | 802 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Mechanical | 100 | 67 | 19 | 84 | 29
802 | 1.2.4.4.1.1.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 801 | 803 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Scaffolder | 100 | 13 | 27 | 48 | 47
803 | 1.2.4.4.1.1.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 802 | 804 | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Excavation | 100 | 10 | 19 | 19 | 26
804 | 1.2.4.4.1.1.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 803 | 805 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Plumber | 100 | 26 | 15 | 76 | 17
805 | 1.2.4.4.1.1.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 804 | 806 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Waterproofer | 100 | 58 | 24 | 36 | 46
806 | 1.2.4.4.1.1.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 805 | 807 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Window | 100 | 35 | 20 | 92 | 7
807 | 1.2.4.4.1.1.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 806 | 808 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Tiler | 100 | 70 | 19 | 69 | 51
808 | 1.2.4.4.1.1.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 807 | 809 | 25 November 2024 8:00 AM | 2024-12-01 17:00 | 6 | Timber Floorer | 100 | 72 | 30 | 56 | 15
809 | 1.2.4.4.1.1.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 808 | 810 | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 4 | Project Manager | 100 | 50 | 27 | 44 | 11
810 | 1.2.4.4.1.1.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 809 | 814,811,812,813 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Landscaper | 100 | 83 | 22 | 90 | 7
811 | 1.2.4.4.1.1.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Plumber | 100 | 97 | 29 | 7 | 5
812 | 1.2.4.4.1.1.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Admin | 100 | 72 | 29 | 94 | 42
813 | 1.2.4.4.1.1.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Excavation | 100 | 40 | 15 | 83 | 22
814 | 1.2.4.4.1.1.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 810,811,812,813 |  | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Hoarding | 100 | 12 | 14 | 17 | 51
815 | 1.2.4.4.1.1.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Renderer | 100 | 13 | 25 | 64 | 40
816 | 1.2.4.4.1.1.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 817 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Hoarding | 100 | 31 | 19 | 79 | 54
817 | 1.2.4.4.1.1.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 816 | 818 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Development Manager | 100 | 15 | 25 | 4 | 49
818 | 1.2.4.4.1.1.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 817 | 819 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Waterproofer | 100 | 64 | 34 | 24 | 34
819 | 1.2.4.4.1.1.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 818 | 820 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Reinforcement Fixer | 100 | 55 | 22 | 68 | 14
820 | 1.2.4.4.1.1.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 819 | 821 | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Window | 100 | 84 | 18 | 61 | 58
821 | 1.2.4.4.1.1.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 820 | 822 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Site Manager | 100 | 16 | 25 | 74 | 46
822 | 1.2.4.4.1.1.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 821 | 823 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Floor Sealer | 100 | 18 | 26 | 65 | 32
823 | 1.2.4.4.1.1.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 822 | 824,825,826,827 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Mechanical | 100 | 56 | 22 | 1 | 25
824 | 1.2.4.4.1.1.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Tiler | 100 | 43 | 24 | 42 | 50
825 | 1.2.4.4.1.1.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Concretor | 100 | 100 | 10 | 96 | 49
826 | 1.2.4.4.1.1.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-28 17:00 | 3 | Head Contractor | 100 | 54 | 34 | 25 | 17
827 | 1.2.4.4.1.1.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Carpenter | 100 | 92 | 27 | 75 | 43
828 | 1.2.4.4.1.1.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 824,825,826,827 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Cleaner | 100 | 70 | 14 | 96 | 27
829 | 1.2.4.4.1.1.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-11-11 17:00 | 0 | Renderer | 100 | 59 | 11 | 42 | 28
830 | 1.2.4.4.1.1.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 758 | 831 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Contract Administrator | 100 | 41 | 27 | 76 | 31
831 | 1.2.4.4.1.1.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 830 |  | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Site Manager | 100 | 78 | 29 | 100 | 6
832 | 1.2.4.4.1.1.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 767 | 835 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Stone Mason | 100 | 12 | 24 | 2 | 60
833 | 1.2.4.4.1.1.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 766 | 835 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Contract Administrator | 100 | 21 | 28 | 24 | 57
834 | 1.2.4.4.1.1.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 763 | 835 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Renderer | 100 | 83 | 35 | 56 | 23
835 | 1.2.4.4.1.1.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 832,833,834 | 836 | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Fire | 100 | 82 | 18 | 43 | 25
836 | 1.2.4.4.1.1.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 835 | 837 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Admin | 100 | 84 | 14 | 34 | 28
837 | 1.2.4.4.1.1.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 836 | 838 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Line Market | 100 | 84 | 23 | 79 | 51
838 | 1.2.4.4.1.1.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 837 | 839 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Contract Administrator | 100 | 52 | 32 | 36 | 27
839 | 1.2.4.4.1.1.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 838 | 840 | 1 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Scaffolder | 100 | 78 | 26 | 17 | 18
840 | 1.2.4.4.1.1.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 839 | 841 | 4 November 2024 8:00 AM | 2024-11-12 17:00 | 7 | Window | 100 | 26 | 35 | 87 | 41
841 | 1.2.4.4.1.1.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 840 | 842 | 6 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Formworker | 100 | 32 | 32 | 93 | 41
842 | 1.2.4.4.1.1.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 841 | 843,844,845,846 | 7 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Renderer | 100 | 23 | 17 | 93 | 13
843 | 1.2.4.4.1.1.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Stone Mason | 100 | 83 | 18 | 41 | 35
844 | 1.2.4.4.1.1.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Carpet | 100 | 12 | 24 | 34 | 7
845 | 1.2.4.4.1.1.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Stone Mason | 100 | 81 | 29 | 7 | 24
846 | 1.2.4.4.1.1.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Timber Floorer | 100 | 89 | 10 | 58 | 49
847 | 1.2.4.4.1.1.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 793,794,795,796,797 | 848 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Plumber | 100 | 26 | 20 | 23 | 22
848 | 1.2.4.4.1.1.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 847 | 849 | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Foreman | 100 | 67 | 20 | 68 | 55
849 | 1.2.4.4.1.1.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 848 | 850 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Fire | 100 | 18 | 30 | 34 | 29
850 | 1.2.4.4.1.1.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 849 |  | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Plasterboarder | 100 | 22 | 11 | 71 | 18
851 | 1.2.4.4.1.2 | Apartment B011 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | 14 October 2024 8:00 AM | 2024-12-05 17:00 | 0 | Formworker | 100 | 42 | 30 | 68 | 27
852 | 1.2.4.4.1.2.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 853,856,857,924 | 14 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Subcontractor | 100 | 73 | 33 | 49 | 59
853 | 1.2.4.4.1.2.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 852 | 855,854 | 16 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Line Market | 100 | 34 | 16 | 57 | 25
854 | 1.2.4.4.1.2.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 853 |  | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Formworker | 100 | 72 | 14 | 22 | 9
855 | 1.2.4.4.1.2.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 853 | 858 | 17 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Development Manager | 100 | 50 | 24 | 19 | 48
856 | 1.2.4.4.1.2.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 865 | 16 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Post Tension | 100 | 26 | 26 | 19 | 44
857 | 1.2.4.4.1.2.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 928 | 16 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Subcontractor | 100 | 71 | 10 | 26 | 20
858 | 1.2.4.4.1.2.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 855 | 859,860,861,862,863 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Landscaper | 100 | 10 | 35 | 1 | 45
859 | 1.2.4.4.1.2.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Carpet | 100 | 86 | 13 | 34 | 25
860 | 1.2.4.4.1.2.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863,927 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Line Market | 100 | 34 | 35 | 73 | 22
861 | 1.2.4.4.1.2.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 926 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Site Manager | 100 | 34 | 17 | 74 | 28
862 | 1.2.4.4.1.2.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 |  | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 1 | Surveyor | 100 | 42 | 28 | 68 | 39
863 | 1.2.4.4.1.2.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 858,859,860 | 864 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Project Manager | 100 | 47 | 15 | 21 | 2
864 | 1.2.4.4.1.2.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 863 | 865 | 26 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Site Manager | 100 | 53 | 11 | 99 | 41
865 | 1.2.4.4.1.2.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 856,864 | 866,867,868,869,871,873 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Hoarding | 100 | 87 | 12 | 46 | 36
866 | 1.2.4.4.1.2.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 870,873 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Admin | 100 | 68 | 35 | 73 | 4
867 | 1.2.4.4.1.2.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 873 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Plasterboarder | 100 | 28 | 20 | 20 | 3
868 | 1.2.4.4.1.2.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 872,873 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Stone Mason | 100 | 18 | 21 | 37 | 39
869 | 1.2.4.4.1.2.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Waterproofer | 100 | 91 | 17 | 7 | 45
870 | 1.2.4.4.1.2.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 866 | 873 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Scaffolder | 100 | 13 | 24 | 8 | 3
871 | 1.2.4.4.1.2.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Waterproofer | 100 | 83 | 16 | 76 | 25
872 | 1.2.4.4.1.2.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 868 | 873 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Surveyor | 100 | 84 | 11 | 12 | 24
873 | 1.2.4.4.1.2.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 865,866,867,868,869,870,871,872 | 874 | 4 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Hoarding | 100 | 100 | 33 | 18 | 27
874 | 1.2.4.4.1.2.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 873 | 875 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Contract Administrator | 100 | 95 | 28 | 85 | 32
875 | 1.2.4.4.1.2.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 874 | 876,893,910 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Fire | 100 | 92 | 14 | 100 | 23
876 | 1.2.4.4.1.2.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 877 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Excavation | 100 | 35 | 14 | 60 | 38
877 | 1.2.4.4.1.2.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 876 | 878 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Development Manager | 100 | 40 | 24 | 95 | 24
878 | 1.2.4.4.1.2.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 877 | 879 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Fire | 100 | 60 | 24 | 8 | 8
879 | 1.2.4.4.1.2.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 878 | 880 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Head Contractor | 100 | 44 | 15 | 34 | 24
880 | 1.2.4.4.1.2.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 879 | 881,882 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Stone Mason | 100 | 78 | 22 | 87 | 58
881 | 1.2.4.4.1.2.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 880 | 885 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Post Tension | 100 | 24 | 14 | 81 | 17
882 | 1.2.4.4.1.2.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 880 | 883 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Plumber | 100 | 96 | 14 | 63 | 58
883 | 1.2.4.4.1.2.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 882 | 884 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Waterproofer | 100 | 91 | 27 | 11 | 3
884 | 1.2.4.4.1.2.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 883 |  | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Reinforcement Fixer | 100 | 57 | 16 | 97 | 17
885 | 1.2.4.4.1.2.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 881 | 886,887,888,889,890 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Head Contractor | 100 | 34 | 13 | 67 | 52
886 | 1.2.4.4.1.2.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 885 |  | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Hoarding | 100 | 36 | 11 | 70 | 6
887 | 1.2.4.4.1.2.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Tiler | 100 | 68 | 22 | 70 | 37
888 | 1.2.4.4.1.2.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Surveyor | 100 | 28 | 31 | 30 | 40
889 | 1.2.4.4.1.2.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Site Manager | 100 | 48 | 24 | 66 | 6
890 | 1.2.4.4.1.2.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Renderer | 100 | 67 | 33 | 28 | 22
891 | 1.2.4.4.1.2.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 941 | 9 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Carpenter | 100 | 81 | 23 | 75 | 50
892 | 1.2.4.4.1.2.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Floor Sealer | 100 | 27 | 26 | 71 | 7
893 | 1.2.4.4.1.2.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 894 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Contract Administrator | 100 | 29 | 11 | 93 | 22
894 | 1.2.4.4.1.2.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 893 | 895 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Site Manager | 100 | 45 | 26 | 28 | 12
895 | 1.2.4.4.1.2.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 894 | 896 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Foreman | 100 | 55 | 20 | 92 | 58
896 | 1.2.4.4.1.2.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 895 | 897 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Scaffolder | 100 | 88 | 25 | 20 | 19
897 | 1.2.4.4.1.2.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 896 | 898 | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Development Manager | 100 | 52 | 18 | 18 | 6
898 | 1.2.4.4.1.2.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 897 | 899 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Project Manager | 100 | 27 | 21 | 24 | 41
899 | 1.2.4.4.1.2.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 898 | 900 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Plumber | 100 | 41 | 14 | 79 | 10
900 | 1.2.4.4.1.2.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 899 | 901 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Head Contractor | 100 | 46 | 11 | 89 | 52
901 | 1.2.4.4.1.2.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 900 | 902 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Hoarding | 100 | 30 | 25 | 35 | 3
902 | 1.2.4.4.1.2.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 901 | 903 | 25 November 2024 8:00 AM | 2024-11-29 17:00 | 4 | Electrician | 100 | 53 | 18 | 44 | 36
903 | 1.2.4.4.1.2.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 902 | 904 | 26 November 2024 8:00 AM | 2024-12-01 17:00 | 5 | Carpet | 100 | 66 | 13 | 94 | 40
904 | 1.2.4.4.1.2.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 903 | 908,905,906,907 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Landscaper | 100 | 46 | 17 | 65 | 50
905 | 1.2.4.4.1.2.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Scaffolder | 100 | 78 | 24 | 14 | 14
906 | 1.2.4.4.1.2.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Stone Mason | 100 | 38 | 24 | 8 | 37
907 | 1.2.4.4.1.2.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Painter | 100 | 57 | 16 | 10 | 41
908 | 1.2.4.4.1.2.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 904,905,906,907 |  | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Line Market | 100 | 94 | 26 | 8 | 53
909 | 1.2.4.4.1.2.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Mechanical | 100 | 96 | 15 | 31 | 42
910 | 1.2.4.4.1.2.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 911 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Scaffolder | 100 | 70 | 34 | 81 | 27
911 | 1.2.4.4.1.2.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 910 | 912 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Line Market | 100 | 10 | 31 | 53 | 46
912 | 1.2.4.4.1.2.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 911 | 913 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Joiner | 100 | 19 | 34 | 27 | 60
913 | 1.2.4.4.1.2.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 912 | 914 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Line Market | 100 | 14 | 28 | 65 | 48
914 | 1.2.4.4.1.2.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 913 | 915 | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Surveyor | 100 | 33 | 24 | 0 | 14
915 | 1.2.4.4.1.2.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 914 | 916 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Renderer | 100 | 54 | 12 | 75 | 30
916 | 1.2.4.4.1.2.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 915 | 917 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Carpet | 100 | 17 | 19 | 39 | 56
917 | 1.2.4.4.1.2.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 916 | 918,919,920,921 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Cleaner | 100 | 48 | 12 | 41 | 33
918 | 1.2.4.4.1.2.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Tiler | 100 | 81 | 16 | 67 | 53
919 | 1.2.4.4.1.2.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Surveyor | 100 | 51 | 16 | 8 | 28
920 | 1.2.4.4.1.2.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Tiler | 100 | 11 | 10 | 62 | 10
921 | 1.2.4.4.1.2.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Reinforcement Fixer | 100 | 48 | 17 | 82 | 26
922 | 1.2.4.4.1.2.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 918,919,920,921 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Stone Mason | 100 | 33 | 10 | 88 | 60
923 | 1.2.4.4.1.2.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-11-11 17:00 | 0 | Project Manager | 100 | 48 | 32 | 94 | 30
924 | 1.2.4.4.1.2.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 852 | 925 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Plasterboarder | 100 | 23 | 20 | 13 | 57
925 | 1.2.4.4.1.2.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 924 |  | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Formworker | 100 | 98 | 30 | 88 | 14
926 | 1.2.4.4.1.2.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 861 | 929 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Renderer | 100 | 75 | 27 | 60 | 44
927 | 1.2.4.4.1.2.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 860 | 929 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Carpenter | 100 | 71 | 35 | 79 | 42
928 | 1.2.4.4.1.2.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 857 | 929 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Timber Floorer | 100 | 92 | 19 | 28 | 36
929 | 1.2.4.4.1.2.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 926,927,928 | 930 | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Line Market | 100 | 38 | 11 | 62 | 50
930 | 1.2.4.4.1.2.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 929 | 931 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Joiner | 100 | 15 | 24 | 65 | 6
931 | 1.2.4.4.1.2.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 930 | 932 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Concretor | 100 | 26 | 29 | 74 | 12
932 | 1.2.4.4.1.2.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 931 | 933 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Timber Floorer | 100 | 45 | 21 | 28 | 38
933 | 1.2.4.4.1.2.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 932 | 934 | 1 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Stone Mason | 100 | 38 | 18 | 1 | 55
934 | 1.2.4.4.1.2.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 933 | 935 | 4 November 2024 8:00 AM | 2024-11-12 17:00 | 7 | Development Manager | 100 | 16 | 10 | 47 | 29
935 | 1.2.4.4.1.2.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 934 | 936 | 6 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Floor Sealer | 100 | 27 | 33 | 98 | 6
936 | 1.2.4.4.1.2.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 935 | 937,938,939,940 | 7 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Hoarding | 100 | 50 | 29 | 24 | 15
937 | 1.2.4.4.1.2.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Formworker | 100 | 67 | 16 | 6 | 31
938 | 1.2.4.4.1.2.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Hoarding | 100 | 37 | 14 | 59 | 10
939 | 1.2.4.4.1.2.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Concretor | 100 | 37 | 20 | 91 | 6
940 | 1.2.4.4.1.2.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Joiner | 100 | 20 | 33 | 64 | 19
941 | 1.2.4.4.1.2.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 887,888,889,890,891 | 942 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Timber Floorer | 100 | 87 | 16 | 30 | 44
942 | 1.2.4.4.1.2.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 941 | 943 | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Tiler | 100 | 48 | 26 | 45 | 7
943 | 1.2.4.4.1.2.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 942 | 944 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Renderer | 100 | 89 | 14 | 34 | 15
944 | 1.2.4.4.1.2.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 943 |  | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Contract Administrator | 100 | 42 | 11 | 66 | 37
945 | 1.2.4.4.1.3 | Apartment B012 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-12-07 17:00 | 0 | Waterproofer | 100 | 77 | 14 | 33 | 17
946 | 1.2.4.4.1.3.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 947,950,951,1018 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Carpet | 100 | 26 | 25 | 71 | 49
947 | 1.2.4.4.1.3.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 946 | 949,948 | 18 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Waterproofer | 100 | 83 | 20 | 77 | 38
948 | 1.2.4.4.1.3.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 947 |  | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Surveyor | 100 | 26 | 24 | 88 | 40
949 | 1.2.4.4.1.3.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 947 | 952 | 19 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Subcontractor | 100 | 42 | 31 | 97 | 4
950 | 1.2.4.4.1.3.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 959 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Scaffolder | 100 | 74 | 20 | 73 | 13
951 | 1.2.4.4.1.3.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 1022 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Electrician | 100 | 41 | 28 | 74 | 57
952 | 1.2.4.4.1.3.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 949 | 953,954,955,956,957 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Fire | 100 | 21 | 34 | 13 | 33
953 | 1.2.4.4.1.3.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Landscaper | 100 | 86 | 24 | 38 | 21
954 | 1.2.4.4.1.3.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957,1021 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Electrician | 100 | 62 | 22 | 90 | 19
955 | 1.2.4.4.1.3.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 1020 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Landscaper | 100 | 37 | 19 | 2 | 56
956 | 1.2.4.4.1.3.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 |  | 25 October 2024 8:00 AM | 2024-10-30 17:00 | 4 | Line Market | 100 | 19 | 31 | 22 | 10
957 | 1.2.4.4.1.3.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 952,953,954 | 958 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Fire | 100 | 65 | 25 | 97 | 41
958 | 1.2.4.4.1.3.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 957 | 959 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Floor Sealer | 100 | 56 | 16 | 33 | 39
959 | 1.2.4.4.1.3.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 950,958 | 960,961,962,963,965,967 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Electrician | 100 | 72 | 31 | 25 | 45
960 | 1.2.4.4.1.3.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 964,967 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Line Market | 100 | 86 | 29 | 14 | 30
961 | 1.2.4.4.1.3.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 967 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Admin | 100 | 34 | 29 | 43 | 10
962 | 1.2.4.4.1.3.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 966,967 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Electrician | 100 | 99 | 13 | 39 | 9
963 | 1.2.4.4.1.3.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Plasterboarder | 100 | 46 | 13 | 61 | 13
964 | 1.2.4.4.1.3.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 960 | 967 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Reinforcement Fixer | 100 | 84 | 13 | 66 | 56
965 | 1.2.4.4.1.3.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Scaffolder | 100 | 32 | 12 | 34 | 23
966 | 1.2.4.4.1.3.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 962 | 967 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Concretor | 100 | 42 | 35 | 81 | 34
967 | 1.2.4.4.1.3.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 959,960,961,962,963,964,965,966 | 968 | 6 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Hoarding | 100 | 64 | 33 | 76 | 17
968 | 1.2.4.4.1.3.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 967 | 969 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Site Manager | 100 | 94 | 33 | 88 | 22
969 | 1.2.4.4.1.3.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 968 | 970,987,1004 | 8 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Cleaner | 100 | 75 | 29 | 17 | 18
970 | 1.2.4.4.1.3.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 971 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Tiler | 100 | 66 | 14 | 42 | 42
971 | 1.2.4.4.1.3.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 970 | 972 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Subcontractor | 100 | 49 | 14 | 46 | 58
972 | 1.2.4.4.1.3.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 971 | 973 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Plasterboarder | 100 | 56 | 10 | 68 | 6
973 | 1.2.4.4.1.3.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 972 | 974 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Excavation | 100 | 34 | 20 | 30 | 46
974 | 1.2.4.4.1.3.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 973 | 975,976 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Mechanical | 100 | 16 | 32 | 93 | 55
975 | 1.2.4.4.1.3.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 974 | 979 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Fire | 100 | 42 | 34 | 39 | 55
976 | 1.2.4.4.1.3.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 974 | 977 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Timber Floorer | 100 | 52 | 10 | 86 | 20
977 | 1.2.4.4.1.3.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 976 | 978 | 20 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Subcontractor | 100 | 59 | 29 | 16 | 25
978 | 1.2.4.4.1.3.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 977 |  | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Excavation | 100 | 91 | 27 | 49 | 5
979 | 1.2.4.4.1.3.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 975 | 980,981,982,983,984 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Metal Work | 100 | 86 | 33 | 75 | 41
980 | 1.2.4.4.1.3.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 979 |  | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Carpenter | 100 | 37 | 26 | 4 | 8
981 | 1.2.4.4.1.3.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Contract Administrator | 100 | 44 | 28 | 75 | 7
982 | 1.2.4.4.1.3.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Carpet | 100 | 43 | 17 | 41 | 50
983 | 1.2.4.4.1.3.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Concretor | 100 | 74 | 35 | 45 | 59
984 | 1.2.4.4.1.3.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Carpet | 100 | 91 | 15 | 98 | 28
985 | 1.2.4.4.1.3.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1035 | 12 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Waterproofer | 100 | 29 | 29 | 71 | 27
986 | 1.2.4.4.1.3.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | 12 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Renderer | 100 | 40 | 27 | 69 | 55
987 | 1.2.4.4.1.3.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 988 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Site Manager | 100 | 16 | 11 | 14 | 21
988 | 1.2.4.4.1.3.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 987 | 989 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Admin | 100 | 81 | 25 | 75 | 27
989 | 1.2.4.4.1.3.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 988 | 990 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Foreman | 100 | 75 | 12 | 26 | 60
990 | 1.2.4.4.1.3.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 989 | 991 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Formworker | 100 | 12 | 31 | 40 | 41
991 | 1.2.4.4.1.3.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 990 | 992 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Formworker | 100 | 53 | 17 | 68 | 19
992 | 1.2.4.4.1.3.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 991 | 993 | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Subcontractor | 100 | 77 | 31 | 35 | 56
993 | 1.2.4.4.1.3.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 992 | 994 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Timber Floorer | 100 | 38 | 35 | 61 | 43
994 | 1.2.4.4.1.3.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 993 | 995 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Concretor | 100 | 41 | 24 | 10 | 28
995 | 1.2.4.4.1.3.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 994 | 996 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Metal Work | 100 | 22 | 18 | 14 | 50
996 | 1.2.4.4.1.3.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 995 | 997 | 27 November 2024 8:00 AM | 2024-11-30 17:00 | 3 | Joiner | 100 | 61 | 27 | 31 | 30
997 | 1.2.4.4.1.3.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 996 | 998 | 28 November 2024 8:00 AM | 2024-12-01 17:00 | 3 | Post Tension | 100 | 33 | 25 | 7 | 5
998 | 1.2.4.4.1.3.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 997 | 1002,999,1000,1001 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Subcontractor | 100 | 78 | 27 | 97 | 52
999 | 1.2.4.4.1.3.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Timber Floorer | 100 | 57 | 35 | 11 | 42
1000 | 1.2.4.4.1.3.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Mechanical | 100 | 24 | 10 | 62 | 56
1001 | 1.2.4.4.1.3.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Reinforcement Fixer | 100 | 77 | 18 | 100 | 6
1002 | 1.2.4.4.1.3.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 998,999,1000,1001 |  | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Cleaner | 100 | 86 | 35 | 71 | 50
1003 | 1.2.4.4.1.3.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | 12 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Fire | 100 | 56 | 12 | 79 | 18
1004 | 1.2.4.4.1.3.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 1005 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Admin | 100 | 39 | 25 | 66 | 31
1005 | 1.2.4.4.1.3.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1004 | 1006 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Admin | 100 | 96 | 28 | 85 | 29
1006 | 1.2.4.4.1.3.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1005 | 1007 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Mechanical | 100 | 56 | 29 | 32 | 39
1007 | 1.2.4.4.1.3.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1006 | 1008 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Excavation | 100 | 30 | 27 | 31 | 43
1008 | 1.2.4.4.1.3.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1007 | 1009 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Contract Administrator | 100 | 24 | 13 | 84 | 38
1009 | 1.2.4.4.1.3.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1008 | 1010 | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Floor Sealer | 100 | 77 | 21 | 92 | 11
1010 | 1.2.4.4.1.3.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1009 | 1011 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Electrician | 100 | 88 | 28 | 70 | 30
1011 | 1.2.4.4.1.3.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1010 | 1012,1013,1014,1015 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Development Manager | 100 | 27 | 32 | 28 | 26
1012 | 1.2.4.4.1.3.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Subcontractor | 100 | 93 | 13 | 29 | 6
1013 | 1.2.4.4.1.3.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Reinforcement Fixer | 100 | 40 | 15 | 48 | 52
1014 | 1.2.4.4.1.3.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 3 | Head Contractor | 100 | 27 | 21 | 14 | 9
1015 | 1.2.4.4.1.3.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Painter | 100 | 28 | 34 | 94 | 24
1016 | 1.2.4.4.1.3.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1012,1013,1014,1015 |  | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Renderer | 100 | 67 | 32 | 97 | 32
1017 | 1.2.4.4.1.3.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | 18 October 2024 8:00 AM | 2024-11-13 17:00 | 0 | Metal Work | 100 | 80 | 10 | 26 | 46
1018 | 1.2.4.4.1.3.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 946 | 1019 | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Carpenter | 100 | 44 | 17 | 93 | 31
1019 | 1.2.4.4.1.3.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1018 |  | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Reinforcement Fixer | 100 | 53 | 28 | 21 | 13
1020 | 1.2.4.4.1.3.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 955 | 1023 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Site Manager | 100 | 72 | 13 | 58 | 3
1021 | 1.2.4.4.1.3.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 954 | 1023 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Site Manager | 100 | 20 | 23 | 35 | 8
1022 | 1.2.4.4.1.3.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 951 | 1023 | 22 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Floor Sealer | 100 | 60 | 32 | 27 | 46
1023 | 1.2.4.4.1.3.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1020,1021,1022 | 1024 | 29 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Post Tension | 100 | 91 | 16 | 21 | 22
1024 | 1.2.4.4.1.3.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1023 | 1025 | 30 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Joiner | 100 | 16 | 12 | 99 | 23
1025 | 1.2.4.4.1.3.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1024 | 1026 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Scaffolder | 100 | 38 | 10 | 96 | 18
1026 | 1.2.4.4.1.3.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1025 | 1027 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Contract Administrator | 100 | 100 | 27 | 17 | 21
1027 | 1.2.4.4.1.3.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1026 | 1028 | 4 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Stone Mason | 100 | 14 | 30 | 79 | 22
1028 | 1.2.4.4.1.3.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1027 | 1029 | 6 November 2024 8:00 AM | 2024-11-12 17:00 | 5 | Excavation | 100 | 69 | 17 | 77 | 11
1029 | 1.2.4.4.1.3.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1028 | 1030 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Line Market | 100 | 28 | 17 | 58 | 38
1030 | 1.2.4.4.1.3.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1029 | 1031,1032,1033,1034 | 9 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Concretor | 100 | 95 | 31 | 89 | 56
1031 | 1.2.4.4.1.3.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Concretor | 100 | 60 | 17 | 5 | 27
1032 | 1.2.4.4.1.3.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Landscaper | 100 | 83 | 18 | 86 | 60
1033 | 1.2.4.4.1.3.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Project Manager | 100 | 46 | 26 | 32 | 47
1034 | 1.2.4.4.1.3.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Stone Mason | 100 | 17 | 11 | 0 | 56
1035 | 1.2.4.4.1.3.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 981,982,983,984,985 | 1036 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Post Tension | 100 | 69 | 21 | 48 | 51
1036 | 1.2.4.4.1.3.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1035 | 1037 | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Landscaper | 100 | 73 | 16 | 92 | 42
1037 | 1.2.4.4.1.3.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1036 | 1038 | 6 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Tiler | 100 | 19 | 20 | 54 | 45
1038 | 1.2.4.4.1.3.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1037 |  | 7 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Renderer | 100 | 55 | 18 | 47 | 13
1039 | 1.2.4.4.1.4 | Apartment B013 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-12-07 17:00 | 0 | Head Contractor | 100 | 25 | 35 | 22 | 42
1040 | 1.2.4.4.1.4.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 1041,1044,1045,1112 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Fire | 100 | 85 | 34 | 10 | 12
1041 | 1.2.4.4.1.4.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 1040 | 1043,1042 | 18 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Contract Administrator | 100 | 95 | 16 | 54 | 23
1042 | 1.2.4.4.1.4.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1041 |  | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Carpet | 100 | 79 | 11 | 96 | 54
1043 | 1.2.4.4.1.4.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1041 | 1046 | 19 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Joiner | 100 | 94 | 15 | 5 | 47
1044 | 1.2.4.4.1.4.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1053 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Reinforcement Fixer | 100 | 59 | 25 | 82 | 55
1045 | 1.2.4.4.1.4.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1116 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Surveyor | 100 | 57 | 18 | 84 | 19
1046 | 1.2.4.4.1.4.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1043 | 1047,1048,1049,1050,1051 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Carpenter | 100 | 49 | 13 | 8 | 41
1047 | 1.2.4.4.1.4.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Development Manager | 100 | 47 | 20 | 61 | 45
1048 | 1.2.4.4.1.4.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051,1115 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Tiler | 100 | 20 | 23 | 75 | 33
1049 | 1.2.4.4.1.4.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1114 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Plumber | 100 | 78 | 15 | 66 | 28
1050 | 1.2.4.4.1.4.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 |  | 25 October 2024 8:00 AM | 2024-11-01 17:00 | 6 | Scaffolder | 100 | 38 | 32 | 6 | 45
1051 | 1.2.4.4.1.4.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1046,1047,1048 | 1052 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Carpet | 100 | 89 | 31 | 44 | 4
1052 | 1.2.4.4.1.4.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1051 | 1053 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Head Contractor | 100 | 96 | 12 | 16 | 38
1053 | 1.2.4.4.1.4.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1044,1052 | 1054,1055,1056,1057,1059,1061 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Carpet | 100 | 71 | 24 | 14 | 6
1054 | 1.2.4.4.1.4.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1058,1061 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Landscaper | 100 | 34 | 24 | 2 | 20
1055 | 1.2.4.4.1.4.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1061 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Contract Administrator | 100 | 67 | 18 | 58 | 27
1056 | 1.2.4.4.1.4.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1060,1061 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Metal Work | 100 | 93 | 13 | 70 | 36
1057 | 1.2.4.4.1.4.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Surveyor | 100 | 40 | 13 | 24 | 55
1058 | 1.2.4.4.1.4.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1054 | 1061 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Window | 100 | 52 | 24 | 89 | 46
1059 | 1.2.4.4.1.4.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Contract Administrator | 100 | 81 | 23 | 2 | 3
1060 | 1.2.4.4.1.4.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1056 | 1061 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Cleaner | 100 | 20 | 24 | 94 | 39
1061 | 1.2.4.4.1.4.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1053,1054,1055,1056,1057,1058,1059,1060 | 1062 | 6 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Reinforcement Fixer | 100 | 23 | 19 | 87 | 52
1062 | 1.2.4.4.1.4.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1061 | 1063 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Development Manager | 100 | 54 | 35 | 66 | 36
1063 | 1.2.4.4.1.4.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1062 | 1064,1081,1098 | 8 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Development Manager | 100 | 77 | 15 | 54 | 55
1064 | 1.2.4.4.1.4.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1065 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Renderer | 100 | 61 | 31 | 70 | 2
1065 | 1.2.4.4.1.4.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1064 | 1066 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Plasterboarder | 100 | 12 | 27 | 83 | 40
1066 | 1.2.4.4.1.4.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1065 | 1067 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Post Tension | 100 | 40 | 25 | 69 | 26
1067 | 1.2.4.4.1.4.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1066 | 1068 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Carpet | 100 | 16 | 20 | 20 | 45
1068 | 1.2.4.4.1.4.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1067 | 1069,1070 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Electrician | 100 | 68 | 17 | 82 | 60
1069 | 1.2.4.4.1.4.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1068 | 1073 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Joiner | 100 | 80 | 35 | 22 | 23
1070 | 1.2.4.4.1.4.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1068 | 1071 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Reinforcement Fixer | 100 | 40 | 17 | 31 | 24
1071 | 1.2.4.4.1.4.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1070 | 1072 | 20 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Waterproofer | 100 | 48 | 17 | 53 | 3
1072 | 1.2.4.4.1.4.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1071 |  | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Window | 100 | 26 | 21 | 5 | 43
1073 | 1.2.4.4.1.4.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1069 | 1074,1075,1076,1077,1078 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Line Market | 100 | 54 | 33 | 90 | 35
1074 | 1.2.4.4.1.4.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1073 |  | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Line Market | 100 | 79 | 11 | 13 | 37
1075 | 1.2.4.4.1.4.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Reinforcement Fixer | 100 | 49 | 24 | 92 | 33
1076 | 1.2.4.4.1.4.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Electrician | 100 | 44 | 27 | 41 | 53
1077 | 1.2.4.4.1.4.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Post Tension | 100 | 45 | 16 | 26 | 42
1078 | 1.2.4.4.1.4.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Plumber | 100 | 99 | 21 | 51 | 54
1079 | 1.2.4.4.1.4.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1129 | 12 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Floor Sealer | 100 | 89 | 35 | 46 | 12
1080 | 1.2.4.4.1.4.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | 12 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Timber Floorer | 100 | 98 | 22 | 80 | 36
1081 | 1.2.4.4.1.4.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1082 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Admin | 100 | 92 | 14 | 0 | 53
1082 | 1.2.4.4.1.4.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1081 | 1083 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Line Market | 100 | 82 | 22 | 75 | 34
1083 | 1.2.4.4.1.4.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1082 | 1084 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Joiner | 100 | 17 | 13 | 98 | 24
1084 | 1.2.4.4.1.4.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1083 | 1085 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Waterproofer | 100 | 77 | 13 | 16 | 26
1085 | 1.2.4.4.1.4.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1084 | 1086 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Plasterboarder | 100 | 60 | 26 | 29 | 7
1086 | 1.2.4.4.1.4.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1085 | 1087 | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Subcontractor | 100 | 48 | 33 | 62 | 17
1087 | 1.2.4.4.1.4.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1086 | 1088 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Metal Work | 100 | 13 | 32 | 71 | 13
1088 | 1.2.4.4.1.4.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1087 | 1089 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Renderer | 100 | 19 | 31 | 84 | 54
1089 | 1.2.4.4.1.4.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1088 | 1090 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Carpenter | 100 | 17 | 27 | 46 | 8
1090 | 1.2.4.4.1.4.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1089 | 1091 | 27 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Timber Floorer | 100 | 68 | 21 | 78 | 22
1091 | 1.2.4.4.1.4.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1090 | 1092 | 28 November 2024 8:00 AM | 2024-12-02 17:00 | 4 | Site Manager | 100 | 43 | 12 | 5 | 43
1092 | 1.2.4.4.1.4.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1091 | 1096,1093,1094,1095 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Head Contractor | 100 | 31 | 22 | 53 | 13
1093 | 1.2.4.4.1.4.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Admin | 100 | 27 | 27 | 54 | 10
1094 | 1.2.4.4.1.4.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Hoarding | 100 | 81 | 12 | 17 | 60
1095 | 1.2.4.4.1.4.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Window | 100 | 80 | 31 | 3 | 16
1096 | 1.2.4.4.1.4.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1092,1093,1094,1095 |  | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Post Tension | 100 | 64 | 30 | 51 | 25
1097 | 1.2.4.4.1.4.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | 12 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Development Manager | 100 | 35 | 30 | 38 | 6
1098 | 1.2.4.4.1.4.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1099 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Tiler | 100 | 58 | 34 | 16 | 9
1099 | 1.2.4.4.1.4.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1098 | 1100 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Project Manager | 100 | 60 | 19 | 77 | 33
1100 | 1.2.4.4.1.4.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1099 | 1101 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Painter | 100 | 29 | 18 | 71 | 17
1101 | 1.2.4.4.1.4.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1100 | 1102 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Contract Administrator | 100 | 16 | 22 | 9 | 30
1102 | 1.2.4.4.1.4.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1101 | 1103 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Plumber | 100 | 12 | 33 | 61 | 17
1103 | 1.2.4.4.1.4.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1102 | 1104 | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Stone Mason | 100 | 91 | 15 | 73 | 28
1104 | 1.2.4.4.1.4.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1103 | 1105 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Landscaper | 100 | 81 | 11 | 20 | 17
1105 | 1.2.4.4.1.4.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1104 | 1106,1107,1108,1109 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Foreman | 100 | 12 | 26 | 83 | 7
1106 | 1.2.4.4.1.4.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Post Tension | 100 | 62 | 20 | 33 | 29
1107 | 1.2.4.4.1.4.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Hoarding | 100 | 36 | 24 | 59 | 37
1108 | 1.2.4.4.1.4.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | 26 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Excavation | 100 | 93 | 25 | 10 | 26
1109 | 1.2.4.4.1.4.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Painter | 100 | 19 | 30 | 94 | 7
1110 | 1.2.4.4.1.4.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1106,1107,1108,1109 |  | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Development Manager | 100 | 81 | 14 | 45 | 10
1111 | 1.2.4.4.1.4.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | 18 October 2024 8:00 AM | 2024-11-13 17:00 | 0 | Landscaper | 100 | 92 | 35 | 4 | 10
1112 | 1.2.4.4.1.4.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 1040 | 1113 | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Electrician | 100 | 51 | 30 | 80 | 10
1113 | 1.2.4.4.1.4.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1112 |  | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Development Manager | 100 | 63 | 34 | 74 | 36
1114 | 1.2.4.4.1.4.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1049 | 1117 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Post Tension | 100 | 49 | 34 | 71 | 9
1115 | 1.2.4.4.1.4.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1048 | 1117 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Post Tension | 100 | 11 | 27 | 60 | 36
1116 | 1.2.4.4.1.4.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1045 | 1117 | 22 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Electrician | 100 | 45 | 18 | 38 | 12
1117 | 1.2.4.4.1.4.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1114,1115,1116 | 1118 | 29 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Surveyor | 100 | 59 | 22 | 65 | 24
1118 | 1.2.4.4.1.4.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1117 | 1119 | 30 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Renderer | 100 | 91 | 29 | 20 | 13
1119 | 1.2.4.4.1.4.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1118 | 1120 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Subcontractor | 100 | 60 | 26 | 97 | 60
1120 | 1.2.4.4.1.4.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1119 | 1121 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Post Tension | 100 | 57 | 29 | 2 | 32
1121 | 1.2.4.4.1.4.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1120 | 1122 | 4 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Plumber | 100 | 67 | 26 | 12 | 20
1122 | 1.2.4.4.1.4.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1121 | 1123 | 6 November 2024 8:00 AM | 2024-11-09 17:00 | 2 | Hoarding | 100 | 27 | 31 | 61 | 36
1123 | 1.2.4.4.1.4.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1122 | 1124 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Contract Administrator | 100 | 12 | 28 | 41 | 37
1124 | 1.2.4.4.1.4.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1123 | 1125,1126,1127,1128 | 9 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Floor Sealer | 100 | 33 | 34 | 34 | 18
1125 | 1.2.4.4.1.4.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Mechanical | 100 | 11 | 33 | 7 | 31
1126 | 1.2.4.4.1.4.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Window | 100 | 80 | 30 | 52 | 24
1127 | 1.2.4.4.1.4.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Painter | 100 | 22 | 23 | 79 | 3
1128 | 1.2.4.4.1.4.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Subcontractor | 100 | 70 | 31 | 6 | 60
1129 | 1.2.4.4.1.4.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1075,1076,1077,1078,1079 | 1130 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Plasterboarder | 100 | 72 | 23 | 81 | 39
1130 | 1.2.4.4.1.4.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1129 | 1131 | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Renderer | 100 | 13 | 23 | 59 | 45
1131 | 1.2.4.4.1.4.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1130 | 1132 | 6 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Foreman | 100 | 17 | 20 | 100 | 21
1132 | 1.2.4.4.1.4.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1131 |  | 7 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Renderer | 100 | 75 | 14 | 23 | 50
1133 | 1.2.4.4.1.5 | Apartment B014 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | 18 October 2024 8:00 AM | 2024-12-10 17:00 | 0 | Joiner | 100 | 96 | 22 | 18 | 47
1134 | 1.2.4.4.1.5.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1135,1138,1139,1206 | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Contract Administrator | 100 | 73 | 12 | 76 | 37
1135 | 1.2.4.4.1.5.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1134 | 1137,1136 | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Formworker | 100 | 97 | 12 | 53 | 47
1136 | 1.2.4.4.1.5.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1135 |  | 22 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Project Manager | 100 | 17 | 10 | 54 | 29
1137 | 1.2.4.4.1.5.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1135 | 1140 | 22 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Line Market | 100 | 50 | 26 | 13 | 50
1138 | 1.2.4.4.1.5.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1147 | 21 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Reinforcement Fixer | 100 | 38 | 17 | 19 | 30
1139 | 1.2.4.4.1.5.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1210 | 21 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Site Manager | 100 | 45 | 18 | 63 | 37
1140 | 1.2.4.4.1.5.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1137 | 1141,1142,1143,1144,1145 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Renderer | 100 | 36 | 13 | 62 | 32
1141 | 1.2.4.4.1.5.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Hoarding | 100 | 80 | 33 | 33 | 25
1142 | 1.2.4.4.1.5.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145,1209 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Project Manager | 100 | 47 | 20 | 87 | 48
1143 | 1.2.4.4.1.5.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1208 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Hoarding | 100 | 74 | 16 | 94 | 33
1144 | 1.2.4.4.1.5.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 |  | 28 October 2024 8:00 AM | 2024-11-05 17:00 | 7 | Scaffolder | 100 | 77 | 20 | 41 | 40
1145 | 1.2.4.4.1.5.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1140,1141,1142 | 1146 | 30 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Timber Floorer | 100 | 100 | 25 | 96 | 37
1146 | 1.2.4.4.1.5.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1145 | 1147 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Electrician | 100 | 54 | 29 | 33 | 48
1147 | 1.2.4.4.1.5.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1138,1146 | 1148,1149,1150,1151,1153,1155 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Cleaner | 100 | 56 | 17 | 58 | 41
1148 | 1.2.4.4.1.5.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1152,1155 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Site Manager | 100 | 59 | 13 | 30 | 18
1149 | 1.2.4.4.1.5.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1155 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Electrician | 100 | 44 | 25 | 20 | 20
1150 | 1.2.4.4.1.5.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1154,1155 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Project Manager | 100 | 84 | 17 | 5 | 56
1151 | 1.2.4.4.1.5.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Waterproofer | 100 | 24 | 32 | 34 | 29
1152 | 1.2.4.4.1.5.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1148 | 1155 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Plumber | 100 | 79 | 25 | 93 | 43
1153 | 1.2.4.4.1.5.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Stone Mason | 100 | 73 | 35 | 56 | 46
1154 | 1.2.4.4.1.5.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1150 | 1155 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Hoarding | 100 | 68 | 29 | 38 | 21
1155 | 1.2.4.4.1.5.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1147,1148,1149,1150,1151,1152,1153,1154 | 1156 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Waterproofer | 100 | 77 | 31 | 20 | 46
1156 | 1.2.4.4.1.5.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1155 | 1157 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Admin | 100 | 33 | 13 | 58 | 36
1157 | 1.2.4.4.1.5.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1156 | 1158,1175,1192 | 11 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Electrician | 100 | 97 | 21 | 26 | 45
1158 | 1.2.4.4.1.5.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1159 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Contract Administrator | 100 | 24 | 14 | 66 | 55
1159 | 1.2.4.4.1.5.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1158 | 1160 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Admin | 100 | 52 | 34 | 24 | 39
1160 | 1.2.4.4.1.5.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1159 | 1161 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Fire | 100 | 38 | 21 | 75 | 15
1161 | 1.2.4.4.1.5.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1160 | 1162 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Plasterboarder | 100 | 88 | 29 | 27 | 47
1162 | 1.2.4.4.1.5.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1161 | 1163,1164 | 20 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Formworker | 100 | 29 | 21 | 100 | 32
1163 | 1.2.4.4.1.5.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1162 | 1167 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Scaffolder | 100 | 49 | 14 | 83 | 19
1164 | 1.2.4.4.1.5.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1162 | 1165 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Contract Administrator | 100 | 98 | 30 | 15 | 39
1165 | 1.2.4.4.1.5.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1164 | 1166 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Development Manager | 100 | 71 | 30 | 37 | 23
1166 | 1.2.4.4.1.5.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1165 |  | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Project Manager | 100 | 35 | 10 | 60 | 9
1167 | 1.2.4.4.1.5.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1163 | 1168,1169,1170,1171,1172 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Admin | 100 | 88 | 28 | 74 | 12
1168 | 1.2.4.4.1.5.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1167 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Admin | 100 | 55 | 29 | 3 | 37
1169 | 1.2.4.4.1.5.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Admin | 100 | 66 | 13 | 81 | 53
1170 | 1.2.4.4.1.5.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Joiner | 100 | 43 | 24 | 30 | 33
1171 | 1.2.4.4.1.5.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Cleaner | 100 | 35 | 14 | 73 | 8
1172 | 1.2.4.4.1.5.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Foreman | 100 | 99 | 14 | 72 | 55
1173 | 1.2.4.4.1.5.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1223 | 14 November 2024 8:00 AM | 2024-12-05 17:00 | 0 | Fire | 100 | 46 | 19 | 94 | 48
1174 | 1.2.4.4.1.5.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | 14 November 2024 8:00 AM | 2024-12-05 17:00 | 0 | Plumber | 100 | 89 | 28 | 26 | 33
1175 | 1.2.4.4.1.5.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1176 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Renderer | 100 | 14 | 26 | 7 | 37
1176 | 1.2.4.4.1.5.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1175 | 1177 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Formworker | 100 | 88 | 11 | 22 | 3
1177 | 1.2.4.4.1.5.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1176 | 1178 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Plumber | 100 | 34 | 24 | 16 | 34
1178 | 1.2.4.4.1.5.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1177 | 1179 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Subcontractor | 100 | 77 | 26 | 71 | 3
1179 | 1.2.4.4.1.5.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1178 | 1180 | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Carpenter | 100 | 87 | 30 | 35 | 51
1180 | 1.2.4.4.1.5.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1179 | 1181 | 22 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Timber Floorer | 100 | 68 | 30 | 93 | 48
1181 | 1.2.4.4.1.5.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1180 | 1182 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Carpenter | 100 | 56 | 29 | 80 | 42
1182 | 1.2.4.4.1.5.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1181 | 1183 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Renderer | 100 | 59 | 35 | 81 | 49
1183 | 1.2.4.4.1.5.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1182 | 1184 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Floor Sealer | 100 | 47 | 23 | 48 | 15
1184 | 1.2.4.4.1.5.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1183 | 1185 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Head Contractor | 100 | 29 | 23 | 45 | 8
1185 | 1.2.4.4.1.5.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1184 | 1186 | 30 November 2024 8:00 AM | 2024-12-01 17:00 | 1 | Development Manager | 100 | 86 | 27 | 28 | 9
1186 | 1.2.4.4.1.5.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1185 | 1190,1187,1188,1189 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Painter | 100 | 90 | 33 | 60 | 20
1187 | 1.2.4.4.1.5.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Development Manager | 100 | 87 | 13 | 81 | 34
1188 | 1.2.4.4.1.5.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Concretor | 100 | 39 | 14 | 73 | 15
1189 | 1.2.4.4.1.5.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Reinforcement Fixer | 100 | 28 | 32 | 96 | 3
1190 | 1.2.4.4.1.5.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1186,1187,1188,1189 |  | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Admin | 100 | 88 | 20 | 83 | 51
1191 | 1.2.4.4.1.5.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 14 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Timber Floorer | 100 | 93 | 11 | 57 | 9
1192 | 1.2.4.4.1.5.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1193 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Painter | 100 | 59 | 27 | 36 | 33
1193 | 1.2.4.4.1.5.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1192 | 1194 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Subcontractor | 100 | 79 | 35 | 49 | 48
1194 | 1.2.4.4.1.5.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1193 | 1195 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Surveyor | 100 | 35 | 15 | 95 | 45
1195 | 1.2.4.4.1.5.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1194 | 1196 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Landscaper | 100 | 94 | 11 | 74 | 29
1196 | 1.2.4.4.1.5.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1195 | 1197 | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Concretor | 100 | 86 | 19 | 3 | 2
1197 | 1.2.4.4.1.5.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1196 | 1198 | 22 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Foreman | 100 | 72 | 25 | 19 | 34
1198 | 1.2.4.4.1.5.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1197 | 1199 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Stone Mason | 100 | 97 | 33 | 48 | 22
1199 | 1.2.4.4.1.5.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1198 | 1200,1201,1202,1203 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Head Contractor | 100 | 11 | 31 | 22 | 45
1200 | 1.2.4.4.1.5.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Surveyor | 100 | 44 | 31 | 56 | 4
1201 | 1.2.4.4.1.5.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Project Manager | 100 | 42 | 34 | 54 | 11
1202 | 1.2.4.4.1.5.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | 28 November 2024 8:00 AM | 2024-12-05 17:00 | 6 | Waterproofer | 100 | 59 | 13 | 94 | 23
1203 | 1.2.4.4.1.5.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Concretor | 100 | 78 | 26 | 49 | 3
1204 | 1.2.4.4.1.5.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1200,1201,1202,1203 |  | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Post Tension | 100 | 59 | 24 | 84 | 27
1205 | 1.2.4.4.1.5.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-15 17:00 | 0 | Mechanical | 100 | 25 | 33 | 53 | 4
1206 | 1.2.4.4.1.5.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1134 | 1207 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Excavation | 100 | 69 | 30 | 67 | 45
1207 | 1.2.4.4.1.5.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1206 |  | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Reinforcement Fixer | 100 | 27 | 31 | 42 | 23
1208 | 1.2.4.4.1.5.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1143 | 1211 | 30 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Renderer | 100 | 19 | 10 | 2 | 32
1209 | 1.2.4.4.1.5.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1142 | 1211 | 30 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Joiner | 100 | 98 | 34 | 97 | 5
1210 | 1.2.4.4.1.5.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1139 | 1211 | 24 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Contract Administrator | 100 | 20 | 25 | 61 | 2
1211 | 1.2.4.4.1.5.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1208,1209,1210 | 1212 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Tiler | 100 | 38 | 26 | 4 | 34
1212 | 1.2.4.4.1.5.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1211 | 1213 | 1 November 2024 8:00 AM | 2024-11-01 17:00 | 0 | Mechanical | 100 | 46 | 14 | 30 | 3
1213 | 1.2.4.4.1.5.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1212 | 1214 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Site Manager | 100 | 42 | 32 | 33 | 13
1214 | 1.2.4.4.1.5.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1213 | 1215 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Site Manager | 100 | 35 | 13 | 22 | 53
1215 | 1.2.4.4.1.5.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1214 | 1216 | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Carpenter | 100 | 58 | 14 | 41 | 59
1216 | 1.2.4.4.1.5.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1215 | 1217 | 8 November 2024 8:00 AM | 2024-11-12 17:00 | 3 | Surveyor | 100 | 70 | 29 | 4 | 20
1217 | 1.2.4.4.1.5.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1216 | 1218 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Formworker | 100 | 59 | 30 | 32 | 38
1218 | 1.2.4.4.1.5.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1217 | 1219,1220,1221,1222 | 12 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Line Market | 100 | 30 | 18 | 6 | 6
1219 | 1.2.4.4.1.5.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Site Manager | 100 | 99 | 34 | 30 | 13
1220 | 1.2.4.4.1.5.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Landscaper | 100 | 40 | 15 | 9 | 51
1221 | 1.2.4.4.1.5.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Post Tension | 100 | 66 | 29 | 91 | 33
1222 | 1.2.4.4.1.5.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Metal Work | 100 | 34 | 27 | 83 | 15
1223 | 1.2.4.4.1.5.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1169,1170,1171,1172,1173 | 1224 | 6 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Window | 100 | 59 | 30 | 49 | 49
1224 | 1.2.4.4.1.5.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1223 | 1225 | 7 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Electrician | 100 | 85 | 29 | 44 | 19
1225 | 1.2.4.4.1.5.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1224 | 1226 | 9 December 2024 8:00 AM | 2024-12-09 17:00 | 0 | Excavation | 100 | 60 | 10 | 49 | 33
1226 | 1.2.4.4.1.5.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1225 |  | 10 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Surveyor | 100 | 36 | 19 | 33 | 24
1227 | 1.2.4.4.1.6 | Apartment B015 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | 18 October 2024 8:00 AM | 2024-12-10 17:00 | 0 | Window | 100 | 46 | 29 | 35 | 41
1228 | 1.2.4.4.1.6.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1229,1232,1233,1300 | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Subcontractor | 100 | 23 | 25 | 76 | 23
1229 | 1.2.4.4.1.6.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1228 | 1231,1230 | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Landscaper | 100 | 34 | 27 | 97 | 33
1230 | 1.2.4.4.1.6.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1229 |  | 22 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Painter | 100 | 25 | 22 | 12 | 59
1231 | 1.2.4.4.1.6.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1229 | 1234 | 22 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Site Manager | 100 | 29 | 10 | 59 | 28
1232 | 1.2.4.4.1.6.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1241 | 21 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Metal Work | 100 | 92 | 22 | 94 | 48
1233 | 1.2.4.4.1.6.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1304 | 21 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Head Contractor | 100 | 56 | 29 | 33 | 26
1234 | 1.2.4.4.1.6.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1231 | 1235,1236,1237,1238,1239 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Scaffolder | 100 | 12 | 19 | 38 | 57
1235 | 1.2.4.4.1.6.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Window | 100 | 51 | 18 | 59 | 50
1236 | 1.2.4.4.1.6.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239,1303 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Development Manager | 100 | 10 | 16 | 52 | 36
1237 | 1.2.4.4.1.6.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1302 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Concretor | 100 | 31 | 32 | 69 | 17
1238 | 1.2.4.4.1.6.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 |  | 28 October 2024 8:00 AM | 2024-11-03 17:00 | 5 | Admin | 100 | 32 | 32 | 45 | 28
1239 | 1.2.4.4.1.6.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1234,1235,1236 | 1240 | 30 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Joiner | 100 | 64 | 29 | 44 | 20
1240 | 1.2.4.4.1.6.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1239 | 1241 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Stone Mason | 100 | 80 | 30 | 97 | 41
1241 | 1.2.4.4.1.6.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1232,1240 | 1242,1243,1244,1245,1247,1249 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Plumber | 100 | 13 | 26 | 17 | 12
1242 | 1.2.4.4.1.6.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1246,1249 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Stone Mason | 100 | 61 | 13 | 19 | 21
1243 | 1.2.4.4.1.6.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1249 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Carpet | 100 | 61 | 27 | 11 | 9
1244 | 1.2.4.4.1.6.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1248,1249 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Waterproofer | 100 | 99 | 10 | 98 | 19
1245 | 1.2.4.4.1.6.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Plumber | 100 | 92 | 33 | 40 | 39
1246 | 1.2.4.4.1.6.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1242 | 1249 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Project Manager | 100 | 96 | 14 | 51 | 3
1247 | 1.2.4.4.1.6.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Concretor | 100 | 99 | 18 | 83 | 2
1248 | 1.2.4.4.1.6.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1244 | 1249 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Cleaner | 100 | 17 | 28 | 20 | 42
1249 | 1.2.4.4.1.6.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1241,1242,1243,1244,1245,1246,1247,1248 | 1250 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Tiler | 100 | 41 | 35 | 90 | 19
1250 | 1.2.4.4.1.6.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1249 | 1251 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Hoarding | 100 | 86 | 27 | 25 | 50
1251 | 1.2.4.4.1.6.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1250 | 1252,1269,1286 | 11 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Surveyor | 100 | 84 | 20 | 84 | 8
1252 | 1.2.4.4.1.6.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1253 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Post Tension | 100 | 71 | 24 | 55 | 50
1253 | 1.2.4.4.1.6.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1252 | 1254 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Site Manager | 100 | 72 | 25 | 45 | 43
1254 | 1.2.4.4.1.6.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1253 | 1255 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Foreman | 100 | 72 | 28 | 94 | 59
1255 | 1.2.4.4.1.6.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1254 | 1256 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Joiner | 100 | 67 | 34 | 51 | 34
1256 | 1.2.4.4.1.6.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1255 | 1257,1258 | 20 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Contract Administrator | 100 | 42 | 34 | 97 | 6
1257 | 1.2.4.4.1.6.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1256 | 1261 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Joiner | 100 | 10 | 35 | 91 | 5
1258 | 1.2.4.4.1.6.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1256 | 1259 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Post Tension | 100 | 100 | 23 | 87 | 51
1259 | 1.2.4.4.1.6.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1258 | 1260 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Renderer | 100 | 16 | 16 | 70 | 21
1260 | 1.2.4.4.1.6.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1259 |  | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Scaffolder | 100 | 42 | 23 | 62 | 57
1261 | 1.2.4.4.1.6.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1257 | 1262,1263,1264,1265,1266 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Joiner | 100 | 40 | 24 | 37 | 32
1262 | 1.2.4.4.1.6.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1261 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Line Market | 100 | 11 | 28 | 5 | 36
1263 | 1.2.4.4.1.6.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Tiler | 100 | 27 | 30 | 68 | 39
1264 | 1.2.4.4.1.6.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Post Tension | 100 | 74 | 11 | 22 | 48
1265 | 1.2.4.4.1.6.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Admin | 100 | 93 | 14 | 85 | 33
1266 | 1.2.4.4.1.6.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Metal Work | 100 | 21 | 15 | 57 | 24
1267 | 1.2.4.4.1.6.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1317 | 14 November 2024 8:00 AM | 2024-12-05 17:00 | 0 | Post Tension | 100 | 68 | 32 | 77 | 19
1268 | 1.2.4.4.1.6.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | 14 November 2024 8:00 AM | 2024-12-05 17:00 | 0 | Renderer | 100 | 45 | 19 | 8 | 20
1269 | 1.2.4.4.1.6.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1270 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Excavation | 100 | 38 | 12 | 2 | 50
1270 | 1.2.4.4.1.6.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1269 | 1271 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Project Manager | 100 | 34 | 21 | 76 | 16
1271 | 1.2.4.4.1.6.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1270 | 1272 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Development Manager | 100 | 85 | 31 | 87 | 36
1272 | 1.2.4.4.1.6.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1271 | 1273 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Renderer | 100 | 14 | 19 | 70 | 30
1273 | 1.2.4.4.1.6.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1272 | 1274 | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Foreman | 100 | 69 | 34 | 0 | 20
1274 | 1.2.4.4.1.6.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1273 | 1275 | 22 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Floor Sealer | 100 | 93 | 25 | 73 | 20
1275 | 1.2.4.4.1.6.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1274 | 1276 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Surveyor | 100 | 30 | 22 | 15 | 2
1276 | 1.2.4.4.1.6.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1275 | 1277 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Subcontractor | 100 | 39 | 32 | 46 | 4
1277 | 1.2.4.4.1.6.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1276 | 1278 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Line Market | 100 | 66 | 11 | 68 | 32
1278 | 1.2.4.4.1.6.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1277 | 1279 | 29 November 2024 8:00 AM | 2024-12-01 17:00 | 2 | Stone Mason | 100 | 12 | 20 | 100 | 15
1279 | 1.2.4.4.1.6.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1278 | 1280 | 30 November 2024 8:00 AM | 2024-12-04 17:00 | 4 | Carpet | 100 | 55 | 13 | 81 | 32
1280 | 1.2.4.4.1.6.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1279 | 1284,1281,1282,1283 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Admin | 100 | 63 | 29 | 91 | 5
1281 | 1.2.4.4.1.6.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Scaffolder | 100 | 80 | 35 | 40 | 44
1282 | 1.2.4.4.1.6.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Landscaper | 100 | 97 | 12 | 99 | 57
1283 | 1.2.4.4.1.6.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Landscaper | 100 | 49 | 17 | 95 | 3
1284 | 1.2.4.4.1.6.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1280,1281,1282,1283 |  | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Subcontractor | 100 | 42 | 33 | 15 | 7
1285 | 1.2.4.4.1.6.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 14 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Metal Work | 100 | 80 | 18 | 2 | 60
1286 | 1.2.4.4.1.6.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1287 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Concretor | 100 | 59 | 15 | 35 | 50
1287 | 1.2.4.4.1.6.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1286 | 1288 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Timber Floorer | 100 | 37 | 28 | 2 | 20
1288 | 1.2.4.4.1.6.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1287 | 1289 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Waterproofer | 100 | 67 | 32 | 72 | 29
1289 | 1.2.4.4.1.6.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1288 | 1290 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Head Contractor | 100 | 44 | 12 | 20 | 28
1290 | 1.2.4.4.1.6.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1289 | 1291 | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Landscaper | 100 | 64 | 20 | 6 | 14
1291 | 1.2.4.4.1.6.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1290 | 1292 | 22 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Development Manager | 100 | 87 | 32 | 87 | 33
1292 | 1.2.4.4.1.6.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1291 | 1293 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Metal Work | 100 | 49 | 18 | 98 | 43
1293 | 1.2.4.4.1.6.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1292 | 1294,1295,1296,1297 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Stone Mason | 100 | 64 | 12 | 32 | 49
1294 | 1.2.4.4.1.6.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Plasterboarder | 100 | 81 | 14 | 50 | 18
1295 | 1.2.4.4.1.6.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Post Tension | 100 | 89 | 30 | 46 | 11
1296 | 1.2.4.4.1.6.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | 28 November 2024 8:00 AM | 2024-12-02 17:00 | 3 | Scaffolder | 100 | 34 | 33 | 89 | 12
1297 | 1.2.4.4.1.6.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Contract Administrator | 100 | 84 | 35 | 28 | 46
1298 | 1.2.4.4.1.6.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1294,1295,1296,1297 |  | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Renderer | 100 | 14 | 35 | 10 | 22
1299 | 1.2.4.4.1.6.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-15 17:00 | 0 | Formworker | 100 | 50 | 24 | 38 | 54
1300 | 1.2.4.4.1.6.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1228 | 1301 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Landscaper | 100 | 47 | 27 | 31 | 29
1301 | 1.2.4.4.1.6.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1300 |  | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Concretor | 100 | 61 | 33 | 36 | 31
1302 | 1.2.4.4.1.6.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1237 | 1305 | 30 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Formworker | 100 | 64 | 17 | 71 | 13
1303 | 1.2.4.4.1.6.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1236 | 1305 | 30 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Waterproofer | 100 | 78 | 17 | 90 | 44
1304 | 1.2.4.4.1.6.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1233 | 1305 | 24 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Painter | 100 | 75 | 20 | 10 | 6
1305 | 1.2.4.4.1.6.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1302,1303,1304 | 1306 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Carpenter | 100 | 50 | 27 | 95 | 27
1306 | 1.2.4.4.1.6.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1305 | 1307 | 1 November 2024 8:00 AM | 2024-11-01 17:00 | 0 | Post Tension | 100 | 19 | 22 | 85 | 3
1307 | 1.2.4.4.1.6.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1306 | 1308 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Concretor | 100 | 94 | 28 | 17 | 46
1308 | 1.2.4.4.1.6.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1307 | 1309 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Mechanical | 100 | 26 | 34 | 54 | 28
1309 | 1.2.4.4.1.6.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1308 | 1310 | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Development Manager | 100 | 45 | 21 | 46 | 60
1310 | 1.2.4.4.1.6.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1309 | 1311 | 8 November 2024 8:00 AM | 2024-11-11 17:00 | 2 | Hoarding | 100 | 56 | 25 | 19 | 7
1311 | 1.2.4.4.1.6.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1310 | 1312 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Subcontractor | 100 | 88 | 23 | 3 | 50
1312 | 1.2.4.4.1.6.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1311 | 1313,1314,1315,1316 | 12 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Plasterboarder | 100 | 37 | 32 | 12 | 57
1313 | 1.2.4.4.1.6.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Plumber | 100 | 38 | 11 | 76 | 44
1314 | 1.2.4.4.1.6.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Mechanical | 100 | 28 | 13 | 26 | 23
1315 | 1.2.4.4.1.6.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Electrician | 100 | 21 | 22 | 15 | 42
1316 | 1.2.4.4.1.6.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Plumber | 100 | 34 | 14 | 12 | 38
1317 | 1.2.4.4.1.6.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1263,1264,1265,1266,1267 | 1318 | 6 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Timber Floorer | 100 | 89 | 27 | 100 | 53
1318 | 1.2.4.4.1.6.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1317 | 1319 | 7 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Excavation | 100 | 53 | 11 | 26 | 51
1319 | 1.2.4.4.1.6.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1318 | 1320 | 9 December 2024 8:00 AM | 2024-12-09 17:00 | 0 | Project Manager | 100 | 46 | 29 | 2 | 59
1320 | 1.2.4.4.1.6.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1319 |  | 10 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Reinforcement Fixer | 100 | 99 | 35 | 4 | 22
1321 | 1.2.4.4.1.7 | Apartment B016 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-12-12 17:00 | 0 | Floor Sealer | 100 | 37 | 17 | 59 | 20
1322 | 1.2.4.4.1.7.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1323,1326,1327,1394 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Window | 100 | 98 | 14 | 12 | 35
1323 | 1.2.4.4.1.7.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1322 | 1325,1324 | 23 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Electrician | 100 | 74 | 11 | 78 | 22
1324 | 1.2.4.4.1.7.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1323 |  | 24 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Subcontractor | 100 | 73 | 35 | 87 | 22
1325 | 1.2.4.4.1.7.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1323 | 1328 | 24 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Mechanical | 100 | 10 | 12 | 56 | 31
1326 | 1.2.4.4.1.7.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1335 | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Scaffolder | 100 | 82 | 17 | 39 | 56
1327 | 1.2.4.4.1.7.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1398 | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Tiler | 100 | 54 | 11 | 91 | 19
1328 | 1.2.4.4.1.7.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1325 | 1329,1330,1331,1332,1333 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Post Tension | 100 | 95 | 31 | 11 | 28
1329 | 1.2.4.4.1.7.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Timber Floorer | 100 | 40 | 11 | 11 | 48
1330 | 1.2.4.4.1.7.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333,1397 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Joiner | 100 | 28 | 21 | 28 | 30
1331 | 1.2.4.4.1.7.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1396 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Excavation | 100 | 55 | 16 | 45 | 21
1332 | 1.2.4.4.1.7.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 |  | 30 October 2024 8:00 AM | 2024-11-06 17:00 | 6 | Line Market | 100 | 51 | 20 | 49 | 12
1333 | 1.2.4.4.1.7.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1328,1329,1330 | 1334 | 1 November 2024 8:00 AM | 2024-11-01 17:00 | 0 | Metal Work | 100 | 20 | 10 | 100 | 14
1334 | 1.2.4.4.1.7.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1333 | 1335 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Hoarding | 100 | 81 | 16 | 18 | 30
1335 | 1.2.4.4.1.7.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1326,1334 | 1336,1337,1338,1339,1341,1343 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Carpet | 100 | 75 | 23 | 69 | 7
1336 | 1.2.4.4.1.7.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1340,1343 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Subcontractor | 100 | 32 | 27 | 3 | 10
1337 | 1.2.4.4.1.7.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1343 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Subcontractor | 100 | 100 | 27 | 47 | 2
1338 | 1.2.4.4.1.7.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1342,1343 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Hoarding | 100 | 59 | 13 | 97 | 4
1339 | 1.2.4.4.1.7.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Excavation | 100 | 43 | 24 | 53 | 24
1340 | 1.2.4.4.1.7.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1336 | 1343 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Tiler | 100 | 77 | 33 | 22 | 51
1341 | 1.2.4.4.1.7.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Post Tension | 100 | 97 | 35 | 87 | 6
1342 | 1.2.4.4.1.7.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1338 | 1343 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Formworker | 100 | 90 | 10 | 46 | 36
1343 | 1.2.4.4.1.7.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1335,1336,1337,1338,1339,1340,1341,1342 | 1344 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Site Manager | 100 | 32 | 16 | 21 | 6
1344 | 1.2.4.4.1.7.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1343 | 1345 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Site Manager | 100 | 84 | 20 | 3 | 15
1345 | 1.2.4.4.1.7.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1344 | 1346,1363,1380 | 13 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Mechanical | 100 | 36 | 32 | 54 | 19
1346 | 1.2.4.4.1.7.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1347 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Reinforcement Fixer | 100 | 50 | 35 | 77 | 54
1347 | 1.2.4.4.1.7.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1346 | 1348 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Window | 100 | 18 | 13 | 52 | 27
1348 | 1.2.4.4.1.7.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1347 | 1349 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Hoarding | 100 | 51 | 28 | 12 | 15
1349 | 1.2.4.4.1.7.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1348 | 1350 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Joiner | 100 | 40 | 19 | 90 | 32
1350 | 1.2.4.4.1.7.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1349 | 1351,1352 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Excavation | 100 | 38 | 23 | 47 | 31
1351 | 1.2.4.4.1.7.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1350 | 1355 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Contract Administrator | 100 | 74 | 15 | 49 | 13
1352 | 1.2.4.4.1.7.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1350 | 1353 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Foreman | 100 | 67 | 28 | 19 | 23
1353 | 1.2.4.4.1.7.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1352 | 1354 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Site Manager | 100 | 45 | 18 | 0 | 5
1354 | 1.2.4.4.1.7.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1353 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Plasterboarder | 100 | 29 | 19 | 40 | 51
1355 | 1.2.4.4.1.7.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1351 | 1356,1357,1358,1359,1360 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Painter | 100 | 91 | 22 | 70 | 41
1356 | 1.2.4.4.1.7.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1355 |  | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Landscaper | 100 | 79 | 27 | 25 | 9
1357 | 1.2.4.4.1.7.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Tiler | 100 | 76 | 17 | 78 | 5
1358 | 1.2.4.4.1.7.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Electrician | 100 | 18 | 31 | 99 | 27
1359 | 1.2.4.4.1.7.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Contract Administrator | 100 | 20 | 11 | 66 | 27
1360 | 1.2.4.4.1.7.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Joiner | 100 | 88 | 15 | 36 | 26
1361 | 1.2.4.4.1.7.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1411 | 16 November 2024 8:00 AM | 2024-12-07 17:00 | 0 | Foreman | 100 | 54 | 20 | 41 | 25
1362 | 1.2.4.4.1.7.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | 16 November 2024 8:00 AM | 2024-12-07 17:00 | 0 | Carpet | 100 | 55 | 27 | 89 | 36
1363 | 1.2.4.4.1.7.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1364 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Joiner | 100 | 64 | 28 | 59 | 43
1364 | 1.2.4.4.1.7.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1363 | 1365 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Project Manager | 100 | 82 | 34 | 43 | 36
1365 | 1.2.4.4.1.7.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1364 | 1366 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Landscaper | 100 | 70 | 24 | 29 | 19
1366 | 1.2.4.4.1.7.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1365 | 1367 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Hoarding | 100 | 67 | 23 | 43 | 58
1367 | 1.2.4.4.1.7.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1366 | 1368 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Contract Administrator | 100 | 31 | 16 | 14 | 43
1368 | 1.2.4.4.1.7.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1367 | 1369 | 25 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Line Market | 100 | 44 | 12 | 69 | 33
1369 | 1.2.4.4.1.7.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1368 | 1370 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Hoarding | 100 | 59 | 21 | 10 | 53
1370 | 1.2.4.4.1.7.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1369 | 1371 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Hoarding | 100 | 90 | 29 | 79 | 35
1371 | 1.2.4.4.1.7.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1370 | 1372 | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Tiler | 100 | 59 | 14 | 62 | 16
1372 | 1.2.4.4.1.7.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1371 | 1373 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Line Market | 100 | 86 | 27 | 86 | 13
1373 | 1.2.4.4.1.7.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1372 | 1374 | 3 December 2024 8:00 AM | 2024-12-10 17:00 | 7 | Electrician | 100 | 66 | 35 | 1 | 23
1374 | 1.2.4.4.1.7.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1373 | 1378,1375,1376,1377 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Development Manager | 100 | 96 | 30 | 78 | 52
1375 | 1.2.4.4.1.7.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | 5 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Project Manager | 100 | 90 | 34 | 51 | 14
1376 | 1.2.4.4.1.7.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | 5 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Site Manager | 100 | 46 | 21 | 6 | 46
1377 | 1.2.4.4.1.7.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | 5 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Joiner | 100 | 31 | 22 | 59 | 40
1378 | 1.2.4.4.1.7.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1374,1375,1376,1377 |  | 7 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Admin | 100 | 27 | 33 | 39 | 37
1379 | 1.2.4.4.1.7.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | 16 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Electrician | 100 | 20 | 13 | 51 | 37
1380 | 1.2.4.4.1.7.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1381 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Subcontractor | 100 | 78 | 34 | 19 | 3
1381 | 1.2.4.4.1.7.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1380 | 1382 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Painter | 100 | 52 | 34 | 97 | 2
1382 | 1.2.4.4.1.7.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1381 | 1383 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Metal Work | 100 | 24 | 28 | 62 | 59
1383 | 1.2.4.4.1.7.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1382 | 1384 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Post Tension | 100 | 26 | 29 | 14 | 11
1384 | 1.2.4.4.1.7.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1383 | 1385 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Landscaper | 100 | 98 | 35 | 58 | 39
1385 | 1.2.4.4.1.7.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1384 | 1386 | 25 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Electrician | 100 | 78 | 14 | 55 | 39
1386 | 1.2.4.4.1.7.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1385 | 1387 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Scaffolder | 100 | 69 | 34 | 66 | 27
1387 | 1.2.4.4.1.7.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1386 | 1388,1389,1390,1391 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Floor Sealer | 100 | 89 | 34 | 62 | 42
1388 | 1.2.4.4.1.7.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Head Contractor | 100 | 56 | 21 | 28 | 35
1389 | 1.2.4.4.1.7.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Carpet | 100 | 60 | 28 | 4 | 21
1390 | 1.2.4.4.1.7.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | 30 November 2024 8:00 AM | 2024-12-06 17:00 | 4 | Scaffolder | 100 | 25 | 30 | 45 | 30
1391 | 1.2.4.4.1.7.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Carpet | 100 | 22 | 18 | 22 | 39
1392 | 1.2.4.4.1.7.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1388,1389,1390,1391 |  | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Tiler | 100 | 68 | 18 | 100 | 57
1393 | 1.2.4.4.1.7.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | 23 October 2024 8:00 AM | 2024-11-18 17:00 | 0 | Excavation | 100 | 53 | 22 | 49 | 2
1394 | 1.2.4.4.1.7.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1322 | 1395 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Scaffolder | 100 | 62 | 30 | 48 | 8
1395 | 1.2.4.4.1.7.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1394 |  | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Tiler | 100 | 29 | 15 | 35 | 4
1396 | 1.2.4.4.1.7.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1331 | 1399 | 1 November 2024 8:00 AM | 2024-11-01 17:00 | 0 | Surveyor | 100 | 74 | 35 | 19 | 48
1397 | 1.2.4.4.1.7.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1330 | 1399 | 1 November 2024 8:00 AM | 2024-11-01 17:00 | 0 | Plasterboarder | 100 | 17 | 15 | 40 | 57
1398 | 1.2.4.4.1.7.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1327 | 1399 | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Line Market | 100 | 81 | 21 | 84 | 42
1399 | 1.2.4.4.1.7.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1396,1397,1398 | 1400 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Hoarding | 100 | 37 | 21 | 90 | 53
1400 | 1.2.4.4.1.7.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1399 | 1401 | 4 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Contract Administrator | 100 | 66 | 35 | 53 | 39
1401 | 1.2.4.4.1.7.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1400 | 1402 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Project Manager | 100 | 23 | 13 | 43 | 50
1402 | 1.2.4.4.1.7.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1401 | 1403 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Waterproofer | 100 | 76 | 19 | 57 | 26
1403 | 1.2.4.4.1.7.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1402 | 1404 | 8 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Line Market | 100 | 83 | 19 | 41 | 22
1404 | 1.2.4.4.1.7.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1403 | 1405 | 11 November 2024 8:00 AM | 2024-11-16 17:00 | 4 | Tiler | 100 | 47 | 29 | 37 | 7
1405 | 1.2.4.4.1.7.41.12 | Grout | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1404 | 1406 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Cleaner | 100 | 11 | 21 | 26 | 44
1406 | 1.2.4.4.1.7.41.13 | Paint/Cladding | 3 | 14 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1405 | 1407,1408,1409,1410 | 14 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Landscaper | 100 | 44 | 35 | 49 | 58
1407 | 1.2.4.4.1.7.41.14 | Silicone | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Reinforcement Fixer | 100 | 51 | 26 | 75 | 24
1408 | 1.2.4.4.1.7.41.15 | Hydraulic Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Subcontractor | 100 | 17 | 30 | 14 | 22
1409 | 1.2.4.4.1.7.41.16 | Electrical Fit Off | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Development Manager | 100 | 83 | 30 | 51 | 15
1410 | 1.2.4.4.1.7.41.17 | Fit Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Waterproofer | 100 | 83 | 16 | 100 | 22
1411 | 1.2.4.4.1.7.42 | Carpet Install | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1357,1358,1359,1360,1361 | 1412 | 9 December 2024 8:00 AM | 2024-12-09 17:00 | 0 | Admin | 100 | 100 | 26 | 97 | 41
1412 | 1.2.4.4.1.7.43 | Paint (FINAL Coat) | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1411 | 1413 | 10 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Carpenter | 100 | 75 | 26 | 74 | 7
1413 | 1.2.4.4.1.7.44 | FINAL CLEAN | 1 | 11 December 2024 8:00 AM | 11 December 2024 5:00 PM | 1412 | 1414 | 11 December 2024 8:00 AM | 2024-12-11 17:00 | 0 | Site Manager | 100 | 51 | 18 | 17 | 46
1414 | 1.2.4.4.1.7.45 | UNIT LOCKED | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 1413 |  | 12 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Subcontractor | 100 | 64 | 14 | 63 | 54
1415 | 1.2.4.4.1.8 | Apartment B017 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-12-12 17:00 | 0 | Post Tension | 100 | 12 | 30 | 70 | 37
1416 | 1.2.4.4.1.8.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1417,1420,1421,1488 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Surveyor | 100 | 46 | 20 | 32 | 26
1417 | 1.2.4.4.1.8.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1416 | 1419,1418 | 23 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Waterproofer | 100 | 95 | 18 | 10 | 50
1418 | 1.2.4.4.1.8.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1417 |  | 24 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Tiler | 100 | 49 | 19 | 91 | 39
1419 | 1.2.4.4.1.8.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1417 | 1422 | 24 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Cleaner | 100 | 24 | 34 | 87 | 38
1420 | 1.2.4.4.1.8.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1429 | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Site Manager | 100 | 76 | 29 | 83 | 39
1421 | 1.2.4.4.1.8.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1492 | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Formworker | 100 | 44 | 27 | 13 | 32
1422 | 1.2.4.4.1.8.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1419 | 1423,1424,1425,1426,1427 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Formworker | 100 | 62 | 11 | 56 | 34
1423 | 1.2.4.4.1.8.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Formworker | 100 | 27 | 26 | 33 | 18
1424 | 1.2.4.4.1.8.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427,1491 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Post Tension | 100 | 21 | 15 | 52 | 22
1425 | 1.2.4.4.1.8.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1490 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Fire | 100 | 21 | 35 | 89 | 30
1426 | 1.2.4.4.1.8.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 |  | 30 October 2024 8:00 AM | 2024-11-07 17:00 | 7 | Carpet | 100 | 36 | 35 | 11 | 54
1427 | 1.2.4.4.1.8.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1422,1423,1424 | 1428 | 1 November 2024 8:00 AM | 2024-11-01 17:00 | 0 | Formworker | 100 | 64 | 24 | 29 | 8
1428 | 1.2.4.4.1.8.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1427 | 1429 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Plasterboarder | 100 | 76 | 14 | 55 | 15
1429 | 1.2.4.4.1.8.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1420,1428 | 1430,1431,1432,1433,1435,1437 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Metal Work | 100 | 11 | 27 | 91 | 45
1430 | 1.2.4.4.1.8.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1434,1437 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Hoarding | 100 | 50 | 33 | 56 | 40
1431 | 1.2.4.4.1.8.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1437 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Carpet | 100 | 33 | 34 | 29 | 31
1432 | 1.2.4.4.1.8.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1436,1437 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Stone Mason | 100 | 73 | 31 | 54 | 19
1433 | 1.2.4.4.1.8.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Renderer | 100 | 95 | 19 | 48 | 8
1434 | 1.2.4.4.1.8.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1430 | 1437 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Foreman | 100 | 28 | 24 | 43 | 50
1435 | 1.2.4.4.1.8.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Tiler | 100 | 39 | 30 | 8 | 8
1436 | 1.2.4.4.1.8.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1432 | 1437 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Timber Floorer | 100 | 80 | 25 | 83 | 58
1437 | 1.2.4.4.1.8.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1429,1430,1431,1432,1433,1434,1435,1436 | 1438 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Mechanical | 100 | 64 | 21 | 98 | 23
1438 | 1.2.4.4.1.8.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1437 | 1439 | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Stone Mason | 100 | 83 | 28 | 42 | 4
1439 | 1.2.4.4.1.8.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1438 | 1440,1457,1474 | 13 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Foreman | 100 | 42 | 32 | 97 | 37
1440 | 1.2.4.4.1.8.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1441 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Contract Administrator | 100 | 56 | 25 | 62 | 31
1441 | 1.2.4.4.1.8.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1440 | 1442 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Carpet | 100 | 43 | 30 | 66 | 57
1442 | 1.2.4.4.1.8.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1441 | 1443 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Floor Sealer | 100 | 11 | 17 | 80 | 17
1443 | 1.2.4.4.1.8.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1442 | 1444 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Reinforcement Fixer | 100 | 39 | 25 | 10 | 58
1444 | 1.2.4.4.1.8.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1443 | 1445,1446 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Line Market | 100 | 47 | 26 | 15 | 35
1445 | 1.2.4.4.1.8.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1444 | 1449 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Hoarding | 100 | 95 | 31 | 28 | 17
1446 | 1.2.4.4.1.8.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1444 | 1447 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Development Manager | 100 | 80 | 16 | 18 | 5
1447 | 1.2.4.4.1.8.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1446 | 1448 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Head Contractor | 100 | 45 | 30 | 41 | 56
1448 | 1.2.4.4.1.8.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1447 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Renderer | 100 | 15 | 18 | 80 | 50
1449 | 1.2.4.4.1.8.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1445 | 1450,1451,1452,1453,1454 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Surveyor | 100 | 91 | 28 | 80 | 51
1450 | 1.2.4.4.1.8.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1449 |  | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Cleaner | 100 | 24 | 27 | 94 | 15
1451 | 1.2.4.4.1.8.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Floor Sealer | 100 | 15 | 18 | 98 | 11
1452 | 1.2.4.4.1.8.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Subcontractor | 100 | 62 | 20 | 89 | 45
1453 | 1.2.4.4.1.8.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Renderer | 100 | 54 | 33 | 34 | 36
1454 | 1.2.4.4.1.8.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Cleaner | 100 | 92 | 22 | 79 | 19
1455 | 1.2.4.4.1.8.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1505 | 16 November 2024 8:00 AM | 2024-12-07 17:00 | 0 | Mechanical | 100 | 97 | 15 | 23 | 48
1456 | 1.2.4.4.1.8.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | 16 November 2024 8:00 AM | 2024-12-07 17:00 | 0 | Carpet | 100 | 70 | 26 | 87 | 54
1457 | 1.2.4.4.1.8.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1458 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Mechanical | 100 | 36 | 27 | 5 | 34
1458 | 1.2.4.4.1.8.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1457 | 1459 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Foreman | 100 | 15 | 33 | 9 | 8
1459 | 1.2.4.4.1.8.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1458 | 1460 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Waterproofer | 100 | 34 | 17 | 34 | 32
1460 | 1.2.4.4.1.8.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1459 | 1461 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 100 | 86 | 31 | 34 | 21
1461 | 1.2.4.4.1.8.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1460 | 1462 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Carpet | 100 | 11 | 18 | 71 | 39
1462 | 1.2.4.4.1.8.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1461 | 1463 | 25 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Admin | 100 | 87 | 10 | 72 | 34
1463 | 1.2.4.4.1.8.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1462 | 1464 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Scaffolder | 100 | 36 | 23 | 54 | 24
1464 | 1.2.4.4.1.8.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1463 | 1465 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Joiner | 100 | 11 | 32 | 15 | 49
1465 | 1.2.4.4.1.8.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1464 | 1466 | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Painter | 100 | 98 | 24 | 73 | 27
1466 | 1.2.4.4.1.8.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1465 | 1467 | 2 December 2024 8:00 AM | 2024-12-04 17:00 | 2 | Foreman | 100 | 13 | 18 | 12 | 35
1467 | 1.2.4.4.1.8.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1466 | 1468 | 3 December 2024 8:00 AM | 2024-12-06 17:00 | 3 | Plasterboarder | 100 | 54 | 13 | 69 | 17
1468 | 1.2.4.4.1.8.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1467 | 1472,1469,1470,1471 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Plasterboarder | 100 | 71 | 19 | 11 | 33
1469 | 1.2.4.4.1.8.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | 5 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Window | 100 | 15 | 30 | 98 | 49
1470 | 1.2.4.4.1.8.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | 5 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Electrician | 100 | 10 | 15 | 69 | 48
1471 | 1.2.4.4.1.8.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | 5 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Reinforcement Fixer | 100 | 41 | 11 | 54 | 54
1472 | 1.2.4.4.1.8.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1468,1469,1470,1471 |  | 7 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Carpenter | 100 | 72 | 17 | 87 | 41
1473 | 1.2.4.4.1.8.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | 16 November 2024 8:00 AM | 2024-12-03 17:00 | 0 | Project Manager | 100 | 92 | 24 | 69 | 59
1474 | 1.2.4.4.1.8.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1475 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Metal Work | 100 | 61 | 23 | 53 | 9
1475 | 1.2.4.4.1.8.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1474 | 1476 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Formworker | 100 | 12 | 25 | 65 | 34
1476 | 1.2.4.4.1.8.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1475 | 1477 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Landscaper | 100 | 59 | 33 | 26 | 23
1477 | 1.2.4.4.1.8.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1476 | 1478 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Fire | 100 | 64 | 31 | 27 | 12
1478 | 1.2.4.4.1.8.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1477 | 1479 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Head Contractor | 100 | 42 | 33 | 82 | 56
1479 | 1.2.4.4.1.8.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1478 | 1480 | 25 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Contract Administrator | 100 | 66 | 28 | 67 | 51
1480 | 1.2.4.4.1.8.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1479 | 1481 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Project Manager | 100 | 52 | 12 | 49 | 16
1481 | 1.2.4.4.1.8.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1480 | 1482,1483,1484,1485 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Window | 100 | 41 | 33 | 15 | 7
1482 | 1.2.4.4.1.8.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Timber Floorer | 100 | 20 | 27 | 10 | 8
1483 | 1.2.4.4.1.8.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Renderer | 100 | 81 | 14 | 37 | 6
1484 | 1.2.4.4.1.8.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | 30 November 2024 8:00 AM | 2024-12-03 17:00 | 1 | Painter | 100 | 16 | 30 | 64 | 37
1485 | 1.2.4.4.1.8.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Plasterboarder | 100 | 59 | 29 | 91 | 10
1486 | 1.2.4.4.1.8.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1482,1483,1484,1485 |  | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Project Manager | 100 | 62 | 33 | 86 | 23
1487 | 1.2.4.4.1.8.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | 23 October 2024 8:00 AM | 2024-11-18 17:00 | 0 | Head Contractor | 100 | 48 | 26 | 37 | 20
1488 | 1.2.4.4.1.8.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1416 | 1489 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Floor Sealer | 100 | 51 | 16 | 32 | 56
1489 | 1.2.4.4.1.8.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1488 |  | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Joiner | 100 | 50 | 21 | 65 | 53
1490 | 1.2.4.4.1.8.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1425 | 1493 | 1 November 2024 8:00 AM | 2024-11-01 17:00 | 0 | Admin | 100 | 24 | 26 | 85 | 48
1491 | 1.2.4.4.1.8.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1424 | 1493 | 1 November 2024 8:00 AM | 2024-11-01 17:00 | 0 | Line Market | 100 | 79 | 11 | 90 | 30
1492 | 1.2.4.4.1.8.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1421 | 1493 | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Scaffolder | 100 | 31 | 12 | 80 | 59
1493 | 1.2.4.4.1.8.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1490,1491,1492 | 1494 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Surveyor | 100 | 63 | 24 | 38 | 55
1494 | 1.2.4.4.1.8.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1493 | 1495 | 4 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Concretor | 100 | 73 | 22 | 82 | 44
1495 | 1.2.4.4.1.8.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1494 | 1496 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Waterproofer | 100 | 99 | 25 | 9 | 24
1496 | 1.2.4.4.1.8.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1495 | 1497 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Development Manager | 100 | 13 | 35 | 65 | 56
1497 | 1.2.4.4.1.8.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1496 | 1498 | 8 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Scaffolder | 100 | 28 | 19 | 44 | 15
1498 | 1.2.4.4.1.8.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1497 | 1499 | 11 November 2024 8:00 AM | 2024-11-18 17:00 | 6 | Surveyor | 100 | 86 | 31 | 94 | 60

## Trade List
Trade Name
Tiler
Line Market
Landscaper
Surveyor | 12
Painter
Reinforcement Fixer
Project Manager
Post Tension
Plumber
Cleaner
Plasterboarder
Joiner
Excavation
Concretor
Waterproofer |  | 2 | 1900-01-04 | 3
Site Manager
Floor Sealer
Fire
Window
Mechanical
Head Contractor
Development Manager
Scaffolder
Hoarding
Carpenter
Admin
Renderer
Subcontractor
Contract Administrator
Carpet
Electrician
Stone Mason
Timber Floorer
Metal Work
Foreman
Formworker