## Task_Table1
ID | Outline_Number | Name | Duration | StartDate | EndDate | Predecessors | Successors | ActualStartDate | ActualEndDate | Delay | Trade | Progress | WorkerScore | Temperature | RainProb | WindSpeed
2 | 1.1 | MILESTONES / KEY DATES | 633 | 17 April 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 17 April 2023 7:00 AM | 2025-06-24 17:00 | 1 | Carpenter | 10 | 35 | 21 | 37 | 7
3 | 1.1.1 | Site Establishment | 0 | 5 June 2023 7:00 AM | 5 June 2023 7:00 AM |  | 25SS | 5 June 2023 7:00 AM | 2023-06-05 07:00 | 0 | Plasterboarder | 79 | 33 | 30 | 69 | 19
4 | 1.1.2 | Basement Completed (B2) | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 88 |  | 2 May 2024 5:00 PM | 2024-05-05 17:00 | 3 | Timber Floorer | 72 | 93 | 24 | 2 | 16
5 | 1.1.3 | Building A Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 444,753,746,714 | 3466,9 | 5 May 2025 5:00 PM | 2025-05-07 17:00 | 2 | Floor Sealer | 16 | 72 | 30 | 36 | 57
6 | 1.1.4 | Building B Complete | 0 | 29 March 2025 5:00 PM | 29 March 2025 5:00 PM | 228,482,306,1737 | 3466,9 | 29 March 2025 5:00 PM | 2025-03-30 17:00 | 1 | Scaffolder | 12 | 89 | 22 | 78 | 33
7 | 1.1.5 | Building C Complete | 0 | 16 April 2025 5:00 PM | 16 April 2025 5:00 PM | 306,360,503,3169 | 3466,9 | 16 April 2025 5:00 PM | 2025-04-20 17:00 | 4 | Painter | 25 | 19 | 14 | 44 | 60
8 | 1.1.6 | Building D Complete | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 360,396,519,3439 | 3466,9 | 17 April 2025 5:00 PM | 2025-04-17 17:00 | 0 | Post Tension | 34 | 72 | 18 | 31 | 43
9 | 1.1.7 | Practical Completion (Net) | 0 | 28 May 2025 5:00 PM | 28 May 2025 5:00 PM | 3465,3440,5,3460,6,7,8 |  | 28 May 2025 5:00 PM | 2025-05-28 17:00 | 0 | Admin | 42 | 56 | 30 | 35 | 39
10 | 1.1.8 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | 28 July 2023 8:00 AM | 2023-08-18 17:00 | 3 | Plasterboarder | 50 | 34 | 14 | 40 | 35
11 | 1.1.9 | Inclement Weatherallowed (Spent) | 19 | 29 May 2025 8:00 AM | 21 June 2025 5:00 PM | 3466 | 12 | 29 May 2025 8:00 AM | 2025-06-24 17:00 | 3 | Subcontractor | 59 | 15 | 12 | 75 | 32
12 | 1.1.10 | Inclement Weatherallowed (Remaining) | 1 | 23 June 2025 8:00 AM | 23 June 2025 5:00 PM | 11 | 3469 | 23 June 2025 8:00 AM | 2025-06-24 17:00 | 1 | Painter | 79 | 50 | 33 | 73 | 35
13 | 1.1.11 | Practical Completion (Gross) - Building Handover | 0 | 23 June 2025 5:00 PM | 23 June 2025 5:00 PM | 3469 |  | 23 June 2025 5:00 PM | 2025-06-23 17:00 | 0 | Contract Administrator | 15 | 88 | 22 | 67 | 45
14 | 1.1.12 | PRE CONSTRUCTION WORKS | 210.13 | 17 April 2023 7:00 AM | 16 January 2024 5:00 PM |  |  | 17 April 2023 7:00 AM | 2024-01-18 17:00 | 2 | Stone Mason | 47 | 70 | 22 | 98 | 35
15 | 1.1.12.1 | Authority Approvals, (Access Deeds by Client etc (Ultra to assist in coordination) These are qualifying causes of delay resulting in EOT time & costs) | 372 | 17 April 2023 7:00 AM | 1 August 2024 5:00 PM |  |  | 17 April 2023 7:00 AM | 2024-08-02 17:00 | 1 | Scaffolder | 44 | 19 | 24 | 60 | 26
16 | 1.1.12.1.1 | Section 73 - BPA Design & Stormwater Works | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | 17 April 2023 7:00 AM | 2023-04-20 07:00 | 3 | Mechanical | 42 | 85 | 35 | 39 | 22
17 | 1.1.12.1.2 | Rail Approval | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  |  | 17 April 2023 7:00 AM | 2023-04-19 07:00 | 2 | Scaffolder | 74 | 63 | 17 | 5 | 5
18 | 1.1.12.1.3 | CC1 - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM |  | 25,19 | 17 April 2023 7:00 AM | 2023-04-19 07:00 | 2 | Electrician | 14 | 93 | 19 | 7 | 35
19 | 1.1.12.1.4 | CC1a - Shoring & Excavations | 0 | 17 April 2023 7:00 AM | 17 April 2023 7:00 AM | 18 | 25,20 | 17 April 2023 7:00 AM | 2023-04-19 07:00 | 2 | Post Tension | 49 | 60 | 35 | 80 | 46
20 | 1.1.12.1.5 | CC2 - Structure (SoG - Podium) | 120 | 17 April 2023 8:00 AM | 12 September 2023 5:00 PM | 19 | 21 | 17 April 2023 8:00 AM | 2023-09-12 17:00 | 0 | Floor Sealer | 41 | 75 | 15 | 51 | 10
21 | 1.1.12.1.6 | CC3 - Structure (Podium - Roof) + Facade | 156 | 13 September 2023 8:00 AM | 8 April 2024 5:00 PM | 20 | 22 | 13 September 2023 8:00 AM | 2024-04-10 17:00 | 2 | Window | 32 | 13 | 24 | 47 | 16
22 | 1.1.12.1.7 | CC4 - Services & Fit Out | 60 | 9 April 2024 8:00 AM | 20 June 2024 5:00 PM | 21 | 23 | 9 April 2024 8:00 AM | 2024-06-23 17:00 | 3 | Plumber | 7 | 71 | 25 | 85 | 39
23 | 1.1.12.1.8 | CC5 - External Works and Public Domain | 36 | 21 June 2024 8:00 AM | 1 August 2024 5:00 PM | 22 |  | 21 June 2024 8:00 AM | 2024-08-05 17:00 | 4 | Development Manager | 33 | 46 | 24 | 87 | 24
24 | 1.1.12.2 | SITE ESTABLISHMENT | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM |  |  | 26 June 2023 8:00 AM | 2023-07-03 17:00 | 3 | Head Contractor | 52 | 85 | 10 | 99 | 53
25 | 1.1.12.2.1 | Site Establishment, Enviro Protection, Survey Set out & Hoardings | 5 | 26 June 2023 8:00 AM | 30 June 2023 5:00 PM | 18,3SS,19 | 28 | 26 June 2023 8:00 AM | 2023-07-02 17:00 | 2 | Painter | 92 | 22 | 30 | 48 | 39
26 | 1.2 | CONSTRUCTION WORKS | 571 | 3 July 2023 7:00 AM | 23 June 2025 5:00 PM |  |  | 3 July 2023 7:00 AM | 2025-06-24 17:00 | 1 | Mechanical | 66 | 65 | 11 | 2 | 33
27 | 1.2.1 | EARTHWORKS, PILING - BASEMENT | 234 | 3 July 2023 7:00 AM | 2 May 2024 5:00 PM |  |  | 3 July 2023 7:00 AM | 2024-05-04 17:00 | 2 | Contract Administrator | 73 | 25 | 23 | 51 | 8
28 | 1.2.1.1 | Demolition, Clear & Cut/Level Site | 6 | 3 July 2023 7:00 AM | 8 July 2023 5:00 PM | 25 | 10SS,29SS | 3 July 2023 7:00 AM | 2023-07-09 17:00 | 1 | Plasterboarder | 27 | 22 | 25 | 82 | 58
29 | 1.2.1.2 | EOT01 - Site Remediation (APPROVED) | 15 | 28 July 2023 8:00 AM | 15 August 2023 5:00 PM | 28SS | 30 | 28 July 2023 8:00 AM | 2023-08-18 17:00 | 3 | Head Contractor | 63 | 26 | 29 | 29 | 19
30 | 1.2.1.3 | Install Piling Matt | 12 | 16 August 2023 8:00 AM | 30 August 2023 5:00 PM | 10,29 | 34FS-6d | 16 August 2023 8:00 AM | 2023-08-31 17:00 | 1 | Tiler | 72 | 11 | 21 | 74 | 41
31 | 1.2.1.4 | Crane Base Ex, Piles & FRP | 8 | 18 December 2023 8:00 AM | 5 January 2024 5:00 PM | 53 | 3442FS+8d | 18 December 2023 8:00 AM | 2024-01-05 17:00 | 0 | Cleaner | 99 | 44 | 29 | 28 | 18
32 | 1.2.1.5 | Piling and Capping Beam | 58 | 28 August 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | 28 August 2023 8:00 AM | 2023-11-11 17:00 | 2 | Concretor | 53 | 14 | 26 | 34 | 47
33 | 1.2.1.5.1 | Buildings A | 28 | 28 August 2023 8:00 AM | 3 October 2023 5:00 PM |  |  | 28 August 2023 8:00 AM | 2023-10-04 17:00 | 1 | Formworker | 82 | 45 | 22 | 36 | 9
34 | 1.2.1.5.1.1 | Perimeter Piling (75 Piles) | 16 | 28 August 2023 8:00 AM | 15 September 2023 5:00 PM | 30FS-6d | 35FS-6d,37,46 | 28 August 2023 8:00 AM | 2023-09-18 17:00 | 3 | Electrician | 54 | 54 | 20 | 97 | 34
35 | 1.2.1.5.1.2 | Capping Beam - Detailed Excavation & FRP | 18 | 9 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34FS-6d |  | 9 September 2023 8:00 AM | 2023-10-06 17:00 | 3 | Metal Work | 87 | 74 | 14 | 48 | 11
36 | 1.2.1.5.2 | Buildings B | 24 | 16 September 2023 8:00 AM | 17 October 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-10-19 17:00 | 2 | Renderer | 95 | 40 | 32 | 55 | 50
37 | 1.2.1.5.2.1 | Perimeter Piling (56 Piles) | 12 | 16 September 2023 8:00 AM | 3 October 2023 5:00 PM | 34 | 38FS-6d,40 | 16 September 2023 8:00 AM | 2023-10-04 17:00 | 1 | Carpenter | 86 | 71 | 11 | 93 | 37
38 | 1.2.1.5.2.2 | Capping Beam - Detailed Excavation & FRP | 18 | 25 September 2023 8:00 AM | 17 October 2023 5:00 PM | 37FS-6d | 56 | 25 September 2023 8:00 AM | 2023-10-17 17:00 | 0 | Development Manager | 18 | 88 | 10 | 11 | 60
39 | 1.2.1.5.3 | Buildings C & D | 30 | 4 October 2023 8:00 AM | 9 November 2023 5:00 PM |  |  | 4 October 2023 8:00 AM | 2023-11-09 17:00 | 0 | Foreman | 32 | 16 | 11 | 37 | 11
40 | 1.2.1.5.3.1 | Foundation Piling (Gnd Lvl) - (17 Piles) | 6 | 4 October 2023 8:00 AM | 10 October 2023 5:00 PM | 37 | 41 | 4 October 2023 8:00 AM | 2023-10-13 17:00 | 3 | Cleaner | 74 | 70 | 34 | 70 | 4
41 | 1.2.1.5.3.2 | Perimeter Piling (82 Piles) | 18 | 11 October 2023 8:00 AM | 1 November 2023 5:00 PM | 40 | 42FS-6d | 11 October 2023 8:00 AM | 2023-11-02 17:00 | 1 | Reinforcement Fixer | 4 | 79 | 19 | 79 | 48
42 | 1.2.1.5.3.3 | Capping Beam - Detailed Excavation & FRP | 12 | 26 October 2023 8:00 AM | 9 November 2023 5:00 PM | 41FS-6d | 66 | 26 October 2023 8:00 AM | 2023-11-09 17:00 | 0 | Excavation | 76 | 30 | 35 | 30 | 58
43 | 1.2.1.6 | Bulk Excavation & Shotcrete | 142 | 16 September 2023 8:00 AM | 22 March 2024 5:00 PM |  |  | 16 September 2023 8:00 AM | 2024-03-22 17:00 | 0 | Reinforcement Fixer | 46 | 32 | 10 | 20 | 3
44 | 1.2.1.6.1 | Building A | 70 | 16 September 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-12-17 17:00 | 1 | Carpet | 78 | 47 | 27 | 11 | 3
45 | 1.2.1.6.1.1 | Excavate - Gnd - B1 | 57 | 16 September 2023 8:00 AM | 28 November 2023 5:00 PM |  |  | 16 September 2023 8:00 AM | 2023-11-30 17:00 | 2 | Hoarding | 32 | 31 | 18 | 47 | 57
46 | 1.2.1.6.1.1.1 | Excavation | 21 | 16 September 2023 8:00 AM | 13 October 2023 5:00 PM | 34 | 47,56,51,71 | 16 September 2023 8:00 AM | 2023-10-13 17:00 | 0 | Carpet | 18 | 94 | 28 | 49 | 30
47 | 1.2.1.6.1.1.2 | Installation of Anchors | 8 | 20 October 2023 8:00 AM | 30 October 2023 5:00 PM | 46 | 48,49SS+11d | 20 October 2023 8:00 AM | 2023-11-01 17:00 | 2 | Plumber | 62 | 37 | 26 | 54 | 53
48 | 1.2.1.6.1.1.3 | Install Bracing | 4 | 31 October 2023 8:00 AM | 3 November 2023 5:00 PM | 47 |  | 31 October 2023 8:00 AM | 2023-11-03 17:00 | 0 | Project Manager | 6 | 95 | 14 | 28 | 46
49 | 1.2.1.6.1.1.4 | Shotcrete | 20 | 3 November 2023 8:00 AM | 28 November 2023 5:00 PM | 47SS+11d |  | 3 November 2023 8:00 AM | 2023-11-30 17:00 | 2 | Painter | 21 | 29 | 12 | 72 | 3
50 | 1.2.1.6.1.2 | Excavate - B1-B2 | 44 | 20 October 2023 8:00 AM | 16 December 2023 5:00 PM |  |  | 20 October 2023 8:00 AM | 2023-12-19 17:00 | 3 | Carpet | 45 | 28 | 16 | 21 | 7
51 | 1.2.1.6.1.2.1 | Excavation | 14 | 20 October 2023 8:00 AM | 7 November 2023 5:00 PM | 46 | 52,53,56,71 | 20 October 2023 8:00 AM | 2023-11-07 17:00 | 0 | Electrician | 72 | 77 | 15 | 71 | 59
52 | 1.2.1.6.1.2.2 | Shotcrete | 16 | 15 November 2023 8:00 AM | 7 December 2023 5:00 PM | 51 | 53 | 15 November 2023 8:00 AM | 2023-12-07 17:00 | 0 | Fire | 7 | 45 | 28 | 74 | 4
53 | 1.2.1.6.1.2.3 | Foundation Piling (Basement 2 Lvl) - (35 Piles) | 8 | 8 December 2023 8:00 AM | 16 December 2023 5:00 PM | 51,52 | 63,31 | 8 December 2023 8:00 AM | 2023-12-16 17:00 | 0 | Formworker | 8 | 71 | 27 | 59 | 40
54 | 1.2.1.6.2 | Building B | 66 | 15 November 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | 15 November 2023 8:00 AM | 2024-02-18 17:00 | 2 | Site Manager | 72 | 77 | 28 | 81 | 47
55 | 1.2.1.6.2.1 | Excavate - Gnd - B1 | 46 | 15 November 2023 8:00 AM | 22 January 2024 5:00 PM |  |  | 15 November 2023 8:00 AM | 2024-01-23 17:00 | 1 | Plumber | 58 | 34 | 23 | 60 | 57
56 | 1.2.1.6.2.1.1 | Excavation | 22 | 15 November 2023 8:00 AM | 14 December 2023 5:00 PM | 38,46,51 | 57,59,61,71 | 15 November 2023 8:00 AM | 2023-12-17 17:00 | 3 | Excavation | 10 | 69 | 18 | 68 | 16
57 | 1.2.1.6.2.1.2 | Installation of Anchors | 8 | 20 December 2023 8:00 AM | 8 January 2024 5:00 PM | 56 | 58 | 20 December 2023 8:00 AM | 2024-01-08 17:00 | 0 | Cleaner | 49 | 62 | 31 | 70 | 45
58 | 1.2.1.6.2.1.3 | Install Bracing | 4 | 9 January 2024 8:00 AM | 12 January 2024 5:00 PM | 57 | 59 | 9 January 2024 8:00 AM | 2024-01-15 17:00 | 3 | Head Contractor | 43 | 21 | 14 | 72 | 38
59 | 1.2.1.6.2.1.4 | Shotcrete | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,58 | 61 | 20 December 2023 8:00 AM | 2024-01-26 17:00 | 4 | Floor Sealer | 46 | 52 | 13 | 62 | 23
60 | 1.2.1.6.2.2 | Excavate - B1-B2 | 40 | 20 December 2023 8:00 AM | 16 February 2024 5:00 PM |  |  | 20 December 2023 8:00 AM | 2024-02-18 17:00 | 2 | Fire | 44 | 61 | 24 | 64 | 15
61 | 1.2.1.6.2.2.1 | Excavation | 20 | 20 December 2023 8:00 AM | 22 January 2024 5:00 PM | 56,59 | 66,63,71,62 | 20 December 2023 8:00 AM | 2024-01-23 17:00 | 1 | Metal Work | 71 | 66 | 19 | 85 | 18
62 | 1.2.1.6.2.2.2 | Shotcrete | 10 | 1 February 2024 8:00 AM | 12 February 2024 5:00 PM | 61 | 63 | 1 February 2024 8:00 AM | 2024-02-14 17:00 | 2 | Contract Administrator | 46 | 56 | 26 | 17 | 44
63 | 1.2.1.6.2.2.3 | Foundation Piling (Basement 2 Lvl) - (23 Piles) | 4 | 13 February 2024 8:00 AM | 16 February 2024 5:00 PM | 61,53,62 | 74 | 13 February 2024 8:00 AM | 2024-02-18 17:00 | 2 | Stone Mason | 56 | 88 | 13 | 37 | 14
64 | 1.2.1.6.3 | Buildings C & D | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | 23 January 2024 8:00 AM | 2024-03-25 17:00 | 3 | Mechanical | 65 | 61 | 21 | 14 | 43
65 | 1.2.1.6.3.1 | Excavate - Gnd - B2 | 50 | 23 January 2024 8:00 AM | 22 March 2024 5:00 PM |  |  | 23 January 2024 8:00 AM | 2024-03-24 17:00 | 2 | Foreman | 58 | 20 | 13 | 44 | 37
66 | 1.2.1.6.3.1.1 | Excavation | 30 | 23 January 2024 8:00 AM | 28 February 2024 5:00 PM | 42,61 | 67,71 | 23 January 2024 8:00 AM | 2024-03-01 17:00 | 2 | Plumber | 56 | 61 | 32 | 20 | 2
67 | 1.2.1.6.3.1.2 | Installation of Anchors | 8 | 29 February 2024 8:00 AM | 8 March 2024 5:00 PM | 66 | 68 | 29 February 2024 8:00 AM | 2024-03-12 17:00 | 4 | Site Manager | 73 | 84 | 28 | 71 | 35
68 | 1.2.1.6.3.1.3 | Install Bracing | 4 | 9 March 2024 8:00 AM | 13 March 2024 5:00 PM | 67 | 69 | 9 March 2024 8:00 AM | 2024-03-15 17:00 | 2 | Fire | 64 | 64 | 12 | 34 | 26
69 | 1.2.1.6.3.1.4 | Shotcrete | 6 | 14 March 2024 8:00 AM | 20 March 2024 5:00 PM | 68 | 70,84 | 14 March 2024 8:00 AM | 2024-03-20 17:00 | 0 | Contract Administrator | 5 | 83 | 31 | 66 | 32
70 | 1.2.1.6.3.1.5 | Foundation Piling (Basement 2 Lvl) - (5 Piles) | 2 | 21 March 2024 8:00 AM | 22 March 2024 5:00 PM | 69 | 86 | 21 March 2024 8:00 AM | 2024-03-26 17:00 | 4 | Mechanical | 20 | 46 | 14 | 21 | 20
71 | 1.2.1.6.4 | Complete Bulk Exacavation | 0 | 28 February 2024 5:00 PM | 28 February 2024 5:00 PM | 46,51,56,61,66 |  | 28 February 2024 5:00 PM | 2024-02-28 17:00 | 0 | Admin | 1 | 78 | 19 | 72 | 21
72 | 1.2.1.7 | Detail Excavation, Services & Base course | 61 | 17 February 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | 17 February 2024 8:00 AM | 2024-05-02 17:00 | 0 | Window | 55 | 97 | 11 | 6 | 28
73 | 1.2.1.7.1 | Stage 1 (Building A) | 32 | 17 February 2024 8:00 AM | 25 March 2024 5:00 PM |  |  | 17 February 2024 8:00 AM | 2024-03-27 17:00 | 2 | Concretor | 75 | 46 | 20 | 55 | 55
74 | 1.2.1.7.1.1 | Detailed Excavation | 11 | 17 February 2024 8:00 AM | 29 February 2024 5:00 PM | 63 | 75,79 | 17 February 2024 8:00 AM | 2024-03-01 17:00 | 1 | Formworker | 88 | 63 | 10 | 29 | 2
75 | 1.2.1.7.1.2 | In-Ground Services | 8 | 1 March 2024 8:00 AM | 9 March 2024 5:00 PM | 74 | 76 | 1 March 2024 8:00 AM | 2024-03-11 17:00 | 2 | Plumber | 86 | 63 | 27 | 4 | 44
76 | 1.2.1.7.1.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 11 March 2024 8:00 AM | 15 March 2024 5:00 PM | 75 | 77 | 11 March 2024 8:00 AM | 2024-03-15 17:00 | 0 | Foreman | 25 | 66 | 35 | 9 | 4
77 | 1.2.1.7.1.4 | Base Course to Basement | 8 | 16 March 2024 8:00 AM | 25 March 2024 5:00 PM | 76 | 88 | 16 March 2024 8:00 AM | 2024-03-27 17:00 | 2 | Metal Work | 19 | 99 | 31 | 70 | 35
78 | 1.2.1.7.2 | Stage 2 (Building B) | 32 | 1 March 2024 8:00 AM | 10 April 2024 5:00 PM |  |  | 1 March 2024 8:00 AM | 2024-04-11 17:00 | 1 | Reinforcement Fixer | 93 | 81 | 25 | 57 | 46
79 | 1.2.1.7.2.1 | Detailed Excavation | 12 | 1 March 2024 8:00 AM | 14 March 2024 5:00 PM | 74 | 80 | 1 March 2024 8:00 AM | 2024-03-15 17:00 | 1 | Surveyor | 11 | 75 | 13 | 36 | 59
80 | 1.2.1.7.2.2 | In-Ground Services | 9 | 15 March 2024 8:00 AM | 25 March 2024 5:00 PM | 79 | 81 | 15 March 2024 8:00 AM | 2024-03-25 17:00 | 0 | Surveyor | 81 | 57 | 16 | 68 | 31
81 | 1.2.1.7.2.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 6 | 26 March 2024 8:00 AM | 4 April 2024 5:00 PM | 80 | 82 | 26 March 2024 8:00 AM | 2024-04-04 17:00 | 0 | Metal Work | 95 | 84 | 33 | 87 | 55
82 | 1.2.1.7.2.4 | Base Course to Basement | 5 | 5 April 2024 8:00 AM | 10 April 2024 5:00 PM | 81 | 93 | 5 April 2024 8:00 AM | 2024-04-13 17:00 | 3 | Window | 91 | 74 | 23 | 47 | 26
83 | 1.2.1.7.3 | Stage 3 (Buildings C&D) | 33 | 21 March 2024 8:00 AM | 2 May 2024 5:00 PM |  |  | 21 March 2024 8:00 AM | 2024-05-03 17:00 | 1 | Development Manager | 0 | 58 | 16 | 40 | 18
84 | 1.2.1.7.3.1 | Detailed Excavation | 12 | 21 March 2024 8:00 AM | 6 April 2024 5:00 PM | 69 | 85 | 21 March 2024 8:00 AM | 2024-04-06 17:00 | 0 | Floor Sealer | 69 | 83 | 24 | 55 | 42
85 | 1.2.1.7.3.2 | In-Ground Services | 8 | 8 April 2024 8:00 AM | 16 April 2024 5:00 PM | 84 | 86 | 8 April 2024 8:00 AM | 2024-04-18 17:00 | 2 | Carpenter | 34 | 49 | 29 | 96 | 44
86 | 1.2.1.7.3.3 | Subsoil Services, Geo-Fabric, Blue Metal, Black Plastic, ect | 5 | 17 April 2024 8:00 AM | 22 April 2024 5:00 PM | 85,70 | 87 | 17 April 2024 8:00 AM | 2024-04-22 17:00 | 0 | Line Market | 0 | 56 | 21 | 86 | 21
87 | 1.2.1.7.3.4 | Base Course to Basement | 8 | 23 April 2024 8:00 AM | 2 May 2024 5:00 PM | 86 | 88 | 23 April 2024 8:00 AM | 2024-05-03 17:00 | 1 | Painter | 50 | 69 | 24 | 95 | 20
88 | 1.2.1.7.4 | Basement Earthworks and Piling Complete | 0 | 2 May 2024 5:00 PM | 2 May 2024 5:00 PM | 87,77 | 122,4 | 2 May 2024 5:00 PM | 2024-05-04 17:00 | 2 | Concretor | 71 | 33 | 29 | 65 | 33
89 | 1.2.2 | STRUCTURE WORKS | 217 | 11 April 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 11 April 2024 8:00 AM | 2025-01-03 17:00 | 0 | Metal Work | 8 | 93 | 29 | 22 | 38
90 | 1.2.2.1 | CC2 - Basement to Podium L1 - A, B, C, D | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  |  | 11 April 2024 8:00 AM | 2024-10-01 17:00 | 1 | Line Market | 27 | 70 | 28 | 43 | 3
91 | 1.2.2.1.1 | Basement to Podium (Level 1 - A & B ) | 145 | 11 April 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | 11 April 2024 8:00 AM | 2024-09-30 17:00 | 0 | Development Manager | 47 | 91 | 25 | 80 | 35
92 | 1.2.2.1.1.1 | Basement 2 - FRP - SoG | 23 | 11 April 2024 8:00 AM | 8 May 2024 5:00 PM |  |  | 11 April 2024 8:00 AM | 2024-05-08 17:00 | 0 | Cleaner | 14 | 34 | 10 | 40 | 32
93 | 1.2.2.1.1.1.1 | Reinforcement Fix | 13 | 11 April 2024 8:00 AM | 26 April 2024 5:00 PM | 82 | 94 | 11 April 2024 8:00 AM | 2024-04-28 17:00 | 2 | Plumber | 34 | 37 | 26 | 87 | 37
94 | 1.2.2.1.1.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 9 | 27 April 2024 8:00 AM | 7 May 2024 5:00 PM | 93 | 95 | 27 April 2024 8:00 AM | 2024-05-07 17:00 | 0 | Stone Mason | 87 | 60 | 20 | 3 | 24
95 | 1.2.2.1.1.1.3 | Pour | 1 | 8 May 2024 8:00 AM | 8 May 2024 5:00 PM | 94 | 97 | 8 May 2024 8:00 AM | 2024-05-08 17:00 | 0 | Landscaper | 64 | 98 | 22 | 82 | 45
96 | 1.2.2.1.1.2 | Basement 1 - FRP - Suspended Slab | 25 | 9 May 2024 8:00 AM | 6 June 2024 5:00 PM |  |  | 9 May 2024 8:00 AM | 2024-06-09 17:00 | 3 | Hoarding | 22 | 75 | 17 | 82 | 59
97 | 1.2.2.1.1.2.1 | Scaffold Stair Removal/Adjustment | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 95 | 98SS | 9 May 2024 8:00 AM | 2024-05-10 17:00 | 0 | Subcontractor | 84 | 51 | 34 | 11 | 7
98 | 1.2.2.1.1.2.2 | Setout and Install Lift/Stair Formwork | 2 | 9 May 2024 8:00 AM | 10 May 2024 5:00 PM | 97SS | 99 | 9 May 2024 8:00 AM | 2024-05-10 17:00 | 0 | Plasterboarder | 61 | 96 | 21 | 14 | 41
99 | 1.2.2.1.1.2.3 | Formworker setout, drop material and 80% Deck | 9 | 11 May 2024 8:00 AM | 21 May 2024 5:00 PM | 98 | 100FS-1d,101 | 11 May 2024 8:00 AM | 2024-05-21 17:00 | 0 | Formworker | 93 | 12 | 19 | 62 | 33
100 | 1.2.2.1.1.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 21 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99FS-1d | 102,103 | 21 May 2024 8:00 AM | 2024-05-24 17:00 | 0 | Plumber | 29 | 10 | 19 | 40 | 37
101 | 1.2.2.1.1.2.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 22 May 2024 8:00 AM | 24 May 2024 5:00 PM | 99 |  | 22 May 2024 8:00 AM | 2024-05-26 17:00 | 2 | Painter | 11 | 61 | 13 | 13 | 59
102 | 1.2.2.1.1.2.6 | Services | 4 | 25 May 2024 8:00 AM | 29 May 2024 5:00 PM | 100 | 104FS-1d | 25 May 2024 8:00 AM | 2024-05-29 17:00 | 0 | Reinforcement Fixer | 70 | 88 | 28 | 69 | 29
103 | 1.2.2.1.1.2.7 | Post Tension | 3 | 25 May 2024 8:00 AM | 28 May 2024 5:00 PM | 100 | 104FS-1d | 25 May 2024 8:00 AM | 2024-05-28 17:00 | 0 | Plasterboarder | 32 | 79 | 33 | 69 | 19
104 | 1.2.2.1.1.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 29 May 2024 8:00 AM | 31 May 2024 5:00 PM | 102FS-1d,103FS-1d | 105 | 29 May 2024 8:00 AM | 2024-05-31 17:00 | 0 | Admin | 94 | 45 | 32 | 46 | 47
105 | 1.2.2.1.1.2.9 | Formworker setdowns and edge boards | 4 | 1 June 2024 8:00 AM | 5 June 2024 5:00 PM | 104 | 106 | 1 June 2024 8:00 AM | 2024-06-05 17:00 | 0 | Window | 18 | 27 | 12 | 89 | 21
106 | 1.2.2.1.1.2.10 | Pour | 1 | 6 June 2024 8:00 AM | 6 June 2024 5:00 PM | 105 | 109 | 6 June 2024 8:00 AM | 2024-06-06 17:00 | 0 | Mechanical | 9 | 99 | 23 | 73 | 48
107 | 1.2.2.1.1.3 | Strip Formwork - Basement 1 | 5 | 7 September 2024 8:00 AM | 12 September 2024 5:00 PM | 161FS+5d | 522 | 7 September 2024 8:00 AM | 2024-09-16 17:00 | 4 | Contract Administrator | 27 | 99 | 26 | 5 | 2
108 | 1.2.2.1.1.4 | Lvl 1 - FRP - Suspended Slab | 28 | 7 June 2024 8:00 AM | 11 July 2024 5:00 PM |  |  | 7 June 2024 8:00 AM | 2024-07-13 17:00 | 2 | Plasterboarder | 8 | 26 | 32 | 4 | 10
109 | 1.2.2.1.1.4.1 | Scaffold Stair Removal/Adjustment | 1 | 7 June 2024 8:00 AM | 7 June 2024 5:00 PM | 106 | 110SS | 7 June 2024 8:00 AM | 2024-06-09 17:00 | 2 | Surveyor | 76 | 68 | 27 | 6 | 52
110 | 1.2.2.1.1.4.2 | Setout and Install Lift/Stair Formwork | 3 | 7 June 2024 8:00 AM | 12 June 2024 5:00 PM | 109SS | 111 | 7 June 2024 8:00 AM | 2024-06-18 17:00 | 6 | Metal Work | 3 | 36 | 18 | 80 | 49
111 | 1.2.2.1.1.4.3 | Formworker setout, drop material and 80% Deck | 10 | 13 June 2024 8:00 AM | 24 June 2024 5:00 PM | 110 | 112FS-1d,113,128 | 13 June 2024 8:00 AM | 2024-06-24 17:00 | 0 | Project Manager | 41 | 24 | 10 | 65 | 53
112 | 1.2.2.1.1.4.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 6 | 24 June 2024 8:00 AM | 29 June 2024 5:00 PM | 111FS-1d | 114,115 | 24 June 2024 8:00 AM | 2024-06-30 17:00 | 1 | Renderer | 73 | 24 | 12 | 4 | 18
113 | 1.2.2.1.1.4.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 25 June 2024 8:00 AM | 28 June 2024 5:00 PM | 111 | 118 | 25 June 2024 8:00 AM | 2024-06-28 17:00 | 0 | Tiler | 39 | 77 | 13 | 3 | 4
114 | 1.2.2.1.1.4.6 | Services | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 112 | 116FS-1d | 1 July 2024 8:00 AM | 2024-07-05 17:00 | 2 | Carpet | 31 | 45 | 11 | 23 | 33
115 | 1.2.2.1.1.4.7 | Post Tension | 4 | 1 July 2024 8:00 AM | 4 July 2024 5:00 PM | 112 | 116FS-1d | 1 July 2024 8:00 AM | 2024-07-05 17:00 | 1 | Reinforcement Fixer | 51 | 69 | 14 | 14 | 45
116 | 1.2.2.1.1.4.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 114FS-1d,115FS-1d | 117,401FS+5d | 4 July 2024 8:00 AM | 2024-07-09 17:00 | 3 | Carpet | 25 | 54 | 32 | 56 | 47
117 | 1.2.2.1.1.4.9 | Formworker setdowns and edge boards | 3 | 8 July 2024 8:00 AM | 10 July 2024 5:00 PM | 116 | 118 | 8 July 2024 8:00 AM | 2024-07-12 17:00 | 2 | Carpenter | 73 | 47 | 27 | 60 | 5
118 | 1.2.2.1.1.4.10 | Pour | 1 | 11 July 2024 8:00 AM | 11 July 2024 5:00 PM | 117,113 | 140 | 11 July 2024 8:00 AM | 2024-07-11 17:00 | 0 | Carpet | 8 | 52 | 13 | 56 | 16
119 | 1.2.2.1.1.5 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d | 535 | 25 September 2024 8:00 AM | 2024-09-30 17:00 | 0 | Painter | 7 | 99 | 22 | 40 | 25
120 | 1.2.2.1.2 | Basement to Podium (Level 1 - C & D) | 127 | 3 May 2024 8:00 AM | 30 September 2024 5:00 PM |  | 397 | 3 May 2024 8:00 AM | 2024-10-01 17:00 | 1 | Concretor | 86 | 80 | 34 | 63 | 14
121 | 1.2.2.1.2.1 | Basement 2 - FRP - SoG | 12 | 3 May 2024 8:00 AM | 16 May 2024 5:00 PM |  |  | 3 May 2024 8:00 AM | 2024-05-16 17:00 | 0 | Subcontractor | 73 | 28 | 23 | 64 | 48
122 | 1.2.2.1.2.1.1 | Reinforcement Fix | 6 | 3 May 2024 8:00 AM | 9 May 2024 5:00 PM | 88 | 123 | 3 May 2024 8:00 AM | 2024-05-11 17:00 | 2 | Cleaner | 86 | 44 | 26 | 11 | 5
123 | 1.2.2.1.2.1.2 | Formwork (EJ, CJ, KJ, SW Pits, Edgeboards & Setdowns) | 5 | 10 May 2024 8:00 AM | 15 May 2024 5:00 PM | 122 | 124 | 10 May 2024 8:00 AM | 2024-05-15 17:00 | 0 | Line Market | 51 | 53 | 21 | 24 | 48
124 | 1.2.2.1.2.1.3 | Pour | 1 | 16 May 2024 8:00 AM | 16 May 2024 5:00 PM | 123 | 126 | 16 May 2024 8:00 AM | 2024-05-16 17:00 | 0 | Stone Mason | 22 | 39 | 27 | 43 | 48
125 | 1.2.2.1.2.2 | Lvl 1 - FRP - Suspended Slab | 48 | 17 May 2024 8:00 AM | 13 July 2024 5:00 PM |  |  | 17 May 2024 8:00 AM | 2024-07-13 17:00 | 0 | Plasterboarder | 66 | 18 | 25 | 20 | 29
126 | 1.2.2.1.2.2.1 | Scaffold Stair Removal/Adjustment | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 124 | 127SS | 17 May 2024 8:00 AM | 2024-05-17 17:00 | 0 | Foreman | 77 | 82 | 25 | 6 | 25
127 | 1.2.2.1.2.2.2 | Setout and Install Lift/Stair Formwork | 1 | 17 May 2024 8:00 AM | 17 May 2024 5:00 PM | 126SS | 128 | 17 May 2024 8:00 AM | 2024-05-20 17:00 | 3 | Plasterboarder | 85 | 82 | 10 | 14 | 31
128 | 1.2.2.1.2.2.3 | Formworker setout, drop material and 80% Deck | 6 | 25 June 2024 8:00 AM | 1 July 2024 5:00 PM | 127,111 | 129FS-1d,130 | 25 June 2024 8:00 AM | 2024-07-01 17:00 | 0 | Electrician | 3 | 13 | 32 | 94 | 17
129 | 1.2.2.1.2.2.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 1 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128FS-1d | 131,132 | 1 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Project Manager | 66 | 63 | 18 | 49 | 36
130 | 1.2.2.1.2.2.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 July 2024 8:00 AM | 3 July 2024 5:00 PM | 128 |  | 2 July 2024 8:00 AM | 2024-07-03 17:00 | 0 | Waterproofer | 86 | 37 | 23 | 9 | 37
131 | 1.2.2.1.2.2.6 | Services | 2 | 4 July 2024 8:00 AM | 5 July 2024 5:00 PM | 129 | 133FS-1d | 4 July 2024 8:00 AM | 2024-07-07 17:00 | 2 | Window | 78 | 26 | 32 | 43 | 18
132 | 1.2.2.1.2.2.7 | Post Tension | 3 | 4 July 2024 8:00 AM | 6 July 2024 5:00 PM | 129 | 133FS-1d | 4 July 2024 8:00 AM | 2024-07-07 17:00 | 1 | Line Market | 96 | 31 | 29 | 60 | 39
133 | 1.2.2.1.2.2.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 6 July 2024 8:00 AM | 9 July 2024 5:00 PM | 131FS-1d,132FS-1d | 134 | 6 July 2024 8:00 AM | 2024-07-10 17:00 | 1 | Line Market | 4 | 24 | 13 | 97 | 51
134 | 1.2.2.1.2.2.9 | Formworker setdowns and edge boards | 3 | 10 July 2024 8:00 AM | 12 July 2024 5:00 PM | 133 | 135 | 10 July 2024 8:00 AM | 2024-07-13 17:00 | 1 | Concretor | 24 | 76 | 31 | 78 | 40
135 | 1.2.2.1.2.2.10 | Pour | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 134 | 309,233 | 13 July 2024 8:00 AM | 2024-07-13 17:00 | 0 | Cleaner | 55 | 60 | 25 | 97 | 51
136 | 1.2.2.1.2.3 | Strip Formwork - Lvl 1 | 5 | 25 September 2024 8:00 AM | 30 September 2024 5:00 PM | 173FS+5d |  | 25 September 2024 8:00 AM | 2024-09-30 17:00 | 0 | Mechanical | 2 | 87 | 20 | 70 | 35
137 | 1.2.2.2 | CC3 - Remainder of Structure | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 12 July 2024 8:00 AM | 2025-01-03 17:00 | 0 | Head Contractor | 59 | 11 | 12 | 74 | 43
138 | 1.2.2.2.1 | Building A | 141 | 12 July 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | 12 July 2024 8:00 AM | 2025-01-04 17:00 | 1 | Landscaper | 79 | 73 | 35 | 83 | 56
139 | 1.2.2.2.1.1 | Lvl 2 - FRP - Suspended Slab | 26 | 12 July 2024 8:00 AM | 10 August 2024 5:00 PM |  |  | 12 July 2024 8:00 AM | 2024-08-11 17:00 | 1 | Reinforcement Fixer | 0 | 12 | 14 | 16 | 47
140 | 1.2.2.2.1.1.1 | Scaffold Perimeter Protection | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 118 | 141SS | 12 July 2024 8:00 AM | 2024-07-16 17:00 | 0 | Tiler | 10 | 71 | 20 | 3 | 30
141 | 1.2.2.2.1.1.2 | Setout and Install Lift/Stair Formwork | 4 | 12 July 2024 8:00 AM | 16 July 2024 5:00 PM | 140SS | 142 | 12 July 2024 8:00 AM | 2024-07-16 17:00 | 0 | Reinforcement Fixer | 22 | 14 | 28 | 59 | 28
142 | 1.2.2.2.1.1.3 | Formworker setout, drop material and 80% Deck | 6 | 17 July 2024 8:00 AM | 23 July 2024 5:00 PM | 141 | 143FS-1d,144 | 17 July 2024 8:00 AM | 2024-07-26 17:00 | 3 | Painter | 46 | 95 | 28 | 48 | 32
143 | 1.2.2.2.1.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 23 July 2024 8:00 AM | 26 July 2024 5:00 PM | 142FS-1d | 145,146 | 23 July 2024 8:00 AM | 2024-07-29 17:00 | 3 | Window | 69 | 44 | 17 | 30 | 18
144 | 1.2.2.2.1.1.5 | Steel Fixer - Drop Prefabricated Columns | 4 | 24 July 2024 8:00 AM | 27 July 2024 5:00 PM | 142 | 146 | 24 July 2024 8:00 AM | 2024-07-29 17:00 | 2 | Post Tension | 87 | 33 | 15 | 46 | 15
145 | 1.2.2.2.1.1.6 | Services | 3 | 27 July 2024 8:00 AM | 30 July 2024 5:00 PM | 143 | 147FS-1d | 27 July 2024 8:00 AM | 2024-07-30 17:00 | 0 | Painter | 72 | 53 | 18 | 21 | 10
146 | 1.2.2.2.1.1.7 | Post Tension | 3 | 29 July 2024 8:00 AM | 31 July 2024 5:00 PM | 143,144 | 147FS-1d | 29 July 2024 8:00 AM | 2024-07-31 17:00 | 0 | Window | 68 | 84 | 29 | 22 | 37
147 | 1.2.2.2.1.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 5 | 31 July 2024 8:00 AM | 5 August 2024 5:00 PM | 145FS-1d,146FS-1d | 148 | 31 July 2024 8:00 AM | 2024-08-08 17:00 | 3 | Foreman | 17 | 72 | 23 | 63 | 47
148 | 1.2.2.2.1.1.9 | Formworker setdowns and edge boards | 4 | 6 August 2024 8:00 AM | 9 August 2024 5:00 PM | 147 | 149 | 6 August 2024 8:00 AM | 2024-08-10 17:00 | 1 | Excavation | 91 | 16 | 12 | 86 | 43
149 | 1.2.2.2.1.1.10 | Pour | 1 | 10 August 2024 8:00 AM | 10 August 2024 5:00 PM | 148 | 152,407FS+5d | 10 August 2024 8:00 AM | 2024-08-11 17:00 | 1 | Fire | 69 | 26 | 31 | 7 | 44
150 | 1.2.2.2.1.2 | Strip Formwork - Lvl 2 | 5 | 15 October 2024 8:00 AM | 19 October 2024 5:00 PM | 185FS+5d | 577,550,409FS-10d | 15 October 2024 8:00 AM | 2024-10-22 17:00 | 3 | Window | 49 | 21 | 32 | 33 | 50
151 | 1.2.2.2.1.3 | Lvl 3 - FRP - Suspended Slab | 18 | 12 August 2024 8:00 AM | 31 August 2024 5:00 PM |  |  | 12 August 2024 8:00 AM | 2024-08-31 17:00 | 0 | Hoarding | 95 | 54 | 21 | 84 | 43
152 | 1.2.2.2.1.3.1 | Scaffold Perimeter Protection | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 149 | 153SS | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 0 | Project Manager | 33 | 73 | 26 | 14 | 53
153 | 1.2.2.2.1.3.2 | Setout and Install Lift/Stair Formwork | 1 | 12 August 2024 8:00 AM | 12 August 2024 5:00 PM | 152SS | 154 | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 1 | Waterproofer | 96 | 58 | 15 | 65 | 49
154 | 1.2.2.2.1.3.3 | Formworker setout, drop material and 80% Deck | 6 | 13 August 2024 8:00 AM | 19 August 2024 5:00 PM | 153 | 155FS-1d,156 | 13 August 2024 8:00 AM | 2024-08-19 17:00 | 0 | Formworker | 77 | 67 | 27 | 20 | 11
155 | 1.2.2.2.1.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 19 August 2024 8:00 AM | 22 August 2024 5:00 PM | 154FS-1d | 157,158 | 19 August 2024 8:00 AM | 2024-08-22 17:00 | 0 | Tiler | 30 | 53 | 28 | 80 | 13
156 | 1.2.2.2.1.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 August 2024 8:00 AM | 21 August 2024 5:00 PM | 154 |  | 20 August 2024 8:00 AM | 2024-08-25 17:00 | 4 | Hoarding | 27 | 21 | 13 | 70 | 55
157 | 1.2.2.2.1.3.6 | Services | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | 23 August 2024 8:00 AM | 2024-08-26 17:00 | 2 | Mechanical | 72 | 92 | 26 | 26 | 24
158 | 1.2.2.2.1.3.7 | Post Tension | 2 | 23 August 2024 8:00 AM | 24 August 2024 5:00 PM | 155 | 159FS-1d | 23 August 2024 8:00 AM | 2024-08-24 17:00 | 0 | Development Manager | 10 | 15 | 22 | 3 | 14
159 | 1.2.2.2.1.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 24 August 2024 8:00 AM | 27 August 2024 5:00 PM | 157FS-1d,158FS-1d | 160 | 24 August 2024 8:00 AM | 2024-08-27 17:00 | 0 | Cleaner | 64 | 66 | 20 | 3 | 40
160 | 1.2.2.2.1.3.9 | Formworker setdowns and edge boards | 3 | 28 August 2024 8:00 AM | 30 August 2024 5:00 PM | 159 | 161 | 28 August 2024 8:00 AM | 2024-08-31 17:00 | 1 | Electrician | 60 | 93 | 10 | 18 | 18
161 | 1.2.2.2.1.3.10 | Pour | 1 | 31 August 2024 8:00 AM | 31 August 2024 5:00 PM | 160 | 164,3445,107FS+5d | 31 August 2024 8:00 AM | 2024-08-31 17:00 | 0 | Floor Sealer | 57 | 31 | 34 | 93 | 35
162 | 1.2.2.2.1.4 | Strip Formwork - Lvl 3 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d |  | 19 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Timber Floorer | 67 | 39 | 21 | 97 | 12
163 | 1.2.2.2.1.5 | Lvl 4 - FRP - Suspended Slab | 15 | 2 September 2024 8:00 AM | 18 September 2024 5:00 PM |  |  | 2 September 2024 8:00 AM | 2024-09-21 17:00 | 3 | Window | 45 | 68 | 18 | 31 | 45
164 | 1.2.2.2.1.5.1 | Scaffold Perimeter Protection | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 161 | 165SS | 2 September 2024 8:00 AM | 2024-09-02 17:00 | 0 | Joiner | 62 | 10 | 20 | 38 | 32
165 | 1.2.2.2.1.5.2 | Setout and Install Lift/Stair Formwork | 1 | 2 September 2024 8:00 AM | 2 September 2024 5:00 PM | 164SS | 166FS-1d | 2 September 2024 8:00 AM | 2024-09-03 17:00 | 1 | Foreman | 15 | 66 | 15 | 38 | 18
166 | 1.2.2.2.1.5.3 | Formworker setout, drop material and 80% Deck | 6 | 2 September 2024 8:00 AM | 7 September 2024 5:00 PM | 165FS-1d | 167FS-1d,168 | 2 September 2024 8:00 AM | 2024-09-08 17:00 | 1 | Head Contractor | 87 | 58 | 28 | 78 | 49
167 | 1.2.2.2.1.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 7 September 2024 8:00 AM | 11 September 2024 5:00 PM | 166FS-1d | 169,170 | 7 September 2024 8:00 AM | 2024-09-12 17:00 | 1 | Landscaper | 61 | 76 | 13 | 63 | 35
168 | 1.2.2.2.1.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 9 September 2024 8:00 AM | 10 September 2024 5:00 PM | 166 |  | 9 September 2024 8:00 AM | 2024-09-11 17:00 | 1 | Timber Floorer | 70 | 98 | 12 | 53 | 38
169 | 1.2.2.2.1.5.6 | Services | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | 12 September 2024 8:00 AM | 2024-09-17 17:00 | 4 | Surveyor | 59 | 17 | 11 | 21 | 54
170 | 1.2.2.2.1.5.7 | Post Tension | 2 | 12 September 2024 8:00 AM | 13 September 2024 5:00 PM | 167 | 171FS-1d | 12 September 2024 8:00 AM | 2024-09-17 17:00 | 4 | Reinforcement Fixer | 78 | 25 | 20 | 49 | 38
171 | 1.2.2.2.1.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 13 September 2024 8:00 AM | 14 September 2024 5:00 PM | 169FS-1d,170FS-1d | 172 | 13 September 2024 8:00 AM | 2024-09-14 17:00 | 0 | Fire | 85 | 35 | 30 | 29 | 49
172 | 1.2.2.2.1.5.9 | Formworker setdowns and edge boards | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 171 | 173 | 16 September 2024 8:00 AM | 2024-09-17 17:00 | 0 | Floor Sealer | 52 | 27 | 30 | 28 | 15
173 | 1.2.2.2.1.5.10 | Pour | 1 | 18 September 2024 8:00 AM | 18 September 2024 5:00 PM | 172 | 176,119FS+5d,136FS+5d | 18 September 2024 8:00 AM | 2024-09-18 17:00 | 0 | Surveyor | 50 | 57 | 28 | 17 | 22
174 | 1.2.2.2.1.6 | Strip Formwork - Lvl 4 | 5 | 19 November 2024 8:00 AM | 23 November 2024 5:00 PM | 209FS+5d | 413FS+5d,604,415FS-10d | 19 November 2024 8:00 AM | 2024-11-24 17:00 | 1 | Window | 11 | 35 | 12 | 75 | 30
175 | 1.2.2.2.1.7 | Lvl 5 - FRP - Suspended Slab | 15 | 19 September 2024 8:00 AM | 8 October 2024 5:00 PM |  |  | 19 September 2024 8:00 AM | 2024-10-10 17:00 | 2 | Site Manager | 20 | 26 | 15 | 40 | 9
176 | 1.2.2.2.1.7.1 | Scaffold Perimeter Protection | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 173 | 177SS | 19 September 2024 8:00 AM | 2024-09-21 17:00 | 2 | Joiner | 70 | 73 | 35 | 64 | 7
177 | 1.2.2.2.1.7.2 | Setout and Install Lift/Stair Formwork | 1 | 19 September 2024 8:00 AM | 19 September 2024 5:00 PM | 176SS | 178FS-1d | 19 September 2024 8:00 AM | 2024-09-19 17:00 | 0 | Tiler | 65 | 57 | 35 | 77 | 60
178 | 1.2.2.2.1.7.3 | Formworker setout, drop material and 80% Deck | 6 | 19 September 2024 8:00 AM | 25 September 2024 5:00 PM | 177FS-1d | 179FS-1d,180 | 19 September 2024 8:00 AM | 2024-09-28 17:00 | 3 | Post Tension | 85 | 69 | 28 | 4 | 37
179 | 1.2.2.2.1.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 25 September 2024 8:00 AM | 28 September 2024 5:00 PM | 178FS-1d | 181,182 | 25 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Tiler | 70 | 82 | 23 | 80 | 49
180 | 1.2.2.2.1.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 26 September 2024 8:00 AM | 27 September 2024 5:00 PM | 178 |  | 26 September 2024 8:00 AM | 2024-09-30 17:00 | 3 | Floor Sealer | 28 | 20 | 20 | 13 | 34
181 | 1.2.2.2.1.7.6 | Services | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | 30 September 2024 8:00 AM | 2024-10-04 17:00 | 3 | Landscaper | 80 | 68 | 32 | 14 | 18
182 | 1.2.2.2.1.7.7 | Post Tension | 2 | 30 September 2024 8:00 AM | 1 October 2024 5:00 PM | 179 | 183FS-1d | 30 September 2024 8:00 AM | 2024-10-03 17:00 | 2 | Electrician | 33 | 47 | 25 | 79 | 6
183 | 1.2.2.2.1.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 1 October 2024 8:00 AM | 2 October 2024 5:00 PM | 181FS-1d,182FS-1d | 184 | 1 October 2024 8:00 AM | 2024-10-02 17:00 | 0 | Painter | 96 | 57 | 35 | 71 | 3
184 | 1.2.2.2.1.7.9 | Formworker setdowns and edge boards | 2 | 3 October 2024 8:00 AM | 4 October 2024 5:00 PM | 183 | 185 | 3 October 2024 8:00 AM | 2024-10-08 17:00 | 4 | Concretor | 40 | 44 | 21 | 46 | 43
185 | 1.2.2.2.1.7.10 | Pour | 1 | 8 October 2024 8:00 AM | 8 October 2024 5:00 PM | 184 | 188,150FS+5d | 8 October 2024 8:00 AM | 2024-10-08 17:00 | 0 | Subcontractor | 79 | 40 | 28 | 7 | 21
186 | 1.2.2.2.1.8 | Strip Formwork - Lvl 5 | 5 | 5 December 2024 8:00 AM | 10 December 2024 5:00 PM | 221FS+5d | 631,421FS-10d,419FS+5d | 5 December 2024 8:00 AM | 2024-12-11 17:00 | 1 | Carpet | 7 | 89 | 33 | 25 | 12
187 | 1.2.2.2.1.9 | Lvl 6 - FRP - Suspended Slab | 15 | 9 October 2024 8:00 AM | 25 October 2024 5:00 PM |  |  | 9 October 2024 8:00 AM | 2024-10-26 17:00 | 1 | Carpet | 30 | 76 | 24 | 22 | 41
188 | 1.2.2.2.1.9.1 | Scaffold Perimeter Protection | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 185 | 189SS | 9 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Contract Administrator | 26 | 80 | 11 | 28 | 60
189 | 1.2.2.2.1.9.2 | Setout and Install Lift/Stair Formwork | 1 | 9 October 2024 8:00 AM | 9 October 2024 5:00 PM | 188SS | 190FS-1d | 9 October 2024 8:00 AM | 2024-10-11 17:00 | 2 | Mechanical | 28 | 34 | 19 | 68 | 34
190 | 1.2.2.2.1.9.3 | Formworker setout, drop material and 80% Deck | 6 | 9 October 2024 8:00 AM | 15 October 2024 5:00 PM | 189FS-1d | 191FS-1d,192 | 9 October 2024 8:00 AM | 2024-10-16 17:00 | 1 | Concretor | 85 | 84 | 24 | 74 | 20
191 | 1.2.2.2.1.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 October 2024 8:00 AM | 18 October 2024 5:00 PM | 190FS-1d | 193,194 | 15 October 2024 8:00 AM | 2024-10-21 17:00 | 3 | Carpenter | 17 | 24 | 23 | 15 | 58
192 | 1.2.2.2.1.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 190 |  | 16 October 2024 8:00 AM | 2024-10-18 17:00 | 1 | Waterproofer | 87 | 80 | 33 | 92 | 10
193 | 1.2.2.2.1.9.6 | Services | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | 19 October 2024 8:00 AM | 2024-10-24 17:00 | 3 | Floor Sealer | 12 | 62 | 13 | 93 | 12
194 | 1.2.2.2.1.9.7 | Post Tension | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 191 | 195FS-1d | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Landscaper | 89 | 10 | 13 | 44 | 45
195 | 1.2.2.2.1.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 193FS-1d,194FS-1d | 196 | 21 October 2024 8:00 AM | 2024-10-25 17:00 | 3 | Contract Administrator | 24 | 62 | 20 | 76 | 15
196 | 1.2.2.2.1.9.9 | Formworker setdowns and edge boards | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 195 | 197 | 23 October 2024 8:00 AM | 2024-10-27 17:00 | 3 | Reinforcement Fixer | 82 | 79 | 25 | 61 | 55
197 | 1.2.2.2.1.9.10 | Pour | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 196 | 200 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Electrician | 43 | 11 | 23 | 50 | 58
198 | 1.2.2.2.1.10 | Strip Formwork - Lvl 6 | 5 | 6 December 2024 8:00 AM | 11 December 2024 5:00 PM | 225 | 657,425FS+5d,427FS-10d | 6 December 2024 8:00 AM | 2024-12-11 17:00 | 0 | Hoarding | 25 | 71 | 25 | 70 | 38
199 | 1.2.2.2.1.11 | Lvl 7 - FRP - Suspended Slab | 15 | 26 October 2024 8:00 AM | 12 November 2024 5:00 PM |  |  | 26 October 2024 8:00 AM | 2024-11-13 17:00 | 1 | Subcontractor | 79 | 19 | 30 | 10 | 19
200 | 1.2.2.2.1.11.1 | Scaffold Perimeter Protection | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 197 | 201SS | 26 October 2024 8:00 AM | 2024-10-31 17:00 | 5 | Metal Work | 14 | 36 | 21 | 71 | 55
201 | 1.2.2.2.1.11.2 | Setout and Install Lift/Stair Formwork | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 200SS | 202FS-1d | 26 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Concretor | 70 | 62 | 30 | 36 | 14
202 | 1.2.2.2.1.11.3 | Formworker setout, drop material and 80% Deck | 6 | 26 October 2024 8:00 AM | 1 November 2024 5:00 PM | 201FS-1d | 203FS-1d,204 | 26 October 2024 8:00 AM | 2024-11-02 17:00 | 1 | Concretor | 54 | 93 | 27 | 83 | 45
203 | 1.2.2.2.1.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 1 November 2024 8:00 AM | 5 November 2024 5:00 PM | 202FS-1d | 205,206 | 1 November 2024 8:00 AM | 2024-11-06 17:00 | 1 | Project Manager | 64 | 20 | 35 | 85 | 35
204 | 1.2.2.2.1.11.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 202 |  | 2 November 2024 8:00 AM | 2024-11-08 17:00 | 4 | Painter | 100 | 59 | 20 | 40 | 17
205 | 1.2.2.2.1.11.6 | Services | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Plasterboarder | 14 | 67 | 31 | 58 | 14
206 | 1.2.2.2.1.11.7 | Post Tension | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 203 | 207FS-1d | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 1 | Admin | 55 | 58 | 31 | 82 | 23
207 | 1.2.2.2.1.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 205FS-1d,206FS-1d | 208 | 7 November 2024 8:00 AM | 2024-11-11 17:00 | 3 | Excavation | 95 | 100 | 17 | 22 | 16
208 | 1.2.2.2.1.11.9 | Formworker setdowns and edge boards | 2 | 9 November 2024 8:00 AM | 11 November 2024 5:00 PM | 207 | 209 | 9 November 2024 8:00 AM | 2024-11-13 17:00 | 2 | Subcontractor | 1 | 11 | 14 | 24 | 9
209 | 1.2.2.2.1.11.10 | Pour | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 208 | 212,162FS+5d,174FS+5d,431FS+5d | 12 November 2024 8:00 AM | 2024-11-15 17:00 | 3 | Carpenter | 44 | 31 | 22 | 62 | 46
210 | 1.2.2.2.1.12 | Strip Formwork - Lvl 7 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 225FS+5d | 690,432FS-10d | 12 December 2024 8:00 AM | 2024-12-17 17:00 | 0 | Concretor | 17 | 70 | 20 | 35 | 15
211 | 1.2.2.2.1.13 | Lvl 8 (Roof) - FRP - Suspended Slab | 14 | 13 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | 13 November 2024 8:00 AM | 2024-11-29 17:00 | 1 | Formworker | 52 | 56 | 10 | 95 | 37
212 | 1.2.2.2.1.13.1 | Scaffold Perimeter Protection | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 209 | 213SS | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Electrician | 4 | 10 | 17 | 73 | 54
213 | 1.2.2.2.1.13.2 | Setout and Install Lift/Stair Formwork | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 212SS | 214FS-1d | 13 November 2024 8:00 AM | 2024-11-16 17:00 | 3 | Joiner | 19 | 50 | 21 | 64 | 35
214 | 1.2.2.2.1.13.3 | Formworker setout, drop material and 80% Deck | 6 | 13 November 2024 8:00 AM | 19 November 2024 5:00 PM | 213FS-1d | 215FS-1d,216 | 13 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Cleaner | 71 | 85 | 11 | 3 | 54
215 | 1.2.2.2.1.13.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214FS-1d | 217,218 | 19 November 2024 8:00 AM | 2024-11-22 17:00 | 1 | Timber Floorer | 41 | 10 | 22 | 18 | 31
216 | 1.2.2.2.1.13.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 214 |  | 20 November 2024 8:00 AM | 2024-11-23 17:00 | 2 | Mechanical | 36 | 47 | 25 | 6 | 48
217 | 1.2.2.2.1.13.6 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Contract Administrator | 1 | 90 | 13 | 59 | 43
218 | 1.2.2.2.1.13.7 | Post Tension | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 215 | 219FS-1d | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Stone Mason | 76 | 87 | 12 | 15 | 58
219 | 1.2.2.2.1.13.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 217FS-1d,218FS-1d | 220 | 23 November 2024 8:00 AM | 2024-11-27 17:00 | 2 | Surveyor | 77 | 68 | 28 | 31 | 3
220 | 1.2.2.2.1.13.9 | Formworker setdowns and edge boards | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 219 | 221 | 26 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Renderer | 70 | 36 | 10 | 44 | 53
221 | 1.2.2.2.1.13.10 | Pour - Structure Top Out | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 220 | 223FS+12d,222,225,186FS+5d,437FS+5d | 28 November 2024 8:00 AM | 2024-11-30 17:00 | 2 | Admin | 85 | 50 | 23 | 37 | 5
222 | 1.2.2.2.1.13.11 | Structure Top Out | 0 | 28 November 2024 5:00 PM | 28 November 2024 5:00 PM | 221 |  | 28 November 2024 5:00 PM | 2024-11-28 17:00 | 0 | Head Contractor | 2 | 92 | 22 | 2 | 16
223 | 1.2.2.2.1.14 | Strip Formwork - Lvl 8 | 4 | 13 December 2024 8:00 AM | 17 December 2024 5:00 PM | 221FS+12d | 716,439FS+10d | 13 December 2024 8:00 AM | 2024-12-19 17:00 | 2 | Development Manager | 25 | 46 | 11 | 45 | 57
224 | 1.2.2.2.1.15 | Lift Shaft | 23 | 29 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 29 November 2024 8:00 AM | 2025-01-03 17:00 | 0 | Plasterboarder | 67 | 69 | 14 | 89 | 28
225 | 1.2.2.2.1.15.1 | FRP Lift Over-run | 6 | 29 November 2024 8:00 AM | 5 December 2024 5:00 PM | 221 | 226FS+5d,228,198,210FS+5d | 29 November 2024 8:00 AM | 2024-12-07 17:00 | 2 | Cleaner | 53 | 88 | 16 | 77 | 14
226 | 1.2.2.2.1.15.2 | Strip Lift Shaft Formwork | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 225FS+5d | 227 | 12 December 2024 8:00 AM | 2024-12-19 17:00 | 3 | Contract Administrator | 55 | 31 | 32 | 89 | 37
227 | 1.2.2.2.1.15.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 17 December 2024 8:00 AM | 3 January 2025 5:00 PM | 226 | 3451 | 17 December 2024 8:00 AM | 2025-01-04 17:00 | 1 | Timber Floorer | 48 | 84 | 21 | 61 | 25
228 | 1.2.2.2.1.15.4 | Building A Structure Complete | 0 | 5 December 2024 5:00 PM | 5 December 2024 5:00 PM | 225 | 6 | 5 December 2024 5:00 PM | 2024-12-07 17:00 | 2 | Reinforcement Fixer | 3 | 25 | 33 | 88 | 26
229 | 1.2.2.2.2 | Building B | 119 | 13 July 2024 8:00 AM | 30 November 2024 5:00 PM |  | 397 | 13 July 2024 8:00 AM | 2024-12-03 17:00 | 3 | Head Contractor | 98 | 77 | 13 | 22 | 10
230 | 1.2.2.2.2.1 | Lvl 2 - FRP - Suspended Slab | 18 | 13 July 2024 8:00 AM | 2 August 2024 5:00 PM |  |  | 13 July 2024 8:00 AM | 2024-08-02 17:00 | 0 | Plumber | 45 | 87 | 16 | 16 | 19
231 | 1.2.2.2.2.1.1 | Scaffold Perimeter Protection | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 232SS |  | 13 July 2024 8:00 AM | 2024-07-19 17:00 | 6 | Window | 29 | 85 | 14 | 22 | 16
232 | 1.2.2.2.2.1.2 | Setout and Install Lift/Stair Formwork | 1 | 13 July 2024 8:00 AM | 15 July 2024 8:00 AM | 233SF | 231SS | 13 July 2024 8:00 AM | 2024-07-16 08:00 | 1 | Plumber | 37 | 42 | 23 | 34 | 45
233 | 1.2.2.2.2.1.3 | Formworker setout, drop material and 80% Deck | 6 | 15 July 2024 8:00 AM | 20 July 2024 5:00 PM | 135 | 234FS-1d,235,232SF | 15 July 2024 8:00 AM | 2024-07-22 17:00 | 2 | Joiner | 49 | 74 | 21 | 8 | 18
234 | 1.2.2.2.2.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 20 July 2024 8:00 AM | 24 July 2024 5:00 PM | 233FS-1d | 236,237 | 20 July 2024 8:00 AM | 2024-07-26 17:00 | 2 | Subcontractor | 33 | 14 | 23 | 99 | 27
235 | 1.2.2.2.2.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 22 July 2024 8:00 AM | 23 July 2024 5:00 PM | 233 |  | 22 July 2024 8:00 AM | 2024-07-23 17:00 | 0 | Floor Sealer | 11 | 86 | 32 | 8 | 43
236 | 1.2.2.2.2.1.6 | Services | 2 | 25 July 2024 8:00 AM | 26 July 2024 5:00 PM | 234 | 238FS-1d | 25 July 2024 8:00 AM | 2024-07-26 17:00 | 0 | Excavation | 6 | 81 | 28 | 46 | 3
237 | 1.2.2.2.2.1.7 | Post Tension | 3 | 25 July 2024 8:00 AM | 27 July 2024 5:00 PM | 234 | 238FS-1d | 25 July 2024 8:00 AM | 2024-07-28 17:00 | 1 | Floor Sealer | 79 | 16 | 12 | 9 | 57
238 | 1.2.2.2.2.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 27 July 2024 8:00 AM | 29 July 2024 5:00 PM | 236FS-1d,237FS-1d | 239 | 27 July 2024 8:00 AM | 2024-08-03 17:00 | 5 | Plumber | 37 | 18 | 35 | 80 | 35
239 | 1.2.2.2.2.1.9 | Formworker setdowns and edge boards | 3 | 30 July 2024 8:00 AM | 1 August 2024 5:00 PM | 238 | 240 | 30 July 2024 8:00 AM | 2024-08-01 17:00 | 0 | Hoarding | 26 | 71 | 33 | 37 | 2
240 | 1.2.2.2.2.1.10 | Pour | 1 | 2 August 2024 8:00 AM | 2 August 2024 5:00 PM | 239 | 243,309FS+30d | 2 August 2024 8:00 AM | 2024-08-02 17:00 | 0 | Hoarding | 13 | 51 | 13 | 53 | 60
241 | 1.2.2.2.2.2 | Strip Formwork - Lvl 2 | 5 | 28 September 2024 8:00 AM | 3 October 2024 5:00 PM | 276 | 447 | 28 September 2024 8:00 AM | 2024-10-05 17:00 | 2 | Excavation | 17 | 46 | 22 | 79 | 17
242 | 1.2.2.2.2.3 | Lvl 3 - FRP - Suspended Slab | 18 | 3 August 2024 8:00 AM | 23 August 2024 5:00 PM |  |  | 3 August 2024 8:00 AM | 2024-08-24 17:00 | 1 | Head Contractor | 94 | 29 | 17 | 51 | 21
243 | 1.2.2.2.2.3.1 | Scaffold Perimeter Protection | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 240 | 244SS | 3 August 2024 8:00 AM | 2024-08-05 17:00 | 2 | Concretor | 98 | 80 | 10 | 4 | 48
244 | 1.2.2.2.2.3.2 | Setout and Install Lift/Stair Formwork | 1 | 3 August 2024 8:00 AM | 3 August 2024 5:00 PM | 243SS | 245 | 3 August 2024 8:00 AM | 2024-08-06 17:00 | 3 | Surveyor | 18 | 66 | 32 | 67 | 54
245 | 1.2.2.2.2.3.3 | Formworker setout, drop material and 80% Deck | 6 | 5 August 2024 8:00 AM | 10 August 2024 5:00 PM | 244 | 246FS-1d,247 | 5 August 2024 8:00 AM | 2024-08-10 17:00 | 0 | Admin | 72 | 79 | 17 | 61 | 51
246 | 1.2.2.2.2.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 10 August 2024 8:00 AM | 14 August 2024 5:00 PM | 245FS-1d | 248,249 | 10 August 2024 8:00 AM | 2024-08-19 17:00 | 5 | Carpenter | 2 | 11 | 32 | 17 | 27
247 | 1.2.2.2.2.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 12 August 2024 8:00 AM | 13 August 2024 5:00 PM | 245 |  | 12 August 2024 8:00 AM | 2024-08-13 17:00 | 0 | Floor Sealer | 98 | 96 | 23 | 80 | 13
248 | 1.2.2.2.2.3.6 | Services | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | 15 August 2024 8:00 AM | 2024-08-17 17:00 | 1 | Carpet | 83 | 11 | 12 | 82 | 25
249 | 1.2.2.2.2.3.7 | Post Tension | 2 | 15 August 2024 8:00 AM | 16 August 2024 5:00 PM | 246 | 250FS-1d | 15 August 2024 8:00 AM | 2024-08-18 17:00 | 2 | Concretor | 64 | 11 | 13 | 70 | 46
250 | 1.2.2.2.2.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 16 August 2024 8:00 AM | 19 August 2024 5:00 PM | 248FS-1d,249FS-1d | 251 | 16 August 2024 8:00 AM | 2024-08-19 17:00 | 0 | Admin | 84 | 89 | 25 | 72 | 5
251 | 1.2.2.2.2.3.9 | Formworker setdowns and edge boards | 3 | 20 August 2024 8:00 AM | 22 August 2024 5:00 PM | 250 | 252 | 20 August 2024 8:00 AM | 2024-08-24 17:00 | 2 | Plumber | 17 | 62 | 24 | 40 | 50
252 | 1.2.2.2.2.3.10 | Pour | 1 | 23 August 2024 8:00 AM | 23 August 2024 5:00 PM | 251 | 255,3447 | 23 August 2024 8:00 AM | 2024-08-23 17:00 | 0 | Fire | 58 | 61 | 12 | 16 | 54
253 | 1.2.2.2.2.4 | Strip Formwork - Lvl 3 | 5 | 21 October 2024 8:00 AM | 25 October 2024 5:00 PM | 288 | 453,1605 | 21 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Scaffolder | 75 | 77 | 24 | 57 | 27
254 | 1.2.2.2.2.5 | Lvl 4 - FRP - Suspended Slab | 15 | 24 August 2024 8:00 AM | 10 September 2024 5:00 PM |  |  | 24 August 2024 8:00 AM | 2024-09-13 17:00 | 3 | Metal Work | 78 | 12 | 14 | 47 | 13
255 | 1.2.2.2.2.5.1 | Scaffold Perimeter Protection | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 252 | 256SS | 24 August 2024 8:00 AM | 2024-08-25 17:00 | 1 | Foreman | 24 | 89 | 31 | 19 | 29
256 | 1.2.2.2.2.5.2 | Setout and Install Lift/Stair Formwork | 1 | 24 August 2024 8:00 AM | 24 August 2024 5:00 PM | 255SS | 257FS-1d | 24 August 2024 8:00 AM | 2024-08-26 17:00 | 2 | Project Manager | 28 | 10 | 25 | 31 | 6
257 | 1.2.2.2.2.5.3 | Formworker setout, drop material and 80% Deck | 6 | 24 August 2024 8:00 AM | 30 August 2024 5:00 PM | 256FS-1d | 258FS-1d,259 | 24 August 2024 8:00 AM | 2024-09-02 17:00 | 3 | Excavation | 23 | 85 | 19 | 29 | 5
258 | 1.2.2.2.2.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 30 August 2024 8:00 AM | 3 September 2024 5:00 PM | 257FS-1d | 260,261 | 30 August 2024 8:00 AM | 2024-09-03 17:00 | 0 | Fire | 11 | 29 | 11 | 0 | 12
259 | 1.2.2.2.2.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 31 August 2024 8:00 AM | 2 September 2024 5:00 PM | 257 |  | 31 August 2024 8:00 AM | 2024-09-04 17:00 | 2 | Plumber | 78 | 50 | 33 | 57 | 59
260 | 1.2.2.2.2.5.6 | Services | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | 4 September 2024 8:00 AM | 2024-09-05 17:00 | 0 | Foreman | 65 | 27 | 10 | 80 | 55
261 | 1.2.2.2.2.5.7 | Post Tension | 2 | 4 September 2024 8:00 AM | 5 September 2024 5:00 PM | 258 | 262FS-1d | 4 September 2024 8:00 AM | 2024-09-05 17:00 | 0 | Waterproofer | 53 | 44 | 23 | 67 | 32
262 | 1.2.2.2.2.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 5 September 2024 8:00 AM | 6 September 2024 5:00 PM | 260FS-1d,261FS-1d | 263 | 5 September 2024 8:00 AM | 2024-09-08 17:00 | 2 | Admin | 84 | 23 | 10 | 1 | 20
263 | 1.2.2.2.2.5.9 | Formworker setdowns and edge boards | 2 | 7 September 2024 8:00 AM | 9 September 2024 5:00 PM | 262 | 264 | 7 September 2024 8:00 AM | 2024-09-11 17:00 | 2 | Window | 91 | 27 | 14 | 19 | 15
264 | 1.2.2.2.2.5.10 | Pour | 1 | 10 September 2024 8:00 AM | 10 September 2024 5:00 PM | 263 | 267 | 10 September 2024 8:00 AM | 2024-09-12 17:00 | 2 | Plasterboarder | 93 | 30 | 26 | 100 | 18
265 | 1.2.2.2.2.6 | Strip Formwork - Lvl 4 | 5 | 11 November 2024 8:00 AM | 15 November 2024 5:00 PM | 300 | 459,1632 | 11 November 2024 8:00 AM | 2024-11-18 17:00 | 3 | Carpet | 91 | 55 | 27 | 95 | 24
266 | 1.2.2.2.2.7 | Lvl 5 - FRP - Suspended Slab | 15 | 11 September 2024 8:00 AM | 27 September 2024 5:00 PM |  |  | 11 September 2024 8:00 AM | 2024-09-27 17:00 | 0 | Plasterboarder | 92 | 41 | 16 | 55 | 29
267 | 1.2.2.2.2.7.1 | Scaffold Perimeter Protection | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 264 | 268SS | 11 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Carpet | 3 | 81 | 28 | 82 | 12
268 | 1.2.2.2.2.7.2 | Setout and Install Lift/Stair Formwork | 1 | 11 September 2024 8:00 AM | 11 September 2024 5:00 PM | 267SS | 269FS-1d | 11 September 2024 8:00 AM | 2024-09-11 17:00 | 0 | Floor Sealer | 90 | 80 | 28 | 59 | 25
269 | 1.2.2.2.2.7.3 | Formworker setout, drop material and 80% Deck | 6 | 11 September 2024 8:00 AM | 17 September 2024 5:00 PM | 268FS-1d | 270FS-1d,271 | 11 September 2024 8:00 AM | 2024-09-18 17:00 | 1 | Excavation | 57 | 78 | 21 | 94 | 36
270 | 1.2.2.2.2.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 17 September 2024 8:00 AM | 20 September 2024 5:00 PM | 269FS-1d | 272,273 | 17 September 2024 8:00 AM | 2024-09-20 17:00 | 0 | Floor Sealer | 88 | 97 | 13 | 12 | 11
271 | 1.2.2.2.2.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 18 September 2024 8:00 AM | 19 September 2024 5:00 PM | 269 |  | 18 September 2024 8:00 AM | 2024-09-22 17:00 | 3 | Line Market | 4 | 16 | 21 | 10 | 43
272 | 1.2.2.2.2.7.6 | Services | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | 21 September 2024 8:00 AM | 2024-09-26 17:00 | 3 | Carpenter | 63 | 30 | 17 | 80 | 15
273 | 1.2.2.2.2.7.7 | Post Tension | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 270 | 274FS-1d | 21 September 2024 8:00 AM | 2024-09-23 17:00 | 0 | Admin | 72 | 41 | 29 | 5 | 11
274 | 1.2.2.2.2.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 23 September 2024 8:00 AM | 24 September 2024 5:00 PM | 272FS-1d,273FS-1d | 275 | 23 September 2024 8:00 AM | 2024-09-26 17:00 | 2 | Plumber | 93 | 92 | 22 | 98 | 18
275 | 1.2.2.2.2.7.9 | Formworker setdowns and edge boards | 2 | 25 September 2024 8:00 AM | 26 September 2024 5:00 PM | 274 | 276 | 25 September 2024 8:00 AM | 2024-09-29 17:00 | 3 | Timber Floorer | 65 | 78 | 16 | 63 | 34
276 | 1.2.2.2.2.7.10 | Pour | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 275 | 279,241 | 27 September 2024 8:00 AM | 2024-10-01 17:00 | 4 | Site Manager | 86 | 89 | 22 | 17 | 56
277 | 1.2.2.2.2.8 | Strip Formwork - Lvl 5 | 5 | 18 November 2024 8:00 AM | 22 November 2024 5:00 PM | 303 | 465,1659 | 18 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Hoarding | 11 | 38 | 13 | 66 | 5
278 | 1.2.2.2.2.9 | Lvl 6 - FRP - Suspended Slab | 17 | 28 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | 28 September 2024 8:00 AM | 2024-10-19 17:00 | 0 | Joiner | 36 | 28 | 29 | 86 | 2
279 | 1.2.2.2.2.9.1 | Scaffold Perimeter Protection | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 276 | 280SS | 28 September 2024 8:00 AM | 2024-10-01 17:00 | 3 | Post Tension | 99 | 70 | 24 | 6 | 18
280 | 1.2.2.2.2.9.2 | Setout and Install Lift/Stair Formwork | 1 | 28 September 2024 8:00 AM | 28 September 2024 5:00 PM | 279SS | 281FS-1d | 28 September 2024 8:00 AM | 2024-09-28 17:00 | 0 | Electrician | 52 | 19 | 31 | 15 | 47
281 | 1.2.2.2.2.9.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 280FS-1d | 282FS-1d,283 | 28 September 2024 8:00 AM | 2024-10-06 17:00 | 2 | Site Manager | 99 | 31 | 12 | 42 | 51
282 | 1.2.2.2.2.9.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 281FS-1d | 284,285 | 4 October 2024 8:00 AM | 2024-10-12 17:00 | 2 | Cleaner | 20 | 42 | 28 | 32 | 26
283 | 1.2.2.2.2.9.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 281 |  | 8 October 2024 8:00 AM | 2024-10-10 17:00 | 1 | Admin | 18 | 47 | 10 | 55 | 40
284 | 1.2.2.2.2.9.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | 11 October 2024 8:00 AM | 2024-10-17 17:00 | 3 | Concretor | 35 | 63 | 32 | 3 | 58
285 | 1.2.2.2.2.9.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 282 | 286FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Mechanical | 26 | 80 | 33 | 84 | 46
286 | 1.2.2.2.2.9.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 284FS-1d,285FS-1d | 287 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Development Manager | 23 | 99 | 27 | 100 | 60
287 | 1.2.2.2.2.9.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 286 | 288 | 17 October 2024 8:00 AM | 2024-10-19 17:00 | 1 | Concretor | 66 | 37 | 21 | 13 | 42
288 | 1.2.2.2.2.9.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 287 | 291,253 | 19 October 2024 8:00 AM | 2024-10-20 17:00 | 1 | Head Contractor | 63 | 87 | 13 | 86 | 53
289 | 1.2.2.2.2.10 | Strip Formwork - Lvl 6 | 5 | 20 November 2024 8:00 AM | 25 November 2024 5:00 PM | 300FS+8d | 657,471,1686 | 20 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Window | 75 | 26 | 23 | 2 | 29
290 | 1.2.2.2.2.11 | Lvl 7 (Roof) - FRP - Suspended Slab | 18 | 21 October 2024 8:00 AM | 9 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-09 17:00 | 0 | Stone Mason | 18 | 35 | 25 | 64 | 32
291 | 1.2.2.2.2.11.1 | Scaffold Perimeter Protection | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 288 | 292SS | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Surveyor | 20 | 44 | 26 | 32 | 29
292 | 1.2.2.2.2.11.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 291SS | 293FS-1d | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Carpenter | 29 | 23 | 12 | 54 | 58
293 | 1.2.2.2.2.11.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 292FS-1d | 294FS-1d,295 | 21 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Fire | 3 | 37 | 13 | 35 | 6
294 | 1.2.2.2.2.11.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293FS-1d | 296,297 | 26 October 2024 8:00 AM | 2024-10-31 17:00 | 1 | Foreman | 67 | 78 | 32 | 87 | 51
295 | 1.2.2.2.2.11.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 28 October 2024 8:00 AM | 30 October 2024 5:00 PM | 293 |  | 28 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Plasterboarder | 44 | 96 | 29 | 13 | 42
296 | 1.2.2.2.2.11.6 | Services | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | 31 October 2024 8:00 AM | 2024-11-03 17:00 | 1 | Formworker | 73 | 17 | 19 | 46 | 16
297 | 1.2.2.2.2.11.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 294 | 298FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Line Market | 97 | 25 | 30 | 95 | 16
298 | 1.2.2.2.2.11.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 296FS-1d,297FS-1d | 299 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Plasterboarder | 42 | 91 | 18 | 39 | 11
299 | 1.2.2.2.2.11.9 | Formworker setdowns and edge boards | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 298 | 300 | 6 November 2024 8:00 AM | 2024-11-11 17:00 | 3 | Electrician | 47 | 60 | 22 | 61 | 28
300 | 1.2.2.2.2.11.10 | Pour | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 299 | 303,289FS+8d,301FS+12d,1739FS+24d,265 | 9 November 2024 8:00 AM | 2024-11-10 17:00 | 1 | Carpenter | 56 | 47 | 13 | 42 | 57
301 | 1.2.2.2.2.12 | Strip Formwork - Lvl 7 | 5 | 25 November 2024 8:00 AM | 29 November 2024 5:00 PM | 300FS+12d | 716,748FS+24d,477,1713 | 25 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Head Contractor | 96 | 73 | 12 | 92 | 46
302 | 1.2.2.2.2.13 | Lift Shaft | 18 | 11 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 11 November 2024 8:00 AM | 2024-12-02 17:00 | 2 | Electrician | 50 | 28 | 12 | 83 | 39
303 | 1.2.2.2.2.13.1 | FRP Lift Over-run | 6 | 11 November 2024 8:00 AM | 16 November 2024 5:00 PM | 300 | 304,277 | 11 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Carpet | 71 | 25 | 12 | 12 | 19
304 | 1.2.2.2.2.13.2 | Strip Lift Shaft Formwork | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 303 | 305 | 18 November 2024 8:00 AM | 2024-11-23 17:00 | 2 | Waterproofer | 37 | 100 | 10 | 61 | 48
305 | 1.2.2.2.2.13.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 304 | 3452,306 | 22 November 2024 8:00 AM | 2024-12-02 17:00 | 2 | Post Tension | 37 | 30 | 12 | 4 | 34
306 | 1.2.2.2.2.13.4 | Building B Structure Complete | 0 | 30 November 2024 5:00 PM | 30 November 2024 5:00 PM | 305 | 7,6 | 30 November 2024 5:00 PM | 2024-12-01 17:00 | 1 | Electrician | 58 | 15 | 19 | 24 | 31
307 | 1.2.2.2.3 | Building C | 90 | 7 September 2024 8:00 AM | 23 December 2024 5:00 PM |  | 397 | 7 September 2024 8:00 AM | 2024-12-24 17:00 | 1 | Metal Work | 21 | 12 | 25 | 39 | 11
308 | 1.2.2.2.3.1 | Lvl 2 - FRP - Suspended Slab | 17 | 7 September 2024 8:00 AM | 26 September 2024 5:00 PM |  |  | 7 September 2024 8:00 AM | 2024-09-26 17:00 | 0 | Joiner | 75 | 25 | 33 | 86 | 59
309 | 1.2.2.2.3.1.1 | Scaffold Stair Removal/Adjustment | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 135,240FS+30d | 310SS | 7 September 2024 8:00 AM | 2024-09-08 17:00 | 1 | Line Market | 39 | 67 | 31 | 25 | 59
310 | 1.2.2.2.3.1.2 | Setout and Install Lift/Stair Formwork | 1 | 7 September 2024 8:00 AM | 7 September 2024 5:00 PM | 309SS | 311 | 7 September 2024 8:00 AM | 2024-09-07 17:00 | 0 | Plasterboarder | 28 | 56 | 13 | 4 | 45
311 | 1.2.2.2.3.1.3 | Formworker setout, drop material and 80% Deck | 6 | 9 September 2024 8:00 AM | 14 September 2024 5:00 PM | 310 | 312FS-1d,313,365FS+10d | 9 September 2024 8:00 AM | 2024-09-17 17:00 | 3 | Plasterboarder | 31 | 78 | 29 | 77 | 3
312 | 1.2.2.2.3.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 14 September 2024 8:00 AM | 18 September 2024 5:00 PM | 311FS-1d | 314,315 | 14 September 2024 8:00 AM | 2024-09-20 17:00 | 2 | Excavation | 0 | 12 | 13 | 66 | 25
313 | 1.2.2.2.3.1.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 September 2024 8:00 AM | 17 September 2024 5:00 PM | 311 |  | 16 September 2024 8:00 AM | 2024-09-17 17:00 | 0 | Development Manager | 74 | 31 | 33 | 72 | 21
314 | 1.2.2.2.3.1.6 | Services | 2 | 19 September 2024 8:00 AM | 20 September 2024 5:00 PM | 312 | 316FS-1d | 19 September 2024 8:00 AM | 2024-09-21 17:00 | 1 | Carpet | 87 | 48 | 22 | 4 | 24
315 | 1.2.2.2.3.1.7 | Post Tension | 3 | 19 September 2024 8:00 AM | 21 September 2024 5:00 PM | 312 | 316FS-1d | 19 September 2024 8:00 AM | 2024-09-23 17:00 | 2 | Project Manager | 66 | 13 | 11 | 9 | 49
316 | 1.2.2.2.3.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 21 September 2024 8:00 AM | 23 September 2024 5:00 PM | 314FS-1d,315FS-1d | 317 | 21 September 2024 8:00 AM | 2024-09-27 17:00 | 4 | Project Manager | 86 | 18 | 24 | 94 | 28
317 | 1.2.2.2.3.1.9 | Formworker setdowns and edge boards | 2 | 24 September 2024 8:00 AM | 25 September 2024 5:00 PM | 316 | 318 | 24 September 2024 8:00 AM | 2024-09-25 17:00 | 0 | Stone Mason | 63 | 11 | 16 | 64 | 18
318 | 1.2.2.2.3.1.10 | Pour | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 317 | 321 | 26 September 2024 8:00 AM | 2024-09-28 17:00 | 2 | Head Contractor | 50 | 75 | 29 | 52 | 48
319 | 1.2.2.2.3.2 | Strip Formwork - Lvl 2 | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 354 | 331FS+5d | 28 November 2024 8:00 AM | 2024-12-04 17:00 | 1 | Carpet | 43 | 57 | 31 | 81 | 35
320 | 1.2.2.2.3.3 | Lvl 3 - FRP - Suspended Slab | 17 | 27 September 2024 8:00 AM | 18 October 2024 5:00 PM |  |  | 27 September 2024 8:00 AM | 2024-10-19 17:00 | 1 | Surveyor | 96 | 28 | 17 | 25 | 10
321 | 1.2.2.2.3.3.1 | Scaffold Stair Removal/Adjustment | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 318 | 322SS | 27 September 2024 8:00 AM | 2024-09-28 17:00 | 1 | Post Tension | 83 | 42 | 35 | 66 | 28
322 | 1.2.2.2.3.3.2 | Setout and Install Lift/Stair Formwork | 1 | 27 September 2024 8:00 AM | 27 September 2024 5:00 PM | 321SS | 323 | 27 September 2024 8:00 AM | 2024-09-28 17:00 | 1 | Timber Floorer | 50 | 10 | 33 | 88 | 5
323 | 1.2.2.2.3.3.3 | Formworker setout, drop material and 80% Deck | 6 | 28 September 2024 8:00 AM | 4 October 2024 5:00 PM | 322 | 324FS-1d,325 | 28 September 2024 8:00 AM | 2024-10-07 17:00 | 3 | Post Tension | 33 | 56 | 31 | 18 | 40
324 | 1.2.2.2.3.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 4 October 2024 8:00 AM | 10 October 2024 5:00 PM | 323FS-1d | 326,327 | 4 October 2024 8:00 AM | 2024-10-12 17:00 | 2 | Plasterboarder | 26 | 27 | 33 | 100 | 40
325 | 1.2.2.2.3.3.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 8 October 2024 8:00 AM | 9 October 2024 5:00 PM | 323 |  | 8 October 2024 8:00 AM | 2024-10-10 17:00 | 1 | Formworker | 64 | 89 | 12 | 11 | 50
326 | 1.2.2.2.3.3.6 | Services | 2 | 11 October 2024 8:00 AM | 12 October 2024 5:00 PM | 324 | 328FS-1d | 11 October 2024 8:00 AM | 2024-10-12 17:00 | 0 | Line Market | 55 | 100 | 35 | 91 | 46
327 | 1.2.2.2.3.3.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 324 | 328FS-1d | 11 October 2024 8:00 AM | 2024-10-15 17:00 | 1 | Reinforcement Fixer | 95 | 80 | 23 | 63 | 58
328 | 1.2.2.2.3.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 326FS-1d,327FS-1d | 329 | 14 October 2024 8:00 AM | 2024-10-15 17:00 | 0 | Metal Work | 59 | 48 | 31 | 80 | 56
329 | 1.2.2.2.3.3.9 | Formworker setdowns and edge boards | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 328 | 330 | 16 October 2024 8:00 AM | 2024-10-18 17:00 | 1 | Waterproofer | 49 | 24 | 22 | 11 | 24
330 | 1.2.2.2.3.3.10 | Pour | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 329 | 333 | 18 October 2024 8:00 AM | 2024-10-24 17:00 | 6 | Excavation | 23 | 99 | 16 | 69 | 16
331 | 1.2.2.2.3.4 | Strip Formwork - Lvl 3 | 5 | 10 December 2024 8:00 AM | 14 December 2024 5:00 PM | 319FS+5d | 490,1748,2151,1774,2177FS+5d | 10 December 2024 8:00 AM | 2024-12-20 17:00 | 6 | Line Market | 30 | 53 | 10 | 24 | 52
332 | 1.2.2.2.3.5 | Lvl 4 - FRP - Suspended Slab | 17 | 19 October 2024 8:00 AM | 7 November 2024 5:00 PM |  |  | 19 October 2024 8:00 AM | 2024-11-09 17:00 | 2 | Hoarding | 73 | 20 | 20 | 8 | 48
333 | 1.2.2.2.3.5.1 | Scaffold Stair Removal/Adjustment | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 330 | 334SS | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Contract Administrator | 62 | 86 | 10 | 45 | 39
334 | 1.2.2.2.3.5.2 | Setout and Install Lift/Stair Formwork | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 333SS | 335 | 19 October 2024 8:00 AM | 2024-10-20 17:00 | 1 | Site Manager | 65 | 55 | 27 | 13 | 30
335 | 1.2.2.2.3.5.3 | Formworker setout, drop material and 80% Deck | 6 | 21 October 2024 8:00 AM | 26 October 2024 5:00 PM | 334 | 336FS-1d,337 | 21 October 2024 8:00 AM | 2024-10-27 17:00 | 1 | Cleaner | 63 | 78 | 27 | 31 | 53
336 | 1.2.2.2.3.5.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 26 October 2024 8:00 AM | 30 October 2024 5:00 PM | 335FS-1d | 338,339 | 26 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Plumber | 94 | 66 | 24 | 13 | 2
337 | 1.2.2.2.3.5.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 335 |  | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Project Manager | 21 | 37 | 16 | 2 | 25
338 | 1.2.2.2.3.5.6 | Services | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 336 | 340FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 1 | Concretor | 31 | 54 | 11 | 23 | 48
339 | 1.2.2.2.3.5.7 | Post Tension | 3 | 31 October 2024 8:00 AM | 2 November 2024 5:00 PM | 336 | 340FS-1d | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 0 | Carpenter | 25 | 34 | 30 | 11 | 31
340 | 1.2.2.2.3.5.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 338FS-1d,339FS-1d | 341 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 1 | Head Contractor | 17 | 24 | 22 | 94 | 59
341 | 1.2.2.2.3.5.9 | Formworker setdowns and edge boards | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 340 | 342 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Mechanical | 69 | 20 | 28 | 46 | 30
342 | 1.2.2.2.3.5.10 | Pour | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 341 | 345 | 7 November 2024 8:00 AM | 2024-11-12 17:00 | 5 | Surveyor | 95 | 13 | 27 | 50 | 2
343 | 1.2.2.2.3.6 | Strip Formwork - Lvl 4 | 5 | 16 December 2024 8:00 AM | 20 December 2024 5:00 PM | 354FS+15d | 495,2648,2674FS+5d | 16 December 2024 8:00 AM | 2024-12-20 17:00 | 0 | Plasterboarder | 12 | 44 | 25 | 20 | 49
344 | 1.2.2.2.3.7 | Lvl 5 (Roof) - FRP - Suspended Slab | 17 | 8 November 2024 8:00 AM | 27 November 2024 5:00 PM |  |  | 8 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Hoarding | 49 | 41 | 16 | 65 | 59
345 | 1.2.2.2.3.7.1 | Scaffold Stair Removal/Adjustment | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 342 | 346SS | 8 November 2024 8:00 AM | 2024-11-10 17:00 | 2 | Waterproofer | 86 | 94 | 20 | 29 | 45
346 | 1.2.2.2.3.7.2 | Setout and Install Lift/Stair Formwork | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 345SS | 347 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Renderer | 46 | 45 | 13 | 45 | 15
347 | 1.2.2.2.3.7.3 | Formworker setout, drop material and 80% Deck | 6 | 9 November 2024 8:00 AM | 15 November 2024 5:00 PM | 346 | 348FS-1d,349 | 9 November 2024 8:00 AM | 2024-11-20 17:00 | 5 | Excavation | 9 | 86 | 23 | 90 | 17
348 | 1.2.2.2.3.7.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 4 | 15 November 2024 8:00 AM | 19 November 2024 5:00 PM | 347FS-1d | 350,351 | 15 November 2024 8:00 AM | 2024-11-22 17:00 | 3 | Carpet | 80 | 62 | 31 | 0 | 48
349 | 1.2.2.2.3.7.5 | Steel Fixer - Drop Prefabricated Columns | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 347 |  | 16 November 2024 8:00 AM | 2024-11-19 17:00 | 1 | Timber Floorer | 22 | 50 | 33 | 21 | 58
350 | 1.2.2.2.3.7.6 | Services | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 348 | 352FS-1d | 20 November 2024 8:00 AM | 2024-11-23 17:00 | 2 | Project Manager | 21 | 48 | 23 | 91 | 43
351 | 1.2.2.2.3.7.7 | Post Tension | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 348 | 352FS-1d | 20 November 2024 8:00 AM | 2024-11-23 17:00 | 1 | Carpet | 47 | 15 | 16 | 45 | 5
352 | 1.2.2.2.3.7.8 | Steel Fixer - Top Steel, setdowns and starter bars | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 350FS-1d,351FS-1d | 353 | 22 November 2024 8:00 AM | 2024-11-24 17:00 | 1 | Fire | 84 | 81 | 25 | 7 | 10
353 | 1.2.2.2.3.7.9 | Formworker setdowns and edge boards | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 352 | 354 | 25 November 2024 8:00 AM | 2024-11-28 17:00 | 2 | Contract Administrator | 32 | 62 | 14 | 26 | 39
354 | 1.2.2.2.3.7.10 | Pour | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 353 | 357,355FS+12d,343FS+15d,360,319 | 27 November 2024 8:00 AM | 2024-12-01 17:00 | 4 | Admin | 37 | 90 | 32 | 90 | 5
355 | 1.2.2.2.3.8 | Strip Formwork - Lvl 5 | 5 | 12 December 2024 8:00 AM | 17 December 2024 5:00 PM | 354FS+12d | 500,3145,3171FS+5d | 12 December 2024 8:00 AM | 2024-12-18 17:00 | 1 | Renderer | 80 | 77 | 28 | 95 | 22
356 | 1.2.2.2.3.9 | Lift Shaft | 22 | 28 November 2024 8:00 AM | 23 December 2024 5:00 PM |  |  | 28 November 2024 8:00 AM | 2024-12-25 17:00 | 2 | Plasterboarder | 71 | 76 | 18 | 87 | 33
357 | 1.2.2.2.3.9.1 | FRP Lift Over-run | 10 | 28 November 2024 8:00 AM | 9 December 2024 5:00 PM | 354 | 358 | 28 November 2024 8:00 AM | 2024-12-11 17:00 | 2 | Plumber | 40 | 87 | 34 | 41 | 50
358 | 1.2.2.2.3.9.2 | Strip Lift Shaft Formwork | 4 | 10 December 2024 8:00 AM | 13 December 2024 5:00 PM | 357 | 359 | 10 December 2024 8:00 AM | 2024-12-13 17:00 | 0 | Project Manager | 47 | 64 | 22 | 33 | 50
359 | 1.2.2.2.3.9.3 | Lift Shaft Make Good and Removal of Scaffold | 8 | 14 December 2024 8:00 AM | 23 December 2024 5:00 PM | 358 | 3453,360 | 14 December 2024 8:00 AM | 2024-12-26 17:00 | 3 | Head Contractor | 45 | 79 | 31 | 19 | 15
360 | 1.2.2.2.3.10 | Building C Structure Complete | 0 | 23 December 2024 5:00 PM | 23 December 2024 5:00 PM | 354,359 | 8,7 | 23 December 2024 5:00 PM | 2024-12-25 17:00 | 2 | Excavation | 35 | 42 | 15 | 38 | 18
361 | 1.2.2.2.4 | Building D | 76 | 26 September 2024 8:00 AM | 3 January 2025 5:00 PM |  | 397 | 26 September 2024 8:00 AM | 2025-01-04 17:00 | 1 | Landscaper | 47 | 21 | 24 | 58 | 35
362 | 1.2.2.2.4.1 | Lvl 2 - FRP - Suspended Slab | 19 | 26 September 2024 8:00 AM | 19 October 2024 5:00 PM |  |  | 26 September 2024 8:00 AM | 2024-10-19 17:00 | 0 | Joiner | 72 | 75 | 22 | 86 | 50
363 | 1.2.2.2.4.1.1 | Scaffold Stair Removal/Adjustment | 1 | 26 September 2024 8:00 AM | 26 September 2024 5:00 PM | 364SS |  | 26 September 2024 8:00 AM | 2024-09-30 17:00 | 4 | Tiler | 0 | 57 | 12 | 77 | 24
364 | 1.2.2.2.4.1.2 | Setout and Install Lift/Stair Formwork | 1 | 26 September 2024 8:00 AM | 27 September 2024 8:00 AM | 365SF | 363SS | 26 September 2024 8:00 AM | 2024-09-27 08:00 | 0 | Fire | 73 | 28 | 15 | 96 | 13
365 | 1.2.2.2.4.1.3 | Formworker setout, drop material and 80% Deck | 6 | 27 September 2024 8:00 AM | 3 October 2024 5:00 PM | 311FS+10d | 366FS-1d,367,364SF | 27 September 2024 8:00 AM | 2024-10-03 17:00 | 0 | Cleaner | 9 | 68 | 23 | 31 | 35
366 | 1.2.2.2.4.1.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 3 October 2024 8:00 AM | 10 October 2024 5:00 PM | 365FS-1d | 368,369 | 3 October 2024 8:00 AM | 2024-10-11 17:00 | 1 | Joiner | 41 | 54 | 19 | 41 | 54
367 | 1.2.2.2.4.1.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 4 October 2024 8:00 AM | 9 October 2024 5:00 PM | 365 |  | 4 October 2024 8:00 AM | 2024-10-09 17:00 | 0 | Head Contractor | 63 | 59 | 15 | 80 | 12
368 | 1.2.2.2.4.1.6 | Services | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | 11 October 2024 8:00 AM | 2024-10-14 17:00 | 0 | Line Market | 82 | 49 | 32 | 36 | 58
369 | 1.2.2.2.4.1.7 | Post Tension | 3 | 11 October 2024 8:00 AM | 14 October 2024 5:00 PM | 366 | 370FS-1d | 11 October 2024 8:00 AM | 2024-10-15 17:00 | 1 | Admin | 83 | 49 | 26 | 41 | 31
370 | 1.2.2.2.4.1.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 14 October 2024 8:00 AM | 16 October 2024 5:00 PM | 368FS-1d,369FS-1d | 371 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Formworker | 88 | 82 | 14 | 37 | 43
371 | 1.2.2.2.4.1.9 | Formworker setdowns and edge boards | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 370 | 372 | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Site Manager | 4 | 83 | 26 | 63 | 13
372 | 1.2.2.2.4.1.10 | Pour | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 371 | 375 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Post Tension | 41 | 88 | 25 | 45 | 5
373 | 1.2.2.2.4.2 | Strip Formwork - Lvl 2 | 5 | 21 November 2024 8:00 AM | 26 November 2024 5:00 PM | 384FS+8d | 485,506 | 21 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Tiler | 36 | 100 | 17 | 91 | 44
374 | 1.2.2.2.4.3 | Lvl 3 - FRP - Suspended Slab | 19 | 21 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-11 17:00 | 0 | Timber Floorer | 71 | 38 | 15 | 46 | 60
375 | 1.2.2.2.4.3.1 | Scaffold Stair Removal/Adjustment | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 372 | 376SS | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Foreman | 29 | 88 | 14 | 31 | 6
376 | 1.2.2.2.4.3.2 | Setout and Install Lift/Stair Formwork | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 375SS | 377 | 21 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Project Manager | 89 | 22 | 14 | 84 | 29
377 | 1.2.2.2.4.3.3 | Formworker setout, drop material and 80% Deck | 6 | 22 October 2024 8:00 AM | 28 October 2024 5:00 PM | 376 | 378FS-1d,379 | 22 October 2024 8:00 AM | 2024-11-02 17:00 | 5 | Fire | 92 | 18 | 29 | 29 | 52
378 | 1.2.2.2.4.3.4 | Steel Fixer - Bottom Steel, ramps, prefab Columns, Stair and Wall | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 377FS-1d | 380,381 | 28 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Contract Administrator | 0 | 24 | 35 | 11 | 26
379 | 1.2.2.2.4.3.5 | Steel Fixer - Drop Prefabricated Columns | 3 | 29 October 2024 8:00 AM | 31 October 2024 5:00 PM | 377 |  | 29 October 2024 8:00 AM | 2024-11-04 17:00 | 4 | Formworker | 16 | 54 | 33 | 68 | 59
380 | 1.2.2.2.4.3.6 | Services | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | 2 November 2024 8:00 AM | 2024-11-06 17:00 | 1 | Project Manager | 99 | 25 | 32 | 83 | 57
381 | 1.2.2.2.4.3.7 | Post Tension | 3 | 2 November 2024 8:00 AM | 5 November 2024 5:00 PM | 378 | 382FS-1d | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Development Manager | 48 | 13 | 10 | 64 | 18
382 | 1.2.2.2.4.3.8 | Steel Fixer - Top Steel, setdowns and starter bars | 3 | 5 November 2024 8:00 AM | 7 November 2024 5:00 PM | 380FS-1d,381FS-1d | 383 | 5 November 2024 8:00 AM | 2024-11-09 17:00 | 2 | Electrician | 35 | 20 | 28 | 19 | 23
383 | 1.2.2.2.4.3.9 | Formworker setdowns and edge boards | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 382 | 384 | 8 November 2024 8:00 AM | 2024-11-11 17:00 | 2 | Electrician | 71 | 63 | 25 | 29 | 19
384 | 1.2.2.2.4.3.10 | Pour | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 383 | 385FS+12d,373FS+8d,387 | 11 November 2024 8:00 AM | 2024-11-13 17:00 | 2 | Contract Administrator | 14 | 62 | 22 | 84 | 16
385 | 1.2.2.2.4.4 | Strip Formwork - Lvl 3 | 5 | 26 November 2024 8:00 AM | 30 November 2024 5:00 PM | 384FS+12d | 511 | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Plasterboarder | 63 | 62 | 21 | 100 | 9
386 | 1.2.2.2.4.5 | L4 Strucutral Steel Roof | 38 | 12 November 2024 8:00 AM | 3 January 2025 5:00 PM |  |  | 12 November 2024 8:00 AM | 2025-01-04 17:00 | 1 | Electrician | 19 | 77 | 15 | 39 | 7
387 | 1.2.2.2.4.5.1 | Scaffold Perimeter Protection | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 384 | 388SS | 12 November 2024 8:00 AM | 2024-11-12 17:00 | 0 | Window | 51 | 52 | 23 | 73 | 38
388 | 1.2.2.2.4.5.2 | Setout | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 387SS | 389 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Metal Work | 11 | 48 | 13 | 47 | 47
389 | 1.2.2.2.4.5.3 | Formworker setout, drop material and 80% Walls | 5 | 14 November 2024 8:00 AM | 19 November 2024 5:00 PM | 388 | 390FS-1d | 14 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Line Market | 70 | 21 | 16 | 11 | 22
390 | 1.2.2.2.4.5.4 | Steel Fixer - Walls | 3 | 19 November 2024 8:00 AM | 21 November 2024 5:00 PM | 389FS-1d | 391 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Cleaner | 38 | 63 | 13 | 28 | 24
391 | 1.2.2.2.4.5.5 | Services | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 390 | 392 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Floor Sealer | 88 | 18 | 16 | 48 | 13
392 | 1.2.2.2.4.5.6 | Pour | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 391 | 393 | 25 November 2024 8:00 AM | 2024-11-27 17:00 | 2 | Renderer | 14 | 13 | 14 | 42 | 34
393 | 1.2.2.2.4.5.7 | Strip Formwork | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 392 | 394 | 26 November 2024 8:00 AM | 2024-12-01 17:00 | 4 | Carpenter | 69 | 17 | 22 | 28 | 56
394 | 1.2.2.2.4.5.8 | Structural Steel Setout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 393 | 395 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 1 | Timber Floorer | 37 | 19 | 10 | 30 | 43
395 | 1.2.2.2.4.5.9 | Install Structural Steel | 8 | 29 November 2024 8:00 AM | 7 December 2024 5:00 PM | 394 | 396 | 29 November 2024 8:00 AM | 2024-12-09 17:00 | 2 | Subcontractor | 71 | 57 | 15 | 78 | 52
396 | 1.2.2.2.4.5.10 | Install Metal Deck Roofing | 15 | 9 December 2024 8:00 AM | 3 January 2025 5:00 PM | 395 | 516,8 | 9 December 2024 8:00 AM | 2025-01-04 17:00 | 1 | Joiner | 74 | 13 | 15 | 19 | 29
397 | 1.2.2.3 | Structural Works Complete | 0 | 3 January 2025 5:00 PM | 3 January 2025 5:00 PM | 120,307,361,91,138,229 |  | 3 January 2025 5:00 PM | 2025-01-07 17:00 | 4 | Subcontractor | 36 | 80 | 10 | 40 | 9
398 | 1.2.3 | FAÇADE WORKS | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | 13 July 2024 8:00 AM | 2025-03-23 17:00 | 1 | Landscaper | 54 | 91 | 30 | 47 | 7
399 | 1.2.3.1 | Building A | 206 | 13 July 2024 8:00 AM | 22 March 2025 5:00 PM |  |  | 13 July 2024 8:00 AM | 2025-03-22 17:00 | 0 | Contract Administrator | 26 | 79 | 31 | 16 | 54
400 | 1.2.3.1.1 | Lvl 1 | 44 | 13 July 2024 8:00 AM | 2 September 2024 5:00 PM |  |  | 13 July 2024 8:00 AM | 2024-09-02 17:00 | 0 | Joiner | 93 | 76 | 30 | 37 | 33
401 | 1.2.3.1.1.1 | Survey & Setout | 1 | 13 July 2024 8:00 AM | 13 July 2024 5:00 PM | 116FS+5d | 402 | 13 July 2024 8:00 AM | 2024-07-15 17:00 | 2 | Surveyor | 74 | 27 | 20 | 0 | 53
402 | 1.2.3.1.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 15 July 2024 8:00 AM | 19 July 2024 5:00 PM | 401 | 403 | 15 July 2024 8:00 AM | 2024-07-21 17:00 | 2 | Concretor | 49 | 69 | 29 | 46 | 39
403 | 1.2.3.1.1.3 | Façade & External Walls | 20 | 20 July 2024 8:00 AM | 12 August 2024 5:00 PM | 402 | 404 | 20 July 2024 8:00 AM | 2024-08-12 17:00 | 0 | Cleaner | 73 | 33 | 10 | 87 | 8
404 | 1.2.3.1.1.4 | Windows Install | 18 | 13 August 2024 8:00 AM | 2 September 2024 5:00 PM | 403 | 405,411 | 13 August 2024 8:00 AM | 2024-09-04 17:00 | 2 | Subcontractor | 17 | 96 | 15 | 65 | 15
405 | 1.2.3.1.1.5 | Level 1 Weathertight | 0 | 2 September 2024 5:00 PM | 2 September 2024 5:00 PM | 404 | 558 | 2 September 2024 5:00 PM | 2024-09-04 17:00 | 2 | Electrician | 47 | 91 | 19 | 14 | 34
406 | 1.2.3.1.2 | Lvl 2 | 83 | 17 August 2024 8:00 AM | 23 November 2024 5:00 PM |  |  | 17 August 2024 8:00 AM | 2024-11-24 17:00 | 1 | Concretor | 48 | 23 | 10 | 64 | 51
407 | 1.2.3.1.2.1 | Survey & Setout | 1 | 17 August 2024 8:00 AM | 17 August 2024 5:00 PM | 149FS+5d | 408 | 17 August 2024 8:00 AM | 2024-08-18 17:00 | 1 | Concretor | 96 | 57 | 15 | 97 | 38
408 | 1.2.3.1.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 19 August 2024 8:00 AM | 23 August 2024 5:00 PM | 407 | 577 | 19 August 2024 8:00 AM | 2024-08-23 17:00 | 0 | Reinforcement Fixer | 68 | 67 | 16 | 10 | 3
409 | 1.2.3.1.2.3 | Façade & External Walls | 22 | 9 October 2024 8:00 AM | 2 November 2024 5:00 PM | 150FS-10d | 410 | 9 October 2024 8:00 AM | 2024-11-05 17:00 | 3 | Metal Work | 73 | 98 | 22 | 20 | 50
410 | 1.2.3.1.2.4 | Windows Install | 18 | 4 November 2024 8:00 AM | 23 November 2024 5:00 PM | 409 | 411 | 4 November 2024 8:00 AM | 2024-11-26 17:00 | 3 | Painter | 36 | 77 | 31 | 94 | 37
411 | 1.2.3.1.2.5 | Level 2 Weathertight | 0 | 23 November 2024 5:00 PM | 23 November 2024 5:00 PM | 404,410 | 585 | 23 November 2024 5:00 PM | 2024-11-24 17:00 | 1 | Electrician | 77 | 96 | 27 | 20 | 55
412 | 1.2.3.1.3 | Lvl 3 | 40 | 13 November 2024 8:00 AM | 7 January 2025 5:00 PM |  |  | 13 November 2024 8:00 AM | 2025-01-10 17:00 | 3 | Metal Work | 6 | 59 | 24 | 27 | 46
413 | 1.2.3.1.3.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 174FS+5d | 414FS-1d | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Renderer | 88 | 12 | 10 | 90 | 39
414 | 1.2.3.1.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 413FS-1d |  | 30 November 2024 8:00 AM | 2024-12-09 17:00 | 5 | Tiler | 49 | 91 | 14 | 53 | 19
415 | 1.2.3.1.3.3 | Façade & External Walls | 22 | 13 November 2024 8:00 AM | 7 December 2024 5:00 PM | 174FS-10d | 416 | 13 November 2024 8:00 AM | 2024-12-07 17:00 | 0 | Stone Mason | 21 | 37 | 18 | 39 | 29
416 | 1.2.3.1.3.4 | Windows Install | 18 | 9 December 2024 8:00 AM | 7 January 2025 5:00 PM | 415 | 610FS-6d,417 | 9 December 2024 8:00 AM | 2025-01-07 17:00 | 0 | Excavation | 81 | 34 | 14 | 73 | 27
417 | 1.2.3.1.3.5 | Level 3 Weathertight | 0 | 7 January 2025 5:00 PM | 7 January 2025 5:00 PM | 416 | 612,444 | 7 January 2025 5:00 PM | 2025-01-07 17:00 | 0 | Waterproofer | 88 | 96 | 19 | 62 | 46
418 | 1.2.3.1.4 | Lvl 4 | 44 | 17 December 2024 8:00 AM | 15 February 2025 5:00 PM |  |  | 17 December 2024 8:00 AM | 2025-02-15 17:00 | 0 | Site Manager | 10 | 74 | 12 | 20 | 55
419 | 1.2.3.1.4.1 | Survey & Setout | 1 | 17 December 2024 8:00 AM | 17 December 2024 5:00 PM | 186FS+5d | 420FS-1d | 17 December 2024 8:00 AM | 2024-12-19 17:00 | 2 | Waterproofer | 33 | 67 | 22 | 67 | 7
420 | 1.2.3.1.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 17 December 2024 8:00 AM | 20 December 2024 5:00 PM | 419FS-1d | 421 | 17 December 2024 8:00 AM | 2024-12-25 17:00 | 5 | Project Manager | 62 | 29 | 14 | 43 | 31
421 | 1.2.3.1.4.3 | Façade & External Walls | 22 | 21 December 2024 8:00 AM | 24 January 2025 5:00 PM | 186FS-10d,420 | 422 | 21 December 2024 8:00 AM | 2025-01-26 17:00 | 2 | Mechanical | 68 | 14 | 33 | 78 | 2
422 | 1.2.3.1.4.4 | Windows Install | 18 | 27 January 2025 8:00 AM | 15 February 2025 5:00 PM | 421 | 637FS-6d,423 | 27 January 2025 8:00 AM | 2025-02-15 17:00 | 0 | Plasterboarder | 87 | 66 | 11 | 41 | 13
423 | 1.2.3.1.4.5 | Level 4 Weathertight | 0 | 15 February 2025 5:00 PM | 15 February 2025 5:00 PM | 422 | 639,444 | 15 February 2025 5:00 PM | 2025-02-18 17:00 | 3 | Landscaper | 49 | 83 | 33 | 19 | 8
424 | 1.2.3.1.5 | Lvl 5 | 40 | 30 November 2024 8:00 AM | 24 January 2025 5:00 PM |  |  | 30 November 2024 8:00 AM | 2025-01-24 17:00 | 0 | Electrician | 96 | 98 | 28 | 100 | 16
425 | 1.2.3.1.5.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 198FS+5d | 426FS-1d | 18 December 2024 8:00 AM | 2024-12-19 17:00 | 1 | Contract Administrator | 58 | 40 | 14 | 30 | 12
426 | 1.2.3.1.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 425FS-1d | 663 | 18 December 2024 8:00 AM | 2024-12-23 17:00 | 2 | Stone Mason | 60 | 19 | 21 | 28 | 56
427 | 1.2.3.1.5.3 | Façade & External Walls | 22 | 30 November 2024 8:00 AM | 3 January 2025 5:00 PM | 198FS-10d | 428 | 30 November 2024 8:00 AM | 2025-01-03 17:00 | 0 | Site Manager | 69 | 67 | 31 | 12 | 56
428 | 1.2.3.1.5.4 | Windows Install | 18 | 4 January 2025 8:00 AM | 24 January 2025 5:00 PM | 427 | 669FS-6d,429,444 | 4 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Surveyor | 75 | 61 | 19 | 96 | 54
429 | 1.2.3.1.5.5 | Level 5 Weathertight | 0 | 24 January 2025 5:00 PM | 24 January 2025 5:00 PM | 428 | 671 | 24 January 2025 5:00 PM | 2025-01-27 17:00 | 3 | Timber Floorer | 73 | 21 | 14 | 65 | 18
430 | 1.2.3.1.6 | Lvl 6 | 59 | 19 November 2024 8:00 AM | 5 February 2025 5:00 PM |  |  | 19 November 2024 8:00 AM | 2025-02-05 17:00 | 0 | Timber Floorer | 70 | 75 | 31 | 91 | 33
431 | 1.2.3.1.6.1 | Survey & Setout | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 209FS+5d | 432 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Admin | 76 | 80 | 18 | 56 | 36
432 | 1.2.3.1.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 6 December 2024 8:00 AM | 10 December 2024 5:00 PM | 210FS-10d,431 | 433,690 | 6 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Tiler | 93 | 17 | 15 | 95 | 46
433 | 1.2.3.1.6.3 | Façade & External Walls | 22 | 11 December 2024 8:00 AM | 14 January 2025 5:00 PM | 432 | 434 | 11 December 2024 8:00 AM | 2025-01-15 17:00 | 1 | Scaffolder | 35 | 96 | 35 | 91 | 32
434 | 1.2.3.1.6.4 | Windows Install | 18 | 15 January 2025 8:00 AM | 5 February 2025 5:00 PM | 433 | 696FS-6d,435 | 15 January 2025 8:00 AM | 2025-02-08 17:00 | 3 | Contract Administrator | 8 | 87 | 15 | 50 | 22
435 | 1.2.3.1.6.5 | Level 6 Weathertight | 0 | 5 February 2025 5:00 PM | 5 February 2025 5:00 PM | 434 | 698,444 | 5 February 2025 5:00 PM | 2025-02-06 17:00 | 1 | Floor Sealer | 97 | 79 | 32 | 11 | 36
436 | 1.2.3.1.7 | Lvl 7 | 59 | 5 December 2024 8:00 AM | 21 February 2025 5:00 PM |  |  | 5 December 2024 8:00 AM | 2025-02-21 17:00 | 0 | Post Tension | 6 | 27 | 26 | 42 | 43
437 | 1.2.3.1.7.1 | Survey & Setout | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 221FS+5d | 438FS-1d | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Metal Work | 92 | 26 | 27 | 61 | 28
438 | 1.2.3.1.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 5 December 2024 8:00 AM | 9 December 2024 5:00 PM | 437FS-1d | 722 | 5 December 2024 8:00 AM | 2024-12-09 17:00 | 0 | Metal Work | 83 | 94 | 31 | 77 | 46
439 | 1.2.3.1.7.3 | Façade & External Walls | 22 | 8 January 2025 8:00 AM | 3 February 2025 5:00 PM | 223FS+10d | 440 | 8 January 2025 8:00 AM | 2025-02-04 17:00 | 1 | Plasterboarder | 65 | 74 | 29 | 65 | 40
440 | 1.2.3.1.7.4 | Windows Install | 16 | 4 February 2025 8:00 AM | 21 February 2025 5:00 PM | 439 | 728FS-6d,441,3446FS-5d | 4 February 2025 8:00 AM | 2025-02-21 17:00 | 0 | Tiler | 27 | 51 | 20 | 13 | 53
441 | 1.2.3.1.7.5 | Level 7 Weathertight | 0 | 21 February 2025 5:00 PM | 21 February 2025 5:00 PM | 440 | 730,442 | 21 February 2025 5:00 PM | 2025-02-21 17:00 | 0 | Floor Sealer | 71 | 82 | 28 | 52 | 10
442 | 1.2.3.1.8 | Defect Rectification | 15 | 22 February 2025 8:00 AM | 11 March 2025 5:00 PM | 441 | 443 | 22 February 2025 8:00 AM | 2025-03-11 17:00 | 0 | Subcontractor | 3 | 53 | 17 | 30 | 56
443 | 1.2.3.1.9 | Strip Scaffold | 10 | 12 March 2025 8:00 AM | 22 March 2025 5:00 PM | 442 | 444,3456 | 12 March 2025 8:00 AM | 2025-03-23 17:00 | 1 | Reinforcement Fixer | 65 | 74 | 19 | 1 | 11
444 | 1.2.3.1.10 | Building A Façade Complete | 0 | 22 March 2025 5:00 PM | 22 March 2025 5:00 PM | 443,435,428,423,417 | 5 | 22 March 2025 5:00 PM | 2025-03-22 17:00 | 0 | Electrician | 39 | 38 | 11 | 61 | 40
445 | 1.2.3.2 | Building B | 89 | 4 October 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | 4 October 2024 8:00 AM | 2025-01-28 17:00 | 0 | Admin | 60 | 45 | 27 | 52 | 17
446 | 1.2.3.2.1 | Lvl 1 | 44 | 4 October 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 4 October 2024 8:00 AM | 2024-11-26 17:00 | 0 | Window | 89 | 62 | 25 | 58 | 11
447 | 1.2.3.2.1.1 | Survey & Setout | 1 | 4 October 2024 8:00 AM | 4 October 2024 5:00 PM | 241 | 448 | 4 October 2024 8:00 AM | 2024-10-05 17:00 | 1 | Window | 12 | 48 | 20 | 10 | 2
448 | 1.2.3.2.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 8 October 2024 8:00 AM | 12 October 2024 5:00 PM | 447 | 449,758,852,1322FS+6d,1510FS+6d,1416FS+6d,946FS+2d,1040FS+2d,1134FS+4d,1228FS+4d | 8 October 2024 8:00 AM | 2024-10-17 17:00 | 5 | Reinforcement Fixer | 16 | 39 | 11 | 83 | 58
449 | 1.2.3.2.1.3 | Façade & External Walls | 20 | 14 October 2024 8:00 AM | 5 November 2024 5:00 PM | 448 | 450 | 14 October 2024 8:00 AM | 2024-11-06 17:00 | 1 | Project Manager | 86 | 87 | 23 | 59 | 30
450 | 1.2.3.2.1.4 | Windows Install | 18 | 6 November 2024 8:00 AM | 26 November 2024 5:00 PM | 449 | 451 | 6 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Plumber | 73 | 89 | 22 | 82 | 38
451 | 1.2.3.2.1.5 | Level 1 Weathertight | 0 | 26 November 2024 5:00 PM | 26 November 2024 5:00 PM | 450 | 1640 | 26 November 2024 5:00 PM | 2024-11-26 17:00 | 0 | Electrician | 80 | 75 | 13 | 15 | 59
452 | 1.2.3.2.2 | Lvl 2 | 42 | 26 October 2024 8:00 AM | 13 December 2024 5:00 PM |  |  | 26 October 2024 8:00 AM | 2024-12-17 17:00 | 4 | Concretor | 15 | 31 | 28 | 24 | 10
453 | 1.2.3.2.2.1 | Survey & Setout | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 253 | 454 | 26 October 2024 8:00 AM | 2024-10-27 17:00 | 1 | Window | 79 | 33 | 31 | 79 | 40
454 | 1.2.3.2.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 October 2024 8:00 AM | 1 November 2024 5:00 PM | 453 | 455 | 28 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Head Contractor | 43 | 16 | 10 | 12 | 59
455 | 1.2.3.2.2.3 | Façade & External Walls | 20 | 2 November 2024 8:00 AM | 25 November 2024 5:00 PM | 454 | 456 | 2 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Painter | 71 | 10 | 29 | 31 | 8
456 | 1.2.3.2.2.4 | Windows Install | 16 | 26 November 2024 8:00 AM | 13 December 2024 5:00 PM | 455 | 457 | 26 November 2024 8:00 AM | 2024-12-15 17:00 | 2 | Mechanical | 94 | 98 | 30 | 18 | 36
457 | 1.2.3.2.2.5 | Level 2 Weathertight | 0 | 13 December 2024 5:00 PM | 13 December 2024 5:00 PM | 456 |  | 13 December 2024 5:00 PM | 2024-12-15 17:00 | 2 | Excavation | 86 | 64 | 29 | 0 | 22
458 | 1.2.3.2.3 | Lvl 3 | 43 | 16 November 2024 8:00 AM | 14 January 2025 5:00 PM |  |  | 16 November 2024 8:00 AM | 2025-01-15 17:00 | 1 | Renderer | 41 | 61 | 35 | 2 | 14
459 | 1.2.3.2.3.1 | Survey & Setout | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 265 | 460 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 2 | Joiner | 75 | 82 | 35 | 42 | 13
460 | 1.2.3.2.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 November 2024 8:00 AM | 21 November 2024 5:00 PM | 459 | 461 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 58 | 73 | 11 | 23 | 51
461 | 1.2.3.2.3.3 | Façade & External Walls | 20 | 22 November 2024 8:00 AM | 14 December 2024 5:00 PM | 460 | 462 | 22 November 2024 8:00 AM | 2024-12-16 17:00 | 2 | Contract Administrator | 54 | 10 | 27 | 47 | 3
462 | 1.2.3.2.3.4 | Windows Install | 18 | 16 December 2024 8:00 AM | 14 January 2025 5:00 PM | 461 | 1638FS-6d,463 | 16 December 2024 8:00 AM | 2025-01-14 17:00 | 0 | Reinforcement Fixer | 18 | 56 | 20 | 94 | 39
463 | 1.2.3.2.3.5 | Level 3 Weathertight | 0 | 14 January 2025 5:00 PM | 14 January 2025 5:00 PM | 462 | 1640 | 14 January 2025 5:00 PM | 2025-01-15 17:00 | 1 | Admin | 52 | 88 | 34 | 32 | 37
464 | 1.2.3.2.4 | Lvl 4 | 42 | 23 November 2024 8:00 AM | 20 January 2025 5:00 PM |  |  | 23 November 2024 8:00 AM | 2025-01-21 17:00 | 1 | Formworker | 17 | 10 | 28 | 85 | 56
465 | 1.2.3.2.4.1 | Survey & Setout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 277 | 466FS-1d | 23 November 2024 8:00 AM | 2024-11-27 17:00 | 4 | Metal Work | 70 | 67 | 10 | 83 | 24
466 | 1.2.3.2.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 23 November 2024 8:00 AM | 27 November 2024 5:00 PM | 465FS-1d | 467 | 23 November 2024 8:00 AM | 2024-12-01 17:00 | 4 | Landscaper | 16 | 16 | 28 | 32 | 10
467 | 1.2.3.2.4.3 | Façade & External Walls | 20 | 28 November 2024 8:00 AM | 20 December 2024 5:00 PM | 466 | 468 | 28 November 2024 8:00 AM | 2024-12-24 17:00 | 4 | Line Market | 13 | 82 | 15 | 4 | 34
468 | 1.2.3.2.4.4 | Windows Install | 18 | 21 December 2024 8:00 AM | 20 January 2025 5:00 PM | 467 | 1665FS-6d,469 | 21 December 2024 8:00 AM | 2025-01-20 17:00 | 0 | Landscaper | 83 | 84 | 31 | 84 | 37
469 | 1.2.3.2.4.5 | Level 4 Weathertight | 0 | 20 January 2025 5:00 PM | 20 January 2025 5:00 PM | 468 | 1665FS-6d | 20 January 2025 5:00 PM | 2025-01-21 17:00 | 1 | Carpet | 1 | 64 | 17 | 59 | 54
470 | 1.2.3.2.5 | Lvl 5 | 42 | 26 November 2024 8:00 AM | 22 January 2025 5:00 PM |  |  | 26 November 2024 8:00 AM | 2025-01-22 17:00 | 0 | Head Contractor | 4 | 18 | 13 | 15 | 57
471 | 1.2.3.2.5.1 | Survey & Setout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 289 | 472FS-1d | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Subcontractor | 45 | 73 | 18 | 44 | 21
472 | 1.2.3.2.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 26 November 2024 8:00 AM | 29 November 2024 5:00 PM | 471FS-1d | 473 | 26 November 2024 8:00 AM | 2024-12-03 17:00 | 4 | Window | 96 | 33 | 16 | 0 | 18
473 | 1.2.3.2.5.3 | Façade & External Walls | 20 | 30 November 2024 8:00 AM | 23 December 2024 5:00 PM | 472 | 474 | 30 November 2024 8:00 AM | 2024-12-23 17:00 | 0 | Timber Floorer | 30 | 100 | 35 | 16 | 11
474 | 1.2.3.2.5.4 | Windows Install | 18 | 24 December 2024 8:00 AM | 22 January 2025 5:00 PM | 473 | 475 | 24 December 2024 8:00 AM | 2025-01-22 17:00 | 0 | Surveyor | 91 | 94 | 16 | 53 | 13
475 | 1.2.3.2.5.5 | Level 5 Weathertight | 0 | 22 January 2025 5:00 PM | 22 January 2025 5:00 PM | 474 | 1692FS-4d | 22 January 2025 5:00 PM | 2025-01-22 17:00 | 0 | Foreman | 41 | 67 | 33 | 38 | 8
476 | 1.2.3.2.6 | Lvl 6 | 42 | 30 November 2024 8:00 AM | 28 January 2025 5:00 PM |  |  | 30 November 2024 8:00 AM | 2025-01-28 17:00 | 0 | Renderer | 41 | 37 | 25 | 13 | 3
477 | 1.2.3.2.6.1 | Survey & Setout | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 301 | 478FS-1d | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Concretor | 96 | 77 | 27 | 46 | 8
478 | 1.2.3.2.6.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 30 November 2024 8:00 AM | 4 December 2024 5:00 PM | 477FS-1d | 479 | 30 November 2024 8:00 AM | 2024-12-05 17:00 | 1 | Fire | 100 | 57 | 14 | 10 | 17
479 | 1.2.3.2.6.3 | Façade & External Walls | 20 | 5 December 2024 8:00 AM | 6 January 2025 5:00 PM | 478 | 480 | 5 December 2024 8:00 AM | 2025-01-06 17:00 | 0 | Window | 55 | 26 | 30 | 99 | 52
480 | 1.2.3.2.6.4 | Windows Install | 18 | 7 January 2025 8:00 AM | 28 January 2025 5:00 PM | 479 | 481 | 7 January 2025 8:00 AM | 2025-02-01 17:00 | 4 | Painter | 20 | 46 | 22 | 90 | 44
481 | 1.2.3.2.6.5 | Level 6 Weathertight | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 480 | 1719FS-6d,482 | 28 January 2025 5:00 PM | 2025-01-30 17:00 | 2 | Excavation | 50 | 63 | 14 | 80 | 9
482 | 1.2.3.2.6.6 | Building B Façade Complete | 0 | 28 January 2025 5:00 PM | 28 January 2025 5:00 PM | 481 | 6 | 28 January 2025 5:00 PM | 2025-01-29 17:00 | 1 | Landscaper | 81 | 59 | 23 | 12 | 56
483 | 1.2.3.3 | Building C | 63 | 27 November 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-02-18 17:00 | 0 | Formworker | 34 | 52 | 24 | 76 | 2
484 | 1.2.3.3.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-01-27 17:00 | 0 | Site Manager | 66 | 51 | 22 | 13 | 7
485 | 1.2.3.3.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 486 | 27 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Timber Floorer | 31 | 30 | 24 | 84 | 51
486 | 1.2.3.3.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 485 | 487 | 28 November 2024 8:00 AM | 2024-12-04 17:00 | 1 | Timber Floorer | 3 | 68 | 32 | 57 | 34
487 | 1.2.3.3.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 486 | 488 | 4 December 2024 8:00 AM | 2025-01-04 17:00 | 0 | Joiner | 63 | 75 | 21 | 52 | 7
488 | 1.2.3.3.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 487 |  | 6 January 2025 8:00 AM | 2025-01-29 17:00 | 2 | Floor Sealer | 11 | 27 | 21 | 33 | 29
489 | 1.2.3.3.2 | Lvl 2 | 44 | 16 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | 16 December 2024 8:00 AM | 2025-02-17 17:00 | 3 | Project Manager | 60 | 40 | 22 | 72 | 57
490 | 1.2.3.3.2.1 | Survey & Setout | 1 | 16 December 2024 8:00 AM | 16 December 2024 5:00 PM | 331 | 491 | 16 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Hoarding | 17 | 46 | 20 | 49 | 11
491 | 1.2.3.3.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 17 December 2024 8:00 AM | 21 December 2024 5:00 PM | 490 | 492 | 17 December 2024 8:00 AM | 2024-12-23 17:00 | 2 | Electrician | 68 | 55 | 31 | 23 | 14
492 | 1.2.3.3.2.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 491 | 493 | 23 December 2024 8:00 AM | 2025-01-24 17:00 | 1 | Tiler | 60 | 49 | 27 | 33 | 47
493 | 1.2.3.3.2.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 492 |  | 24 January 2025 8:00 AM | 2025-02-14 17:00 | 0 | Window | 54 | 35 | 35 | 100 | 52
494 | 1.2.3.3.3 | Lvl 3 | 42 | 21 December 2024 8:00 AM | 18 February 2025 5:00 PM |  |  | 21 December 2024 8:00 AM | 2025-02-18 17:00 | 0 | Waterproofer | 48 | 66 | 14 | 80 | 32
495 | 1.2.3.3.3.1 | Survey & Setout | 1 | 21 December 2024 8:00 AM | 21 December 2024 5:00 PM | 343 | 496FS-1d | 21 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Excavation | 10 | 50 | 14 | 72 | 14
496 | 1.2.3.3.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 21 December 2024 8:00 AM | 3 January 2025 5:00 PM | 495FS-1d | 497 | 21 December 2024 8:00 AM | 2025-01-03 17:00 | 0 | Stone Mason | 88 | 90 | 22 | 53 | 3
497 | 1.2.3.3.3.3 | Façade & External Walls | 20 | 4 January 2025 8:00 AM | 28 January 2025 5:00 PM | 496 | 498 | 4 January 2025 8:00 AM | 2025-01-29 17:00 | 1 | Waterproofer | 56 | 12 | 29 | 40 | 4
498 | 1.2.3.3.3.4 | Windows Install | 18 | 29 January 2025 8:00 AM | 18 February 2025 5:00 PM | 497 | 2654FS-6d | 29 January 2025 8:00 AM | 2025-02-18 17:00 | 0 | Tiler | 94 | 82 | 24 | 98 | 38
499 | 1.2.3.3.4 | Lvl 4 | 42 | 18 December 2024 8:00 AM | 14 February 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-02-14 17:00 | 0 | Admin | 57 | 56 | 13 | 19 | 58
500 | 1.2.3.3.4.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 355 | 501FS-1d | 18 December 2024 8:00 AM | 2024-12-22 17:00 | 4 | Carpenter | 18 | 80 | 33 | 92 | 50
501 | 1.2.3.3.4.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 500FS-1d | 502 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Timber Floorer | 83 | 17 | 33 | 94 | 51
502 | 1.2.3.3.4.3 | Façade & External Walls | 20 | 23 December 2024 8:00 AM | 23 January 2025 5:00 PM | 501 | 503 | 23 December 2024 8:00 AM | 2025-01-24 17:00 | 1 | Development Manager | 41 | 56 | 35 | 78 | 59
503 | 1.2.3.3.4.4 | Windows Install | 18 | 24 January 2025 8:00 AM | 14 February 2025 5:00 PM | 502 | 3151FS-6d,7 | 24 January 2025 8:00 AM | 2025-02-17 17:00 | 3 | Cleaner | 3 | 10 | 26 | 50 | 22
504 | 1.2.3.4 | Building D | 62 | 27 November 2024 8:00 AM | 17 February 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-02-18 17:00 | 1 | Landscaper | 75 | 67 | 12 | 11 | 54
505 | 1.2.3.4.1 | Lvl 1 | 44 | 27 November 2024 8:00 AM | 27 January 2025 5:00 PM |  |  | 27 November 2024 8:00 AM | 2025-01-27 17:00 | 0 | Electrician | 64 | 74 | 21 | 86 | 30
506 | 1.2.3.4.1.1 | Survey & Setout | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 373 | 507 | 27 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Mechanical | 23 | 66 | 24 | 83 | 49
507 | 1.2.3.4.1.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 28 November 2024 8:00 AM | 3 December 2024 5:00 PM | 506 | 508,3361 | 28 November 2024 8:00 AM | 2024-12-05 17:00 | 2 | Stone Mason | 80 | 76 | 13 | 96 | 10
508 | 1.2.3.4.1.3 | Façade & External Walls | 20 | 4 December 2024 8:00 AM | 4 January 2025 5:00 PM | 507 | 509 | 4 December 2024 8:00 AM | 2025-01-04 17:00 | 0 | Electrician | 14 | 66 | 16 | 70 | 26
509 | 1.2.3.4.1.4 | Windows Install | 18 | 6 January 2025 8:00 AM | 27 January 2025 5:00 PM | 508 |  | 6 January 2025 8:00 AM | 2025-01-28 17:00 | 1 | Tiler | 30 | 14 | 19 | 78 | 58
510 | 1.2.3.4.2 | Lvl 2 | 44 | 2 December 2024 8:00 AM | 31 January 2025 5:00 PM |  |  | 2 December 2024 8:00 AM | 2025-02-02 17:00 | 2 | Admin | 46 | 20 | 30 | 80 | 28
511 | 1.2.3.4.2.1 | Survey & Setout | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 385 | 512 | 2 December 2024 8:00 AM | 2024-12-08 17:00 | 6 | Cleaner | 24 | 18 | 11 | 72 | 41
512 | 1.2.3.4.2.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 5 | 3 December 2024 8:00 AM | 7 December 2024 5:00 PM | 511 | 513,3388 | 3 December 2024 8:00 AM | 2024-12-09 17:00 | 2 | Tiler | 61 | 21 | 11 | 94 | 35
513 | 1.2.3.4.2.3 | Façade & External Walls | 20 | 9 December 2024 8:00 AM | 9 January 2025 5:00 PM | 512 | 514 | 9 December 2024 8:00 AM | 2025-01-12 17:00 | 3 | Subcontractor | 43 | 67 | 16 | 12 | 3
514 | 1.2.3.4.2.4 | Windows Install | 18 | 10 January 2025 8:00 AM | 31 January 2025 5:00 PM | 513 |  | 10 January 2025 8:00 AM | 2025-02-01 17:00 | 1 | Mechanical | 78 | 91 | 20 | 6 | 26
515 | 1.2.3.4.3 | Lvl 3 | 37 | 4 January 2025 8:00 AM | 17 February 2025 5:00 PM |  |  | 4 January 2025 8:00 AM | 2025-02-18 17:00 | 1 | Fire | 11 | 49 | 16 | 38 | 19
516 | 1.2.3.4.3.1 | Survey & Setout | 1 | 4 January 2025 8:00 AM | 4 January 2025 5:00 PM | 396 | 517FS-1d | 4 January 2025 8:00 AM | 2025-01-05 17:00 | 1 | Development Manager | 31 | 44 | 15 | 71 | 31
517 | 1.2.3.4.3.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 3 | 4 January 2025 8:00 AM | 7 January 2025 5:00 PM | 516FS-1d | 518,3415 | 4 January 2025 8:00 AM | 2025-01-08 17:00 | 1 | Hoarding | 18 | 47 | 28 | 91 | 6
518 | 1.2.3.4.3.3 | Façade & External Walls | 18 | 8 January 2025 8:00 AM | 29 January 2025 5:00 PM | 517 | 519 | 8 January 2025 8:00 AM | 2025-01-29 17:00 | 0 | Excavation | 42 | 71 | 16 | 93 | 52
519 | 1.2.3.4.3.4 | Windows Install | 16 | 30 January 2025 8:00 AM | 17 February 2025 5:00 PM | 518 | 3421FS-6d,8 | 30 January 2025 8:00 AM | 2025-02-18 17:00 | 1 | Carpenter | 44 | 85 | 28 | 29 | 43
520 | 1.2.4 | FIT-OUT WORKS | 185 | 13 September 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 13 September 2024 8:00 AM | 2025-05-07 17:00 | 2 | Hoarding | 29 | 11 | 17 | 61 | 51
521 | 1.2.4.1 | Basement 2 - Services & Fitoff | 140 | 13 September 2024 8:00 AM | 7 March 2025 5:00 PM |  |  | 13 September 2024 8:00 AM | 2025-03-10 17:00 | 3 | Landscaper | 4 | 43 | 27 | 67 | 13
522 | 1.2.4.1.1 | Services rough in | 60 | 13 September 2024 8:00 AM | 23 November 2024 5:00 PM | 107 | 523 | 13 September 2024 8:00 AM | 2024-11-24 17:00 | 1 | Plumber | 59 | 58 | 33 | 81 | 31
523 | 1.2.4.1.2 | Block walls (Metal Door Frames) | 6 | 25 November 2024 8:00 AM | 30 November 2024 5:00 PM | 522 | 524,525 | 25 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Window | 62 | 57 | 31 | 65 | 10
524 | 1.2.4.1.3 | Render works as specified | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 527 | 2 December 2024 8:00 AM | 2024-12-15 17:00 | 1 | Reinforcement Fixer | 24 | 39 | 27 | 92 | 16
525 | 1.2.4.1.4 | Carpentry fitoff | 12 | 2 December 2024 8:00 AM | 14 December 2024 5:00 PM | 523 | 526 | 2 December 2024 8:00 AM | 2024-12-14 17:00 | 0 | Painter | 31 | 79 | 13 | 2 | 50
526 | 1.2.4.1.5 | Services Plant & Equipment Install | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 525 |  | 16 December 2024 8:00 AM | 2025-01-07 17:00 | 0 | Post Tension | 31 | 54 | 24 | 59 | 3
527 | 1.2.4.1.6 | Doors & Hardware | 12 | 16 December 2024 8:00 AM | 7 January 2025 5:00 PM | 524 | 528 | 16 December 2024 8:00 AM | 2025-01-08 17:00 | 1 | Carpet | 45 | 34 | 34 | 93 | 12
528 | 1.2.4.1.7 | Services Fitoff | 12 | 8 January 2025 8:00 AM | 21 January 2025 5:00 PM | 527 | 529 | 8 January 2025 8:00 AM | 2025-01-24 17:00 | 3 | Carpet | 70 | 11 | 35 | 69 | 33
529 | 1.2.4.1.8 | Finishes & Painting | 12 | 22 January 2025 8:00 AM | 5 February 2025 5:00 PM | 528 | 530 | 22 January 2025 8:00 AM | 2025-02-05 17:00 | 0 | Carpet | 17 | 81 | 23 | 76 | 58
530 | 1.2.4.1.9 | Metalwork Items | 8 | 6 February 2025 8:00 AM | 14 February 2025 5:00 PM | 529 | 531 | 6 February 2025 8:00 AM | 2025-02-15 17:00 | 1 | Carpet | 21 | 27 | 26 | 22 | 18
531 | 1.2.4.1.10 | Builders Clean | 6 | 15 February 2025 8:00 AM | 21 February 2025 5:00 PM | 530 | 532 | 15 February 2025 8:00 AM | 2025-02-22 17:00 | 1 | Painter | 9 | 61 | 20 | 60 | 9
532 | 1.2.4.1.11 | Car Park Clean, Patch and Floor Sealer | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 531 | 533 | 22 February 2025 8:00 AM | 2025-03-03 17:00 | 0 | Waterproofer | 27 | 72 | 31 | 23 | 38
533 | 1.2.4.1.12 | Line Marking | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 532 |  | 4 March 2025 8:00 AM | 2025-03-08 17:00 | 1 | Excavation | 30 | 93 | 31 | 3 | 27
534 | 1.2.4.2 | Basement 1 - Services & Fitoff | 140 | 1 October 2024 8:00 AM | 25 March 2025 5:00 PM |  |  | 1 October 2024 8:00 AM | 2025-03-25 17:00 | 0 | Painter | 75 | 47 | 22 | 79 | 3
535 | 1.2.4.2.1 | Services rough in | 60 | 1 October 2024 8:00 AM | 11 December 2024 5:00 PM | 119 | 536 | 1 October 2024 8:00 AM | 2024-12-13 17:00 | 2 | Electrician | 24 | 89 | 18 | 24 | 34
536 | 1.2.4.2.2 | Block walls (Metal Door Frames) | 6 | 12 December 2024 8:00 AM | 18 December 2024 5:00 PM | 535 | 537,538 | 12 December 2024 8:00 AM | 2024-12-18 17:00 | 0 | Plasterboarder | 45 | 81 | 24 | 44 | 31
537 | 1.2.4.2.3 | Render works as specified | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 540 | 19 December 2024 8:00 AM | 2025-01-10 17:00 | 0 | Carpet | 72 | 40 | 20 | 22 | 15
538 | 1.2.4.2.4 | Carpentry fitoff | 12 | 19 December 2024 8:00 AM | 10 January 2025 5:00 PM | 536 | 539 | 19 December 2024 8:00 AM | 2025-01-11 17:00 | 1 | Timber Floorer | 10 | 46 | 22 | 0 | 41
539 | 1.2.4.2.5 | Services Plant & Equipment Install | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 538 |  | 11 January 2025 8:00 AM | 2025-01-24 17:00 | 0 | Subcontractor | 45 | 67 | 16 | 77 | 36
540 | 1.2.4.2.6 | Doors & Hardware | 12 | 11 January 2025 8:00 AM | 24 January 2025 5:00 PM | 537 | 541 | 11 January 2025 8:00 AM | 2025-01-30 17:00 | 6 | Joiner | 31 | 83 | 32 | 11 | 27
541 | 1.2.4.2.7 | Services Fitoff | 12 | 27 January 2025 8:00 AM | 8 February 2025 5:00 PM | 540 | 542 | 27 January 2025 8:00 AM | 2025-02-08 17:00 | 0 | Hoarding | 40 | 92 | 14 | 63 | 43
542 | 1.2.4.2.8 | Finishes & Painting | 12 | 10 February 2025 8:00 AM | 22 February 2025 5:00 PM | 541 | 543 | 10 February 2025 8:00 AM | 2025-02-22 17:00 | 0 | Head Contractor | 29 | 59 | 22 | 30 | 11
543 | 1.2.4.2.9 | Metalwork Items | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 542 | 544 | 24 February 2025 8:00 AM | 2025-03-06 17:00 | 2 | Concretor | 14 | 100 | 19 | 7 | 53
544 | 1.2.4.2.10 | Builders Clean | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 543 | 545 | 5 March 2025 8:00 AM | 2025-03-11 17:00 | 0 | Reinforcement Fixer | 19 | 99 | 33 | 94 | 29
545 | 1.2.4.2.11 | Car Park Clean, Patch and Floor Sealer | 8 | 12 March 2025 8:00 AM | 20 March 2025 5:00 PM | 544 | 546 | 12 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Concretor | 15 | 93 | 33 | 72 | 28
546 | 1.2.4.2.12 | Line Marking | 4 | 21 March 2025 8:00 AM | 25 March 2025 5:00 PM | 545 |  | 21 March 2025 8:00 AM | 2025-03-26 17:00 | 1 | Electrician | 14 | 67 | 20 | 100 | 35
547 | 1.2.4.3 | Building A | 155 | 21 October 2024 8:00 AM | 5 May 2025 5:00 PM |  | 3440 | 21 October 2024 8:00 AM | 2025-05-05 17:00 | 0 | Tiler | 57 | 83 | 19 | 61 | 32
548 | 1.2.4.3.1 | Lvl 1 - Services & Finishes | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-13 17:00 | 0 | Metal Work | 13 | 73 | 13 | 48 | 17
549 | 1.2.4.3.1.1 | Internal Works | 91 | 21 October 2024 8:00 AM | 13 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-13 17:00 | 0 | Scaffolder | 86 | 83 | 34 | 44 | 35
550 | 1.2.4.3.1.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 150 | 551FS-2d | 21 October 2024 8:00 AM | 2024-10-23 17:00 | 1 | Site Manager | 27 | 59 | 35 | 31 | 51
551 | 1.2.4.3.1.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 550FS-2d | 552 | 21 October 2024 8:00 AM | 2024-11-03 17:00 | 3 | Landscaper | 47 | 75 | 12 | 67 | 49
552 | 1.2.4.3.1.1.3 | Internal Wall Framing | 10 | 1 November 2024 8:00 AM | 12 November 2024 5:00 PM | 551 | 554,553 | 1 November 2024 8:00 AM | 2024-11-14 17:00 | 2 | Floor Sealer | 99 | 22 | 22 | 76 | 45
553 | 1.2.4.3.1.1.4 | Sheet one side of walls | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 556,555 | 13 November 2024 8:00 AM | 2024-11-22 17:00 | 1 | Excavation | 60 | 53 | 28 | 29 | 24
554 | 1.2.4.3.1.1.5 | Service Rough-In | 8 | 13 November 2024 8:00 AM | 21 November 2024 5:00 PM | 552 | 555 | 13 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Cleaner | 56 | 47 | 28 | 97 | 26
555 | 1.2.4.3.1.1.6 | ITP for services in the walls | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 553,554 | 556,562 | 22 November 2024 8:00 AM | 2024-11-25 17:00 | 2 | Reinforcement Fixer | 7 | 73 | 29 | 73 | 42
556 | 1.2.4.3.1.1.7 | Sheet other side of walls | 8 | 25 November 2024 8:00 AM | 3 December 2024 5:00 PM | 553,555 | 557 | 25 November 2024 8:00 AM | 2024-12-04 17:00 | 1 | Stone Mason | 96 | 70 | 15 | 12 | 40
557 | 1.2.4.3.1.1.8 | Frame & Sheet Ceilings | 8 | 4 December 2024 8:00 AM | 12 December 2024 5:00 PM | 556 | 558 | 4 December 2024 8:00 AM | 2024-12-14 17:00 | 2 | Excavation | 2 | 76 | 34 | 73 | 3
558 | 1.2.4.3.1.1.9 | Sheet, Set & Sand Ceilings | 8 | 13 December 2024 8:00 AM | 21 December 2024 5:00 PM | 557,405 | 559 | 13 December 2024 8:00 AM | 2024-12-22 17:00 | 1 | Formworker | 52 | 51 | 27 | 13 | 4
559 | 1.2.4.3.1.1.10 | Paint undercoat | 4 | 23 December 2024 8:00 AM | 4 January 2025 5:00 PM | 558 | 560 | 23 December 2024 8:00 AM | 2025-01-05 17:00 | 1 | Window | 57 | 84 | 27 | 82 | 10
560 | 1.2.4.3.1.1.11 | Floor Levelling and Floor Finish | 6 | 6 January 2025 8:00 AM | 11 January 2025 5:00 PM | 559 | 561 | 6 January 2025 8:00 AM | 2025-01-11 17:00 | 0 | Hoarding | 9 | 51 | 20 | 38 | 39
561 | 1.2.4.3.1.1.12 | Timber Flooring | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 560 | 567,568,563 | 13 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Line Market | 39 | 81 | 24 | 88 | 18
562 | 1.2.4.3.1.1.13 | Measure & Manufacture Joinery | 40 | 25 November 2024 8:00 AM | 18 January 2025 5:00 PM | 555 | 563 | 25 November 2024 8:00 AM | 2025-01-21 17:00 | 3 | Mechanical | 64 | 57 | 17 | 8 | 20
563 | 1.2.4.3.1.1.14 | Install Joinery | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 561,562 | 565 | 22 January 2025 8:00 AM | 2025-02-02 17:00 | 2 | Cleaner | 80 | 91 | 27 | 64 | 6
564 | 1.2.4.3.1.1.15 | Measure & Manufacture Stone Benchtops | 12 | 17 January 2025 8:00 AM | 1 February 2025 8:00 AM | 565SF |  | 17 January 2025 8:00 AM | 2025-02-02 08:00 | 1 | Project Manager | 29 | 59 | 16 | 15 | 52
565 | 1.2.4.3.1.1.16 | Install Stone Benchtops | 5 | 1 February 2025 8:00 AM | 6 February 2025 5:00 PM | 563 | 564SF,566 | 1 February 2025 8:00 AM | 2025-02-09 17:00 | 3 | Contract Administrator | 1 | 43 | 30 | 30 | 29
566 | 1.2.4.3.1.1.17 | Fixtures & Fittings Fit-off | 3 | 7 February 2025 8:00 AM | 10 February 2025 5:00 PM | 565 | 574 | 7 February 2025 8:00 AM | 2025-02-11 17:00 | 1 | Surveyor | 22 | 44 | 30 | 46 | 13
567 | 1.2.4.3.1.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 561 | 569 | 22 January 2025 8:00 AM | 2025-01-29 17:00 | 2 | Cleaner | 64 | 83 | 15 | 32 | 27
568 | 1.2.4.3.1.1.19 | Lighting Fit-off | 3 | 22 January 2025 8:00 AM | 24 January 2025 5:00 PM | 561 | 569 | 22 January 2025 8:00 AM | 2025-01-26 17:00 | 2 | Site Manager | 22 | 35 | 23 | 18 | 57
569 | 1.2.4.3.1.1.20 | Setting Defects | 4 | 28 January 2025 8:00 AM | 31 January 2025 5:00 PM | 567,568 | 570 | 28 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Landscaper | 97 | 90 | 31 | 80 | 7
570 | 1.2.4.3.1.1.21 | Paint Finish Coat | 4 | 1 February 2025 8:00 AM | 5 February 2025 5:00 PM | 569 | 573,571 | 1 February 2025 8:00 AM | 2025-02-06 17:00 | 1 | Development Manager | 68 | 16 | 34 | 94 | 22
571 | 1.2.4.3.1.1.22 | Carpet | 3 | 6 February 2025 8:00 AM | 8 February 2025 5:00 PM | 570 | 572 | 6 February 2025 8:00 AM | 2025-02-12 17:00 | 4 | Head Contractor | 93 | 26 | 29 | 74 | 55
572 | 1.2.4.3.1.1.23 | Final Clean & Commissioning | 4 | 10 February 2025 8:00 AM | 13 February 2025 5:00 PM | 571 |  | 10 February 2025 8:00 AM | 2025-02-17 17:00 | 4 | Cleaner | 85 | 23 | 31 | 0 | 10
573 | 1.2.4.3.1.1.24 | Defects Inspections & Rectifications | 6 | 6 February 2025 8:00 AM | 12 February 2025 5:00 PM | 570 | 574 | 6 February 2025 8:00 AM | 2025-02-14 17:00 | 2 | Carpenter | 4 | 48 | 15 | 56 | 10
574 | 1.2.4.3.1.2 | LVL 1 - FITOUT COMPLETE | 0 | 12 February 2025 5:00 PM | 12 February 2025 5:00 PM | 566,573 |  | 12 February 2025 5:00 PM | 2025-02-12 17:00 | 0 | Project Manager | 58 | 40 | 22 | 65 | 37
575 | 1.2.4.3.2 | Lvl 2 - Services & Finishes | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-07 17:00 | 1 | Window | 3 | 18 | 28 | 79 | 12
576 | 1.2.4.3.2.1 | Internal Works | 85 | 21 October 2024 8:00 AM | 6 February 2025 5:00 PM |  |  | 21 October 2024 8:00 AM | 2025-02-06 17:00 | 0 | Plumber | 90 | 27 | 19 | 42 | 60
577 | 1.2.4.3.2.1.1 | Pre-load Levels | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 408,150 | 578FS-2d | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Fire | 70 | 67 | 20 | 94 | 20
578 | 1.2.4.3.2.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 21 October 2024 8:00 AM | 31 October 2024 5:00 PM | 577FS-2d | 579 | 21 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Hoarding | 73 | 31 | 14 | 67 | 34
579 | 1.2.4.3.2.1.3 | Internal Wall Framing | 8 | 1 November 2024 8:00 AM | 9 November 2024 5:00 PM | 578 | 581,580 | 1 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Carpet | 18 | 79 | 19 | 63 | 33
580 | 1.2.4.3.2.1.4 | Sheet one side of walls | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 583,582 | 11 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Contract Administrator | 15 | 91 | 30 | 89 | 25
581 | 1.2.4.3.2.1.5 | Service Rough-In | 8 | 11 November 2024 8:00 AM | 19 November 2024 5:00 PM | 579 | 582 | 11 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Carpenter | 37 | 73 | 12 | 13 | 40
582 | 1.2.4.3.2.1.6 | ITP for services in the walls | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 580,581 | 583,589 | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 1 | Mechanical | 21 | 66 | 22 | 30 | 39
583 | 1.2.4.3.2.1.7 | Sheet other side of walls | 8 | 22 November 2024 8:00 AM | 30 November 2024 5:00 PM | 580,582 | 584 | 22 November 2024 8:00 AM | 2024-12-02 17:00 | 2 | Contract Administrator | 85 | 66 | 34 | 18 | 45
584 | 1.2.4.3.2.1.8 | Frame & Sheet Ceilings | 8 | 2 December 2024 8:00 AM | 10 December 2024 5:00 PM | 583 | 585 | 2 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Head Contractor | 28 | 80 | 23 | 70 | 7
585 | 1.2.4.3.2.1.9 | Sheet, Set & Sand Ceilings | 8 | 11 December 2024 8:00 AM | 19 December 2024 5:00 PM | 584,411 | 586 | 11 December 2024 8:00 AM | 2024-12-19 17:00 | 0 | Line Market | 64 | 61 | 18 | 62 | 31
586 | 1.2.4.3.2.1.10 | Paint undercoat | 4 | 20 December 2024 8:00 AM | 24 December 2024 5:00 PM | 585 | 587 | 20 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Foreman | 18 | 80 | 12 | 26 | 8
587 | 1.2.4.3.2.1.11 | Floor Levelling and Floor Finish | 6 | 3 January 2025 8:00 AM | 9 January 2025 5:00 PM | 586 | 588 | 3 January 2025 8:00 AM | 2025-01-09 17:00 | 0 | Concretor | 61 | 72 | 30 | 38 | 38
588 | 1.2.4.3.2.1.12 | Timber Flooring | 6 | 10 January 2025 8:00 AM | 16 January 2025 5:00 PM | 587 | 594,595,590 | 10 January 2025 8:00 AM | 2025-01-22 17:00 | 6 | Head Contractor | 12 | 44 | 32 | 67 | 10
589 | 1.2.4.3.2.1.13 | Measure & Manufacture Joinery | 40 | 22 November 2024 8:00 AM | 16 January 2025 5:00 PM | 582 | 590 | 22 November 2024 8:00 AM | 2025-01-16 17:00 | 0 | Hoarding | 26 | 44 | 10 | 45 | 49
590 | 1.2.4.3.2.1.14 | Install Joinery | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 588,589 | 592 | 17 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Plumber | 60 | 25 | 29 | 85 | 19
591 | 1.2.4.3.2.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 January 2025 8:00 AM | 28 January 2025 8:00 AM | 592SF |  | 13 January 2025 8:00 AM | 2025-01-28 08:00 | 0 | Metal Work | 57 | 66 | 24 | 95 | 25
592 | 1.2.4.3.2.1.16 | Install Stone Benchtops | 5 | 28 January 2025 8:00 AM | 1 February 2025 5:00 PM | 590 | 591SF,593 | 28 January 2025 8:00 AM | 2025-02-04 17:00 | 3 | Concretor | 21 | 36 | 11 | 73 | 44
593 | 1.2.4.3.2.1.17 | Fixtures & Fittings Fit-off | 3 | 3 February 2025 8:00 AM | 5 February 2025 5:00 PM | 592 | 601 | 3 February 2025 8:00 AM | 2025-02-08 17:00 | 3 | Plumber | 39 | 59 | 22 | 44 | 18
594 | 1.2.4.3.2.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 17 January 2025 8:00 AM | 21 January 2025 5:00 PM | 588 | 596 | 17 January 2025 8:00 AM | 2025-01-23 17:00 | 2 | Formworker | 45 | 36 | 13 | 27 | 48
595 | 1.2.4.3.2.1.19 | Lighting Fit-off | 3 | 17 January 2025 8:00 AM | 20 January 2025 5:00 PM | 588 | 596 | 17 January 2025 8:00 AM | 2025-01-20 17:00 | 0 | Painter | 98 | 96 | 15 | 29 | 31
596 | 1.2.4.3.2.1.20 | Setting Defects | 4 | 22 January 2025 8:00 AM | 27 January 2025 5:00 PM | 594,595 | 597 | 22 January 2025 8:00 AM | 2025-01-27 17:00 | 0 | Formworker | 20 | 33 | 33 | 86 | 9
597 | 1.2.4.3.2.1.21 | Paint Finish Coat | 3 | 28 January 2025 8:00 AM | 30 January 2025 5:00 PM | 596 | 600,598 | 28 January 2025 8:00 AM | 2025-01-30 17:00 | 0 | Electrician | 99 | 40 | 19 | 61 | 5
598 | 1.2.4.3.2.1.22 | Carpet | 2 | 31 January 2025 8:00 AM | 1 February 2025 5:00 PM | 597 | 599 | 31 January 2025 8:00 AM | 2025-02-02 17:00 | 1 | Post Tension | 5 | 58 | 20 | 17 | 47
599 | 1.2.4.3.2.1.23 | Final Clean & Commissioning | 4 | 3 February 2025 8:00 AM | 6 February 2025 5:00 PM | 598 |  | 3 February 2025 8:00 AM | 2025-02-07 17:00 | 1 | Waterproofer | 76 | 27 | 32 | 89 | 27
600 | 1.2.4.3.2.1.24 | Defects Inspections & Rectifications | 6 | 31 January 2025 8:00 AM | 6 February 2025 5:00 PM | 597 | 601 | 31 January 2025 8:00 AM | 2025-02-06 17:00 | 0 | Plasterboarder | 83 | 75 | 21 | 82 | 32
601 | 1.2.4.3.2.2 | LVL 2 - FITOUT COMPLETE | 0 | 6 February 2025 5:00 PM | 6 February 2025 5:00 PM | 593,600 |  | 6 February 2025 5:00 PM | 2025-02-07 17:00 | 1 | Carpenter | 52 | 92 | 34 | 14 | 53
602 | 1.2.4.3.3 | Lvl 3 - Services & Finishes | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | 25 November 2024 8:00 AM | 2025-03-17 17:00 | 0 | Scaffolder | 72 | 92 | 27 | 92 | 7
603 | 1.2.4.3.3.1 | Internal Works | 88 | 25 November 2024 8:00 AM | 17 March 2025 5:00 PM |  |  | 25 November 2024 8:00 AM | 2025-03-19 17:00 | 2 | Foreman | 85 | 24 | 27 | 76 | 22
604 | 1.2.4.3.3.1.1 | Pre-load Levels | 2 | 25 November 2024 8:00 AM | 26 November 2024 5:00 PM | 174 | 605FS-2d | 25 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Carpenter | 34 | 70 | 21 | 11 | 60
605 | 1.2.4.3.3.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 25 November 2024 8:00 AM | 5 December 2024 5:00 PM | 604FS-2d | 606 | 25 November 2024 8:00 AM | 2024-12-06 17:00 | 1 | Stone Mason | 10 | 36 | 27 | 51 | 47
606 | 1.2.4.3.3.1.3 | Internal Wall Framing | 8 | 6 December 2024 8:00 AM | 14 December 2024 5:00 PM | 605 | 608,607 | 6 December 2024 8:00 AM | 2024-12-15 17:00 | 1 | Surveyor | 74 | 28 | 30 | 2 | 15
607 | 1.2.4.3.3.1.4 | Sheet one side of walls | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 610,609 | 16 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Renderer | 47 | 59 | 19 | 60 | 60
608 | 1.2.4.3.3.1.5 | Service Rough-In | 8 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | 606 | 609 | 16 December 2024 8:00 AM | 2024-12-24 17:00 | 0 | Carpet | 98 | 82 | 14 | 10 | 17
609 | 1.2.4.3.3.1.6 | ITP for services in the walls | 2 | 3 January 2025 8:00 AM | 4 January 2025 5:00 PM | 607,608 | 610,616 | 3 January 2025 8:00 AM | 2025-01-04 17:00 | 0 | Subcontractor | 0 | 85 | 15 | 41 | 46
610 | 1.2.4.3.3.1.7 | Sheet other side of walls | 8 | 6 January 2025 8:00 AM | 14 January 2025 5:00 PM | 607,609,416FS-6d | 611 | 6 January 2025 8:00 AM | 2025-01-14 17:00 | 0 | Fire | 43 | 97 | 19 | 28 | 22
611 | 1.2.4.3.3.1.8 | Frame & Sheet Ceilings | 8 | 15 January 2025 8:00 AM | 23 January 2025 5:00 PM | 610 | 612 | 15 January 2025 8:00 AM | 2025-01-25 17:00 | 2 | Reinforcement Fixer | 17 | 91 | 29 | 19 | 19
612 | 1.2.4.3.3.1.9 | Sheet, Set & Sand Ceilings | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 611,417 | 613 | 24 January 2025 8:00 AM | 2025-02-04 17:00 | 1 | Fire | 2 | 38 | 26 | 2 | 39
613 | 1.2.4.3.3.1.10 | Paint undercoat | 4 | 4 February 2025 8:00 AM | 7 February 2025 5:00 PM | 612 | 614 | 4 February 2025 8:00 AM | 2025-02-09 17:00 | 2 | Mechanical | 11 | 94 | 13 | 3 | 59
614 | 1.2.4.3.3.1.11 | Floor Levelling and Floor Finish | 7 | 8 February 2025 8:00 AM | 15 February 2025 5:00 PM | 613 | 615 | 8 February 2025 8:00 AM | 2025-02-15 17:00 | 0 | Surveyor | 34 | 80 | 34 | 75 | 48
615 | 1.2.4.3.3.1.12 | Timber Flooring | 6 | 17 February 2025 8:00 AM | 22 February 2025 5:00 PM | 614 | 621,622,617 | 17 February 2025 8:00 AM | 2025-02-23 17:00 | 1 | Plasterboarder | 7 | 63 | 24 | 42 | 51
616 | 1.2.4.3.3.1.13 | Measure & Manufacture Joinery | 40 | 6 January 2025 8:00 AM | 21 February 2025 5:00 PM | 609 | 617 | 6 January 2025 8:00 AM | 2025-02-21 17:00 | 0 | Metal Work | 92 | 91 | 11 | 40 | 36
617 | 1.2.4.3.3.1.14 | Install Joinery | 8 | 24 February 2025 8:00 AM | 4 March 2025 5:00 PM | 615,616 | 619 | 24 February 2025 8:00 AM | 2025-03-06 17:00 | 2 | Renderer | 42 | 15 | 32 | 55 | 14
618 | 1.2.4.3.3.1.15 | Measure & Manufacture Stone Benchtops | 12 | 19 February 2025 8:00 AM | 5 March 2025 8:00 AM | 619SF |  | 19 February 2025 8:00 AM | 2025-03-05 08:00 | 0 | Carpet | 79 | 77 | 34 | 38 | 29
619 | 1.2.4.3.3.1.16 | Install Stone Benchtops | 6 | 5 March 2025 8:00 AM | 11 March 2025 5:00 PM | 617 | 618SF,620 | 5 March 2025 8:00 AM | 2025-03-14 17:00 | 3 | Tiler | 69 | 99 | 31 | 51 | 44
620 | 1.2.4.3.3.1.17 | Fixtures & Fittings Fit-off | 3 | 12 March 2025 8:00 AM | 14 March 2025 5:00 PM | 619 | 628 | 12 March 2025 8:00 AM | 2025-03-15 17:00 | 1 | Foreman | 9 | 10 | 28 | 2 | 14
621 | 1.2.4.3.3.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 24 February 2025 8:00 AM | 27 February 2025 5:00 PM | 615 | 623 | 24 February 2025 8:00 AM | 2025-02-27 17:00 | 0 | Head Contractor | 34 | 15 | 16 | 80 | 23
622 | 1.2.4.3.3.1.19 | Lighting Fit-off | 3 | 24 February 2025 8:00 AM | 26 February 2025 5:00 PM | 615 | 623 | 24 February 2025 8:00 AM | 2025-02-28 17:00 | 2 | Formworker | 41 | 43 | 34 | 89 | 35
623 | 1.2.4.3.3.1.20 | Setting Defects | 4 | 28 February 2025 8:00 AM | 4 March 2025 5:00 PM | 621,622 | 624 | 28 February 2025 8:00 AM | 2025-03-05 17:00 | 1 | Concretor | 53 | 43 | 16 | 75 | 19
624 | 1.2.4.3.3.1.21 | Paint Finish Coat | 3 | 5 March 2025 8:00 AM | 7 March 2025 5:00 PM | 623 | 627,625 | 5 March 2025 8:00 AM | 2025-03-08 17:00 | 1 | Plasterboarder | 3 | 68 | 30 | 22 | 46
625 | 1.2.4.3.3.1.22 | Carpet | 2 | 8 March 2025 8:00 AM | 10 March 2025 5:00 PM | 624 | 626 | 8 March 2025 8:00 AM | 2025-03-15 17:00 | 5 | Plumber | 30 | 29 | 21 | 10 | 52
626 | 1.2.4.3.3.1.23 | Final Clean & Commissioning | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 625 |  | 11 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Hoarding | 64 | 50 | 11 | 93 | 48
627 | 1.2.4.3.3.1.24 | Defects Inspections & Rectifications | 8 | 8 March 2025 8:00 AM | 17 March 2025 5:00 PM | 624 | 628 | 8 March 2025 8:00 AM | 2025-03-17 17:00 | 0 | Head Contractor | 22 | 40 | 10 | 75 | 23
628 | 1.2.4.3.3.2 | LVL 3 - FITOUT COMPLETE | 0 | 17 March 2025 5:00 PM | 17 March 2025 5:00 PM | 620,627 | 753 | 17 March 2025 5:00 PM | 2025-03-17 17:00 | 0 | Project Manager | 26 | 24 | 13 | 28 | 40
629 | 1.2.4.3.4 | Lvl 4 - Services & Finishes | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | 11 December 2024 8:00 AM | 2025-04-22 17:00 | 0 | Renderer | 94 | 14 | 34 | 100 | 22
630 | 1.2.4.3.4.1 | Internal Works | 102 | 11 December 2024 8:00 AM | 22 April 2025 5:00 PM |  |  | 11 December 2024 8:00 AM | 2025-04-23 17:00 | 1 | Renderer | 33 | 82 | 18 | 41 | 26
631 | 1.2.4.3.4.1.1 | Pre-load Levels | 2 | 11 December 2024 8:00 AM | 12 December 2024 5:00 PM | 186 | 632FS-2d | 11 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Tiler | 11 | 13 | 31 | 12 | 31
632 | 1.2.4.3.4.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 11 December 2024 8:00 AM | 21 December 2024 5:00 PM | 631FS-2d | 633 | 11 December 2024 8:00 AM | 2024-12-22 17:00 | 1 | Renderer | 35 | 31 | 21 | 15 | 12
633 | 1.2.4.3.4.1.3 | Internal Wall Framing | 8 | 23 December 2024 8:00 AM | 9 January 2025 5:00 PM | 632 | 635,634 | 23 December 2024 8:00 AM | 2025-01-11 17:00 | 2 | Waterproofer | 77 | 64 | 33 | 14 | 24
634 | 1.2.4.3.4.1.4 | Sheet one side of walls | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 637,636 | 10 January 2025 8:00 AM | 2025-01-18 17:00 | 0 | Reinforcement Fixer | 12 | 98 | 18 | 56 | 44
635 | 1.2.4.3.4.1.5 | Service Rough-In | 8 | 10 January 2025 8:00 AM | 18 January 2025 5:00 PM | 633 | 636 | 10 January 2025 8:00 AM | 2025-01-18 17:00 | 0 | Development Manager | 47 | 20 | 10 | 7 | 17
636 | 1.2.4.3.4.1.6 | ITP for services in the walls | 2 | 20 January 2025 8:00 AM | 21 January 2025 5:00 PM | 634,635 | 637,643 | 20 January 2025 8:00 AM | 2025-01-21 17:00 | 0 | Renderer | 15 | 23 | 28 | 56 | 25
637 | 1.2.4.3.4.1.7 | Sheet other side of walls | 8 | 10 February 2025 8:00 AM | 18 February 2025 5:00 PM | 634,636,422FS-6d | 638 | 10 February 2025 8:00 AM | 2025-02-18 17:00 | 0 | Concretor | 5 | 100 | 22 | 22 | 51
638 | 1.2.4.3.4.1.8 | Frame & Sheet Ceilings | 8 | 19 February 2025 8:00 AM | 27 February 2025 5:00 PM | 637 | 639 | 19 February 2025 8:00 AM | 2025-02-27 17:00 | 0 | Carpenter | 77 | 79 | 12 | 63 | 20
639 | 1.2.4.3.4.1.9 | Sheet, Set & Sand Ceilings | 8 | 28 February 2025 8:00 AM | 8 March 2025 5:00 PM | 638,423 | 640 | 28 February 2025 8:00 AM | 2025-03-09 17:00 | 1 | Timber Floorer | 90 | 25 | 16 | 9 | 38
640 | 1.2.4.3.4.1.10 | Paint undercoat | 4 | 10 March 2025 8:00 AM | 13 March 2025 5:00 PM | 639 | 641 | 10 March 2025 8:00 AM | 2025-03-14 17:00 | 1 | Tiler | 62 | 34 | 26 | 56 | 52
641 | 1.2.4.3.4.1.11 | Floor Levelling and Floor Finish | 6 | 14 March 2025 8:00 AM | 20 March 2025 5:00 PM | 640 | 642 | 14 March 2025 8:00 AM | 2025-03-20 17:00 | 0 | Post Tension | 65 | 70 | 28 | 21 | 49
642 | 1.2.4.3.4.1.12 | Timber Flooring | 6 | 21 March 2025 8:00 AM | 27 March 2025 5:00 PM | 641 | 648,649,644 | 21 March 2025 8:00 AM | 2025-03-27 17:00 | 0 | Electrician | 96 | 27 | 20 | 3 | 14
643 | 1.2.4.3.4.1.13 | Measure & Manufacture Joinery | 40 | 22 January 2025 8:00 AM | 10 March 2025 5:00 PM | 636 | 644 | 22 January 2025 8:00 AM | 2025-03-10 17:00 | 0 | Carpet | 2 | 26 | 30 | 28 | 29
644 | 1.2.4.3.4.1.14 | Install Joinery | 8 | 28 March 2025 8:00 AM | 5 April 2025 5:00 PM | 642,643 | 646 | 28 March 2025 8:00 AM | 2025-04-06 17:00 | 1 | Mechanical | 93 | 49 | 31 | 60 | 48
645 | 1.2.4.3.4.1.15 | Measure & Manufacture Stone Benchtops | 12 | 24 March 2025 8:00 AM | 7 April 2025 8:00 AM | 646SF |  | 24 March 2025 8:00 AM | 2025-04-10 08:00 | 3 | Development Manager | 56 | 17 | 34 | 30 | 47
646 | 1.2.4.3.4.1.16 | Install Stone Benchtops | 6 | 7 April 2025 8:00 AM | 12 April 2025 5:00 PM | 644 | 645SF,647 | 7 April 2025 8:00 AM | 2025-04-12 17:00 | 0 | Fire | 28 | 26 | 31 | 58 | 39
647 | 1.2.4.3.4.1.17 | Fixtures & Fittings Fit-off | 3 | 14 April 2025 8:00 AM | 16 April 2025 5:00 PM | 646 | 655 | 14 April 2025 8:00 AM | 2025-04-16 17:00 | 0 | Plumber | 83 | 55 | 19 | 34 | 25
648 | 1.2.4.3.4.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 28 March 2025 8:00 AM | 1 April 2025 5:00 PM | 642 | 650 | 28 March 2025 8:00 AM | 2025-04-02 17:00 | 1 | Metal Work | 73 | 59 | 17 | 67 | 54
649 | 1.2.4.3.4.1.19 | Lighting Fit-off | 3 | 28 March 2025 8:00 AM | 31 March 2025 5:00 PM | 642 | 650 | 28 March 2025 8:00 AM | 2025-04-03 17:00 | 3 | Electrician | 10 | 42 | 11 | 43 | 46
650 | 1.2.4.3.4.1.20 | Setting Defects | 4 | 2 April 2025 8:00 AM | 5 April 2025 5:00 PM | 648,649 | 651 | 2 April 2025 8:00 AM | 2025-04-07 17:00 | 2 | Plasterboarder | 38 | 19 | 28 | 75 | 54
651 | 1.2.4.3.4.1.21 | Paint Finish Coat | 3 | 7 April 2025 8:00 AM | 9 April 2025 5:00 PM | 650 | 654,652 | 7 April 2025 8:00 AM | 2025-04-09 17:00 | 0 | Subcontractor | 28 | 65 | 26 | 87 | 54
652 | 1.2.4.3.4.1.22 | Carpet | 2 | 10 April 2025 8:00 AM | 11 April 2025 5:00 PM | 651 | 653 | 10 April 2025 8:00 AM | 2025-04-13 17:00 | 2 | Cleaner | 66 | 77 | 11 | 66 | 5
653 | 1.2.4.3.4.1.23 | Final Clean & Commissioning | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 652 |  | 12 April 2025 8:00 AM | 2025-04-23 17:00 | 1 | Metal Work | 56 | 92 | 31 | 33 | 43
654 | 1.2.4.3.4.1.24 | Defects Inspections & Rectifications | 8 | 10 April 2025 8:00 AM | 22 April 2025 5:00 PM | 651 | 655 | 10 April 2025 8:00 AM | 2025-04-23 17:00 | 1 | Concretor | 16 | 68 | 19 | 96 | 23
655 | 1.2.4.3.4.2 | LVL 4 - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 647,654 | 753 | 22 April 2025 5:00 PM | 2025-04-25 17:00 | 3 | Timber Floorer | 14 | 13 | 30 | 94 | 45
656 | 1.2.4.3.5 | Lvl 5 - Services & Finishes | 100 | 12 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | 12 December 2024 8:00 AM | 2025-04-18 17:00 | 1 | Development Manager | 44 | 70 | 19 | 59 | 10
657 | 1.2.4.3.5.1 | Survey & Setout | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 289,198 | 658FS-1d | 12 December 2024 8:00 AM | 2024-12-13 17:00 | 1 | Landscaper | 78 | 95 | 16 | 42 | 25
658 | 1.2.4.3.5.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 12 December 2024 8:00 AM | 16 December 2024 5:00 PM | 657FS-1d | 660,663 | 12 December 2024 8:00 AM | 2024-12-16 17:00 | 0 | Scaffolder | 65 | 57 | 13 | 46 | 39
659 | 1.2.4.3.5.3 | External Works | 34 | 17 December 2024 8:00 AM | 4 February 2025 5:00 PM |  |  | 17 December 2024 8:00 AM | 2025-02-04 17:00 | 0 | Project Manager | 15 | 45 | 13 | 9 | 23
660 | 1.2.4.3.5.3.1 | Façade & External Walls | 18 | 17 December 2024 8:00 AM | 15 January 2025 5:00 PM | 658 | 661 | 17 December 2024 8:00 AM | 2025-01-17 17:00 | 2 | Electrician | 34 | 89 | 18 | 89 | 35
661 | 1.2.4.3.5.3.2 | Windows Install | 16 | 16 January 2025 8:00 AM | 4 February 2025 5:00 PM | 660 | 669FS-6d | 16 January 2025 8:00 AM | 2025-02-09 17:00 | 5 | Surveyor | 68 | 91 | 24 | 92 | 50
662 | 1.2.4.3.5.4 | Internal Works | 91 | 23 December 2024 8:00 AM | 17 April 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-04-17 17:00 | 0 | Painter | 10 | 10 | 26 | 28 | 39
663 | 1.2.4.3.5.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 658,426 | 664FS-2d | 23 December 2024 8:00 AM | 2024-12-26 17:00 | 2 | Project Manager | 38 | 25 | 25 | 33 | 17
664 | 1.2.4.3.5.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 663FS-2d | 665 | 23 December 2024 8:00 AM | 2025-01-14 17:00 | 3 | Joiner | 21 | 95 | 23 | 52 | 17
665 | 1.2.4.3.5.4.3 | Internal Wall Framing | 8 | 13 January 2025 8:00 AM | 21 January 2025 5:00 PM | 664 | 667,666 | 13 January 2025 8:00 AM | 2025-01-27 17:00 | 6 | Mechanical | 92 | 25 | 17 | 54 | 3
666 | 1.2.4.3.5.4.4 | Sheet one side of walls | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 669,668 | 22 January 2025 8:00 AM | 2025-01-31 17:00 | 0 | Window | 93 | 48 | 33 | 18 | 58
667 | 1.2.4.3.5.4.5 | Service Rough-In | 8 | 22 January 2025 8:00 AM | 31 January 2025 5:00 PM | 665 | 668 | 22 January 2025 8:00 AM | 2025-02-01 17:00 | 1 | Landscaper | 23 | 26 | 20 | 86 | 54
668 | 1.2.4.3.5.4.6 | ITP for services in the walls | 2 | 1 February 2025 8:00 AM | 3 February 2025 5:00 PM | 666,667 | 669,675 | 1 February 2025 8:00 AM | 2025-02-03 17:00 | 0 | Cleaner | 23 | 32 | 24 | 85 | 55
669 | 1.2.4.3.5.4.7 | Sheet other side of walls | 8 | 4 February 2025 8:00 AM | 12 February 2025 5:00 PM | 661FS-6d,666,668,428FS-6d | 670 | 4 February 2025 8:00 AM | 2025-02-13 17:00 | 1 | Stone Mason | 20 | 98 | 28 | 22 | 31
670 | 1.2.4.3.5.4.8 | Frame & Sheet Ceilings | 8 | 13 February 2025 8:00 AM | 21 February 2025 5:00 PM | 669 | 671 | 13 February 2025 8:00 AM | 2025-02-22 17:00 | 1 | Hoarding | 6 | 72 | 33 | 21 | 18
671 | 1.2.4.3.5.4.9 | Sheet, Set & Sand Ceilings | 8 | 22 February 2025 8:00 AM | 3 March 2025 5:00 PM | 670,429 | 672 | 22 February 2025 8:00 AM | 2025-03-04 17:00 | 1 | Waterproofer | 33 | 94 | 28 | 34 | 18
672 | 1.2.4.3.5.4.10 | Paint undercoat | 4 | 4 March 2025 8:00 AM | 7 March 2025 5:00 PM | 671 | 673 | 4 March 2025 8:00 AM | 2025-03-11 17:00 | 4 | Renderer | 13 | 56 | 12 | 56 | 51
673 | 1.2.4.3.5.4.11 | Floor Levelling and Floor Finish | 6 | 8 March 2025 8:00 AM | 14 March 2025 5:00 PM | 672 | 674 | 8 March 2025 8:00 AM | 2025-03-14 17:00 | 0 | Excavation | 53 | 36 | 22 | 100 | 60
674 | 1.2.4.3.5.4.12 | Timber Flooring | 6 | 15 March 2025 8:00 AM | 21 March 2025 5:00 PM | 673 | 680,681,676 | 15 March 2025 8:00 AM | 2025-03-21 17:00 | 0 | Plumber | 97 | 72 | 35 | 60 | 40
675 | 1.2.4.3.5.4.13 | Measure & Manufacture Joinery | 40 | 4 February 2025 8:00 AM | 21 March 2025 5:00 PM | 668 | 676 | 4 February 2025 8:00 AM | 2025-03-21 17:00 | 0 | Window | 67 | 27 | 15 | 20 | 5
676 | 1.2.4.3.5.4.14 | Install Joinery | 8 | 22 March 2025 8:00 AM | 31 March 2025 5:00 PM | 674,675 | 678 | 22 March 2025 8:00 AM | 2025-03-31 17:00 | 0 | Site Manager | 66 | 93 | 10 | 6 | 26
677 | 1.2.4.3.5.4.15 | Measure & Manufacture Stone Benchtops | 15 | 14 March 2025 8:00 AM | 1 April 2025 8:00 AM | 678SF | 687 | 14 March 2025 8:00 AM | 2025-04-02 08:00 | 1 | Foreman | 48 | 22 | 28 | 88 | 43
678 | 1.2.4.3.5.4.16 | Install Stone Benchtops | 6 | 1 April 2025 8:00 AM | 7 April 2025 5:00 PM | 676 | 677SF,679 | 1 April 2025 8:00 AM | 2025-04-08 17:00 | 1 | Scaffolder | 94 | 77 | 11 | 97 | 41
679 | 1.2.4.3.5.4.17 | Fixtures & Fittings Fit-off | 8 | 8 April 2025 8:00 AM | 16 April 2025 5:00 PM | 678 | 687 | 8 April 2025 8:00 AM | 2025-04-17 17:00 | 1 | Head Contractor | 99 | 20 | 32 | 99 | 3
680 | 1.2.4.3.5.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 674 | 682 | 22 March 2025 8:00 AM | 2025-03-28 17:00 | 2 | Waterproofer | 50 | 93 | 21 | 9 | 37
681 | 1.2.4.3.5.4.19 | Lighting Fit-off | 3 | 22 March 2025 8:00 AM | 25 March 2025 5:00 PM | 674 | 682 | 22 March 2025 8:00 AM | 2025-03-29 17:00 | 4 | Contract Administrator | 81 | 26 | 19 | 42 | 28
682 | 1.2.4.3.5.4.20 | Setting Defects | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 680,681 | 683 | 27 March 2025 8:00 AM | 2025-04-03 17:00 | 3 | Tiler | 77 | 60 | 32 | 59 | 17
683 | 1.2.4.3.5.4.21 | Paint Finish Coat | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 682 | 686,684 | 1 April 2025 8:00 AM | 2025-04-03 17:00 | 0 | Painter | 47 | 58 | 24 | 14 | 36
684 | 1.2.4.3.5.4.22 | Carpet | 2 | 4 April 2025 8:00 AM | 5 April 2025 5:00 PM | 683 | 685 | 4 April 2025 8:00 AM | 2025-04-05 17:00 | 0 | Head Contractor | 73 | 51 | 13 | 28 | 38
685 | 1.2.4.3.5.4.23 | Final Clean & Commissioning | 10 | 7 April 2025 8:00 AM | 17 April 2025 5:00 PM | 684 | 687 | 7 April 2025 8:00 AM | 2025-04-17 17:00 | 0 | Plasterboarder | 12 | 76 | 32 | 42 | 13
686 | 1.2.4.3.5.4.24 | Defects Inspections & Rectifications | 8 | 4 April 2025 8:00 AM | 12 April 2025 5:00 PM | 683 | 687 | 4 April 2025 8:00 AM | 2025-04-12 17:00 | 0 | Waterproofer | 60 | 12 | 34 | 47 | 13
687 | 1.2.4.3.5.5 | LVL 5 - FITOUT COMPLETE | 0 | 17 April 2025 5:00 PM | 17 April 2025 5:00 PM | 679,686,685,677 |  | 17 April 2025 5:00 PM | 2025-04-22 17:00 | 5 | Site Manager | 82 | 58 | 34 | 96 | 20
688 | 1.2.4.3.6 | Lvl 6 - Services & Finishes | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-04-16 17:00 | 1 | Head Contractor | 86 | 75 | 26 | 38 | 12
689 | 1.2.4.3.6.1 | Internal Works | 93 | 18 December 2024 8:00 AM | 15 April 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-04-17 17:00 | 2 | Excavation | 90 | 50 | 11 | 43 | 24
690 | 1.2.4.3.6.1.1 | Pre-load Levels | 2 | 18 December 2024 8:00 AM | 19 December 2024 5:00 PM | 432,210 | 691FS-2d | 18 December 2024 8:00 AM | 2024-12-20 17:00 | 1 | Project Manager | 34 | 11 | 11 | 31 | 44
691 | 1.2.4.3.6.1.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 18 December 2024 8:00 AM | 7 January 2025 5:00 PM | 690FS-2d | 692 | 18 December 2024 8:00 AM | 2025-01-08 17:00 | 1 | Carpet | 32 | 59 | 20 | 63 | 37
692 | 1.2.4.3.6.1.3 | Internal Wall Framing | 8 | 8 January 2025 8:00 AM | 16 January 2025 5:00 PM | 691 | 694,693 | 8 January 2025 8:00 AM | 2025-01-17 17:00 | 1 | Plumber | 98 | 67 | 29 | 3 | 59
693 | 1.2.4.3.6.1.4 | Sheet one side of walls | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 696,695 | 17 January 2025 8:00 AM | 2025-01-31 17:00 | 4 | Subcontractor | 9 | 17 | 16 | 36 | 24
694 | 1.2.4.3.6.1.5 | Service Rough-In | 8 | 17 January 2025 8:00 AM | 27 January 2025 5:00 PM | 692 | 695 | 17 January 2025 8:00 AM | 2025-01-28 17:00 | 1 | Waterproofer | 27 | 56 | 33 | 28 | 49
695 | 1.2.4.3.6.1.6 | ITP for services in the walls | 2 | 28 January 2025 8:00 AM | 29 January 2025 5:00 PM | 693,694 | 696,702 | 28 January 2025 8:00 AM | 2025-02-04 17:00 | 6 | Foreman | 81 | 82 | 22 | 59 | 46
696 | 1.2.4.3.6.1.7 | Sheet other side of walls | 8 | 30 January 2025 8:00 AM | 7 February 2025 5:00 PM | 693,695,434FS-6d | 697 | 30 January 2025 8:00 AM | 2025-02-07 17:00 | 0 | Subcontractor | 0 | 39 | 13 | 97 | 6
697 | 1.2.4.3.6.1.8 | Frame & Sheet Ceilings | 8 | 8 February 2025 8:00 AM | 17 February 2025 5:00 PM | 696 | 698 | 8 February 2025 8:00 AM | 2025-02-17 17:00 | 0 | Scaffolder | 23 | 33 | 20 | 78 | 15
698 | 1.2.4.3.6.1.9 | Sheet, Set & Sand Ceilings | 8 | 18 February 2025 8:00 AM | 26 February 2025 5:00 PM | 697,435 | 699 | 18 February 2025 8:00 AM | 2025-02-27 17:00 | 1 | Stone Mason | 81 | 59 | 16 | 74 | 48
699 | 1.2.4.3.6.1.10 | Paint undercoat | 4 | 27 February 2025 8:00 AM | 3 March 2025 5:00 PM | 698 | 700 | 27 February 2025 8:00 AM | 2025-03-07 17:00 | 4 | Floor Sealer | 8 | 86 | 17 | 47 | 59
700 | 1.2.4.3.6.1.11 | Floor Levelling and Floor Finish | 6 | 4 March 2025 8:00 AM | 10 March 2025 5:00 PM | 699 | 701 | 4 March 2025 8:00 AM | 2025-03-10 17:00 | 0 | Renderer | 65 | 86 | 20 | 62 | 39
701 | 1.2.4.3.6.1.12 | Timber Flooring | 6 | 11 March 2025 8:00 AM | 17 March 2025 5:00 PM | 700 | 707,708,703 | 11 March 2025 8:00 AM | 2025-03-20 17:00 | 3 | Carpet | 0 | 18 | 30 | 38 | 34
702 | 1.2.4.3.6.1.13 | Measure & Manufacture Joinery | 40 | 30 January 2025 8:00 AM | 17 March 2025 5:00 PM | 695 | 703 | 30 January 2025 8:00 AM | 2025-03-17 17:00 | 0 | Project Manager | 63 | 17 | 30 | 51 | 11
703 | 1.2.4.3.6.1.14 | Install Joinery | 8 | 18 March 2025 8:00 AM | 26 March 2025 5:00 PM | 701,702 | 705 | 18 March 2025 8:00 AM | 2025-03-29 17:00 | 3 | Metal Work | 7 | 22 | 25 | 29 | 58
704 | 1.2.4.3.6.1.15 | Measure & Manufacture Stone Benchtops | 12 | 13 March 2025 8:00 AM | 27 March 2025 8:00 AM | 705SF |  | 13 March 2025 8:00 AM | 2025-03-28 08:00 | 1 | Reinforcement Fixer | 57 | 49 | 18 | 92 | 14
705 | 1.2.4.3.6.1.16 | Install Stone Benchtops | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 703 | 704SF,706 | 27 March 2025 8:00 AM | 2025-04-02 17:00 | 0 | Metal Work | 37 | 35 | 13 | 97 | 55
706 | 1.2.4.3.6.1.17 | Fixtures & Fittings Fit-off | 7 | 3 April 2025 8:00 AM | 10 April 2025 5:00 PM | 705 | 714 | 3 April 2025 8:00 AM | 2025-04-17 17:00 | 7 | Formworker | 91 | 18 | 26 | 72 | 56
707 | 1.2.4.3.6.1.18 | Carpentry fitoff (Skirtings, Doors, etc) | 4 | 18 March 2025 8:00 AM | 21 March 2025 5:00 PM | 701 | 709 | 18 March 2025 8:00 AM | 2025-03-22 17:00 | 1 | Post Tension | 12 | 49 | 24 | 9 | 8
708 | 1.2.4.3.6.1.19 | Lighting Fit-off | 3 | 18 March 2025 8:00 AM | 20 March 2025 5:00 PM | 701 | 709 | 18 March 2025 8:00 AM | 2025-03-24 17:00 | 4 | Development Manager | 60 | 63 | 24 | 48 | 24
709 | 1.2.4.3.6.1.20 | Setting Defects | 4 | 22 March 2025 8:00 AM | 26 March 2025 5:00 PM | 707,708 | 710 | 22 March 2025 8:00 AM | 2025-03-26 17:00 | 0 | Waterproofer | 7 | 42 | 10 | 85 | 34
710 | 1.2.4.3.6.1.21 | Paint Finish Coat | 4 | 27 March 2025 8:00 AM | 31 March 2025 5:00 PM | 709 | 713,711 | 27 March 2025 8:00 AM | 2025-04-03 17:00 | 3 | Subcontractor | 5 | 50 | 14 | 7 | 10
711 | 1.2.4.3.6.1.22 | Carpet | 3 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | 710 | 712 | 1 April 2025 8:00 AM | 2025-04-05 17:00 | 2 | Admin | 98 | 30 | 13 | 22 | 28
712 | 1.2.4.3.6.1.23 | Final Clean & Commissioning | 10 | 4 April 2025 8:00 AM | 15 April 2025 5:00 PM | 711 |  | 4 April 2025 8:00 AM | 2025-04-15 17:00 | 0 | Development Manager | 39 | 94 | 12 | 39 | 9
713 | 1.2.4.3.6.1.24 | Defects Inspections & Rectifications | 8 | 1 April 2025 8:00 AM | 9 April 2025 5:00 PM | 710 | 714 | 1 April 2025 8:00 AM | 2025-04-11 17:00 | 2 | Waterproofer | 17 | 76 | 24 | 75 | 35
714 | 1.2.4.3.6.2 | LVL 6 - FITOUT COMPLETE | 0 | 10 April 2025 5:00 PM | 10 April 2025 5:00 PM | 706,713 | 5 | 10 April 2025 5:00 PM | 2025-04-10 17:00 | 0 | Surveyor | 86 | 95 | 34 | 44 | 9
715 | 1.2.4.3.7 | Lvl 7 - Services & Finishes | 105 | 18 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 18 December 2024 8:00 AM | 2025-05-08 17:00 | 3 | Development Manager | 79 | 69 | 33 | 76 | 3
716 | 1.2.4.3.7.1 | Survey & Setout | 1 | 18 December 2024 8:00 AM | 18 December 2024 5:00 PM | 301,223 | 717FS-1d | 18 December 2024 8:00 AM | 2024-12-22 17:00 | 4 | Window | 75 | 34 | 23 | 7 | 12
717 | 1.2.4.3.7.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 18 December 2024 8:00 AM | 21 December 2024 5:00 PM | 716FS-1d | 719,722 | 18 December 2024 8:00 AM | 2024-12-21 17:00 | 0 | Plumber | 29 | 48 | 26 | 48 | 29
718 | 1.2.4.3.7.3 | External Works | 34 | 23 December 2024 8:00 AM | 10 February 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-02-12 17:00 | 2 | Site Manager | 2 | 96 | 31 | 23 | 51
719 | 1.2.4.3.7.3.1 | Façade & External Walls | 18 | 23 December 2024 8:00 AM | 21 January 2025 5:00 PM | 717 | 720 | 23 December 2024 8:00 AM | 2025-01-23 17:00 | 2 | Metal Work | 53 | 96 | 27 | 72 | 51
720 | 1.2.4.3.7.3.2 | Windows Install | 16 | 22 January 2025 8:00 AM | 10 February 2025 5:00 PM | 719 | 728FS-6d | 22 January 2025 8:00 AM | 2025-02-12 17:00 | 2 | Window | 44 | 70 | 30 | 88 | 53
721 | 1.2.4.3.7.4 | Internal Works | 101 | 23 December 2024 8:00 AM | 5 May 2025 5:00 PM |  |  | 23 December 2024 8:00 AM | 2025-05-05 17:00 | 0 | Hoarding | 42 | 32 | 14 | 26 | 58
722 | 1.2.4.3.7.4.1 | Pre-load Levels | 2 | 23 December 2024 8:00 AM | 24 December 2024 5:00 PM | 717,438 | 723FS-2d | 23 December 2024 8:00 AM | 2024-12-26 17:00 | 2 | Reinforcement Fixer | 44 | 77 | 20 | 86 | 58
723 | 1.2.4.3.7.4.2 | Intertenancy Walls & Fire Rated Frame Installation | 10 | 23 December 2024 8:00 AM | 11 January 2025 5:00 PM | 722FS-2d | 724 | 23 December 2024 8:00 AM | 2025-01-11 17:00 | 0 | Carpet | 4 | 81 | 18 | 41 | 60
724 | 1.2.4.3.7.4.3 | Internal Wall Framing | 10 | 13 January 2025 8:00 AM | 23 January 2025 5:00 PM | 723 | 726,725 | 13 January 2025 8:00 AM | 2025-01-27 17:00 | 4 | Foreman | 45 | 30 | 12 | 89 | 43
725 | 1.2.4.3.7.4.4 | Sheet one side of walls | 9 | 24 January 2025 8:00 AM | 4 February 2025 5:00 PM | 724 | 728,727 | 24 January 2025 8:00 AM | 2025-02-06 17:00 | 2 | Head Contractor | 20 | 37 | 18 | 82 | 13
726 | 1.2.4.3.7.4.5 | Service Rough-In | 8 | 24 January 2025 8:00 AM | 3 February 2025 5:00 PM | 724 | 727 | 24 January 2025 8:00 AM | 2025-02-04 17:00 | 1 | Stone Mason | 73 | 50 | 24 | 18 | 56
727 | 1.2.4.3.7.4.6 | ITP for services in the walls | 2 | 5 February 2025 8:00 AM | 6 February 2025 5:00 PM | 725,726 | 728,734 | 5 February 2025 8:00 AM | 2025-02-07 17:00 | 1 | Painter | 38 | 77 | 17 | 86 | 47
728 | 1.2.4.3.7.4.7 | Sheet other side of walls | 8 | 15 February 2025 8:00 AM | 24 February 2025 5:00 PM | 720FS-6d,725,727,440FS-6d | 729 | 15 February 2025 8:00 AM | 2025-03-01 17:00 | 5 | Metal Work | 55 | 57 | 17 | 25 | 58
729 | 1.2.4.3.7.4.8 | Frame & Sheet Ceilings | 8 | 25 February 2025 8:00 AM | 5 March 2025 5:00 PM | 728 | 730 | 25 February 2025 8:00 AM | 2025-03-05 17:00 | 0 | Tiler | 25 | 50 | 19 | 25 | 51
730 | 1.2.4.3.7.4.9 | Sheet, Set & Sand Ceilings | 8 | 6 March 2025 8:00 AM | 14 March 2025 5:00 PM | 729,441 | 731 | 6 March 2025 8:00 AM | 2025-03-14 17:00 | 0 | Concretor | 69 | 91 | 33 | 1 | 57
731 | 1.2.4.3.7.4.10 | Paint undercoat | 4 | 15 March 2025 8:00 AM | 19 March 2025 5:00 PM | 730 | 732 | 15 March 2025 8:00 AM | 2025-03-21 17:00 | 2 | Tiler | 78 | 31 | 27 | 87 | 30
732 | 1.2.4.3.7.4.11 | Floor Levelling and Floor Finish | 6 | 20 March 2025 8:00 AM | 26 March 2025 5:00 PM | 731 | 733 | 20 March 2025 8:00 AM | 2025-03-29 17:00 | 3 | Stone Mason | 31 | 11 | 17 | 42 | 35
733 | 1.2.4.3.7.4.12 | Timber Flooring | 6 | 27 March 2025 8:00 AM | 2 April 2025 5:00 PM | 732 | 739,740,735 | 27 March 2025 8:00 AM | 2025-04-02 17:00 | 0 | Subcontractor | 47 | 38 | 17 | 63 | 56
734 | 1.2.4.3.7.4.13 | Measure & Manufacture Joinery | 40 | 7 February 2025 8:00 AM | 25 March 2025 5:00 PM | 727 | 735 | 7 February 2025 8:00 AM | 2025-03-27 17:00 | 2 | Surveyor | 93 | 47 | 18 | 68 | 3
735 | 1.2.4.3.7.4.14 | Install Joinery | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733,734 | 737 | 3 April 2025 8:00 AM | 2025-04-11 17:00 | 0 | Metal Work | 33 | 64 | 34 | 18 | 26
736 | 1.2.4.3.7.4.15 | Measure & Manufacture Stone Benchtops | 12 | 29 March 2025 8:00 AM | 12 April 2025 8:00 AM | 737SF | 746 | 29 March 2025 8:00 AM | 2025-04-13 08:00 | 1 | Contract Administrator | 28 | 29 | 17 | 24 | 36
737 | 1.2.4.3.7.4.16 | Install Stone Benchtops | 6 | 12 April 2025 8:00 AM | 22 April 2025 5:00 PM | 735 | 736SF,738 | 12 April 2025 8:00 AM | 2025-04-22 17:00 | 0 | Renderer | 75 | 98 | 34 | 94 | 13
738 | 1.2.4.3.7.4.17 | Fixtures & Fittings Fit-off | 7 | 23 April 2025 8:00 AM | 2 May 2025 5:00 PM | 737 | 746 | 23 April 2025 8:00 AM | 2025-05-02 17:00 | 0 | Foreman | 5 | 18 | 26 | 40 | 24
739 | 1.2.4.3.7.4.18 | Carpentry fitoff (Skirtings, Doors, etc) | 8 | 3 April 2025 8:00 AM | 11 April 2025 5:00 PM | 733 | 741 | 3 April 2025 8:00 AM | 2025-04-11 17:00 | 0 | Mechanical | 89 | 32 | 34 | 96 | 55
740 | 1.2.4.3.7.4.19 | Lighting Fit-off | 5 | 3 April 2025 8:00 AM | 8 April 2025 5:00 PM | 733 | 741 | 3 April 2025 8:00 AM | 2025-04-11 17:00 | 3 | Hoarding | 10 | 41 | 27 | 65 | 20
741 | 1.2.4.3.7.4.20 | Setting Defects | 4 | 12 April 2025 8:00 AM | 16 April 2025 5:00 PM | 739,740 | 742 | 12 April 2025 8:00 AM | 2025-04-17 17:00 | 1 | Cleaner | 47 | 46 | 27 | 81 | 59
742 | 1.2.4.3.7.4.21 | Paint Finish Coat | 4 | 17 April 2025 8:00 AM | 24 April 2025 5:00 PM | 741 | 745,743 | 17 April 2025 8:00 AM | 2025-04-24 17:00 | 0 | Cleaner | 76 | 40 | 31 | 56 | 23
743 | 1.2.4.3.7.4.22 | Carpet | 3 | 28 April 2025 8:00 AM | 30 April 2025 5:00 PM | 742 | 744 | 28 April 2025 8:00 AM | 2025-05-01 17:00 | 1 | Contract Administrator | 19 | 60 | 24 | 92 | 22
744 | 1.2.4.3.7.4.23 | Final Clean & Commissioning | 4 | 1 May 2025 8:00 AM | 5 May 2025 5:00 PM | 743 | 746 | 1 May 2025 8:00 AM | 2025-05-07 17:00 | 2 | Painter | 16 | 21 | 14 | 10 | 5
745 | 1.2.4.3.7.4.24 | Defects Inspections & Rectifications | 6 | 28 April 2025 8:00 AM | 3 May 2025 5:00 PM | 742 | 746 | 28 April 2025 8:00 AM | 2025-05-05 17:00 | 2 | Window | 8 | 75 | 11 | 92 | 36
746 | 1.2.4.3.7.5 | LVL 7 - FITOUT COMPLETE | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 738,745,744,736 | 5,754 | 5 May 2025 5:00 PM | 2025-05-07 17:00 | 2 | Tiler | 79 | 91 | 16 | 37 | 46
747 | 1.2.4.3.8 | Lvl 8 (Roof) - Services | 96 | 7 January 2025 8:00 AM | 5 May 2025 5:00 PM |  |  | 7 January 2025 8:00 AM | 2025-05-05 17:00 | 0 | Concretor | 70 | 62 | 35 | 34 | 55
748 | 1.2.4.3.8.1 | Survey & Setout | 1 | 7 January 2025 8:00 AM | 7 January 2025 5:00 PM | 301FS+24d | 749FS-1d | 7 January 2025 8:00 AM | 2025-01-09 17:00 | 2 | Tiler | 84 | 41 | 11 | 98 | 58
749 | 1.2.4.3.8.2 | Concrete Rectifications (Wet Areas, Hobs & Setdowns) | 4 | 7 January 2025 8:00 AM | 10 January 2025 5:00 PM | 748FS-1d | 751 | 7 January 2025 8:00 AM | 2025-01-14 17:00 | 4 | Plasterboarder | 34 | 65 | 17 | 27 | 3
750 | 1.2.4.3.8.3 | External Services (Plant) | 56 | 11 January 2025 8:00 AM | 18 March 2025 5:00 PM |  |  | 11 January 2025 8:00 AM | 2025-03-20 17:00 | 2 | Excavation | 33 | 60 | 26 | 27 | 19
751 | 1.2.4.3.8.3.1 | Heat Pumps & Associated Services | 32 | 11 January 2025 8:00 AM | 18 February 2025 5:00 PM | 749 | 752 | 11 January 2025 8:00 AM | 2025-02-20 17:00 | 2 | Reinforcement Fixer | 36 | 95 | 29 | 53 | 54
752 | 1.2.4.3.8.3.2 | Louvres, Balustrades & Roof Safety System | 24 | 19 February 2025 8:00 AM | 18 March 2025 5:00 PM | 751 | 753 | 19 February 2025 8:00 AM | 2025-03-20 17:00 | 2 | Subcontractor | 76 | 31 | 25 | 38 | 47
753 | 1.2.4.3.8.4 | LVL 8 (ROOF) - FITOUT COMPLETE | 0 | 22 April 2025 5:00 PM | 22 April 2025 5:00 PM | 752,655,628 | 5,754 | 22 April 2025 5:00 PM | 2025-04-26 17:00 | 4 | Fire | 12 | 33 | 19 | 1 | 35
754 | 1.2.4.3.8.5 | Building A Fitout Complete | 0 | 5 May 2025 5:00 PM | 5 May 2025 5:00 PM | 753,746 |  | 5 May 2025 5:00 PM | 2025-05-05 17:00 | 0 | Head Contractor | 52 | 97 | 13 | 52 | 6
755 | 1.2.4.4 | Building B | 135 | 14 October 2024 8:00 AM | 29 March 2025 5:00 PM |  | 3440 | 14 October 2024 8:00 AM | 2025-04-01 17:00 | 3 | Stone Mason | 23 | 13 | 24 | 92 | 10
756 | 1.2.4.4.1 | Level 1 | 52 | 14 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | 14 October 2024 8:00 AM | 2024-12-13 17:00 | 1 | Carpet | 71 | 66 | 33 | 49 | 52
757 | 1.2.4.4.1.1 | Apartment B010 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | 14 October 2024 8:00 AM | 2024-12-08 17:00 | 3 | Renderer | 10 | 32 | 12 | 22 | 36
758 | 1.2.4.4.1.1.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 759,762,763,830 | 14 October 2024 8:00 AM | 2024-10-19 17:00 | 4 | Electrician | 82 | 85 | 16 | 54 | 39
759 | 1.2.4.4.1.1.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 758 | 761,760 | 16 October 2024 8:00 AM | 2024-10-16 17:00 | 0 | Painter | 47 | 87 | 11 | 1 | 41
760 | 1.2.4.4.1.1.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 759 |  | 17 October 2024 8:00 AM | 2024-10-20 17:00 | 2 | Metal Work | 54 | 92 | 18 | 75 | 46
761 | 1.2.4.4.1.1.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 759 | 764 | 17 October 2024 8:00 AM | 2024-10-20 17:00 | 1 | Project Manager | 31 | 99 | 19 | 12 | 8
762 | 1.2.4.4.1.1.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 771 | 16 October 2024 8:00 AM | 2024-10-19 17:00 | 1 | Carpenter | 79 | 22 | 27 | 2 | 16
763 | 1.2.4.4.1.1.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 758 | 834 | 16 October 2024 8:00 AM | 2024-10-20 17:00 | 2 | Development Manager | 54 | 30 | 21 | 82 | 25
764 | 1.2.4.4.1.1.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 761 | 765,766,767,768,769 | 21 October 2024 8:00 AM | 2024-10-25 17:00 | 3 | Contract Administrator | 66 | 38 | 31 | 91 | 7
765 | 1.2.4.4.1.1.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769 | 23 October 2024 8:00 AM | 2024-10-27 17:00 | 3 | Development Manager | 85 | 68 | 30 | 71 | 34
766 | 1.2.4.4.1.1.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 769,833 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Timber Floorer | 84 | 18 | 29 | 92 | 18
767 | 1.2.4.4.1.1.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 | 832 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Foreman | 34 | 14 | 23 | 47 | 25
768 | 1.2.4.4.1.1.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 764 |  | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Waterproofer | 3 | 27 | 21 | 49 | 51
769 | 1.2.4.4.1.1.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 764,765,766 | 770 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Timber Floorer | 1 | 78 | 23 | 87 | 16
770 | 1.2.4.4.1.1.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 769 | 771 | 26 October 2024 8:00 AM | 2024-10-29 17:00 | 1 | Tiler | 71 | 44 | 10 | 63 | 44
771 | 1.2.4.4.1.1.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 762,770 | 772,773,774,775,777,779 | 29 October 2024 8:00 AM | 2024-11-01 17:00 | 2 | Contract Administrator | 73 | 29 | 13 | 81 | 33
772 | 1.2.4.4.1.1.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 776,779 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Stone Mason | 17 | 92 | 20 | 44 | 19
773 | 1.2.4.4.1.1.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 779 | 31 October 2024 8:00 AM | 2024-11-04 17:00 | 3 | Scaffolder | 53 | 99 | 32 | 73 | 32
774 | 1.2.4.4.1.1.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 771 | 778,779 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Foreman | 32 | 65 | 11 | 81 | 18
775 | 1.2.4.4.1.1.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 2 | Surveyor | 2 | 21 | 26 | 49 | 39
776 | 1.2.4.4.1.1.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 772 | 779 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 3 | Cleaner | 49 | 14 | 29 | 62 | 24
777 | 1.2.4.4.1.1.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 771 | 779 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 1 | Fire | 83 | 31 | 28 | 89 | 18
778 | 1.2.4.4.1.1.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 774 | 779 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Foreman | 18 | 81 | 12 | 96 | 15
779 | 1.2.4.4.1.1.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 771,772,773,774,775,776,777,778 | 780 | 4 November 2024 8:00 AM | 2024-11-07 17:00 | 3 | Post Tension | 33 | 90 | 14 | 88 | 32
780 | 1.2.4.4.1.1.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 779 | 781 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Joiner | 10 | 38 | 24 | 55 | 48
781 | 1.2.4.4.1.1.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 780 | 782,799,816 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Floor Sealer | 69 | 22 | 30 | 15 | 33
782 | 1.2.4.4.1.1.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 783 | 9 November 2024 8:00 AM | 2024-11-11 17:00 | 2 | Waterproofer | 10 | 77 | 25 | 2 | 58
783 | 1.2.4.4.1.1.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 782 | 784 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Head Contractor | 5 | 62 | 35 | 25 | 13
784 | 1.2.4.4.1.1.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 783 | 785 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Carpet | 64 | 68 | 22 | 63 | 56
785 | 1.2.4.4.1.1.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 784 | 786 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Hoarding | 10 | 23 | 11 | 97 | 19
786 | 1.2.4.4.1.1.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 785 | 787,788 | 15 November 2024 8:00 AM | 2024-11-20 17:00 | 5 | Landscaper | 15 | 54 | 31 | 76 | 3
787 | 1.2.4.4.1.1.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 786 | 791 | 16 November 2024 8:00 AM | 2024-11-19 17:00 | 1 | Window | 55 | 81 | 20 | 66 | 18
788 | 1.2.4.4.1.1.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 786 | 789 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Metal Work | 4 | 41 | 24 | 2 | 57
789 | 1.2.4.4.1.1.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 788 | 790 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 3 | Painter | 5 | 10 | 26 | 55 | 60
790 | 1.2.4.4.1.1.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 789 |  | 19 November 2024 8:00 AM | 2024-11-22 17:00 | 3 | Development Manager | 82 | 92 | 26 | 36 | 21
791 | 1.2.4.4.1.1.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 787 | 792,793,794,795,796 | 19 November 2024 8:00 AM | 2024-11-23 17:00 | 3 | Site Manager | 86 | 46 | 15 | 77 | 46
792 | 1.2.4.4.1.1.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 791 |  | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Renderer | 88 | 93 | 30 | 80 | 45
793 | 1.2.4.4.1.1.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Plumber | 91 | 71 | 24 | 58 | 5
794 | 1.2.4.4.1.1.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Floor Sealer | 81 | 100 | 23 | 41 | 4
795 | 1.2.4.4.1.1.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Waterproofer | 60 | 80 | 13 | 16 | 58
796 | 1.2.4.4.1.1.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 791 | 847 | 21 November 2024 8:00 AM | 2024-11-28 17:00 | 6 | Stone Mason | 79 | 36 | 14 | 99 | 23
797 | 1.2.4.4.1.1.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 847 | 9 November 2024 8:00 AM | 2024-12-01 17:00 | 1 | Electrician | 54 | 25 | 35 | 34 | 36
798 | 1.2.4.4.1.1.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-12-04 17:00 | 4 | Hoarding | 81 | 90 | 28 | 90 | 32
799 | 1.2.4.4.1.1.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 800 | 9 November 2024 8:00 AM | 2024-11-11 17:00 | 2 | Window | 73 | 97 | 27 | 14 | 10
800 | 1.2.4.4.1.1.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 799 | 801 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Concretor | 90 | 15 | 24 | 52 | 9
801 | 1.2.4.4.1.1.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 800 | 802 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Mechanical | 72 | 67 | 19 | 84 | 29
802 | 1.2.4.4.1.1.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 801 | 803 | 14 November 2024 8:00 AM | 2024-11-18 17:00 | 4 | Scaffolder | 15 | 13 | 27 | 48 | 47
803 | 1.2.4.4.1.1.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 802 | 804 | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Excavation | 20 | 10 | 19 | 19 | 26
804 | 1.2.4.4.1.1.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 803 | 805 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 1 | Plumber | 49 | 26 | 15 | 76 | 17
805 | 1.2.4.4.1.1.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 804 | 806 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Waterproofer | 20 | 58 | 24 | 36 | 46
806 | 1.2.4.4.1.1.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 805 | 807 | 22 November 2024 8:00 AM | 2024-11-28 17:00 | 6 | Window | 9 | 35 | 20 | 92 | 7
807 | 1.2.4.4.1.1.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 806 | 808 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Tiler | 90 | 70 | 19 | 69 | 51
808 | 1.2.4.4.1.1.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 807 | 809 | 25 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Timber Floorer | 88 | 72 | 30 | 56 | 15
809 | 1.2.4.4.1.1.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 808 | 810 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Project Manager | 89 | 50 | 27 | 44 | 11
810 | 1.2.4.4.1.1.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 809 | 814,811,812,813 | 27 November 2024 8:00 AM | 2024-11-29 17:00 | 2 | Landscaper | 29 | 83 | 22 | 90 | 7
811 | 1.2.4.4.1.1.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | 28 November 2024 8:00 AM | 2024-12-01 17:00 | 2 | Plumber | 95 | 97 | 29 | 7 | 5
812 | 1.2.4.4.1.1.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | 28 November 2024 8:00 AM | 2024-11-30 17:00 | 1 | Admin | 61 | 72 | 29 | 94 | 42
813 | 1.2.4.4.1.1.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 810 | 814 | 28 November 2024 8:00 AM | 2024-12-02 17:00 | 3 | Excavation | 15 | 40 | 15 | 83 | 22
814 | 1.2.4.4.1.1.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 810,811,812,813 |  | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Hoarding | 77 | 12 | 14 | 17 | 51
815 | 1.2.4.4.1.1.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Renderer | 14 | 13 | 25 | 64 | 40
816 | 1.2.4.4.1.1.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 781 | 817 | 9 November 2024 8:00 AM | 2024-11-10 17:00 | 1 | Hoarding | 10 | 31 | 19 | 79 | 54
817 | 1.2.4.4.1.1.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 816 | 818 | 11 November 2024 8:00 AM | 2024-11-13 17:00 | 2 | Development Manager | 51 | 15 | 25 | 4 | 49
818 | 1.2.4.4.1.1.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 817 | 819 | 12 November 2024 8:00 AM | 2024-11-15 17:00 | 2 | Waterproofer | 22 | 64 | 34 | 24 | 34
819 | 1.2.4.4.1.1.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 818 | 820 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Reinforcement Fixer | 61 | 55 | 22 | 68 | 14
820 | 1.2.4.4.1.1.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 819 | 821 | 15 November 2024 8:00 AM | 2024-11-19 17:00 | 3 | Window | 85 | 84 | 18 | 61 | 58
821 | 1.2.4.4.1.1.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 820 | 822 | 18 November 2024 8:00 AM | 2024-11-22 17:00 | 2 | Site Manager | 57 | 16 | 25 | 74 | 46
822 | 1.2.4.4.1.1.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 821 | 823 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 1 | Floor Sealer | 90 | 18 | 26 | 65 | 32
823 | 1.2.4.4.1.1.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 822 | 824,825,826,827 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 1 | Mechanical | 14 | 56 | 22 | 1 | 25
824 | 1.2.4.4.1.1.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Tiler | 62 | 43 | 24 | 42 | 50
825 | 1.2.4.4.1.1.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 2 | Concretor | 82 | 100 | 10 | 96 | 49
826 | 1.2.4.4.1.1.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Head Contractor | 96 | 54 | 34 | 25 | 17
827 | 1.2.4.4.1.1.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 823 | 828 | 23 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Carpenter | 13 | 92 | 27 | 75 | 43
828 | 1.2.4.4.1.1.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 824,825,826,827 |  | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 1 | Cleaner | 57 | 70 | 14 | 96 | 27
829 | 1.2.4.4.1.1.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-11-12 17:00 | 1 | Renderer | 85 | 59 | 11 | 42 | 28
830 | 1.2.4.4.1.1.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 758 | 831 | 16 October 2024 8:00 AM | 2024-10-17 17:00 | 0 | Contract Administrator | 33 | 41 | 27 | 76 | 31
831 | 1.2.4.4.1.1.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 830 |  | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Site Manager | 76 | 78 | 29 | 100 | 6
832 | 1.2.4.4.1.1.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 767 | 835 | 25 October 2024 8:00 AM | 2024-10-28 17:00 | 3 | Stone Mason | 98 | 12 | 24 | 2 | 60
833 | 1.2.4.4.1.1.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 766 | 835 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Contract Administrator | 41 | 21 | 28 | 24 | 57
834 | 1.2.4.4.1.1.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 763 | 835 | 19 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Renderer | 73 | 83 | 35 | 56 | 23
835 | 1.2.4.4.1.1.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 832,833,834 | 836 | 26 October 2024 8:00 AM | 2024-10-27 17:00 | 1 | Fire | 98 | 82 | 18 | 43 | 25
836 | 1.2.4.4.1.1.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 835 | 837 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 1 | Admin | 94 | 84 | 14 | 34 | 28
837 | 1.2.4.4.1.1.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 836 | 838 | 29 October 2024 8:00 AM | 2024-10-31 17:00 | 1 | Line Market | 23 | 84 | 23 | 79 | 51
838 | 1.2.4.4.1.1.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 837 | 839 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Contract Administrator | 5 | 52 | 32 | 36 | 27
839 | 1.2.4.4.1.1.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 838 | 840 | 1 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Scaffolder | 46 | 78 | 26 | 17 | 18
840 | 1.2.4.4.1.1.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 839 | 841 | 4 November 2024 8:00 AM | 2024-11-06 17:00 | 1 | Window | 86 | 26 | 35 | 87 | 41
841 | 1.2.4.4.1.1.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 840 | 842 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 2 | Formworker | 2 | 32 | 32 | 93 | 41
842 | 1.2.4.4.1.1.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 841 | 843,844,845,846 | 7 November 2024 8:00 AM | 2024-11-10 17:00 | 1 | Renderer | 24 | 23 | 17 | 93 | 13
843 | 1.2.4.4.1.1.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Stone Mason | 24 | 83 | 18 | 41 | 35
844 | 1.2.4.4.1.1.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-13 17:00 | 2 | Carpet | 18 | 12 | 24 | 34 | 7
845 | 1.2.4.4.1.1.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Stone Mason | 55 | 81 | 29 | 7 | 24
846 | 1.2.4.4.1.1.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 842 |  | 11 November 2024 8:00 AM | 2024-11-12 17:00 | 1 | Timber Floorer | 89 | 89 | 10 | 58 | 49
847 | 1.2.4.4.1.1.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 793,794,795,796,797 | 848 | 2 December 2024 8:00 AM | 2024-12-03 17:00 | 1 | Plumber | 51 | 26 | 20 | 23 | 22
848 | 1.2.4.4.1.1.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 847 | 849 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 1 | Foreman | 72 | 67 | 20 | 68 | 55
849 | 1.2.4.4.1.1.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 848 | 850 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Fire | 23 | 18 | 30 | 34 | 29
850 | 1.2.4.4.1.1.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 849 |  | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Plasterboarder | 50 | 22 | 11 | 71 | 18
851 | 1.2.4.4.1.2 | Apartment B011 | 46 | 14 October 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | 14 October 2024 8:00 AM | 2024-12-06 17:00 | 1 | Formworker | 89 | 42 | 30 | 68 | 27
852 | 1.2.4.4.1.2.1 | External and Intertenancy Wall Framing | 2 | 14 October 2024 8:00 AM | 15 October 2024 5:00 PM | 448 | 853,856,857,924 | 14 October 2024 8:00 AM | 2024-10-16 17:00 | 1 | Subcontractor | 59 | 73 | 33 | 49 | 59
853 | 1.2.4.4.1.2.2 | Waterproofing Wall & Window | 1 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | 852 | 855,854 | 16 October 2024 8:00 AM | 2024-10-20 17:00 | 4 | Line Market | 68 | 34 | 16 | 57 | 25
854 | 1.2.4.4.1.2.3 | External & Intertenancy Wall / Hebal | 2 | 17 October 2024 8:00 AM | 18 October 2024 5:00 PM | 853 |  | 17 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Formworker | 60 | 72 | 14 | 22 | 9
855 | 1.2.4.4.1.2.4 | Windows Install | 3 | 17 October 2024 8:00 AM | 19 October 2024 5:00 PM | 853 | 858 | 17 October 2024 8:00 AM | 2024-10-21 17:00 | 2 | Development Manager | 76 | 50 | 24 | 19 | 48
856 | 1.2.4.4.1.2.5 | Mechanical Overheads | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 865 | 16 October 2024 8:00 AM | 2024-10-19 17:00 | 1 | Post Tension | 33 | 26 | 26 | 19 | 44
857 | 1.2.4.4.1.2.6 | Fire Sprinklers Mains | 3 | 16 October 2024 8:00 AM | 18 October 2024 5:00 PM | 852 | 928 | 16 October 2024 8:00 AM | 2024-10-19 17:00 | 1 | Subcontractor | 62 | 71 | 10 | 26 | 20
858 | 1.2.4.4.1.2.7 | Internal Wall Framing & Door Frames | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 855 | 859,860,861,862,863 | 21 October 2024 8:00 AM | 2024-10-25 17:00 | 3 | Landscaper | 14 | 10 | 35 | 1 | 45
859 | 1.2.4.4.1.2.8 | Mechanical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863 | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 1 | Carpet | 9 | 86 | 13 | 34 | 25
860 | 1.2.4.4.1.2.9 | Plumbing Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 863,927 | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 1 | Line Market | 28 | 34 | 35 | 73 | 22
861 | 1.2.4.4.1.2.10 | Electrical Wall Roughin | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 | 926 | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Site Manager | 50 | 34 | 17 | 74 | 28
862 | 1.2.4.4.1.2.11 | Fire Detection (Dry) | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 858 |  | 23 October 2024 8:00 AM | 2024-10-27 17:00 | 3 | Surveyor | 23 | 42 | 28 | 68 | 39
863 | 1.2.4.4.1.2.12 | Noggin Rough in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 858,859,860 | 864 | 25 October 2024 8:00 AM | 2024-10-27 17:00 | 2 | Project Manager | 1 | 47 | 15 | 21 | 2
864 | 1.2.4.4.1.2.13 | Sheet Walls | 2 | 26 October 2024 8:00 AM | 28 October 2024 5:00 PM | 863 | 865 | 26 October 2024 8:00 AM | 2024-10-30 17:00 | 2 | Site Manager | 75 | 53 | 11 | 99 | 41
865 | 1.2.4.4.1.2.14 | Ceiling Grids | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 856,864 | 866,867,868,869,871,873 | 29 October 2024 8:00 AM | 2024-10-31 17:00 | 1 | Hoarding | 86 | 87 | 12 | 46 | 36
866 | 1.2.4.4.1.2.15 | Electrical Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 870,873 | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 1 | Admin | 88 | 68 | 35 | 73 | 4
867 | 1.2.4.4.1.2.16 | Fire Detection (Dry) | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 873 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Plasterboarder | 24 | 28 | 20 | 20 | 3
868 | 1.2.4.4.1.2.17 | Plumbing Rough-in | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 865 | 872,873 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Stone Mason | 12 | 18 | 21 | 37 | 39
869 | 1.2.4.4.1.2.18 | Fire Sprinklers Droppers | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Waterproofer | 81 | 91 | 17 | 7 | 45
870 | 1.2.4.4.1.2.19 | Fire Rating Electrical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 866 | 873 | 2 November 2024 8:00 AM | 2024-11-03 17:00 | 1 | Scaffolder | 0 | 13 | 24 | 8 | 3
871 | 1.2.4.4.1.2.20 | Fire Rating Mechanical | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 865 | 873 | 31 October 2024 8:00 AM | 2024-11-02 17:00 | 2 | Waterproofer | 26 | 83 | 16 | 76 | 25
872 | 1.2.4.4.1.2.21 | Fire Rating Hydraulic | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 868 | 873 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 3 | Surveyor | 56 | 84 | 11 | 12 | 24
873 | 1.2.4.4.1.2.22 | Noggin Rough in | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 865,866,867,868,869,870,871,872 | 874 | 4 November 2024 8:00 AM | 2024-11-05 17:00 | 1 | Hoarding | 18 | 100 | 33 | 18 | 27
874 | 1.2.4.4.1.2.23 | Sheet Ceilings | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 873 | 875 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Contract Administrator | 60 | 95 | 28 | 85 | 32
875 | 1.2.4.4.1.2.24 | Setting / Sanding | 3 | 6 November 2024 8:00 AM | 8 November 2024 5:00 PM | 874 | 876,893,910 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Fire | 13 | 92 | 14 | 100 | 23
876 | 1.2.4.4.1.2.25 | Paint Undercoat (1st Coat) | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 877 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Excavation | 24 | 35 | 14 | 60 | 38
877 | 1.2.4.4.1.2.26 | Paint Undercoat (2nd Coat) | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 876 | 878 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Development Manager | 23 | 40 | 24 | 95 | 24
878 | 1.2.4.4.1.2.27 | Floor Leveling | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 877 | 879 | 12 November 2024 8:00 AM | 2024-11-17 17:00 | 4 | Fire | 60 | 60 | 24 | 8 | 8
879 | 1.2.4.4.1.2.28 | Timber Floor Install | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 878 | 880 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 1 | Head Contractor | 33 | 44 | 15 | 34 | 24
880 | 1.2.4.4.1.2.29 | Joinery Kickers | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 879 | 881,882 | 15 November 2024 8:00 AM | 2024-11-19 17:00 | 4 | Stone Mason | 5 | 78 | 22 | 87 | 58
881 | 1.2.4.4.1.2.30 | Joinery Kitchen | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 880 | 885 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Post Tension | 67 | 24 | 14 | 81 | 17
882 | 1.2.4.4.1.2.31 | Joinery Bedroom | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 880 | 883 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Plumber | 89 | 96 | 14 | 63 | 58
883 | 1.2.4.4.1.2.32 | Door Hanging | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 882 | 884 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 2 | Waterproofer | 75 | 91 | 27 | 11 | 3
884 | 1.2.4.4.1.2.33 | Door Hardware | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 883 |  | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 1 | Reinforcement Fixer | 81 | 57 | 16 | 97 | 17
885 | 1.2.4.4.1.2.34 | Stone Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 881 | 886,887,888,889,890 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Head Contractor | 58 | 34 | 13 | 67 | 52
886 | 1.2.4.4.1.2.35 | Carpentry skirtings | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 885 |  | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Hoarding | 28 | 36 | 11 | 70 | 6
887 | 1.2.4.4.1.2.36 | Hydraulic Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-24 17:00 | 2 | Tiler | 70 | 68 | 22 | 70 | 37
888 | 1.2.4.4.1.2.37 | Electrical Living Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Surveyor | 47 | 28 | 31 | 30 | 40
889 | 1.2.4.4.1.2.38 | Electrical Kitchen Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-23 17:00 | 1 | Site Manager | 50 | 48 | 24 | 66 | 6
890 | 1.2.4.4.1.2.39 | Mechanical Fitoff Install | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 885 | 941 | 21 November 2024 8:00 AM | 2024-11-25 17:00 | 3 | Renderer | 55 | 67 | 33 | 28 | 22
891 | 1.2.4.4.1.2.40 | Internal Wet Areas | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  | 941 | 9 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Carpenter | 62 | 81 | 23 | 75 | 50
892 | 1.2.4.4.1.2.40.1 | Bathrooms | 19 | 9 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-12-02 17:00 | 2 | Floor Sealer | 91 | 27 | 26 | 71 | 7
893 | 1.2.4.4.1.2.40.1.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 894 | 9 November 2024 8:00 AM | 2024-11-10 17:00 | 1 | Contract Administrator | 1 | 29 | 11 | 93 | 22
894 | 1.2.4.4.1.2.40.1.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 893 | 895 | 11 November 2024 8:00 AM | 2024-11-12 17:00 | 1 | Site Manager | 92 | 45 | 26 | 28 | 12
895 | 1.2.4.4.1.2.40.1.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 894 | 896 | 12 November 2024 8:00 AM | 2024-11-18 17:00 | 5 | Foreman | 55 | 55 | 20 | 92 | 58
896 | 1.2.4.4.1.2.40.1.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 895 | 897 | 14 November 2024 8:00 AM | 2024-11-19 17:00 | 5 | Scaffolder | 21 | 88 | 25 | 20 | 19
897 | 1.2.4.4.1.2.40.1.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 896 | 898 | 15 November 2024 8:00 AM | 2024-11-18 17:00 | 2 | Development Manager | 68 | 52 | 18 | 18 | 6
898 | 1.2.4.4.1.2.40.1.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 897 | 899 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Project Manager | 40 | 27 | 21 | 24 | 41
899 | 1.2.4.4.1.2.40.1.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 898 | 900 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Plumber | 35 | 41 | 14 | 79 | 10
900 | 1.2.4.4.1.2.40.1.8 | Joinery Bathroom | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 899 | 901 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Head Contractor | 27 | 46 | 11 | 89 | 52
901 | 1.2.4.4.1.2.40.1.9 | Stone | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 900 | 902 | 23 November 2024 8:00 AM | 2024-11-24 17:00 | 1 | Hoarding | 91 | 30 | 25 | 35 | 3
902 | 1.2.4.4.1.2.40.1.10 | Shower Screens | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 901 | 903 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Electrician | 100 | 53 | 18 | 44 | 36
903 | 1.2.4.4.1.2.40.1.11 | Mirrors | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 902 | 904 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 1 | Carpet | 42 | 66 | 13 | 94 | 40
904 | 1.2.4.4.1.2.40.1.12 | Bathroom Fittings Fitoff | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 903 | 908,905,906,907 | 27 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Landscaper | 40 | 46 | 17 | 65 | 50
905 | 1.2.4.4.1.2.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | 28 November 2024 8:00 AM | 2024-11-30 17:00 | 1 | Scaffolder | 47 | 78 | 24 | 14 | 14
906 | 1.2.4.4.1.2.40.1.14 | Electrical Bathroom Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Stone Mason | 20 | 38 | 24 | 8 | 37
907 | 1.2.4.4.1.2.40.1.15 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 904 | 908 | 28 November 2024 8:00 AM | 2024-12-01 17:00 | 2 | Painter | 84 | 57 | 16 | 10 | 41
908 | 1.2.4.4.1.2.40.1.16 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 904,905,906,907 |  | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Line Market | 60 | 94 | 26 | 8 | 53
909 | 1.2.4.4.1.2.40.2 | Laundry | 15 | 9 November 2024 8:00 AM | 26 November 2024 5:00 PM |  |  | 9 November 2024 8:00 AM | 2024-11-27 17:00 | 1 | Mechanical | 48 | 96 | 15 | 31 | 42
910 | 1.2.4.4.1.2.40.2.1 | Prepare for Waterproof | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 875 | 911 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Scaffolder | 1 | 70 | 34 | 81 | 27
911 | 1.2.4.4.1.2.40.2.2 | Install Angles | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 910 | 912 | 11 November 2024 8:00 AM | 2024-11-12 17:00 | 1 | Line Market | 32 | 10 | 31 | 53 | 46
912 | 1.2.4.4.1.2.40.2.3 | Waterproof | 2 | 12 November 2024 8:00 AM | 13 November 2024 5:00 PM | 911 | 913 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Joiner | 31 | 19 | 34 | 27 | 60
913 | 1.2.4.4.1.2.40.2.4 | Water Testing | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 912 | 914 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Line Market | 66 | 14 | 28 | 65 | 48
914 | 1.2.4.4.1.2.40.2.5 | Tile Bed and Cure | 2 | 15 November 2024 8:00 AM | 16 November 2024 5:00 PM | 913 | 915 | 15 November 2024 8:00 AM | 2024-11-21 17:00 | 5 | Surveyor | 11 | 33 | 24 | 0 | 14
915 | 1.2.4.4.1.2.40.2.6 | Tile Wall & Floor | 3 | 18 November 2024 8:00 AM | 20 November 2024 5:00 PM | 914 | 916 | 18 November 2024 8:00 AM | 2024-11-22 17:00 | 2 | Renderer | 31 | 54 | 12 | 75 | 30
916 | 1.2.4.4.1.2.40.2.7 | Grout | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 915 | 917 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 1 | Carpet | 36 | 17 | 19 | 39 | 56
917 | 1.2.4.4.1.2.40.2.8 | Joinery Laundry | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 916 | 918,919,920,921 | 22 November 2024 8:00 AM | 2024-11-25 17:00 | 3 | Cleaner | 89 | 48 | 12 | 41 | 33
918 | 1.2.4.4.1.2.40.2.9 | Laundry Fittings Fitoff | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-24 17:00 | 1 | Tiler | 80 | 81 | 16 | 67 | 53
919 | 1.2.4.4.1.2.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Surveyor | 89 | 51 | 16 | 8 | 28
920 | 1.2.4.4.1.2.40.2.11 | Electrical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-27 17:00 | 2 | Tiler | 32 | 11 | 10 | 62 | 10
921 | 1.2.4.4.1.2.40.2.12 | Mechanical Laundry Fitoff | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 917 | 922 | 23 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Reinforcement Fixer | 60 | 48 | 17 | 82 | 26
922 | 1.2.4.4.1.2.40.2.13 | Silicone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 918,919,920,921 |  | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 4 | Stone Mason | 28 | 33 | 10 | 88 | 60
923 | 1.2.4.4.1.2.41 | Balcony | 23 | 16 October 2024 8:00 AM | 11 November 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-11-16 17:00 | 5 | Project Manager | 50 | 48 | 32 | 94 | 30
924 | 1.2.4.4.1.2.41.1 | Balustrade Prep | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 852 | 925 | 16 October 2024 8:00 AM | 2024-10-19 17:00 | 2 | Plasterboarder | 50 | 23 | 20 | 13 | 57
925 | 1.2.4.4.1.2.41.2 | Balustrade Install | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 924 |  | 18 October 2024 8:00 AM | 2024-10-23 17:00 | 4 | Formworker | 70 | 98 | 30 | 88 | 14
926 | 1.2.4.4.1.2.41.3 | Electrical Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 861 | 929 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 1 | Renderer | 30 | 75 | 27 | 60 | 44
927 | 1.2.4.4.1.2.41.4 | Plumbing Rough-in | 1 | 25 October 2024 8:00 AM | 25 October 2024 5:00 PM | 860 | 929 | 25 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Carpenter | 86 | 71 | 35 | 79 | 42
928 | 1.2.4.4.1.2.41.5 | Fire Sprinklers | 1 | 19 October 2024 8:00 AM | 19 October 2024 5:00 PM | 857 | 929 | 19 October 2024 8:00 AM | 2024-10-21 17:00 | 2 | Timber Floorer | 77 | 92 | 19 | 28 | 36
929 | 1.2.4.4.1.2.41.6 | Prepare for Waterproof | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 926,927,928 | 930 | 26 October 2024 8:00 AM | 2024-10-28 17:00 | 2 | Line Market | 74 | 38 | 11 | 62 | 50
930 | 1.2.4.4.1.2.41.7 | Install Angles | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 929 | 931 | 28 October 2024 8:00 AM | 2024-11-02 17:00 | 5 | Joiner | 77 | 15 | 24 | 65 | 6
931 | 1.2.4.4.1.2.41.8 | Waterproof | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 930 | 932 | 29 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Concretor | 10 | 26 | 29 | 74 | 12
932 | 1.2.4.4.1.2.41.9 | Water Testing | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 931 | 933 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Timber Floorer | 55 | 45 | 21 | 28 | 38
933 | 1.2.4.4.1.2.41.10 | Tile Bed and Cure | 2 | 1 November 2024 8:00 AM | 2 November 2024 5:00 PM | 932 | 934 | 1 November 2024 8:00 AM | 2024-11-08 17:00 | 6 | Stone Mason | 32 | 38 | 18 | 1 | 55
934 | 1.2.4.4.1.2.41.11 | Tiling | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 933 | 935 | 4 November 2024 8:00 AM | 2024-11-08 17:00 | 3 | Development Manager | 14 | 16 | 10 | 47 | 29
935 | 1.2.4.4.1.2.41.12 | Grout | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 934 | 936 | 6 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Floor Sealer | 58 | 27 | 33 | 98 | 6
936 | 1.2.4.4.1.2.41.13 | Paint/Cladding | 3 | 7 November 2024 8:00 AM | 9 November 2024 5:00 PM | 935 | 937,938,939,940 | 7 November 2024 8:00 AM | 2024-11-11 17:00 | 2 | Hoarding | 24 | 50 | 29 | 24 | 15
937 | 1.2.4.4.1.2.41.14 | Silicone | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Formworker | 88 | 67 | 16 | 6 | 31
938 | 1.2.4.4.1.2.41.15 | Hydraulic Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-12 17:00 | 1 | Hoarding | 74 | 37 | 14 | 59 | 10
939 | 1.2.4.4.1.2.41.16 | Electrical Fit Off | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-14 17:00 | 3 | Concretor | 53 | 37 | 20 | 91 | 6
940 | 1.2.4.4.1.2.41.17 | Fit Fitoff | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 936 |  | 11 November 2024 8:00 AM | 2024-11-14 17:00 | 3 | Joiner | 45 | 20 | 33 | 64 | 19
941 | 1.2.4.4.1.2.42 | Carpet Install | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 887,888,889,890,891 | 942 | 2 December 2024 8:00 AM | 2024-12-03 17:00 | 1 | Timber Floorer | 56 | 87 | 16 | 30 | 44
942 | 1.2.4.4.1.2.43 | Paint (FINAL Coat) | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 941 | 943 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 1 | Tiler | 66 | 48 | 26 | 45 | 7
943 | 1.2.4.4.1.2.44 | FINAL CLEAN | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 942 | 944 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Renderer | 0 | 89 | 14 | 34 | 15
944 | 1.2.4.4.1.2.45 | UNIT LOCKED | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 943 |  | 5 December 2024 8:00 AM | 2024-12-06 17:00 | 1 | Contract Administrator | 89 | 42 | 11 | 66 | 37
945 | 1.2.4.4.1.3 | Apartment B012 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-12-07 17:00 | 0 | Waterproofer | 30 | 77 | 14 | 33 | 17
946 | 1.2.4.4.1.3.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 947,950,951,1018 | 16 October 2024 8:00 AM | 2024-10-19 17:00 | 2 | Carpet | 71 | 26 | 25 | 71 | 49
947 | 1.2.4.4.1.3.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 946 | 949,948 | 18 October 2024 8:00 AM | 2024-10-18 17:00 | 0 | Waterproofer | 92 | 83 | 20 | 77 | 38
948 | 1.2.4.4.1.3.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 947 |  | 19 October 2024 8:00 AM | 2024-10-22 17:00 | 1 | Surveyor | 45 | 26 | 24 | 88 | 40
949 | 1.2.4.4.1.3.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 947 | 952 | 19 October 2024 8:00 AM | 2024-10-23 17:00 | 1 | Subcontractor | 61 | 42 | 31 | 97 | 4
950 | 1.2.4.4.1.3.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 959 | 18 October 2024 8:00 AM | 2024-10-23 17:00 | 2 | Scaffolder | 71 | 74 | 20 | 73 | 13
951 | 1.2.4.4.1.3.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 946 | 1022 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Electrician | 95 | 41 | 28 | 74 | 57
952 | 1.2.4.4.1.3.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 949 | 953,954,955,956,957 | 23 October 2024 8:00 AM | 2024-10-26 17:00 | 2 | Fire | 58 | 21 | 34 | 13 | 33
953 | 1.2.4.4.1.3.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957 | 25 October 2024 8:00 AM | 2024-10-27 17:00 | 1 | Landscaper | 47 | 86 | 24 | 38 | 21
954 | 1.2.4.4.1.3.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 957,1021 | 25 October 2024 8:00 AM | 2024-10-29 17:00 | 3 | Electrician | 5 | 62 | 22 | 90 | 19
955 | 1.2.4.4.1.3.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 | 1020 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Landscaper | 30 | 37 | 19 | 2 | 56
956 | 1.2.4.4.1.3.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 952 |  | 25 October 2024 8:00 AM | 2024-10-28 17:00 | 2 | Line Market | 58 | 19 | 31 | 22 | 10
957 | 1.2.4.4.1.3.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 952,953,954 | 958 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 1 | Fire | 9 | 65 | 25 | 97 | 41
958 | 1.2.4.4.1.3.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 957 | 959 | 29 October 2024 8:00 AM | 2024-11-02 17:00 | 3 | Floor Sealer | 19 | 56 | 16 | 33 | 39
959 | 1.2.4.4.1.3.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 950,958 | 960,961,962,963,965,967 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Electrician | 54 | 72 | 31 | 25 | 45
960 | 1.2.4.4.1.3.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 964,967 | 2 November 2024 8:00 AM | 2024-11-07 17:00 | 3 | Line Market | 96 | 86 | 29 | 14 | 30
961 | 1.2.4.4.1.3.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 967 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Admin | 23 | 34 | 29 | 43 | 10
962 | 1.2.4.4.1.3.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 959 | 966,967 | 2 November 2024 8:00 AM | 2024-11-07 17:00 | 3 | Electrician | 85 | 99 | 13 | 39 | 9
963 | 1.2.4.4.1.3.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Plasterboarder | 9 | 46 | 13 | 61 | 13
964 | 1.2.4.4.1.3.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 960 | 967 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 1 | Reinforcement Fixer | 71 | 84 | 13 | 66 | 56
965 | 1.2.4.4.1.3.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 959 | 967 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Scaffolder | 10 | 32 | 12 | 34 | 23
966 | 1.2.4.4.1.3.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 962 | 967 | 5 November 2024 8:00 AM | 2024-11-10 17:00 | 5 | Concretor | 27 | 42 | 35 | 81 | 34
967 | 1.2.4.4.1.3.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 959,960,961,962,963,964,965,966 | 968 | 6 November 2024 8:00 AM | 2024-11-13 17:00 | 7 | Hoarding | 21 | 64 | 33 | 76 | 17
968 | 1.2.4.4.1.3.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 967 | 969 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Site Manager | 24 | 94 | 33 | 88 | 22
969 | 1.2.4.4.1.3.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 968 | 970,987,1004 | 8 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Cleaner | 61 | 75 | 29 | 17 | 18
970 | 1.2.4.4.1.3.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 971 | 12 November 2024 8:00 AM | 2024-11-14 17:00 | 2 | Tiler | 100 | 66 | 14 | 42 | 42
971 | 1.2.4.4.1.3.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 970 | 972 | 13 November 2024 8:00 AM | 2024-11-15 17:00 | 2 | Subcontractor | 75 | 49 | 14 | 46 | 58
972 | 1.2.4.4.1.3.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 971 | 973 | 14 November 2024 8:00 AM | 2024-11-17 17:00 | 2 | Plasterboarder | 74 | 56 | 10 | 68 | 6
973 | 1.2.4.4.1.3.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 972 | 974 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Excavation | 17 | 34 | 20 | 30 | 46
974 | 1.2.4.4.1.3.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 973 | 975,976 | 18 November 2024 8:00 AM | 2024-11-24 17:00 | 6 | Mechanical | 52 | 16 | 32 | 93 | 55
975 | 1.2.4.4.1.3.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 974 | 979 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 1 | Fire | 85 | 42 | 34 | 39 | 55
976 | 1.2.4.4.1.3.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 974 | 977 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Timber Floorer | 44 | 52 | 10 | 86 | 20
977 | 1.2.4.4.1.3.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 976 | 978 | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 1 | Subcontractor | 47 | 59 | 29 | 16 | 25
978 | 1.2.4.4.1.3.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 977 |  | 21 November 2024 8:00 AM | 2024-11-23 17:00 | 2 | Excavation | 72 | 91 | 27 | 49 | 5
979 | 1.2.4.4.1.3.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 975 | 980,981,982,983,984 | 21 November 2024 8:00 AM | 2024-11-23 17:00 | 1 | Metal Work | 16 | 86 | 33 | 75 | 41
980 | 1.2.4.4.1.3.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 979 |  | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Carpenter | 55 | 37 | 26 | 4 | 8
981 | 1.2.4.4.1.3.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Contract Administrator | 64 | 44 | 28 | 75 | 7
982 | 1.2.4.4.1.3.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Carpet | 47 | 43 | 17 | 41 | 50
983 | 1.2.4.4.1.3.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Concretor | 42 | 74 | 35 | 45 | 59
984 | 1.2.4.4.1.3.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 979 | 1035 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Carpet | 92 | 91 | 15 | 98 | 28
985 | 1.2.4.4.1.3.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1035 | 12 November 2024 8:00 AM | 2024-12-04 17:00 | 1 | Waterproofer | 31 | 29 | 29 | 71 | 27
986 | 1.2.4.4.1.3.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | 12 November 2024 8:00 AM | 2024-12-05 17:00 | 2 | Renderer | 77 | 40 | 27 | 69 | 55
987 | 1.2.4.4.1.3.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 988 | 12 November 2024 8:00 AM | 2024-11-14 17:00 | 2 | Site Manager | 30 | 16 | 11 | 14 | 21
988 | 1.2.4.4.1.3.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 987 | 989 | 13 November 2024 8:00 AM | 2024-11-14 17:00 | 1 | Admin | 58 | 81 | 25 | 75 | 27
989 | 1.2.4.4.1.3.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 988 | 990 | 14 November 2024 8:00 AM | 2024-11-18 17:00 | 3 | Foreman | 42 | 75 | 12 | 26 | 60
990 | 1.2.4.4.1.3.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 989 | 991 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Formworker | 97 | 12 | 31 | 40 | 41
991 | 1.2.4.4.1.3.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 990 | 992 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Formworker | 6 | 53 | 17 | 68 | 19
992 | 1.2.4.4.1.3.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 991 | 993 | 20 November 2024 8:00 AM | 2024-11-24 17:00 | 2 | Subcontractor | 91 | 77 | 31 | 35 | 56
993 | 1.2.4.4.1.3.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 992 | 994 | 23 November 2024 8:00 AM | 2024-11-27 17:00 | 4 | Timber Floorer | 49 | 38 | 35 | 61 | 43
994 | 1.2.4.4.1.3.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 993 | 995 | 25 November 2024 8:00 AM | 2024-12-01 17:00 | 6 | Concretor | 93 | 41 | 24 | 10 | 28
995 | 1.2.4.4.1.3.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 994 | 996 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 1 | Metal Work | 54 | 22 | 18 | 14 | 50
996 | 1.2.4.4.1.3.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 995 | 997 | 27 November 2024 8:00 AM | 2024-12-02 17:00 | 5 | Joiner | 58 | 61 | 27 | 31 | 30
997 | 1.2.4.4.1.3.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 996 | 998 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 1 | Post Tension | 94 | 33 | 25 | 7 | 5
998 | 1.2.4.4.1.3.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 997 | 1002,999,1000,1001 | 29 November 2024 8:00 AM | 2024-11-30 17:00 | 1 | Subcontractor | 10 | 78 | 27 | 97 | 52
999 | 1.2.4.4.1.3.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Timber Floorer | 92 | 57 | 35 | 11 | 42
1000 | 1.2.4.4.1.3.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | 30 November 2024 8:00 AM | 2024-12-04 17:00 | 2 | Mechanical | 60 | 24 | 10 | 62 | 56
1001 | 1.2.4.4.1.3.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 998 | 1002 | 30 November 2024 8:00 AM | 2024-12-03 17:00 | 1 | Reinforcement Fixer | 49 | 77 | 18 | 100 | 6
1002 | 1.2.4.4.1.3.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 998,999,1000,1001 |  | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Cleaner | 40 | 86 | 35 | 71 | 50
1003 | 1.2.4.4.1.3.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | 12 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Fire | 23 | 56 | 12 | 79 | 18
1004 | 1.2.4.4.1.3.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 969 | 1005 | 12 November 2024 8:00 AM | 2024-11-13 17:00 | 1 | Admin | 50 | 39 | 25 | 66 | 31
1005 | 1.2.4.4.1.3.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1004 | 1006 | 13 November 2024 8:00 AM | 2024-11-14 17:00 | 1 | Admin | 84 | 96 | 28 | 85 | 29
1006 | 1.2.4.4.1.3.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1005 | 1007 | 14 November 2024 8:00 AM | 2024-11-17 17:00 | 2 | Mechanical | 30 | 56 | 29 | 32 | 39
1007 | 1.2.4.4.1.3.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1006 | 1008 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Excavation | 26 | 30 | 27 | 31 | 43
1008 | 1.2.4.4.1.3.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1007 | 1009 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 1 | Contract Administrator | 87 | 24 | 13 | 84 | 38
1009 | 1.2.4.4.1.3.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1008 | 1010 | 20 November 2024 8:00 AM | 2024-11-23 17:00 | 1 | Floor Sealer | 83 | 77 | 21 | 92 | 11
1010 | 1.2.4.4.1.3.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1009 | 1011 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Electrician | 67 | 88 | 28 | 70 | 30
1011 | 1.2.4.4.1.3.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1010 | 1012,1013,1014,1015 | 25 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Development Manager | 59 | 27 | 32 | 28 | 26
1012 | 1.2.4.4.1.3.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Subcontractor | 96 | 93 | 13 | 29 | 6
1013 | 1.2.4.4.1.3.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-29 17:00 | 3 | Reinforcement Fixer | 12 | 40 | 15 | 48 | 52
1014 | 1.2.4.4.1.3.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Head Contractor | 92 | 27 | 21 | 14 | 9
1015 | 1.2.4.4.1.3.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1011 | 1016 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Painter | 100 | 28 | 34 | 94 | 24
1016 | 1.2.4.4.1.3.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1012,1013,1014,1015 |  | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 1 | Renderer | 64 | 67 | 32 | 97 | 32
1017 | 1.2.4.4.1.3.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | 18 October 2024 8:00 AM | 2024-11-13 17:00 | 0 | Metal Work | 7 | 80 | 10 | 26 | 46
1018 | 1.2.4.4.1.3.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 946 | 1019 | 18 October 2024 8:00 AM | 2024-10-23 17:00 | 4 | Carpenter | 39 | 44 | 17 | 93 | 31
1019 | 1.2.4.4.1.3.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1018 |  | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Reinforcement Fixer | 82 | 53 | 28 | 21 | 13
1020 | 1.2.4.4.1.3.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 955 | 1023 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 1 | Site Manager | 41 | 72 | 13 | 58 | 3
1021 | 1.2.4.4.1.3.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 954 | 1023 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Site Manager | 78 | 20 | 23 | 35 | 8
1022 | 1.2.4.4.1.3.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 951 | 1023 | 22 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Floor Sealer | 27 | 60 | 32 | 27 | 46
1023 | 1.2.4.4.1.3.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1020,1021,1022 | 1024 | 29 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Post Tension | 96 | 91 | 16 | 21 | 22
1024 | 1.2.4.4.1.3.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1023 | 1025 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 1 | Joiner | 85 | 16 | 12 | 99 | 23
1025 | 1.2.4.4.1.3.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1024 | 1026 | 31 October 2024 8:00 AM | 2024-11-04 17:00 | 3 | Scaffolder | 92 | 38 | 10 | 96 | 18
1026 | 1.2.4.4.1.3.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1025 | 1027 | 2 November 2024 8:00 AM | 2024-11-03 17:00 | 1 | Contract Administrator | 4 | 100 | 27 | 17 | 21
1027 | 1.2.4.4.1.3.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1026 | 1028 | 4 November 2024 8:00 AM | 2024-11-08 17:00 | 3 | Stone Mason | 58 | 14 | 30 | 79 | 22
1028 | 1.2.4.4.1.3.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1027 | 1029 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 1 | Excavation | 94 | 69 | 17 | 77 | 11
1029 | 1.2.4.4.1.3.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1028 | 1030 | 8 November 2024 8:00 AM | 2024-11-09 17:00 | 1 | Line Market | 98 | 28 | 17 | 58 | 38
1030 | 1.2.4.4.1.3.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1029 | 1031,1032,1033,1034 | 9 November 2024 8:00 AM | 2024-11-15 17:00 | 3 | Concretor | 29 | 95 | 31 | 89 | 56
1031 | 1.2.4.4.1.3.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Concretor | 32 | 60 | 17 | 5 | 27
1032 | 1.2.4.4.1.3.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Landscaper | 59 | 83 | 18 | 86 | 60
1033 | 1.2.4.4.1.3.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Project Manager | 30 | 46 | 26 | 32 | 47
1034 | 1.2.4.4.1.3.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1030 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Stone Mason | 96 | 17 | 11 | 0 | 56
1035 | 1.2.4.4.1.3.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 981,982,983,984,985 | 1036 | 4 December 2024 8:00 AM | 2024-12-05 17:00 | 1 | Post Tension | 38 | 69 | 21 | 48 | 51
1036 | 1.2.4.4.1.3.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1035 | 1037 | 5 December 2024 8:00 AM | 2024-12-06 17:00 | 1 | Landscaper | 36 | 73 | 16 | 92 | 42
1037 | 1.2.4.4.1.3.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1036 | 1038 | 6 December 2024 8:00 AM | 2024-12-09 17:00 | 3 | Tiler | 34 | 19 | 20 | 54 | 45
1038 | 1.2.4.4.1.3.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1037 |  | 7 December 2024 8:00 AM | 2024-12-08 17:00 | 1 | Renderer | 82 | 55 | 18 | 47 | 13
1039 | 1.2.4.4.1.4 | Apartment B013 | 46 | 16 October 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | 16 October 2024 8:00 AM | 2024-12-08 17:00 | 1 | Head Contractor | 68 | 25 | 35 | 22 | 42
1040 | 1.2.4.4.1.4.1 | External and Intertenancy Wall Framing | 2 | 16 October 2024 8:00 AM | 17 October 2024 5:00 PM | 448FS+2d | 1041,1044,1045,1112 | 16 October 2024 8:00 AM | 2024-10-18 17:00 | 1 | Fire | 49 | 85 | 34 | 10 | 12
1041 | 1.2.4.4.1.4.2 | Waterproofing Wall & Window | 1 | 18 October 2024 8:00 AM | 18 October 2024 5:00 PM | 1040 | 1043,1042 | 18 October 2024 8:00 AM | 2024-10-23 17:00 | 5 | Contract Administrator | 19 | 95 | 16 | 54 | 23
1042 | 1.2.4.4.1.4.3 | External & Intertenancy Wall / Hebal | 2 | 19 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1041 |  | 19 October 2024 8:00 AM | 2024-10-24 17:00 | 3 | Carpet | 70 | 79 | 11 | 96 | 54
1043 | 1.2.4.4.1.4.4 | Windows Install | 3 | 19 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1041 | 1046 | 19 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Joiner | 35 | 94 | 15 | 5 | 47
1044 | 1.2.4.4.1.4.5 | Mechanical Overheads | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1053 | 18 October 2024 8:00 AM | 2024-10-24 17:00 | 3 | Reinforcement Fixer | 93 | 59 | 25 | 82 | 55
1045 | 1.2.4.4.1.4.6 | Fire Sprinklers Mains | 3 | 18 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1040 | 1116 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 0 | Surveyor | 44 | 57 | 18 | 84 | 19
1046 | 1.2.4.4.1.4.7 | Internal Wall Framing & Door Frames | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1043 | 1047,1048,1049,1050,1051 | 23 October 2024 8:00 AM | 2024-10-27 17:00 | 3 | Carpenter | 89 | 49 | 13 | 8 | 41
1047 | 1.2.4.4.1.4.8 | Mechanical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051 | 25 October 2024 8:00 AM | 2024-10-28 17:00 | 2 | Development Manager | 96 | 47 | 20 | 61 | 45
1048 | 1.2.4.4.1.4.9 | Plumbing Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1051,1115 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Tiler | 35 | 20 | 23 | 75 | 33
1049 | 1.2.4.4.1.4.10 | Electrical Wall Roughin | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 | 1114 | 25 October 2024 8:00 AM | 2024-10-30 17:00 | 4 | Plumber | 50 | 78 | 15 | 66 | 28
1050 | 1.2.4.4.1.4.11 | Fire Detection (Dry) | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1046 |  | 25 October 2024 8:00 AM | 2024-10-28 17:00 | 2 | Scaffolder | 0 | 38 | 32 | 6 | 45
1051 | 1.2.4.4.1.4.12 | Noggin Rough in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1046,1047,1048 | 1052 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 1 | Carpet | 60 | 89 | 31 | 44 | 4
1052 | 1.2.4.4.1.4.13 | Sheet Walls | 2 | 29 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1051 | 1053 | 29 October 2024 8:00 AM | 2024-10-31 17:00 | 1 | Head Contractor | 49 | 96 | 12 | 16 | 38
1053 | 1.2.4.4.1.4.14 | Ceiling Grids | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1044,1052 | 1054,1055,1056,1057,1059,1061 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Carpet | 63 | 71 | 24 | 14 | 6
1054 | 1.2.4.4.1.4.15 | Electrical Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1058,1061 | 2 November 2024 8:00 AM | 2024-11-10 17:00 | 6 | Landscaper | 99 | 34 | 24 | 2 | 20
1055 | 1.2.4.4.1.4.16 | Fire Detection (Dry) | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1061 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Contract Administrator | 1 | 67 | 18 | 58 | 27
1056 | 1.2.4.4.1.4.17 | Plumbing Rough-in | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1053 | 1060,1061 | 2 November 2024 8:00 AM | 2024-11-07 17:00 | 3 | Metal Work | 60 | 93 | 13 | 70 | 36
1057 | 1.2.4.4.1.4.18 | Fire Sprinklers Droppers | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Surveyor | 7 | 40 | 13 | 24 | 55
1058 | 1.2.4.4.1.4.19 | Fire Rating Electrical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1054 | 1061 | 5 November 2024 8:00 AM | 2024-11-07 17:00 | 2 | Window | 4 | 52 | 24 | 89 | 46
1059 | 1.2.4.4.1.4.20 | Fire Rating Mechanical | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1053 | 1061 | 2 November 2024 8:00 AM | 2024-11-03 17:00 | 1 | Contract Administrator | 80 | 81 | 23 | 2 | 3
1060 | 1.2.4.4.1.4.21 | Fire Rating Hydraulic | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1056 | 1061 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Cleaner | 18 | 20 | 24 | 94 | 39
1061 | 1.2.4.4.1.4.22 | Noggin Rough in | 1 | 6 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1053,1054,1055,1056,1057,1058,1059,1060 | 1062 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 2 | Reinforcement Fixer | 73 | 23 | 19 | 87 | 52
1062 | 1.2.4.4.1.4.23 | Sheet Ceilings | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1061 | 1063 | 7 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Development Manager | 32 | 54 | 35 | 66 | 36
1063 | 1.2.4.4.1.4.24 | Setting / Sanding | 3 | 8 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1062 | 1064,1081,1098 | 8 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Development Manager | 19 | 77 | 15 | 54 | 55
1064 | 1.2.4.4.1.4.25 | Paint Undercoat (1st Coat) | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1065 | 12 November 2024 8:00 AM | 2024-11-15 17:00 | 3 | Renderer | 12 | 61 | 31 | 70 | 2
1065 | 1.2.4.4.1.4.26 | Paint Undercoat (2nd Coat) | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1064 | 1066 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Plasterboarder | 0 | 12 | 27 | 83 | 40
1066 | 1.2.4.4.1.4.27 | Floor Leveling | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1065 | 1067 | 14 November 2024 8:00 AM | 2024-11-17 17:00 | 2 | Post Tension | 17 | 40 | 25 | 69 | 26
1067 | 1.2.4.4.1.4.28 | Timber Floor Install | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1066 | 1068 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 2 | Carpet | 33 | 16 | 20 | 20 | 45
1068 | 1.2.4.4.1.4.29 | Joinery Kickers | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1067 | 1069,1070 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Electrician | 9 | 68 | 17 | 82 | 60
1069 | 1.2.4.4.1.4.30 | Joinery Kitchen | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1068 | 1073 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 1 | Joiner | 64 | 80 | 35 | 22 | 23
1070 | 1.2.4.4.1.4.31 | Joinery Bedroom | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1068 | 1071 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Reinforcement Fixer | 12 | 40 | 17 | 31 | 24
1071 | 1.2.4.4.1.4.32 | Door Hanging | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1070 | 1072 | 20 November 2024 8:00 AM | 2024-11-23 17:00 | 3 | Waterproofer | 62 | 48 | 17 | 53 | 3
1072 | 1.2.4.4.1.4.33 | Door Hardware | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1071 |  | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 1 | Window | 93 | 26 | 21 | 5 | 43
1073 | 1.2.4.4.1.4.34 | Stone Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1069 | 1074,1075,1076,1077,1078 | 21 November 2024 8:00 AM | 2024-11-27 17:00 | 5 | Line Market | 30 | 54 | 33 | 90 | 35
1074 | 1.2.4.4.1.4.35 | Carpentry skirtings | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1073 |  | 23 November 2024 8:00 AM | 2024-11-27 17:00 | 4 | Line Market | 79 | 79 | 11 | 13 | 37
1075 | 1.2.4.4.1.4.36 | Hydraulic Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | 23 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Reinforcement Fixer | 52 | 49 | 24 | 92 | 33
1076 | 1.2.4.4.1.4.37 | Electrical Living Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | 23 November 2024 8:00 AM | 2024-11-28 17:00 | 3 | Electrician | 48 | 44 | 27 | 41 | 53
1077 | 1.2.4.4.1.4.38 | Electrical Kitchen Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | 23 November 2024 8:00 AM | 2024-12-01 17:00 | 6 | Post Tension | 84 | 45 | 16 | 26 | 42
1078 | 1.2.4.4.1.4.39 | Mechanical Fitoff Install | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1073 | 1129 | 23 November 2024 8:00 AM | 2024-11-29 17:00 | 4 | Plumber | 45 | 99 | 21 | 51 | 54
1079 | 1.2.4.4.1.4.40 | Internal Wet Areas | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  | 1129 | 12 November 2024 8:00 AM | 2024-12-06 17:00 | 3 | Floor Sealer | 35 | 89 | 35 | 46 | 12
1080 | 1.2.4.4.1.4.40.1 | Bathrooms | 19 | 12 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | 12 November 2024 8:00 AM | 2024-12-04 17:00 | 1 | Timber Floorer | 0 | 98 | 22 | 80 | 36
1081 | 1.2.4.4.1.4.40.1.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1082 | 12 November 2024 8:00 AM | 2024-11-14 17:00 | 2 | Admin | 65 | 92 | 14 | 0 | 53
1082 | 1.2.4.4.1.4.40.1.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1081 | 1083 | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Line Market | 22 | 82 | 22 | 75 | 34
1083 | 1.2.4.4.1.4.40.1.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1082 | 1084 | 14 November 2024 8:00 AM | 2024-11-17 17:00 | 2 | Joiner | 6 | 17 | 13 | 98 | 24
1084 | 1.2.4.4.1.4.40.1.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1083 | 1085 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Waterproofer | 21 | 77 | 13 | 16 | 26
1085 | 1.2.4.4.1.4.40.1.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1084 | 1086 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Plasterboarder | 13 | 60 | 26 | 29 | 7
1086 | 1.2.4.4.1.4.40.1.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1085 | 1087 | 20 November 2024 8:00 AM | 2024-11-25 17:00 | 3 | Subcontractor | 34 | 48 | 33 | 62 | 17
1087 | 1.2.4.4.1.4.40.1.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1086 | 1088 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Metal Work | 68 | 13 | 32 | 71 | 13
1088 | 1.2.4.4.1.4.40.1.8 | Joinery Bathroom | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1087 | 1089 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Renderer | 12 | 19 | 31 | 84 | 54
1089 | 1.2.4.4.1.4.40.1.9 | Stone | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1088 | 1090 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Carpenter | 56 | 17 | 27 | 46 | 8
1090 | 1.2.4.4.1.4.40.1.10 | Shower Screens | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1089 | 1091 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Timber Floorer | 58 | 68 | 21 | 78 | 22
1091 | 1.2.4.4.1.4.40.1.11 | Mirrors | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1090 | 1092 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Site Manager | 65 | 43 | 12 | 5 | 43
1092 | 1.2.4.4.1.4.40.1.12 | Bathroom Fittings Fitoff | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1091 | 1096,1093,1094,1095 | 29 November 2024 8:00 AM | 2024-12-01 17:00 | 2 | Head Contractor | 91 | 31 | 22 | 53 | 13
1093 | 1.2.4.4.1.4.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | 30 November 2024 8:00 AM | 2024-12-03 17:00 | 1 | Admin | 93 | 27 | 27 | 54 | 10
1094 | 1.2.4.4.1.4.40.1.14 | Electrical Bathroom Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Hoarding | 96 | 81 | 12 | 17 | 60
1095 | 1.2.4.4.1.4.40.1.15 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1092 | 1096 | 30 November 2024 8:00 AM | 2024-12-05 17:00 | 3 | Window | 26 | 80 | 31 | 3 | 16
1096 | 1.2.4.4.1.4.40.1.16 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1092,1093,1094,1095 |  | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 1 | Post Tension | 11 | 64 | 30 | 51 | 25
1097 | 1.2.4.4.1.4.40.2 | Laundry | 15 | 12 November 2024 8:00 AM | 28 November 2024 5:00 PM |  |  | 12 November 2024 8:00 AM | 2024-12-04 17:00 | 6 | Development Manager | 73 | 35 | 30 | 38 | 6
1098 | 1.2.4.4.1.4.40.2.1 | Prepare for Waterproof | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1063 | 1099 | 12 November 2024 8:00 AM | 2024-11-14 17:00 | 2 | Tiler | 45 | 58 | 34 | 16 | 9
1099 | 1.2.4.4.1.4.40.2.2 | Install Angles | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1098 | 1100 | 13 November 2024 8:00 AM | 2024-11-16 17:00 | 3 | Project Manager | 28 | 60 | 19 | 77 | 33
1100 | 1.2.4.4.1.4.40.2.3 | Waterproof | 2 | 14 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1099 | 1101 | 14 November 2024 8:00 AM | 2024-11-17 17:00 | 2 | Painter | 21 | 29 | 18 | 71 | 17
1101 | 1.2.4.4.1.4.40.2.4 | Water Testing | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1100 | 1102 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Contract Administrator | 38 | 16 | 22 | 9 | 30
1102 | 1.2.4.4.1.4.40.2.5 | Tile Bed and Cure | 2 | 18 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1101 | 1103 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 2 | Plumber | 8 | 12 | 33 | 61 | 17
1103 | 1.2.4.4.1.4.40.2.6 | Tile Wall & Floor | 3 | 20 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1102 | 1104 | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Stone Mason | 69 | 91 | 15 | 73 | 28
1104 | 1.2.4.4.1.4.40.2.7 | Grout | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1103 | 1105 | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Landscaper | 57 | 81 | 11 | 20 | 17
1105 | 1.2.4.4.1.4.40.2.8 | Joinery Laundry | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1104 | 1106,1107,1108,1109 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Foreman | 17 | 12 | 26 | 83 | 7
1106 | 1.2.4.4.1.4.40.2.9 | Laundry Fittings Fitoff | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Post Tension | 34 | 62 | 20 | 33 | 29
1107 | 1.2.4.4.1.4.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1105 | 1110 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 1 | Hoarding | 9 | 36 | 24 | 59 | 37
1108 | 1.2.4.4.1.4.40.2.11 | Electrical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Excavation | 100 | 93 | 25 | 10 | 26
1109 | 1.2.4.4.1.4.40.2.12 | Mechanical Laundry Fitoff | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1105 | 1110 | 26 November 2024 8:00 AM | 2024-12-01 17:00 | 4 | Painter | 97 | 19 | 30 | 94 | 7
1110 | 1.2.4.4.1.4.40.2.13 | Silicone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1106,1107,1108,1109 |  | 28 November 2024 8:00 AM | 2024-12-01 17:00 | 3 | Development Manager | 23 | 81 | 14 | 45 | 10
1111 | 1.2.4.4.1.4.41 | Balcony | 23 | 18 October 2024 8:00 AM | 13 November 2024 5:00 PM |  |  | 18 October 2024 8:00 AM | 2024-11-15 17:00 | 2 | Landscaper | 90 | 92 | 35 | 4 | 10
1112 | 1.2.4.4.1.4.41.1 | Balustrade Prep | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 1040 | 1113 | 18 October 2024 8:00 AM | 2024-10-21 17:00 | 2 | Electrician | 17 | 51 | 30 | 80 | 10
1113 | 1.2.4.4.1.4.41.2 | Balustrade Install | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1112 |  | 21 October 2024 8:00 AM | 2024-10-23 17:00 | 1 | Development Manager | 72 | 63 | 34 | 74 | 36
1114 | 1.2.4.4.1.4.41.3 | Electrical Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1049 | 1117 | 28 October 2024 8:00 AM | 2024-10-28 17:00 | 0 | Post Tension | 34 | 49 | 34 | 71 | 9
1115 | 1.2.4.4.1.4.41.4 | Plumbing Rough-in | 1 | 28 October 2024 8:00 AM | 28 October 2024 5:00 PM | 1048 | 1117 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 1 | Post Tension | 56 | 11 | 27 | 60 | 36
1116 | 1.2.4.4.1.4.41.5 | Fire Sprinklers | 1 | 22 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1045 | 1117 | 22 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Electrician | 8 | 45 | 18 | 38 | 12
1117 | 1.2.4.4.1.4.41.6 | Prepare for Waterproof | 1 | 29 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1114,1115,1116 | 1118 | 29 October 2024 8:00 AM | 2024-11-02 17:00 | 4 | Surveyor | 68 | 59 | 22 | 65 | 24
1118 | 1.2.4.4.1.4.41.7 | Install Angles | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1117 | 1119 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 1 | Renderer | 25 | 91 | 29 | 20 | 13
1119 | 1.2.4.4.1.4.41.8 | Waterproof | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1118 | 1120 | 31 October 2024 8:00 AM | 2024-11-04 17:00 | 3 | Subcontractor | 51 | 60 | 26 | 97 | 60
1120 | 1.2.4.4.1.4.41.9 | Water Testing | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1119 | 1121 | 2 November 2024 8:00 AM | 2024-11-03 17:00 | 1 | Post Tension | 23 | 57 | 29 | 2 | 32
1121 | 1.2.4.4.1.4.41.10 | Tile Bed and Cure | 2 | 4 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1120 | 1122 | 4 November 2024 8:00 AM | 2024-11-07 17:00 | 2 | Plumber | 3 | 67 | 26 | 12 | 20
1122 | 1.2.4.4.1.4.41.11 | Tiling | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1121 | 1123 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 1 | Hoarding | 79 | 27 | 31 | 61 | 36
1123 | 1.2.4.4.1.4.41.12 | Grout | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1122 | 1124 | 8 November 2024 8:00 AM | 2024-11-10 17:00 | 2 | Contract Administrator | 25 | 12 | 28 | 41 | 37
1124 | 1.2.4.4.1.4.41.13 | Paint/Cladding | 3 | 9 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1123 | 1125,1126,1127,1128 | 9 November 2024 8:00 AM | 2024-11-13 17:00 | 1 | Floor Sealer | 31 | 33 | 34 | 34 | 18
1125 | 1.2.4.4.1.4.41.14 | Silicone | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | 13 November 2024 8:00 AM | 2024-11-15 17:00 | 2 | Mechanical | 96 | 11 | 33 | 7 | 31
1126 | 1.2.4.4.1.4.41.15 | Hydraulic Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | 13 November 2024 8:00 AM | 2024-11-15 17:00 | 2 | Window | 2 | 80 | 30 | 52 | 24
1127 | 1.2.4.4.1.4.41.16 | Electrical Fit Off | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Painter | 60 | 22 | 23 | 79 | 3
1128 | 1.2.4.4.1.4.41.17 | Fit Fitoff | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1124 |  | 13 November 2024 8:00 AM | 2024-11-13 17:00 | 0 | Subcontractor | 6 | 70 | 31 | 6 | 60
1129 | 1.2.4.4.1.4.42 | Carpet Install | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1075,1076,1077,1078,1079 | 1130 | 4 December 2024 8:00 AM | 2024-12-07 17:00 | 3 | Plasterboarder | 77 | 72 | 23 | 81 | 39
1130 | 1.2.4.4.1.4.43 | Paint (FINAL Coat) | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1129 | 1131 | 5 December 2024 8:00 AM | 2024-12-05 17:00 | 0 | Renderer | 10 | 13 | 23 | 59 | 45
1131 | 1.2.4.4.1.4.44 | FINAL CLEAN | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1130 | 1132 | 6 December 2024 8:00 AM | 2024-12-08 17:00 | 2 | Foreman | 21 | 17 | 20 | 100 | 21
1132 | 1.2.4.4.1.4.45 | UNIT LOCKED | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1131 |  | 7 December 2024 8:00 AM | 2024-12-10 17:00 | 3 | Renderer | 6 | 75 | 14 | 23 | 50
1133 | 1.2.4.4.1.5 | Apartment B014 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | 18 October 2024 8:00 AM | 2024-12-10 17:00 | 0 | Joiner | 32 | 96 | 22 | 18 | 47
1134 | 1.2.4.4.1.5.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1135,1138,1139,1206 | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Contract Administrator | 52 | 73 | 12 | 76 | 37
1135 | 1.2.4.4.1.5.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1134 | 1137,1136 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 1 | Formworker | 62 | 97 | 12 | 53 | 47
1136 | 1.2.4.4.1.5.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1135 |  | 22 October 2024 8:00 AM | 2024-10-25 17:00 | 2 | Project Manager | 39 | 17 | 10 | 54 | 29
1137 | 1.2.4.4.1.5.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1135 | 1140 | 22 October 2024 8:00 AM | 2024-10-27 17:00 | 3 | Line Market | 32 | 50 | 26 | 13 | 50
1138 | 1.2.4.4.1.5.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1147 | 21 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Reinforcement Fixer | 32 | 38 | 17 | 19 | 30
1139 | 1.2.4.4.1.5.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1134 | 1210 | 21 October 2024 8:00 AM | 2024-10-24 17:00 | 1 | Site Manager | 100 | 45 | 18 | 63 | 37
1140 | 1.2.4.4.1.5.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1137 | 1141,1142,1143,1144,1145 | 25 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Renderer | 97 | 36 | 13 | 62 | 32
1141 | 1.2.4.4.1.5.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145 | 28 October 2024 8:00 AM | 2024-11-03 17:00 | 5 | Hoarding | 13 | 80 | 33 | 33 | 25
1142 | 1.2.4.4.1.5.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1145,1209 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Project Manager | 81 | 47 | 20 | 87 | 48
1143 | 1.2.4.4.1.5.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 | 1208 | 28 October 2024 8:00 AM | 2024-10-31 17:00 | 2 | Hoarding | 10 | 74 | 16 | 94 | 33
1144 | 1.2.4.4.1.5.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1140 |  | 28 October 2024 8:00 AM | 2024-10-31 17:00 | 2 | Scaffolder | 94 | 77 | 20 | 41 | 40
1145 | 1.2.4.4.1.5.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1140,1141,1142 | 1146 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 1 | Timber Floorer | 63 | 100 | 25 | 96 | 37
1146 | 1.2.4.4.1.5.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1145 | 1147 | 31 October 2024 8:00 AM | 2024-11-01 17:00 | 0 | Electrician | 43 | 54 | 29 | 33 | 48
1147 | 1.2.4.4.1.5.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1138,1146 | 1148,1149,1150,1151,1153,1155 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Cleaner | 32 | 56 | 17 | 58 | 41
1148 | 1.2.4.4.1.5.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1152,1155 | 5 November 2024 8:00 AM | 2024-11-08 17:00 | 2 | Site Manager | 39 | 59 | 13 | 30 | 18
1149 | 1.2.4.4.1.5.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1155 | 5 November 2024 8:00 AM | 2024-11-08 17:00 | 2 | Electrician | 5 | 44 | 25 | 20 | 20
1150 | 1.2.4.4.1.5.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1147 | 1154,1155 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Project Manager | 13 | 84 | 17 | 5 | 56
1151 | 1.2.4.4.1.5.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Waterproofer | 81 | 24 | 32 | 34 | 29
1152 | 1.2.4.4.1.5.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1148 | 1155 | 7 November 2024 8:00 AM | 2024-11-10 17:00 | 3 | Plumber | 23 | 79 | 25 | 93 | 43
1153 | 1.2.4.4.1.5.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1147 | 1155 | 5 November 2024 8:00 AM | 2024-11-08 17:00 | 3 | Stone Mason | 86 | 73 | 35 | 56 | 46
1154 | 1.2.4.4.1.5.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1150 | 1155 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 1 | Hoarding | 58 | 68 | 29 | 38 | 21
1155 | 1.2.4.4.1.5.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1147,1148,1149,1150,1151,1152,1153,1154 | 1156 | 8 November 2024 8:00 AM | 2024-11-09 17:00 | 1 | Waterproofer | 10 | 77 | 31 | 20 | 46
1156 | 1.2.4.4.1.5.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1155 | 1157 | 9 November 2024 8:00 AM | 2024-11-12 17:00 | 3 | Admin | 85 | 33 | 13 | 58 | 36
1157 | 1.2.4.4.1.5.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1156 | 1158,1175,1192 | 11 November 2024 8:00 AM | 2024-11-16 17:00 | 3 | Electrician | 86 | 97 | 21 | 26 | 45
1158 | 1.2.4.4.1.5.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1159 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Contract Administrator | 61 | 24 | 14 | 66 | 55
1159 | 1.2.4.4.1.5.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1158 | 1160 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Admin | 92 | 52 | 34 | 24 | 39
1160 | 1.2.4.4.1.5.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1159 | 1161 | 16 November 2024 8:00 AM | 2024-11-20 17:00 | 2 | Fire | 43 | 38 | 21 | 75 | 15
1161 | 1.2.4.4.1.5.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1160 | 1162 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 2 | Plasterboarder | 90 | 88 | 29 | 27 | 47
1162 | 1.2.4.4.1.5.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1161 | 1163,1164 | 20 November 2024 8:00 AM | 2024-11-22 17:00 | 2 | Formworker | 9 | 29 | 21 | 100 | 32
1163 | 1.2.4.4.1.5.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1162 | 1167 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Scaffolder | 41 | 49 | 14 | 83 | 19
1164 | 1.2.4.4.1.5.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1162 | 1165 | 21 November 2024 8:00 AM | 2024-11-24 17:00 | 3 | Contract Administrator | 88 | 98 | 30 | 15 | 39
1165 | 1.2.4.4.1.5.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1164 | 1166 | 22 November 2024 8:00 AM | 2024-11-25 17:00 | 3 | Development Manager | 60 | 71 | 30 | 37 | 23
1166 | 1.2.4.4.1.5.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1165 |  | 23 November 2024 8:00 AM | 2024-11-26 17:00 | 3 | Project Manager | 30 | 35 | 10 | 60 | 9
1167 | 1.2.4.4.1.5.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1163 | 1168,1169,1170,1171,1172 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Admin | 66 | 88 | 28 | 74 | 12
1168 | 1.2.4.4.1.5.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1167 |  | 26 November 2024 8:00 AM | 2024-11-29 17:00 | 3 | Admin | 57 | 55 | 29 | 3 | 37
1169 | 1.2.4.4.1.5.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | 26 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Admin | 23 | 66 | 13 | 81 | 53
1170 | 1.2.4.4.1.5.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | 26 November 2024 8:00 AM | 2024-11-30 17:00 | 3 | Joiner | 78 | 43 | 24 | 30 | 33
1171 | 1.2.4.4.1.5.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Cleaner | 84 | 35 | 14 | 73 | 8
1172 | 1.2.4.4.1.5.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1167 | 1223 | 26 November 2024 8:00 AM | 2024-11-29 17:00 | 2 | Foreman | 57 | 99 | 14 | 72 | 55
1173 | 1.2.4.4.1.5.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1223 | 14 November 2024 8:00 AM | 2024-12-08 17:00 | 3 | Fire | 92 | 46 | 19 | 94 | 48
1174 | 1.2.4.4.1.5.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | 14 November 2024 8:00 AM | 2024-12-05 17:00 | 0 | Plumber | 89 | 89 | 28 | 26 | 33
1175 | 1.2.4.4.1.5.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1176 | 14 November 2024 8:00 AM | 2024-11-17 17:00 | 3 | Renderer | 64 | 14 | 26 | 7 | 37
1176 | 1.2.4.4.1.5.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1175 | 1177 | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 1 | Formworker | 55 | 88 | 11 | 22 | 3
1177 | 1.2.4.4.1.5.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1176 | 1178 | 16 November 2024 8:00 AM | 2024-11-19 17:00 | 1 | Plumber | 74 | 34 | 24 | 16 | 34
1178 | 1.2.4.4.1.5.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1177 | 1179 | 19 November 2024 8:00 AM | 2024-11-22 17:00 | 3 | Subcontractor | 82 | 77 | 26 | 71 | 3
1179 | 1.2.4.4.1.5.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1178 | 1180 | 20 November 2024 8:00 AM | 2024-11-23 17:00 | 2 | Carpenter | 4 | 87 | 30 | 35 | 51
1180 | 1.2.4.4.1.5.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1179 | 1181 | 22 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Timber Floorer | 86 | 68 | 30 | 93 | 48
1181 | 1.2.4.4.1.5.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1180 | 1182 | 26 November 2024 8:00 AM | 2024-11-28 17:00 | 2 | Carpenter | 34 | 56 | 29 | 80 | 42
1182 | 1.2.4.4.1.5.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1181 | 1183 | 27 November 2024 8:00 AM | 2024-12-02 17:00 | 5 | Renderer | 32 | 59 | 35 | 81 | 49
1183 | 1.2.4.4.1.5.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1182 | 1184 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Floor Sealer | 9 | 47 | 23 | 48 | 15
1184 | 1.2.4.4.1.5.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1183 | 1185 | 29 November 2024 8:00 AM | 2024-12-01 17:00 | 2 | Head Contractor | 35 | 29 | 23 | 45 | 8
1185 | 1.2.4.4.1.5.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1184 | 1186 | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Development Manager | 17 | 86 | 27 | 28 | 9
1186 | 1.2.4.4.1.5.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1185 | 1190,1187,1188,1189 | 2 December 2024 8:00 AM | 2024-12-05 17:00 | 3 | Painter | 66 | 90 | 33 | 60 | 20
1187 | 1.2.4.4.1.5.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Development Manager | 61 | 87 | 13 | 81 | 34
1188 | 1.2.4.4.1.5.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | 3 December 2024 8:00 AM | 2024-12-07 17:00 | 3 | Concretor | 6 | 39 | 14 | 73 | 15
1189 | 1.2.4.4.1.5.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1186 | 1190 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Reinforcement Fixer | 32 | 28 | 32 | 96 | 3
1190 | 1.2.4.4.1.5.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1186,1187,1188,1189 |  | 5 December 2024 8:00 AM | 2024-12-08 17:00 | 3 | Admin | 95 | 88 | 20 | 83 | 51
1191 | 1.2.4.4.1.5.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 14 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Timber Floorer | 81 | 93 | 11 | 57 | 9
1192 | 1.2.4.4.1.5.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1157 | 1193 | 14 November 2024 8:00 AM | 2024-11-15 17:00 | 1 | Painter | 56 | 59 | 27 | 36 | 33
1193 | 1.2.4.4.1.5.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1192 | 1194 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Subcontractor | 2 | 79 | 35 | 49 | 48
1194 | 1.2.4.4.1.5.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1193 | 1195 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Surveyor | 64 | 35 | 15 | 95 | 45
1195 | 1.2.4.4.1.5.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1194 | 1196 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Landscaper | 85 | 94 | 11 | 74 | 29
1196 | 1.2.4.4.1.5.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1195 | 1197 | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Concretor | 32 | 86 | 19 | 3 | 2
1197 | 1.2.4.4.1.5.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1196 | 1198 | 22 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Foreman | 57 | 72 | 25 | 19 | 34
1198 | 1.2.4.4.1.5.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1197 | 1199 | 26 November 2024 8:00 AM | 2024-11-28 17:00 | 2 | Stone Mason | 10 | 97 | 33 | 48 | 22
1199 | 1.2.4.4.1.5.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1198 | 1200,1201,1202,1203 | 27 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Head Contractor | 16 | 11 | 31 | 22 | 45
1200 | 1.2.4.4.1.5.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Surveyor | 20 | 44 | 31 | 56 | 4
1201 | 1.2.4.4.1.5.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1199 | 1204 | 28 November 2024 8:00 AM | 2024-12-01 17:00 | 3 | Project Manager | 23 | 42 | 34 | 54 | 11
1202 | 1.2.4.4.1.5.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Waterproofer | 85 | 59 | 13 | 94 | 23
1203 | 1.2.4.4.1.5.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1199 | 1204 | 28 November 2024 8:00 AM | 2024-12-02 17:00 | 3 | Concretor | 75 | 78 | 26 | 49 | 3
1204 | 1.2.4.4.1.5.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1200,1201,1202,1203 |  | 30 November 2024 8:00 AM | 2024-12-01 17:00 | 1 | Post Tension | 49 | 59 | 24 | 84 | 27
1205 | 1.2.4.4.1.5.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-17 17:00 | 2 | Mechanical | 17 | 25 | 33 | 53 | 4
1206 | 1.2.4.4.1.5.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1134 | 1207 | 21 October 2024 8:00 AM | 2024-10-23 17:00 | 1 | Excavation | 33 | 69 | 30 | 67 | 45
1207 | 1.2.4.4.1.5.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1206 |  | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 1 | Reinforcement Fixer | 37 | 27 | 31 | 42 | 23
1208 | 1.2.4.4.1.5.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1143 | 1211 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 1 | Renderer | 21 | 19 | 10 | 2 | 32
1209 | 1.2.4.4.1.5.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1142 | 1211 | 30 October 2024 8:00 AM | 2024-10-30 17:00 | 0 | Joiner | 89 | 98 | 34 | 97 | 5
1210 | 1.2.4.4.1.5.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1139 | 1211 | 24 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Contract Administrator | 69 | 20 | 25 | 61 | 2
1211 | 1.2.4.4.1.5.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1208,1209,1210 | 1212 | 31 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Tiler | 82 | 38 | 26 | 4 | 34
1212 | 1.2.4.4.1.5.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1211 | 1213 | 1 November 2024 8:00 AM | 2024-11-02 17:00 | 1 | Mechanical | 17 | 46 | 14 | 30 | 3
1213 | 1.2.4.4.1.5.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1212 | 1214 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 1 | Site Manager | 30 | 42 | 32 | 33 | 13
1214 | 1.2.4.4.1.5.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1213 | 1215 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Site Manager | 24 | 35 | 13 | 22 | 53
1215 | 1.2.4.4.1.5.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1214 | 1216 | 6 November 2024 8:00 AM | 2024-11-07 17:00 | 0 | Carpenter | 99 | 58 | 14 | 41 | 59
1216 | 1.2.4.4.1.5.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1215 | 1217 | 8 November 2024 8:00 AM | 2024-11-10 17:00 | 1 | Surveyor | 60 | 70 | 29 | 4 | 20
1217 | 1.2.4.4.1.5.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1216 | 1218 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Formworker | 51 | 59 | 30 | 32 | 38
1218 | 1.2.4.4.1.5.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1217 | 1219,1220,1221,1222 | 12 November 2024 8:00 AM | 2024-11-16 17:00 | 2 | Line Market | 25 | 30 | 18 | 6 | 6
1219 | 1.2.4.4.1.5.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Site Manager | 2 | 99 | 34 | 30 | 13
1220 | 1.2.4.4.1.5.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | 15 November 2024 8:00 AM | 2024-11-20 17:00 | 5 | Landscaper | 70 | 40 | 15 | 9 | 51
1221 | 1.2.4.4.1.5.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | 15 November 2024 8:00 AM | 2024-11-16 17:00 | 1 | Post Tension | 1 | 66 | 29 | 91 | 33
1222 | 1.2.4.4.1.5.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1218 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Metal Work | 35 | 34 | 27 | 83 | 15
1223 | 1.2.4.4.1.5.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1169,1170,1171,1172,1173 | 1224 | 6 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Window | 82 | 59 | 30 | 49 | 49
1224 | 1.2.4.4.1.5.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1223 | 1225 | 7 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Electrician | 31 | 85 | 29 | 44 | 19
1225 | 1.2.4.4.1.5.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1224 | 1226 | 9 December 2024 8:00 AM | 2024-12-09 17:00 | 0 | Excavation | 31 | 60 | 10 | 49 | 33
1226 | 1.2.4.4.1.5.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1225 |  | 10 December 2024 8:00 AM | 2024-12-10 17:00 | 0 | Surveyor | 89 | 36 | 19 | 33 | 24
1227 | 1.2.4.4.1.6 | Apartment B015 | 46 | 18 October 2024 8:00 AM | 10 December 2024 5:00 PM |  |  | 18 October 2024 8:00 AM | 2024-12-11 17:00 | 1 | Window | 48 | 46 | 29 | 35 | 41
1228 | 1.2.4.4.1.6.1 | External and Intertenancy Wall Framing | 2 | 18 October 2024 8:00 AM | 19 October 2024 5:00 PM | 448FS+4d | 1229,1232,1233,1300 | 18 October 2024 8:00 AM | 2024-10-19 17:00 | 0 | Subcontractor | 65 | 23 | 25 | 76 | 23
1229 | 1.2.4.4.1.6.2 | Waterproofing Wall & Window | 1 | 21 October 2024 8:00 AM | 21 October 2024 5:00 PM | 1228 | 1231,1230 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 1 | Landscaper | 77 | 34 | 27 | 97 | 33
1230 | 1.2.4.4.1.6.3 | External & Intertenancy Wall / Hebal | 2 | 22 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1229 |  | 22 October 2024 8:00 AM | 2024-10-24 17:00 | 1 | Painter | 99 | 25 | 22 | 12 | 59
1231 | 1.2.4.4.1.6.4 | Windows Install | 3 | 22 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1229 | 1234 | 22 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Site Manager | 68 | 29 | 10 | 59 | 28
1232 | 1.2.4.4.1.6.5 | Mechanical Overheads | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1241 | 21 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Metal Work | 78 | 92 | 22 | 94 | 48
1233 | 1.2.4.4.1.6.6 | Fire Sprinklers Mains | 3 | 21 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1228 | 1304 | 21 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Head Contractor | 3 | 56 | 29 | 33 | 26
1234 | 1.2.4.4.1.6.7 | Internal Wall Framing & Door Frames | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1231 | 1235,1236,1237,1238,1239 | 25 October 2024 8:00 AM | 2024-10-27 17:00 | 1 | Scaffolder | 91 | 12 | 19 | 38 | 57
1235 | 1.2.4.4.1.6.8 | Mechanical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239 | 28 October 2024 8:00 AM | 2024-10-31 17:00 | 2 | Window | 3 | 51 | 18 | 59 | 50
1236 | 1.2.4.4.1.6.9 | Plumbing Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1239,1303 | 28 October 2024 8:00 AM | 2024-11-02 17:00 | 4 | Development Manager | 76 | 10 | 16 | 52 | 36
1237 | 1.2.4.4.1.6.10 | Electrical Wall Roughin | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 | 1302 | 28 October 2024 8:00 AM | 2024-10-31 17:00 | 2 | Concretor | 95 | 31 | 32 | 69 | 17
1238 | 1.2.4.4.1.6.11 | Fire Detection (Dry) | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1234 |  | 28 October 2024 8:00 AM | 2024-10-30 17:00 | 1 | Admin | 63 | 32 | 32 | 45 | 28
1239 | 1.2.4.4.1.6.12 | Noggin Rough in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1234,1235,1236 | 1240 | 30 October 2024 8:00 AM | 2024-11-06 17:00 | 7 | Joiner | 33 | 64 | 29 | 44 | 20
1240 | 1.2.4.4.1.6.13 | Sheet Walls | 2 | 31 October 2024 8:00 AM | 1 November 2024 5:00 PM | 1239 | 1241 | 31 October 2024 8:00 AM | 2024-11-03 17:00 | 2 | Stone Mason | 50 | 80 | 30 | 97 | 41
1241 | 1.2.4.4.1.6.14 | Ceiling Grids | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1232,1240 | 1242,1243,1244,1245,1247,1249 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 1 | Plumber | 66 | 13 | 26 | 17 | 12
1242 | 1.2.4.4.1.6.15 | Electrical Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1246,1249 | 5 November 2024 8:00 AM | 2024-11-07 17:00 | 1 | Stone Mason | 80 | 61 | 13 | 19 | 21
1243 | 1.2.4.4.1.6.16 | Fire Detection (Dry) | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1249 | 5 November 2024 8:00 AM | 2024-11-11 17:00 | 5 | Carpet | 46 | 61 | 27 | 11 | 9
1244 | 1.2.4.4.1.6.17 | Plumbing Rough-in | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1241 | 1248,1249 | 5 November 2024 8:00 AM | 2024-11-07 17:00 | 1 | Waterproofer | 91 | 99 | 10 | 98 | 19
1245 | 1.2.4.4.1.6.18 | Fire Sprinklers Droppers | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Plumber | 11 | 92 | 33 | 40 | 39
1246 | 1.2.4.4.1.6.19 | Fire Rating Electrical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1242 | 1249 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 1 | Project Manager | 20 | 96 | 14 | 51 | 3
1247 | 1.2.4.4.1.6.20 | Fire Rating Mechanical | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1241 | 1249 | 5 November 2024 8:00 AM | 2024-11-05 17:00 | 0 | Concretor | 94 | 99 | 18 | 83 | 2
1248 | 1.2.4.4.1.6.21 | Fire Rating Hydraulic | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1244 | 1249 | 7 November 2024 8:00 AM | 2024-11-09 17:00 | 2 | Cleaner | 49 | 17 | 28 | 20 | 42
1249 | 1.2.4.4.1.6.22 | Noggin Rough in | 1 | 8 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1241,1242,1243,1244,1245,1246,1247,1248 | 1250 | 8 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Tiler | 86 | 41 | 35 | 90 | 19
1250 | 1.2.4.4.1.6.23 | Sheet Ceilings | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1249 | 1251 | 9 November 2024 8:00 AM | 2024-11-11 17:00 | 2 | Hoarding | 20 | 86 | 27 | 25 | 50
1251 | 1.2.4.4.1.6.24 | Setting / Sanding | 3 | 11 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1250 | 1252,1269,1286 | 11 November 2024 8:00 AM | 2024-11-15 17:00 | 2 | Surveyor | 50 | 84 | 20 | 84 | 8
1252 | 1.2.4.4.1.6.25 | Paint Undercoat (1st Coat) | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1253 | 14 November 2024 8:00 AM | 2024-11-16 17:00 | 2 | Post Tension | 8 | 71 | 24 | 55 | 50
1253 | 1.2.4.4.1.6.26 | Paint Undercoat (2nd Coat) | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1252 | 1254 | 15 November 2024 8:00 AM | 2024-11-18 17:00 | 3 | Site Manager | 83 | 72 | 25 | 45 | 43
1254 | 1.2.4.4.1.6.27 | Floor Leveling | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1253 | 1255 | 16 November 2024 8:00 AM | 2024-11-22 17:00 | 4 | Foreman | 95 | 72 | 28 | 94 | 59
1255 | 1.2.4.4.1.6.28 | Timber Floor Install | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1254 | 1256 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Joiner | 1 | 67 | 34 | 51 | 34
1256 | 1.2.4.4.1.6.29 | Joinery Kickers | 1 | 20 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1255 | 1257,1258 | 20 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Contract Administrator | 24 | 42 | 34 | 97 | 6
1257 | 1.2.4.4.1.6.30 | Joinery Kitchen | 2 | 21 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1256 | 1261 | 21 November 2024 8:00 AM | 2024-11-26 17:00 | 4 | Joiner | 6 | 10 | 35 | 91 | 5
1258 | 1.2.4.4.1.6.31 | Joinery Bedroom | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1256 | 1259 | 21 November 2024 8:00 AM | 2024-11-22 17:00 | 1 | Post Tension | 90 | 100 | 23 | 87 | 51
1259 | 1.2.4.4.1.6.32 | Door Hanging | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1258 | 1260 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 1 | Renderer | 31 | 16 | 16 | 70 | 21
1260 | 1.2.4.4.1.6.33 | Door Hardware | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1259 |  | 23 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Scaffolder | 23 | 42 | 23 | 62 | 57
1261 | 1.2.4.4.1.6.34 | Stone Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1257 | 1262,1263,1264,1265,1266 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Joiner | 69 | 40 | 24 | 37 | 32
1262 | 1.2.4.4.1.6.35 | Carpentry skirtings | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1261 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Line Market | 47 | 11 | 28 | 5 | 36
1263 | 1.2.4.4.1.6.36 | Hydraulic Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Tiler | 59 | 27 | 30 | 68 | 39
1264 | 1.2.4.4.1.6.37 | Electrical Living Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Post Tension | 83 | 74 | 11 | 22 | 48
1265 | 1.2.4.4.1.6.38 | Electrical Kitchen Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | 26 November 2024 8:00 AM | 2024-11-29 17:00 | 2 | Admin | 70 | 93 | 14 | 85 | 33
1266 | 1.2.4.4.1.6.39 | Mechanical Fitoff Install | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1261 | 1317 | 26 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Metal Work | 78 | 21 | 15 | 57 | 24
1267 | 1.2.4.4.1.6.40 | Internal Wet Areas | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  | 1317 | 14 November 2024 8:00 AM | 2024-12-07 17:00 | 2 | Post Tension | 23 | 68 | 32 | 77 | 19
1268 | 1.2.4.4.1.6.40.1 | Bathrooms | 19 | 14 November 2024 8:00 AM | 5 December 2024 5:00 PM |  |  | 14 November 2024 8:00 AM | 2024-12-05 17:00 | 0 | Renderer | 40 | 45 | 19 | 8 | 20
1269 | 1.2.4.4.1.6.40.1.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1270 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Excavation | 23 | 38 | 12 | 2 | 50
1270 | 1.2.4.4.1.6.40.1.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1269 | 1271 | 15 November 2024 8:00 AM | 2024-11-18 17:00 | 3 | Project Manager | 15 | 34 | 21 | 76 | 16
1271 | 1.2.4.4.1.6.40.1.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1270 | 1272 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Development Manager | 9 | 85 | 31 | 87 | 36
1272 | 1.2.4.4.1.6.40.1.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1271 | 1273 | 19 November 2024 8:00 AM | 2024-11-19 17:00 | 0 | Renderer | 86 | 14 | 19 | 70 | 30
1273 | 1.2.4.4.1.6.40.1.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1272 | 1274 | 20 November 2024 8:00 AM | 2024-11-24 17:00 | 3 | Foreman | 8 | 69 | 34 | 0 | 20
1274 | 1.2.4.4.1.6.40.1.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1273 | 1275 | 22 November 2024 8:00 AM | 2024-11-27 17:00 | 2 | Floor Sealer | 13 | 93 | 25 | 73 | 20
1275 | 1.2.4.4.1.6.40.1.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1274 | 1276 | 26 November 2024 8:00 AM | 2024-11-27 17:00 | 1 | Surveyor | 26 | 30 | 22 | 15 | 2
1276 | 1.2.4.4.1.6.40.1.8 | Joinery Bathroom | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1275 | 1277 | 27 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Subcontractor | 79 | 39 | 32 | 46 | 4
1277 | 1.2.4.4.1.6.40.1.9 | Stone | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1276 | 1278 | 28 November 2024 8:00 AM | 2024-11-30 17:00 | 2 | Line Market | 99 | 66 | 11 | 68 | 32
1278 | 1.2.4.4.1.6.40.1.10 | Shower Screens | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1277 | 1279 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Stone Mason | 66 | 12 | 20 | 100 | 15
1279 | 1.2.4.4.1.6.40.1.11 | Mirrors | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1278 | 1280 | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Carpet | 54 | 55 | 13 | 81 | 32
1280 | 1.2.4.4.1.6.40.1.12 | Bathroom Fittings Fitoff | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1279 | 1284,1281,1282,1283 | 2 December 2024 8:00 AM | 2024-12-03 17:00 | 1 | Admin | 15 | 63 | 29 | 91 | 5
1281 | 1.2.4.4.1.6.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Scaffolder | 95 | 80 | 35 | 40 | 44
1282 | 1.2.4.4.1.6.40.1.14 | Electrical Bathroom Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | 3 December 2024 8:00 AM | 2024-12-07 17:00 | 3 | Landscaper | 43 | 97 | 12 | 99 | 57
1283 | 1.2.4.4.1.6.40.1.15 | Mechanical Laundry Fitoff | 2 | 3 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1280 | 1284 | 3 December 2024 8:00 AM | 2024-12-08 17:00 | 4 | Landscaper | 40 | 49 | 17 | 95 | 3
1284 | 1.2.4.4.1.6.40.1.16 | Silicone | 1 | 5 December 2024 8:00 AM | 5 December 2024 5:00 PM | 1280,1281,1282,1283 |  | 5 December 2024 8:00 AM | 2024-12-08 17:00 | 3 | Subcontractor | 64 | 42 | 33 | 15 | 7
1285 | 1.2.4.4.1.6.40.2 | Laundry | 15 | 14 November 2024 8:00 AM | 30 November 2024 5:00 PM |  |  | 14 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Metal Work | 93 | 80 | 18 | 2 | 60
1286 | 1.2.4.4.1.6.40.2.1 | Prepare for Waterproof | 1 | 14 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1251 | 1287 | 14 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Concretor | 63 | 59 | 15 | 35 | 50
1287 | 1.2.4.4.1.6.40.2.2 | Install Angles | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1286 | 1288 | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Timber Floorer | 42 | 37 | 28 | 2 | 20
1288 | 1.2.4.4.1.6.40.2.3 | Waterproof | 2 | 16 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1287 | 1289 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Waterproofer | 78 | 67 | 32 | 72 | 29
1289 | 1.2.4.4.1.6.40.2.4 | Water Testing | 1 | 19 November 2024 8:00 AM | 19 November 2024 5:00 PM | 1288 | 1290 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 1 | Head Contractor | 41 | 44 | 12 | 20 | 28
1290 | 1.2.4.4.1.6.40.2.5 | Tile Bed and Cure | 2 | 20 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1289 | 1291 | 20 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Landscaper | 66 | 64 | 20 | 6 | 14
1291 | 1.2.4.4.1.6.40.2.6 | Tile Wall & Floor | 3 | 22 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1290 | 1292 | 22 November 2024 8:00 AM | 2024-11-30 17:00 | 5 | Development Manager | 74 | 87 | 32 | 87 | 33
1292 | 1.2.4.4.1.6.40.2.7 | Grout | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1291 | 1293 | 26 November 2024 8:00 AM | 2024-11-28 17:00 | 2 | Metal Work | 98 | 49 | 18 | 98 | 43
1293 | 1.2.4.4.1.6.40.2.8 | Joinery Laundry | 1 | 27 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1292 | 1294,1295,1296,1297 | 27 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Stone Mason | 26 | 64 | 12 | 32 | 49
1294 | 1.2.4.4.1.6.40.2.9 | Laundry Fittings Fitoff | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Plasterboarder | 37 | 81 | 14 | 50 | 18
1295 | 1.2.4.4.1.6.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1293 | 1298 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Post Tension | 77 | 89 | 30 | 46 | 11
1296 | 1.2.4.4.1.6.40.2.11 | Electrical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Scaffolder | 77 | 34 | 33 | 89 | 12
1297 | 1.2.4.4.1.6.40.2.12 | Mechanical Laundry Fitoff | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1293 | 1298 | 28 November 2024 8:00 AM | 2024-12-01 17:00 | 2 | Contract Administrator | 37 | 84 | 35 | 28 | 46
1298 | 1.2.4.4.1.6.40.2.13 | Silicone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1294,1295,1296,1297 |  | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Renderer | 34 | 14 | 35 | 10 | 22
1299 | 1.2.4.4.1.6.41 | Balcony | 23 | 21 October 2024 8:00 AM | 15 November 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-11-16 17:00 | 1 | Formworker | 89 | 50 | 24 | 38 | 54
1300 | 1.2.4.4.1.6.41.1 | Balustrade Prep | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 1228 | 1301 | 21 October 2024 8:00 AM | 2024-10-24 17:00 | 2 | Landscaper | 47 | 47 | 27 | 31 | 29
1301 | 1.2.4.4.1.6.41.2 | Balustrade Install | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1300 |  | 23 October 2024 8:00 AM | 2024-10-24 17:00 | 0 | Concretor | 33 | 61 | 33 | 36 | 31
1302 | 1.2.4.4.1.6.41.3 | Electrical Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1237 | 1305 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 1 | Formworker | 50 | 64 | 17 | 71 | 13
1303 | 1.2.4.4.1.6.41.4 | Plumbing Rough-in | 1 | 30 October 2024 8:00 AM | 30 October 2024 5:00 PM | 1236 | 1305 | 30 October 2024 8:00 AM | 2024-11-01 17:00 | 2 | Waterproofer | 1 | 78 | 17 | 90 | 44
1304 | 1.2.4.4.1.6.41.5 | Fire Sprinklers | 1 | 24 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1233 | 1305 | 24 October 2024 8:00 AM | 2024-10-26 17:00 | 2 | Painter | 78 | 75 | 20 | 10 | 6
1305 | 1.2.4.4.1.6.41.6 | Prepare for Waterproof | 1 | 31 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1302,1303,1304 | 1306 | 31 October 2024 8:00 AM | 2024-11-05 17:00 | 5 | Carpenter | 100 | 50 | 27 | 95 | 27
1306 | 1.2.4.4.1.6.41.7 | Install Angles | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1305 | 1307 | 1 November 2024 8:00 AM | 2024-11-07 17:00 | 6 | Post Tension | 17 | 19 | 22 | 85 | 3
1307 | 1.2.4.4.1.6.41.8 | Waterproof | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1306 | 1308 | 2 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Concretor | 5 | 94 | 28 | 17 | 46
1308 | 1.2.4.4.1.6.41.9 | Water Testing | 1 | 5 November 2024 8:00 AM | 5 November 2024 5:00 PM | 1307 | 1309 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 1 | Mechanical | 46 | 26 | 34 | 54 | 28
1309 | 1.2.4.4.1.6.41.10 | Tile Bed and Cure | 2 | 6 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1308 | 1310 | 6 November 2024 8:00 AM | 2024-11-08 17:00 | 1 | Development Manager | 56 | 45 | 21 | 46 | 60
1310 | 1.2.4.4.1.6.41.11 | Tiling | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1309 | 1311 | 8 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Hoarding | 95 | 56 | 25 | 19 | 7
1311 | 1.2.4.4.1.6.41.12 | Grout | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1310 | 1312 | 11 November 2024 8:00 AM | 2024-11-11 17:00 | 0 | Subcontractor | 0 | 88 | 23 | 3 | 50
1312 | 1.2.4.4.1.6.41.13 | Paint/Cladding | 3 | 12 November 2024 8:00 AM | 14 November 2024 5:00 PM | 1311 | 1313,1314,1315,1316 | 12 November 2024 8:00 AM | 2024-11-14 17:00 | 0 | Plasterboarder | 10 | 37 | 32 | 12 | 57
1313 | 1.2.4.4.1.6.41.14 | Silicone | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Plumber | 17 | 38 | 11 | 76 | 44
1314 | 1.2.4.4.1.6.41.15 | Hydraulic Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | 15 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Mechanical | 85 | 28 | 13 | 26 | 23
1315 | 1.2.4.4.1.6.41.16 | Electrical Fit Off | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | 15 November 2024 8:00 AM | 2024-11-17 17:00 | 2 | Electrician | 56 | 21 | 22 | 15 | 42
1316 | 1.2.4.4.1.6.41.17 | Fit Fitoff | 1 | 15 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1312 |  | 15 November 2024 8:00 AM | 2024-11-22 17:00 | 7 | Plumber | 2 | 34 | 14 | 12 | 38
1317 | 1.2.4.4.1.6.42 | Carpet Install | 1 | 6 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1263,1264,1265,1266,1267 | 1318 | 6 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Timber Floorer | 12 | 89 | 27 | 100 | 53
1318 | 1.2.4.4.1.6.43 | Paint (FINAL Coat) | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1317 | 1319 | 7 December 2024 8:00 AM | 2024-12-09 17:00 | 2 | Excavation | 59 | 53 | 11 | 26 | 51
1319 | 1.2.4.4.1.6.44 | FINAL CLEAN | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1318 | 1320 | 9 December 2024 8:00 AM | 2024-12-10 17:00 | 1 | Project Manager | 42 | 46 | 29 | 2 | 59
1320 | 1.2.4.4.1.6.45 | UNIT LOCKED | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1319 |  | 10 December 2024 8:00 AM | 2024-12-11 17:00 | 1 | Reinforcement Fixer | 6 | 99 | 35 | 4 | 22
1321 | 1.2.4.4.1.7 | Apartment B016 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-12-13 17:00 | 1 | Floor Sealer | 93 | 37 | 17 | 59 | 20
1322 | 1.2.4.4.1.7.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1323,1326,1327,1394 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Window | 15 | 98 | 14 | 12 | 35
1323 | 1.2.4.4.1.7.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1322 | 1325,1324 | 23 October 2024 8:00 AM | 2024-10-23 17:00 | 0 | Electrician | 37 | 74 | 11 | 78 | 22
1324 | 1.2.4.4.1.7.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1323 |  | 24 October 2024 8:00 AM | 2024-10-29 17:00 | 4 | Subcontractor | 41 | 73 | 35 | 87 | 22
1325 | 1.2.4.4.1.7.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1323 | 1328 | 24 October 2024 8:00 AM | 2024-10-29 17:00 | 3 | Mechanical | 66 | 10 | 12 | 56 | 31
1326 | 1.2.4.4.1.7.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1335 | 23 October 2024 8:00 AM | 2024-10-29 17:00 | 4 | Scaffolder | 100 | 82 | 17 | 39 | 56
1327 | 1.2.4.4.1.7.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1322 | 1398 | 23 October 2024 8:00 AM | 2024-10-30 17:00 | 5 | Tiler | 51 | 54 | 11 | 91 | 19
1328 | 1.2.4.4.1.7.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1325 | 1329,1330,1331,1332,1333 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Post Tension | 0 | 95 | 31 | 11 | 28
1329 | 1.2.4.4.1.7.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333 | 30 October 2024 8:00 AM | 2024-11-01 17:00 | 1 | Timber Floorer | 80 | 40 | 11 | 11 | 48
1330 | 1.2.4.4.1.7.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1333,1397 | 30 October 2024 8:00 AM | 2024-11-03 17:00 | 3 | Joiner | 75 | 28 | 21 | 28 | 30
1331 | 1.2.4.4.1.7.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 | 1396 | 30 October 2024 8:00 AM | 2024-11-01 17:00 | 1 | Excavation | 62 | 55 | 16 | 45 | 21
1332 | 1.2.4.4.1.7.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1328 |  | 30 October 2024 8:00 AM | 2024-11-03 17:00 | 3 | Line Market | 94 | 51 | 20 | 49 | 12
1333 | 1.2.4.4.1.7.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1328,1329,1330 | 1334 | 1 November 2024 8:00 AM | 2024-11-01 17:00 | 0 | Metal Work | 99 | 20 | 10 | 100 | 14
1334 | 1.2.4.4.1.7.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1333 | 1335 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 1 | Hoarding | 53 | 81 | 16 | 18 | 30
1335 | 1.2.4.4.1.7.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1326,1334 | 1336,1337,1338,1339,1341,1343 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Carpet | 40 | 75 | 23 | 69 | 7
1336 | 1.2.4.4.1.7.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1340,1343 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Subcontractor | 8 | 32 | 27 | 3 | 10
1337 | 1.2.4.4.1.7.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1343 | 7 November 2024 8:00 AM | 2024-11-10 17:00 | 2 | Subcontractor | 12 | 100 | 27 | 47 | 2
1338 | 1.2.4.4.1.7.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1335 | 1342,1343 | 7 November 2024 8:00 AM | 2024-11-10 17:00 | 2 | Hoarding | 7 | 59 | 13 | 97 | 4
1339 | 1.2.4.4.1.7.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 1 | Excavation | 36 | 43 | 24 | 53 | 24
1340 | 1.2.4.4.1.7.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1336 | 1343 | 9 November 2024 8:00 AM | 2024-11-12 17:00 | 3 | Tiler | 31 | 77 | 33 | 22 | 51
1341 | 1.2.4.4.1.7.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1335 | 1343 | 7 November 2024 8:00 AM | 2024-11-11 17:00 | 4 | Post Tension | 41 | 97 | 35 | 87 | 6
1342 | 1.2.4.4.1.7.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1338 | 1343 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Formworker | 21 | 90 | 10 | 46 | 36
1343 | 1.2.4.4.1.7.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1335,1336,1337,1338,1339,1340,1341,1342 | 1344 | 11 November 2024 8:00 AM | 2024-11-13 17:00 | 2 | Site Manager | 75 | 32 | 16 | 21 | 6
1344 | 1.2.4.4.1.7.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1343 | 1345 | 12 November 2024 8:00 AM | 2024-11-14 17:00 | 2 | Site Manager | 1 | 84 | 20 | 3 | 15
1345 | 1.2.4.4.1.7.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1344 | 1346,1363,1380 | 13 November 2024 8:00 AM | 2024-11-15 17:00 | 0 | Mechanical | 44 | 36 | 32 | 54 | 19
1346 | 1.2.4.4.1.7.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1347 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Reinforcement Fixer | 92 | 50 | 35 | 77 | 54
1347 | 1.2.4.4.1.7.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1346 | 1348 | 18 November 2024 8:00 AM | 2024-11-20 17:00 | 2 | Window | 38 | 18 | 13 | 52 | 27
1348 | 1.2.4.4.1.7.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1347 | 1349 | 19 November 2024 8:00 AM | 2024-11-24 17:00 | 4 | Hoarding | 83 | 51 | 28 | 12 | 15
1349 | 1.2.4.4.1.7.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1348 | 1350 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Joiner | 37 | 40 | 19 | 90 | 32
1350 | 1.2.4.4.1.7.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1349 | 1351,1352 | 22 November 2024 8:00 AM | 2024-11-22 17:00 | 0 | Excavation | 15 | 38 | 23 | 47 | 31
1351 | 1.2.4.4.1.7.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1350 | 1355 | 23 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Contract Administrator | 44 | 74 | 15 | 49 | 13
1352 | 1.2.4.4.1.7.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1350 | 1353 | 23 November 2024 8:00 AM | 2024-11-28 17:00 | 5 | Foreman | 28 | 67 | 28 | 19 | 23
1353 | 1.2.4.4.1.7.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1352 | 1354 | 25 November 2024 8:00 AM | 2024-11-30 17:00 | 5 | Site Manager | 5 | 45 | 18 | 0 | 5
1354 | 1.2.4.4.1.7.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1353 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Plasterboarder | 36 | 29 | 19 | 40 | 51
1355 | 1.2.4.4.1.7.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1351 | 1356,1357,1358,1359,1360 | 26 November 2024 8:00 AM | 2024-11-29 17:00 | 2 | Painter | 40 | 91 | 22 | 70 | 41
1356 | 1.2.4.4.1.7.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1355 |  | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Landscaper | 7 | 79 | 27 | 25 | 9
1357 | 1.2.4.4.1.7.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | 28 November 2024 8:00 AM | 2024-12-02 17:00 | 3 | Tiler | 98 | 76 | 17 | 78 | 5
1358 | 1.2.4.4.1.7.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Electrician | 81 | 18 | 31 | 99 | 27
1359 | 1.2.4.4.1.7.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 4 | Contract Administrator | 11 | 20 | 11 | 66 | 27
1360 | 1.2.4.4.1.7.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1355 | 1411 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Joiner | 33 | 88 | 15 | 36 | 26
1361 | 1.2.4.4.1.7.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1411 | 16 November 2024 8:00 AM | 2024-12-09 17:00 | 2 | Foreman | 93 | 54 | 20 | 41 | 25
1362 | 1.2.4.4.1.7.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | 16 November 2024 8:00 AM | 2024-12-09 17:00 | 2 | Carpet | 21 | 55 | 27 | 89 | 36
1363 | 1.2.4.4.1.7.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1364 | 16 November 2024 8:00 AM | 2024-11-19 17:00 | 3 | Joiner | 98 | 64 | 28 | 59 | 43
1364 | 1.2.4.4.1.7.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1363 | 1365 | 18 November 2024 8:00 AM | 2024-11-21 17:00 | 3 | Project Manager | 20 | 82 | 34 | 43 | 36
1365 | 1.2.4.4.1.7.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1364 | 1366 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 1 | Landscaper | 40 | 70 | 24 | 29 | 19
1366 | 1.2.4.4.1.7.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1365 | 1367 | 21 November 2024 8:00 AM | 2024-11-24 17:00 | 3 | Hoarding | 69 | 67 | 23 | 43 | 58
1367 | 1.2.4.4.1.7.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1366 | 1368 | 22 November 2024 8:00 AM | 2024-11-24 17:00 | 1 | Contract Administrator | 25 | 31 | 16 | 14 | 43
1368 | 1.2.4.4.1.7.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1367 | 1369 | 25 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Line Market | 68 | 44 | 12 | 69 | 33
1369 | 1.2.4.4.1.7.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1368 | 1370 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Hoarding | 21 | 59 | 21 | 10 | 53
1370 | 1.2.4.4.1.7.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1369 | 1371 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Hoarding | 87 | 90 | 29 | 79 | 35
1371 | 1.2.4.4.1.7.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1370 | 1372 | 30 November 2024 8:00 AM | 2024-12-01 17:00 | 1 | Tiler | 63 | 59 | 14 | 62 | 16
1372 | 1.2.4.4.1.7.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1371 | 1373 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Line Market | 58 | 86 | 27 | 86 | 13
1373 | 1.2.4.4.1.7.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1372 | 1374 | 3 December 2024 8:00 AM | 2024-12-04 17:00 | 1 | Electrician | 37 | 66 | 35 | 1 | 23
1374 | 1.2.4.4.1.7.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1373 | 1378,1375,1376,1377 | 4 December 2024 8:00 AM | 2024-12-06 17:00 | 2 | Development Manager | 7 | 96 | 30 | 78 | 52
1375 | 1.2.4.4.1.7.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | 5 December 2024 8:00 AM | 2024-12-07 17:00 | 1 | Project Manager | 7 | 90 | 34 | 51 | 14
1376 | 1.2.4.4.1.7.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | 5 December 2024 8:00 AM | 2024-12-10 17:00 | 4 | Site Manager | 30 | 46 | 21 | 6 | 46
1377 | 1.2.4.4.1.7.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1374 | 1378 | 5 December 2024 8:00 AM | 2024-12-08 17:00 | 2 | Joiner | 24 | 31 | 22 | 59 | 40
1378 | 1.2.4.4.1.7.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1374,1375,1376,1377 |  | 7 December 2024 8:00 AM | 2024-12-09 17:00 | 2 | Admin | 86 | 27 | 33 | 39 | 37
1379 | 1.2.4.4.1.7.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | 16 November 2024 8:00 AM | 2024-12-04 17:00 | 1 | Electrician | 7 | 20 | 13 | 51 | 37
1380 | 1.2.4.4.1.7.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1345 | 1381 | 16 November 2024 8:00 AM | 2024-11-16 17:00 | 0 | Subcontractor | 67 | 78 | 34 | 19 | 3
1381 | 1.2.4.4.1.7.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1380 | 1382 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 1 | Painter | 67 | 52 | 34 | 97 | 2
1382 | 1.2.4.4.1.7.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1381 | 1383 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Metal Work | 69 | 24 | 28 | 62 | 59
1383 | 1.2.4.4.1.7.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1382 | 1384 | 21 November 2024 8:00 AM | 2024-11-24 17:00 | 3 | Post Tension | 92 | 26 | 29 | 14 | 11
1384 | 1.2.4.4.1.7.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1383 | 1385 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Landscaper | 28 | 98 | 35 | 58 | 39
1385 | 1.2.4.4.1.7.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1384 | 1386 | 25 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Electrician | 88 | 78 | 14 | 55 | 39
1386 | 1.2.4.4.1.7.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1385 | 1387 | 28 November 2024 8:00 AM | 2024-11-30 17:00 | 2 | Scaffolder | 21 | 69 | 34 | 66 | 27
1387 | 1.2.4.4.1.7.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1386 | 1388,1389,1390,1391 | 29 November 2024 8:00 AM | 2024-12-01 17:00 | 2 | Floor Sealer | 41 | 89 | 34 | 62 | 42
1388 | 1.2.4.4.1.7.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 2 | Head Contractor | 77 | 56 | 21 | 28 | 35
1389 | 1.2.4.4.1.7.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1387 | 1392 | 30 November 2024 8:00 AM | 2024-12-01 17:00 | 1 | Carpet | 5 | 60 | 28 | 4 | 21
1390 | 1.2.4.4.1.7.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | 30 November 2024 8:00 AM | 2024-12-03 17:00 | 1 | Scaffolder | 33 | 25 | 30 | 45 | 30
1391 | 1.2.4.4.1.7.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1387 | 1392 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Carpet | 57 | 22 | 18 | 22 | 39
1392 | 1.2.4.4.1.7.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1388,1389,1390,1391 |  | 3 December 2024 8:00 AM | 2024-12-07 17:00 | 4 | Tiler | 80 | 68 | 18 | 100 | 57
1393 | 1.2.4.4.1.7.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | 23 October 2024 8:00 AM | 2024-11-18 17:00 | 0 | Excavation | 74 | 53 | 22 | 49 | 2
1394 | 1.2.4.4.1.7.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1322 | 1395 | 23 October 2024 8:00 AM | 2024-10-26 17:00 | 2 | Scaffolder | 16 | 62 | 30 | 48 | 8
1395 | 1.2.4.4.1.7.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1394 |  | 25 October 2024 8:00 AM | 2024-11-02 17:00 | 7 | Tiler | 36 | 29 | 15 | 35 | 4
1396 | 1.2.4.4.1.7.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1331 | 1399 | 1 November 2024 8:00 AM | 2024-11-01 17:00 | 0 | Surveyor | 74 | 74 | 35 | 19 | 48
1397 | 1.2.4.4.1.7.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1330 | 1399 | 1 November 2024 8:00 AM | 2024-11-04 17:00 | 3 | Plasterboarder | 97 | 17 | 15 | 40 | 57
1398 | 1.2.4.4.1.7.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1327 | 1399 | 26 October 2024 8:00 AM | 2024-10-27 17:00 | 1 | Line Market | 85 | 81 | 21 | 84 | 42
1399 | 1.2.4.4.1.7.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1396,1397,1398 | 1400 | 2 November 2024 8:00 AM | 2024-11-02 17:00 | 0 | Hoarding | 74 | 37 | 21 | 90 | 53
1400 | 1.2.4.4.1.7.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1399 | 1401 | 4 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Contract Administrator | 8 | 66 | 35 | 53 | 39
1401 | 1.2.4.4.1.7.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1400 | 1402 | 5 November 2024 8:00 AM | 2024-11-07 17:00 | 1 | Project Manager | 17 | 23 | 13 | 43 | 50
1402 | 1.2.4.4.1.7.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1401 | 1403 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 1 | Waterproofer | 96 | 76 | 19 | 57 | 26
1403 | 1.2.4.4.1.7.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1402 | 1404 | 8 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Line Market | 12 | 83 | 19 | 41 | 22
1404 | 1.2.4.4.1.7.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1403 | 1405 | 11 November 2024 8:00 AM | 2024-11-14 17:00 | 2 | Tiler | 56 | 47 | 29 | 37 | 7
1405 | 1.2.4.4.1.7.41.12 | Grout | 1 | 13 November 2024 8:00 AM | 13 November 2024 5:00 PM | 1404 | 1406 | 13 November 2024 8:00 AM | 2024-11-16 17:00 | 3 | Cleaner | 37 | 11 | 21 | 26 | 44
1406 | 1.2.4.4.1.7.41.13 | Paint/Cladding | 3 | 14 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1405 | 1407,1408,1409,1410 | 14 November 2024 8:00 AM | 2024-11-18 17:00 | 2 | Landscaper | 61 | 44 | 35 | 49 | 58
1407 | 1.2.4.4.1.7.41.14 | Silicone | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | 18 November 2024 8:00 AM | 2024-11-23 17:00 | 5 | Reinforcement Fixer | 15 | 51 | 26 | 75 | 24
1408 | 1.2.4.4.1.7.41.15 | Hydraulic Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Subcontractor | 83 | 17 | 30 | 14 | 22
1409 | 1.2.4.4.1.7.41.16 | Electrical Fit Off | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 1 | Development Manager | 12 | 83 | 30 | 51 | 15
1410 | 1.2.4.4.1.7.41.17 | Fit Fitoff | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1406 |  | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Waterproofer | 33 | 83 | 16 | 100 | 22
1411 | 1.2.4.4.1.7.42 | Carpet Install | 1 | 9 December 2024 8:00 AM | 9 December 2024 5:00 PM | 1357,1358,1359,1360,1361 | 1412 | 9 December 2024 8:00 AM | 2024-12-11 17:00 | 2 | Admin | 24 | 100 | 26 | 97 | 41
1412 | 1.2.4.4.1.7.43 | Paint (FINAL Coat) | 1 | 10 December 2024 8:00 AM | 10 December 2024 5:00 PM | 1411 | 1413 | 10 December 2024 8:00 AM | 2024-12-11 17:00 | 1 | Carpenter | 78 | 75 | 26 | 74 | 7
1413 | 1.2.4.4.1.7.44 | FINAL CLEAN | 1 | 11 December 2024 8:00 AM | 11 December 2024 5:00 PM | 1412 | 1414 | 11 December 2024 8:00 AM | 2024-12-12 17:00 | 1 | Site Manager | 18 | 51 | 18 | 17 | 46
1414 | 1.2.4.4.1.7.45 | UNIT LOCKED | 1 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | 1413 |  | 12 December 2024 8:00 AM | 2024-12-12 17:00 | 0 | Subcontractor | 96 | 64 | 14 | 63 | 54
1415 | 1.2.4.4.1.8 | Apartment B017 | 46 | 21 October 2024 8:00 AM | 12 December 2024 5:00 PM |  |  | 21 October 2024 8:00 AM | 2024-12-13 17:00 | 1 | Post Tension | 5 | 12 | 30 | 70 | 37
1416 | 1.2.4.4.1.8.1 | External and Intertenancy Wall Framing | 2 | 21 October 2024 8:00 AM | 22 October 2024 5:00 PM | 448FS+6d | 1417,1420,1421,1488 | 21 October 2024 8:00 AM | 2024-10-22 17:00 | 0 | Surveyor | 22 | 46 | 20 | 32 | 26
1417 | 1.2.4.4.1.8.2 | Waterproofing Wall & Window | 1 | 23 October 2024 8:00 AM | 23 October 2024 5:00 PM | 1416 | 1419,1418 | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 2 | Waterproofer | 20 | 95 | 18 | 10 | 50
1418 | 1.2.4.4.1.8.3 | External & Intertenancy Wall / Hebal | 2 | 24 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1417 |  | 24 October 2024 8:00 AM | 2024-10-27 17:00 | 2 | Tiler | 16 | 49 | 19 | 91 | 39
1419 | 1.2.4.4.1.8.4 | Windows Install | 3 | 24 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1417 | 1422 | 24 October 2024 8:00 AM | 2024-10-26 17:00 | 0 | Cleaner | 16 | 24 | 34 | 87 | 38
1420 | 1.2.4.4.1.8.5 | Mechanical Overheads | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1429 | 23 October 2024 8:00 AM | 2024-10-26 17:00 | 1 | Site Manager | 0 | 76 | 29 | 83 | 39
1421 | 1.2.4.4.1.8.6 | Fire Sprinklers Mains | 3 | 23 October 2024 8:00 AM | 25 October 2024 5:00 PM | 1416 | 1492 | 23 October 2024 8:00 AM | 2024-10-25 17:00 | 0 | Formworker | 62 | 44 | 27 | 13 | 32
1422 | 1.2.4.4.1.8.7 | Internal Wall Framing & Door Frames | 2 | 28 October 2024 8:00 AM | 29 October 2024 5:00 PM | 1419 | 1423,1424,1425,1426,1427 | 28 October 2024 8:00 AM | 2024-10-29 17:00 | 0 | Formworker | 19 | 62 | 11 | 56 | 34
1423 | 1.2.4.4.1.8.8 | Mechanical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Formworker | 68 | 27 | 26 | 33 | 18
1424 | 1.2.4.4.1.8.9 | Plumbing Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1427,1491 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Post Tension | 83 | 21 | 15 | 52 | 22
1425 | 1.2.4.4.1.8.10 | Electrical Wall Roughin | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 | 1490 | 30 October 2024 8:00 AM | 2024-10-31 17:00 | 0 | Fire | 93 | 21 | 35 | 89 | 30
1426 | 1.2.4.4.1.8.11 | Fire Detection (Dry) | 2 | 30 October 2024 8:00 AM | 31 October 2024 5:00 PM | 1422 |  | 30 October 2024 8:00 AM | 2024-11-01 17:00 | 1 | Carpet | 32 | 36 | 35 | 11 | 54
1427 | 1.2.4.4.1.8.12 | Noggin Rough in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1422,1423,1424 | 1428 | 1 November 2024 8:00 AM | 2024-11-02 17:00 | 1 | Formworker | 76 | 64 | 24 | 29 | 8
1428 | 1.2.4.4.1.8.13 | Sheet Walls | 2 | 2 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1427 | 1429 | 2 November 2024 8:00 AM | 2024-11-05 17:00 | 1 | Plasterboarder | 8 | 76 | 14 | 55 | 15
1429 | 1.2.4.4.1.8.14 | Ceiling Grids | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1420,1428 | 1430,1431,1432,1433,1435,1437 | 5 November 2024 8:00 AM | 2024-11-06 17:00 | 0 | Metal Work | 55 | 11 | 27 | 91 | 45
1430 | 1.2.4.4.1.8.15 | Electrical Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1434,1437 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Hoarding | 92 | 50 | 33 | 56 | 40
1431 | 1.2.4.4.1.8.16 | Fire Detection (Dry) | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1437 | 7 November 2024 8:00 AM | 2024-11-09 17:00 | 1 | Carpet | 76 | 33 | 34 | 29 | 31
1432 | 1.2.4.4.1.8.17 | Plumbing Rough-in | 2 | 7 November 2024 8:00 AM | 8 November 2024 5:00 PM | 1429 | 1436,1437 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 0 | Stone Mason | 61 | 73 | 31 | 54 | 19
1433 | 1.2.4.4.1.8.18 | Fire Sprinklers Droppers | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | 7 November 2024 8:00 AM | 2024-11-09 17:00 | 2 | Renderer | 92 | 95 | 19 | 48 | 8
1434 | 1.2.4.4.1.8.19 | Fire Rating Electrical | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1430 | 1437 | 9 November 2024 8:00 AM | 2024-11-10 17:00 | 1 | Foreman | 8 | 28 | 24 | 43 | 50
1435 | 1.2.4.4.1.8.20 | Fire Rating Mechanical | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1429 | 1437 | 7 November 2024 8:00 AM | 2024-11-09 17:00 | 2 | Tiler | 70 | 39 | 30 | 8 | 8
1436 | 1.2.4.4.1.8.21 | Fire Rating Hydraulic | 1 | 9 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1432 | 1437 | 9 November 2024 8:00 AM | 2024-11-09 17:00 | 0 | Timber Floorer | 23 | 80 | 25 | 83 | 58
1437 | 1.2.4.4.1.8.22 | Noggin Rough in | 1 | 11 November 2024 8:00 AM | 11 November 2024 5:00 PM | 1429,1430,1431,1432,1433,1434,1435,1436 | 1438 | 11 November 2024 8:00 AM | 2024-11-13 17:00 | 2 | Mechanical | 68 | 64 | 21 | 98 | 23
1438 | 1.2.4.4.1.8.23 | Sheet Ceilings | 1 | 12 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1437 | 1439 | 12 November 2024 8:00 AM | 2024-11-14 17:00 | 2 | Stone Mason | 89 | 83 | 28 | 42 | 4
1439 | 1.2.4.4.1.8.24 | Setting / Sanding | 3 | 13 November 2024 8:00 AM | 15 November 2024 5:00 PM | 1438 | 1440,1457,1474 | 13 November 2024 8:00 AM | 2024-11-16 17:00 | 1 | Foreman | 44 | 42 | 32 | 97 | 37
1440 | 1.2.4.4.1.8.25 | Paint Undercoat (1st Coat) | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1441 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 2 | Contract Administrator | 2 | 56 | 25 | 62 | 31
1441 | 1.2.4.4.1.8.26 | Paint Undercoat (2nd Coat) | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1440 | 1442 | 18 November 2024 8:00 AM | 2024-11-18 17:00 | 0 | Carpet | 29 | 43 | 30 | 66 | 57
1442 | 1.2.4.4.1.8.27 | Floor Leveling | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1441 | 1443 | 19 November 2024 8:00 AM | 2024-11-22 17:00 | 2 | Floor Sealer | 4 | 11 | 17 | 80 | 17
1443 | 1.2.4.4.1.8.28 | Timber Floor Install | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1442 | 1444 | 21 November 2024 8:00 AM | 2024-11-25 17:00 | 4 | Reinforcement Fixer | 37 | 39 | 25 | 10 | 58
1444 | 1.2.4.4.1.8.29 | Joinery Kickers | 1 | 22 November 2024 8:00 AM | 22 November 2024 5:00 PM | 1443 | 1445,1446 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 1 | Line Market | 77 | 47 | 26 | 15 | 35
1445 | 1.2.4.4.1.8.30 | Joinery Kitchen | 2 | 23 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1444 | 1449 | 23 November 2024 8:00 AM | 2024-11-26 17:00 | 1 | Hoarding | 21 | 95 | 31 | 28 | 17
1446 | 1.2.4.4.1.8.31 | Joinery Bedroom | 1 | 23 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1444 | 1447 | 23 November 2024 8:00 AM | 2024-11-26 17:00 | 3 | Development Manager | 87 | 80 | 16 | 18 | 5
1447 | 1.2.4.4.1.8.32 | Door Hanging | 1 | 25 November 2024 8:00 AM | 25 November 2024 5:00 PM | 1446 | 1448 | 25 November 2024 8:00 AM | 2024-11-25 17:00 | 0 | Head Contractor | 7 | 45 | 30 | 41 | 56
1448 | 1.2.4.4.1.8.33 | Door Hardware | 1 | 26 November 2024 8:00 AM | 26 November 2024 5:00 PM | 1447 |  | 26 November 2024 8:00 AM | 2024-11-26 17:00 | 0 | Renderer | 99 | 15 | 18 | 80 | 50
1449 | 1.2.4.4.1.8.34 | Stone Kitchen | 2 | 26 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1445 | 1450,1451,1452,1453,1454 | 26 November 2024 8:00 AM | 2024-11-28 17:00 | 1 | Surveyor | 29 | 91 | 28 | 80 | 51
1450 | 1.2.4.4.1.8.35 | Carpentry skirtings | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1449 |  | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 1 | Cleaner | 54 | 24 | 27 | 94 | 15
1451 | 1.2.4.4.1.8.36 | Hydraulic Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | 28 November 2024 8:00 AM | 2024-11-30 17:00 | 1 | Floor Sealer | 43 | 15 | 18 | 98 | 11
1452 | 1.2.4.4.1.8.37 | Electrical Living Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | 28 November 2024 8:00 AM | 2024-12-03 17:00 | 4 | Subcontractor | 39 | 62 | 20 | 89 | 45
1453 | 1.2.4.4.1.8.38 | Electrical Kitchen Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | 28 November 2024 8:00 AM | 2024-12-02 17:00 | 3 | Renderer | 78 | 54 | 33 | 34 | 36
1454 | 1.2.4.4.1.8.39 | Mechanical Fitoff Install | 2 | 28 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1449 | 1505 | 28 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Cleaner | 66 | 92 | 22 | 79 | 19
1455 | 1.2.4.4.1.8.40 | Internal Wet Areas | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  | 1505 | 16 November 2024 8:00 AM | 2024-12-07 17:00 | 0 | Mechanical | 21 | 97 | 15 | 23 | 48
1456 | 1.2.4.4.1.8.40.1 | Bathrooms | 19 | 16 November 2024 8:00 AM | 7 December 2024 5:00 PM |  |  | 16 November 2024 8:00 AM | 2024-12-07 17:00 | 0 | Carpet | 19 | 70 | 26 | 87 | 54
1457 | 1.2.4.4.1.8.40.1.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1458 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 2 | Mechanical | 5 | 36 | 27 | 5 | 34
1458 | 1.2.4.4.1.8.40.1.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1457 | 1459 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 1 | Foreman | 68 | 15 | 33 | 9 | 8
1459 | 1.2.4.4.1.8.40.1.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1458 | 1460 | 19 November 2024 8:00 AM | 2024-11-21 17:00 | 1 | Waterproofer | 26 | 34 | 17 | 34 | 32
1460 | 1.2.4.4.1.8.40.1.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1459 | 1461 | 21 November 2024 8:00 AM | 2024-11-21 17:00 | 0 | Project Manager | 22 | 86 | 31 | 34 | 21
1461 | 1.2.4.4.1.8.40.1.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1460 | 1462 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Carpet | 41 | 11 | 18 | 71 | 39
1462 | 1.2.4.4.1.8.40.1.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1461 | 1463 | 25 November 2024 8:00 AM | 2024-11-27 17:00 | 0 | Admin | 51 | 87 | 10 | 72 | 34
1463 | 1.2.4.4.1.8.40.1.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1462 | 1464 | 28 November 2024 8:00 AM | 2024-11-28 17:00 | 0 | Scaffolder | 50 | 36 | 23 | 54 | 24
1464 | 1.2.4.4.1.8.40.1.8 | Joinery Bathroom | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1463 | 1465 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Joiner | 66 | 11 | 32 | 15 | 49
1465 | 1.2.4.4.1.8.40.1.9 | Stone | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1464 | 1466 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 2 | Painter | 64 | 98 | 24 | 73 | 27
1466 | 1.2.4.4.1.8.40.1.10 | Shower Screens | 1 | 2 December 2024 8:00 AM | 2 December 2024 5:00 PM | 1465 | 1467 | 2 December 2024 8:00 AM | 2024-12-02 17:00 | 0 | Foreman | 86 | 13 | 18 | 12 | 35
1467 | 1.2.4.4.1.8.40.1.11 | Mirrors | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1466 | 1468 | 3 December 2024 8:00 AM | 2024-12-07 17:00 | 4 | Plasterboarder | 31 | 54 | 13 | 69 | 17
1468 | 1.2.4.4.1.8.40.1.12 | Bathroom Fittings Fitoff | 1 | 4 December 2024 8:00 AM | 4 December 2024 5:00 PM | 1467 | 1472,1469,1470,1471 | 4 December 2024 8:00 AM | 2024-12-04 17:00 | 0 | Plasterboarder | 68 | 71 | 19 | 11 | 33
1469 | 1.2.4.4.1.8.40.1.13 | Hydraulic Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | 5 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Window | 32 | 15 | 30 | 98 | 49
1470 | 1.2.4.4.1.8.40.1.14 | Electrical Bathroom Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | 5 December 2024 8:00 AM | 2024-12-06 17:00 | 0 | Electrician | 17 | 10 | 15 | 69 | 48
1471 | 1.2.4.4.1.8.40.1.15 | Mechanical Laundry Fitoff | 2 | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | 1468 | 1472 | 5 December 2024 8:00 AM | 2024-12-09 17:00 | 3 | Reinforcement Fixer | 10 | 41 | 11 | 54 | 54
1472 | 1.2.4.4.1.8.40.1.16 | Silicone | 1 | 7 December 2024 8:00 AM | 7 December 2024 5:00 PM | 1468,1469,1470,1471 |  | 7 December 2024 8:00 AM | 2024-12-07 17:00 | 0 | Carpenter | 95 | 72 | 17 | 87 | 41
1473 | 1.2.4.4.1.8.40.2 | Laundry | 15 | 16 November 2024 8:00 AM | 3 December 2024 5:00 PM |  |  | 16 November 2024 8:00 AM | 2024-12-04 17:00 | 1 | Project Manager | 3 | 92 | 24 | 69 | 59
1474 | 1.2.4.4.1.8.40.2.1 | Prepare for Waterproof | 1 | 16 November 2024 8:00 AM | 16 November 2024 5:00 PM | 1439 | 1475 | 16 November 2024 8:00 AM | 2024-11-18 17:00 | 2 | Metal Work | 42 | 61 | 23 | 53 | 9
1475 | 1.2.4.4.1.8.40.2.2 | Install Angles | 1 | 18 November 2024 8:00 AM | 18 November 2024 5:00 PM | 1474 | 1476 | 18 November 2024 8:00 AM | 2024-11-19 17:00 | 1 | Formworker | 47 | 12 | 25 | 65 | 34
1476 | 1.2.4.4.1.8.40.2.3 | Waterproof | 2 | 19 November 2024 8:00 AM | 20 November 2024 5:00 PM | 1475 | 1477 | 19 November 2024 8:00 AM | 2024-11-20 17:00 | 0 | Landscaper | 98 | 59 | 33 | 26 | 23
1477 | 1.2.4.4.1.8.40.2.4 | Water Testing | 1 | 21 November 2024 8:00 AM | 21 November 2024 5:00 PM | 1476 | 1478 | 21 November 2024 8:00 AM | 2024-11-23 17:00 | 2 | Fire | 54 | 64 | 31 | 27 | 12
1478 | 1.2.4.4.1.8.40.2.5 | Tile Bed and Cure | 2 | 22 November 2024 8:00 AM | 23 November 2024 5:00 PM | 1477 | 1479 | 22 November 2024 8:00 AM | 2024-11-23 17:00 | 0 | Head Contractor | 9 | 42 | 33 | 82 | 56
1479 | 1.2.4.4.1.8.40.2.6 | Tile Wall & Floor | 3 | 25 November 2024 8:00 AM | 27 November 2024 5:00 PM | 1478 | 1480 | 25 November 2024 8:00 AM | 2024-11-29 17:00 | 2 | Contract Administrator | 37 | 66 | 28 | 67 | 51
1480 | 1.2.4.4.1.8.40.2.7 | Grout | 1 | 28 November 2024 8:00 AM | 28 November 2024 5:00 PM | 1479 | 1481 | 28 November 2024 8:00 AM | 2024-12-01 17:00 | 3 | Project Manager | 76 | 52 | 12 | 49 | 16
1481 | 1.2.4.4.1.8.40.2.8 | Joinery Laundry | 1 | 29 November 2024 8:00 AM | 29 November 2024 5:00 PM | 1480 | 1482,1483,1484,1485 | 29 November 2024 8:00 AM | 2024-11-29 17:00 | 0 | Window | 60 | 41 | 33 | 15 | 7
1482 | 1.2.4.4.1.8.40.2.9 | Laundry Fittings Fitoff | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | 30 November 2024 8:00 AM | 2024-12-03 17:00 | 3 | Timber Floorer | 86 | 20 | 27 | 10 | 8
1483 | 1.2.4.4.1.8.40.2.10 | Hydraulic Laundry Fitoff Install | 1 | 30 November 2024 8:00 AM | 30 November 2024 5:00 PM | 1481 | 1486 | 30 November 2024 8:00 AM | 2024-11-30 17:00 | 0 | Renderer | 63 | 81 | 14 | 37 | 6
1484 | 1.2.4.4.1.8.40.2.11 | Electrical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Painter | 21 | 16 | 30 | 64 | 37
1485 | 1.2.4.4.1.8.40.2.12 | Mechanical Laundry Fitoff | 2 | 30 November 2024 8:00 AM | 2 December 2024 5:00 PM | 1481 | 1486 | 30 November 2024 8:00 AM | 2024-12-02 17:00 | 0 | Plasterboarder | 26 | 59 | 29 | 91 | 10
1486 | 1.2.4.4.1.8.40.2.13 | Silicone | 1 | 3 December 2024 8:00 AM | 3 December 2024 5:00 PM | 1482,1483,1484,1485 |  | 3 December 2024 8:00 AM | 2024-12-03 17:00 | 0 | Project Manager | 91 | 62 | 33 | 86 | 23
1487 | 1.2.4.4.1.8.41 | Balcony | 23 | 23 October 2024 8:00 AM | 18 November 2024 5:00 PM |  |  | 23 October 2024 8:00 AM | 2024-11-21 17:00 | 3 | Head Contractor | 81 | 48 | 26 | 37 | 20
1488 | 1.2.4.4.1.8.41.1 | Balustrade Prep | 2 | 23 October 2024 8:00 AM | 24 October 2024 5:00 PM | 1416 | 1489 | 23 October 2024 8:00 AM | 2024-10-27 17:00 | 3 | Floor Sealer | 37 | 51 | 16 | 32 | 56
1489 | 1.2.4.4.1.8.41.2 | Balustrade Install | 2 | 25 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1488 |  | 25 October 2024 8:00 AM | 2024-10-28 17:00 | 2 | Joiner | 7 | 50 | 21 | 65 | 53
1490 | 1.2.4.4.1.8.41.3 | Electrical Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1425 | 1493 | 1 November 2024 8:00 AM | 2024-11-04 17:00 | 3 | Admin | 80 | 24 | 26 | 85 | 48
1491 | 1.2.4.4.1.8.41.4 | Plumbing Rough-in | 1 | 1 November 2024 8:00 AM | 1 November 2024 5:00 PM | 1424 | 1493 | 1 November 2024 8:00 AM | 2024-11-03 17:00 | 2 | Line Market | 10 | 79 | 11 | 90 | 30
1492 | 1.2.4.4.1.8.41.5 | Fire Sprinklers | 1 | 26 October 2024 8:00 AM | 26 October 2024 5:00 PM | 1421 | 1493 | 26 October 2024 8:00 AM | 2024-10-28 17:00 | 2 | Scaffolder | 21 | 31 | 12 | 80 | 59
1493 | 1.2.4.4.1.8.41.6 | Prepare for Waterproof | 1 | 2 November 2024 8:00 AM | 2 November 2024 5:00 PM | 1490,1491,1492 | 1494 | 2 November 2024 8:00 AM | 2024-11-03 17:00 | 1 | Surveyor | 80 | 63 | 24 | 38 | 55
1494 | 1.2.4.4.1.8.41.7 | Install Angles | 1 | 4 November 2024 8:00 AM | 4 November 2024 5:00 PM | 1493 | 1495 | 4 November 2024 8:00 AM | 2024-11-04 17:00 | 0 | Concretor | 61 | 73 | 22 | 82 | 44
1495 | 1.2.4.4.1.8.41.8 | Waterproof | 2 | 5 November 2024 8:00 AM | 6 November 2024 5:00 PM | 1494 | 1496 | 5 November 2024 8:00 AM | 2024-11-10 17:00 | 4 | Waterproofer | 70 | 99 | 25 | 9 | 24
1496 | 1.2.4.4.1.8.41.9 | Water Testing | 1 | 7 November 2024 8:00 AM | 7 November 2024 5:00 PM | 1495 | 1497 | 7 November 2024 8:00 AM | 2024-11-08 17:00 | 1 | Development Manager | 76 | 13 | 35 | 65 | 56
1497 | 1.2.4.4.1.8.41.10 | Tile Bed and Cure | 2 | 8 November 2024 8:00 AM | 9 November 2024 5:00 PM | 1496 | 1498 | 8 November 2024 8:00 AM | 2024-11-10 17:00 | 1 | Scaffolder | 29 | 28 | 19 | 44 | 15
1498 | 1.2.4.4.1.8.41.11 | Tiling | 2 | 11 November 2024 8:00 AM | 12 November 2024 5:00 PM | 1497 | 1499 | 11 November 2024 8:00 AM | 2024-11-15 17:00 | 3 | Surveyor | 53 | 86 | 31 | 94 | 60

## Trade List
Trade Name
Tiler
Line Market
Landscaper
Surveyor
Painter
Reinforcement Fixer
Project Manager
Post Tension
Plumber
Cleaner
Plasterboarder
Joiner
Excavation
Concretor
Waterproofer
Site Manager
Floor Sealer
Fire
Window
Mechanical
Head Contractor
Development Manager
Scaffolder
Hoarding
Carpenter
Admin
Renderer
Subcontractor
Contract Administrator
Carpet
Electrician
Stone Mason
Timber Floorer
Metal Work
Foreman
Formworker